**ANNEX 6**

|  |  |  |
| --- | --- | --- |
|  | SUN Movement  Multi-Partner Trust Fund | UN Logo |

**PROGRAMME1 QUARTERLY PROGRESS UPDATE**

***as of 30 of June,2015***

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Participating UN Organization:** | UNICEF | | | | |
| **Implementing Partner(s):** | Public Fund “Innovative Solution”  Kyrgyz Association of Producers of Salt  Public Association “Centre of Monitoring” | | | | |
| **Programme Number:** |  | | | | |
| **Programme Title:** | Creating of enabling environment/structural support to improve nutrition for the sake of justice and future generations in the Kyrgyz Republic | | | | |
| **Total Approved Programme Budget:** | **US$ 235,000** | | | | |
| **Location:** | **Kyrgyz Republic** | | | | |
| **MC Approval Date:** | **27.11.2013** | | | | |
| **Programme Duration:** | **24 months** | **Starting Date:** | **1 January, 2014** | **Completion Date:** | **31 December, 2015** |
| **Funds Committed:** | **US$\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_** | | | **Percentage of Approved:** |  |
| **Funds Disbursed:** | **US$\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_** | | | **Percentage of Approved:** |  |
| **Expected Programme Duration:** |  | **Forecast Final Date:** |  | **Delay (Months):** |  |

|  |  |  |
| --- | --- | --- |
| **Outcomes:** | **Achievements/Results:** | **Percentage of planned:** |
| **Outcome 1.** **It is established the national, political, state structures and mechanisms for developing, coordinating, monitoring of nutrition policy** |  |  |
| Mapping of institutions, resources, accomplishments/results/ practices in the field of nutrition, sanitation and hygiene, access to water and health services | Map of institutions, resources, accomplishments / results / practices in the field of nutrition, sanitation and hygiene, access to water and health services. Report on mapping with recommendations to coordinate and improve nutrition. | 100 % |
| Analysis of sectoral policies on issues related to nutrition, sanitation and hygiene, access to water and health services | Reveal the gaps nutrition and collisions in the legislation in the sphere of food are revealed and the directions in improvement of the legislation are designated/ Report on results of analysis of national nutrition legislation for compliance with international obligations in the field of human rights and development | 100 % |
| Creating of a cross-sectoral platform of CSO representatives, business community, government agencies, donor agencies and development agencies, and academic institutions. | General meeting for establishment of Alliance of Civil Society, Engagement of business to establish business network | 100 % |
| Public hearings on improvement of the legislation | Non-governmental public and civil society organizations, donors sounded problems of application of the legislation and made the suggestions for improvement. | 100% |
|  | Consultations for interested partners provided by platform members regarding creation of National Mechanism | 50% |
|  | Conduction of National and regional public hearings on establishment of national structures and mechanisms in the field of nutrition.  Проведение экспертного совещания в мае 2015 года | 100% |
| It is established national regulatory mechanisms for implementing nutrition policy | Concept paper on National Nutrition Policy/ Functional analysis of architecture of coordinating mechanism on nutrition | 10 % |
| **Outcome 2. It is established national regulatory mechanisms for implementing nutrition policy** |  |  |
| Inventory of the national legislation of the Kyrgyz Republic for compliance with the international obligations of the Kyrgyz Republic in the field of human rights and development (including legal obligations on MDGs), synchronization of sectoral policies, development of legal mechanisms for implementation of nutrition policy of the Kyrgyz Republic through examination and analysis of and changes in laws | Report on results of analysis of national nutrition legislation for compliance with international obligations in the field of human rights and development. | 100 % |

|  |
| --- |
| **Qualitative achievements against outcomes and results:** |
| These main and baseline activities will help to understand the general situation and identify main stakeholders in nutrition. Will give us clear picture on whom we work and what and how we do next. In terms of Law and Legislations, which laws need to be newly developed and which laws, can be amended. |

The term “programme” is used for projects, programmes and joint programmes.