**ANNEX 6**

|  |  |  |
| --- | --- | --- |
|  | SUN Movement  Multi-Partner Trust Fund | UN Logo |

**PROGRAMME1 QUARTERLY PROGRESS UPDATE**

***as of 30 of September,2015***

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Participating UN Organization:** | UNICEF | | | | |
| **Implementing Partner(s):** | Public Fund “Innovative Solution”  Kyrgyz Association of Producers of Salt  Public Association “Centre of Monitoring”  Public Association “Alliance of Civil Society for Nutrition and Food Security” | | | | |
| **Programme Number:** |  | | | | |
| **Programme Title:** | Creating of enabling environment/structural support to improve nutrition for the sake of justice and future generations in the Kyrgyz Republic | | | | |
| **Total Approved Programme Budget:** | **US$ 235,000** | | | | |
| **Location:** | **Kyrgyz Republic** | | | | |
| **MC Approval Date:** | **27.11.2013** | | | | |
| **Programme Duration:** | **24 months** | **Starting Date:** | **1 January, 2014** | **Completion Date:** | **31 December, 2015** |
| **Funds Committed:** | **US$220.000** | | | **Percentage of Approved:** | **93%** |
| **Funds Disbursed:** | **US$ 132,05** | | | **Percentage of Approved:** | **67%** |
| **Expected Programme Duration:** | **9 months** | **Forecast Final Date:** | **May, 2016** | **Delay (Months):** | **1 month** |

|  |  |  |
| --- | --- | --- |
| **Outcomes:** | **Achievements/Results:** | **Percentage of planned:** |
| **Outcome 1.** **It is established the national, political, state structures and mechanisms for developing, coordinating, monitoring of nutrition policy** |  |  |
| Mapping of institutions, resources, accomplishments/results/ practices in the field of nutrition, sanitation and hygiene, access to water and health services | Map of institutions, resources, accomplishments / results / practices in the field of nutrition, sanitation and hygiene, access to water and health services. Report on mapping with recommendations to coordinate and improve nutrition. | 100 % |
| Analysis of sectoral policies on issues related to nutrition, sanitation and hygiene, access to water and health services | Reveal the gaps and collisions in the legislation in the sphere of food and the directions in improvement of the legislation are designated/ Report on results of analysis of national nutrition legislation for compliance with international obligations in the field of human rights and development | 70 % |
| Creating of a cross-sectoral platform of CSO representatives, business community, government agencies, donor agencies and development agencies, and academic institutions. | Establishment of Alliance of Civil Society, Engagement of business to establish business network | 100 % |
| Public hearings on improvement of the legislation | Non-governmental public and civil society organizations, donors sounded problems of application of the legislation and made the suggestions for improvement. | 100% |
| Lobbying through an advocacy campaign for establishment of a national coordination structure (Council, Committee, etc.) and mechanisms (Secretariat, Commission, etc.) to develop and monitor a coherent national nutrition policy | Development and production of video and booklet about Multi-stakeholder platform | 50% |
|  | Consultations for interested partners provided by platform members regarding creation of National Mechanism | 100% |
| It is established national regulatory mechanisms for implementing nutrition policy | Concept paper on National Nutrition Policy/ Functional analysis of architecture of coordinating mechanism on nutrition | 30 % |
| **Outcome 2. It is established national regulatory mechanisms for implementing nutrition policy** |  |  |
| Inventory of the national legislation of the Kyrgyz Republic for compliance with the international obligations of the Kyrgyz Republic in the field of human rights and development (including legal obligations on MDGs), synchronization of sectoral policies, development of legal mechanisms for implementation of nutrition policy of the Kyrgyz Republic through examination and analysis of and changes in laws | Report on results of analysis of national nutrition legislation for compliance with international obligations in the field of human rights and development. | 100 % |
| **Outcome 3. It is created a favorable environment and structural support in society at national and local levels to implement nutrition policies** |  |  |
|  | Development of neural tube defects register: key elements of NTD Register ( the instruction /case management of the NTD)  Routine registration forms are developed and integrated into existing HMIS  Developed the structure for the data base of NTD | 10 % |

|  |
| --- |
| **Qualitative achievements against outcomes and results:** |
| Due to delay of Approval of the national Food Security and Nutrition program, some of the activities related to Coordination mechanism are postponed. It is well understood by key partners the necessity to develop CRF with budget and clear M&E plan.  The NTD surveillance system will be used as example to show the impact of flour fortification program.  The concept of Coordination mechanism and understanding of role of each network and Government is discussed and bringing more and more players. |

The term “programme” is used for projects, programmes and joint programmes.