# RUNO Half Yearly Reporting 					TEMPLATE 4.3

[COUNTRY: Myanmar]

PROJECT HALF YEARLY PROGRESS UPDATE

PERIOD COVERED: JANUARY – JUNE 2016

| Project No & Title: | PBF/IRF-114, Establishment of the Center for Diversity and National Harmony (CDNH) - Myanmar |
| --- | --- |
| Recipient Organization(s): | UNOPS |
| Implementing Partners (Government, UN agencies, NGOs etc): | Center for Diversity and National Harmony (CDNH) |
| Total Approved Budget : | USD 2,538,122 |
| Preliminary data on funds committed : | USD 2,190,135 | % of funds committed / total approved budget: | 86.3% |
| Expenditure: | USD 2,099,011.892 | % of expenditure / total budget: (Delivery rate) | 82.70% |
| Project Approval Date: | 16/02/2015 | Possible delay in operational closure date (Number of months) |  |
| Project Start Date: | 01/03/2015 |  |  |
| Expected Operational Project Closure Date: | 31/08/2015 |  |  |
| Project Outcomes: | 1. Enhanced comprehension of the current situation of violence, its nature, the local context and trends through systematic information gathering and research 2. The mitigation of risks is enhanced and responses to threats of social violence are improved through the setting up and maintenance of an early warning system. 3. Local capacities for conflict resolution are enhanced and acceptance of differences through public outreach, awareness raising and training is increased and a growing constituency for social harmony is created and fostered. 4. CDNH is recognised as an effective institution for reducing community tensions in Myanmar and its continued existence is assured |
| PBF Focus Area (select one of the Focus Areas listed below) | Promote coexistence and peaceful resolution of conflicts (Priority Area 2) - (2.1) National reconciliation |

# Qualitative assessment of progress

| For each intended outcome, provide evidence of progress during the reporting period. In addition, for each outcome include the outputs achieved. (1000 characters max per outcome.) | Outcome 1: CDNH has submitted an action plan, a needs assessment report, 12 memos on policy issues, 14 memos on election violence and 7 memos on communal tension and hate speech to relevant government agencies. Due to their highly sensitive content, these memos are not attached. However these memos can be shown to the auditor or officials from UNOPS or any designated official from the UN system upon request. CDNH has conducted field data collection on Social Harmony and Political Process Research in three states and six regions. The graph books for the research of one state and four regions have been published. In addition, a report on communal violence in West Bago Region was published. Furthermore, the team has been conducting the research for the Supplementary Rakhine Needs Assessment. Outcome 2: The Early Warning Early Response (EWER) System is now fully established. A range of stakeholders including Civil Society Organizations were equipped with the knowledge of EWER through trainings targeting a range of different genders, religion and communities. As a result of the trainings, community level information sharing networks have been set up in six clusters and social media monitoring has been conducted since August 2015. CDNH has also worked quite closely with Rakhine State government officials in sharing information about communal violence. CDNH advised Rakhine State government officials how to handle population count in Aung Mingalar quarter without causing any misunderstanding and violence. CDNH also advised the senior officials from the Union government with regard to how the issuing of the new blue ID cards should be conducted and how potential spoilers should be dealt with. Outcome 3: The training team has organized "Building Capacity on Tolerance and Social Harmony" trainings designed to enhance the capacity of stakeholders to improve their activities. 16 reconciliation meetings have been organized in collaboration with moderate leaders of the two communities in Sittwe, Maungdaw, Kyaukphyu, Ramree, Meikhtila, Thazi and Yangon. In order to promote the role of women in conflict prevention, CDNH has organized two women’s forums with participation from the two communities from Rakhine State as well as women of different religions from different parts of the country. Most of the participants from CDNH’s meetings and trainings noted that the knowledge and understanding they had made them realize that communal violence was not inevitable and began to realize their role in conflict prevention. In collaboration with UNESCO, CDNH undertook a Training of Trainers (TOT) on peace building with 310 public school teachers both in Rakhine State and Yangon Region. Outcome 4: Anecdotal evidence indicates that several stakeholders recognize CDNH’s contributions to conflict prevention. The successful Rakhine Needs Assessment is one piece of evidence along with a high demand to join the mailing lists for distribution of the situation updates. As a result of the expansion of the mailing list on a request basis, more individuals are now receiving information. Coupled with internal distribution among UN agencies, situation updates are now reaching several hundred individuals. More than 20 international organizations and foreign embassies have noted that they have used CDNH’s bi-weekly early warning update, weekly supplement and the needs assessment report to inform their work. In addition, a number of organizations contact CDNH regularly to clarify or gather information and seek analysis from its staff members. UN Resident Coordinator publicly praised CDNH’s contribution to conflict prevention and communal harmony in Rakhine State. |
| --- | --- |
| Do you see evidence that the project is having a positive impact on peacebuilding? (1000 characters max.) | CDNH has contributed to the prevention and escalation of further violence by writing timely memos on incidents and potential hotspots. As a result of reconciliation meetings, moderate members of both communities in Maungdaw and Buditaung have established a joint committee. Rakhine representatives from Ramree and Sittwe have discussed the establishment of a similar joint committee. However, due to unfriendly attack from religious extremists, community leaders from the latter three townships have conducted their interactions in an informal manner. CDNH organized a meeting between community leaders from Rakhine State and leaders of the diplomatic community and was able to produce an outline for trust building among various communities in Rakhine State and the role that the international community should play in such an effort. As the result of participation in reconciliation meetings, leaders of both communities have begun to some joint activities in their local areas. |
| Were there catalytic effects from the project in the period reported, including additional funding commitments or unleashing/ unblocking of any peace relevant processes? (1000 characters max.) | The project has received additional funding from Switzerland, Norway and the Peace Support Fund (PSF). The Danish government will provide USD 700,000 starting in June 2016. |
| If progress has been slow or inadequate, provide main reasons and what is being done to address them. (1000 characters max.) | There is no major variance based on the budgeted targeted during the reporting period. |
| What are the main activities/expected results for the rest of the year? (1000 characters max.) | CDNH will organize six capacity building trainings with the support of Norwegian and Danish embassies and one workshop on women’s leadership between now and August. EWERP will organize six coordination meetings and two information sharing sessions, publish two more research reports on Social Harmony and Political Process and five reconciliation meetings (with the support of the Norwegian and Danish embassies). |
| Is there any need to adjust project strategies/ duration/budget etc.? (1000 characters max.) | All the remaining planned activities for phase three will be implemented in a timely manner. |
| What is the project budget expenditure to date (percentage of allocated project budget expensed by the date of the report) – preliminary figures only? (1000 characters max.) | USD 2,099,011.892 |
| Any other information that the project needs to convey to PBSO (and JSC) at this stage? (1500 characters max.) | Since CDNH works on politically and socially sensitive communal issues, its partners and staff members can be vulnerable to criticism and harassment from hardliners from both sides. In all the partnership meetings, CDNH always included government officials and explained to them the safety problems CDNH and its partners could encounter. The government officials always provide CDNH staff members security whenever trips were made to security sensitive areas. CDNH has made it possible for its partners from both communities to contact the state minister directly whenever they were concerned about their own safety. From January 2016 to the present, RCO have participated in the ongoing work of CDNH in bringing the two communities together through workshops conducted between the two communities. The collaboration includes facilitation of workshop as needed including provision assistance in editing reports. Inputs are also provided to the organisation’s public outreach such as contribution to seminars as a resource. |

INDICATOR BASED PERFORMANCE ASSESSMENT: Using the Project Results Framework as per the approved project document- provide an update on the achievement of key indicators at both the outcome and output level in the table below. Where it has not been possible to collect data on indicators, state this and provide any explanation in the qualitative text above. (250 characters max per entry)

|  | Performance Indicators | Indicator Baseline | End of project Indicator Target | Current indicator progress | Reasons for Variance/ Delay (if any) | Adjustment of target (if any) |
| --- | --- | --- | --- | --- | --- | --- |
| Outcome 1 Enhanced comprehension of the current situation of violence, its nature, the local context and trends through systematic information gathering and research | Indicator 1.1 Number of decisions (mitigation and operational actions in response to violence) taken by stakeholders (govt., CBOs, security forces) using the CDNH analysis provided | Four Rakhine commission reports were published on communal violence | Research team mobilized and producing high-quality and regular research outputs for policy making and mitigation decisions/actions being taken as a result of this timely analysis | CDNH submitted an action plan, a needs assessment report, report on communal tensions in West Bago, 27 memos on political, social and economic issues which both the government and relevant stakeholders drew on in making their policy decisions. |  |  |
|  | Indicator 1.2 Increase of culturally, gender-sensitive and conflict-sensitive reactions and activities by stakeholders of CDNH | Ten per cent of the activities of CDNH’s stakeholders are related to culturally sensitive issues, less than ten per cent are related to gender issues and between 50 and 60 per cent are related to conflict-sensitive issues. | Stakeholders engaging with CDNH as a result of its performance and reputation and same stakeholders displaying conflict sensitive and gender-sensitive behaviour | The training team conducted six "Building Capacity on Tolerance and Social Harmony" trainings and two women’s forum which contributed to enhancing the capacity of stakeholders to improve their activities. |  |  |
|  | Indicator 1.3 |  |  |  |  |  |
| Output 1.1 Recruitment of research and operations personnel | Indicator 1.1.1 Initial personnel recruited for start-up phase by UNOPS | 0 | 38 (+2 UNOPS project management personnel), disaggregated by sex | Initial 38 (Male-21, Female – 17) personnel were recruitment for the start-up phase. |  |  |
|  | Indicator 1.1.2 Number of total personnel vs. planned personnel | 0 | 49, disaggregated by sex | Planned 58 personnel based on the revised budget - Total 58 (Male – 34, Female – 24) were recruited. |  |  |
| Output 1.2 | Indicator 1.2.1 Number of equipment items delivered vs. planned | No equipment | Exact equipment planned in budget | Planned equipment items for 18 months - 12 Items All 12 items were delivered during the reporting period. |  | The register can be reviewed for details about the quantity of items, fixed assets and inventory. |
|  | Indicator 1.2.2 | No equipment | Delivery within first 6 months of project | All 12 planned items were timely delivered during the reporting period. |  |  |
| Output 1.3 | Indicator 1.3.1 |  |  |  |  |  |
|  | Indicator 1.3.2 |  |  |  |  |  |
| Outcome 2 The mitigation of risks is enhanced and responses to threats of social violence are improved through the setting up and maintenance of an Early Warning System. | Indicator 2.1 Key institutions and stakeholders, (i.e. Union and State govt., security forces (police), communities (e.g. Rakhine nationalist communities, Muslim activist networks) and community based organisations) use information from EWS and respond to warnings | Only government agencies were provided with the information. | Widespread use of information provided by CDNH in conflict prevention. | Not only have the Union and State government agencies used the information provided by CDNH effectively but also the entire diplomatic community and major Political Parties. In total, more than 600 stakeholders are using EWS information. |  |  |
|  | Indicator 2.2 CDNH creates and implements policies, strategies and actions that respond to, and directly result from, the information produced by their EWS, thus showing a high level of responsiveness to the EWS | No EWS was available. | CDNH is able to use EWS to respond to warnings and adjust its activities accordingly, and warnings shared with relevant stakeholders. | The Early Warning System is now fully established. Community level information sharing networks have been set up in all six clusters. Social media monitoring is underway. There are 26 Facebook pages being monitored and data collected 3 times a week. |  | CDNH has regularly written memos to senior government officials on the issues that could lead to violence. All community tensions were closely monitored and any developing tensions were reported to government. There was evidence that the government a |
| Output 2.1 Missions conducted between CDNH and conflict areas | Indicator 2.1.1 Number of personnel conducting missions for EWS | 0 | CDNH undertaking missions for establishment of EWS | 11 personnel from EW team conducted mission for coordination meeting in Taunggyi, Ramree and Hpa-an Township. |  |  |
|  | Indicator 2.1.2 Funds spent on missions for EWS purposes | USD 0 | Funding used to visit 6 clusters for EWS set up | USD 4,899 |  |  |
| Output 2.2 Training sessions for staff and local communities on EWS | Indicator 2.2.1 Number of trainings delivered | 0 | Trainings held by end of project in 6 clusters | CDNH organized six awareness trainings, six EWER set up trainings and four information sharing session in Rakhine State, Bago Region, Magway Region and Mandalay Region during the reporting period. |  |  |
|  | Indicator 2.2.2 Broad spectrum of people trained, e.g. different gender, religion, organisations, communities etc. | 0 | All relevant stakeholders trained | Stakeholders as well as Civil Society Organizations were equipped with the knowledge of EWER by the participation of different genders, religion and communities. As a result of the trainings, all planned local information network has been established |  |  |
| Output 2.3 Procurement of communication equipment for early warning system | Indicator 2.3.1 Number of equipment items delivered | No equipment | Exact communications equipment procured as planned in budget | UNOPS took responsibility for procurement of communication equipment. CDNH has received the communication equipment in June 2015. |  |  |
|  | Indicator 2.3.2 Timely delivery of equipment | No equipment | Delivery within first 6 months of project | UNOPS took responsibility for procurement of communication equipment. CDNH has received the communication equipment in June 2015. |  |  |
| Outcome 3 Local capacities for conflict resolution are enhanced and acceptance of differences through public outreach, awareness raising and training is increased and a growing constituency for social harmony is created and fostered. | Indicator 3.1 Perception levels of members of targeted communities on the level of inter-communal violence in their community and their own safety (disaggregated by religion and gender) | 50% of the survey participants answered that the security has improved; the same number of participants (50%) said they still felt unsafe. Of the people who were concerned about communal violence, the number of men (53%) exceeded that of women (47%) | To convince at least 50 % of the targeted population that communal violence could be avoided. | A survey with 500 people from 7 selected areas with communal tension noted that thanks to the public awareness raising activities, more and more residents of respective areas accept that they would have to find a way to work them to curb violence |  |  |
|  | Indicator 3.2 Perception levels by members of targeted communities on the efforts by key institutions and stakeholders to pre-emptively and effectively address potential tensions and hence prevent violence (disaggregated by religion and gender) | From survey result, the perception by targeted communities was: Buddhist Groups:10% positive (on the government), 30% positive (on CSOs), 5% (on international organizations) Muslim groups: 5% positive (on the government) 20% positive (on CSOs) 30% | 50% of members of Buddhist Groups and CSOs see key institutions actions as positive 50% of members of Muslims groups see key institutions actions as positive 50% of members of CSOs see key institutions actions as positive 50% of members of Christian | The results of a survey with about 500 participants of CDNH’s trainings and meetings are Buddhist Groups 18% positive(on government), 20% (on international organizations) Muslim groups 10% positive (on government) 30% (on international organization) |  |  |
| Output 3.1 | Indicator 3.1.1 |  |  |  |  |  |
|  | Indicator 3.1.2 |  |  |  |  |  |
| Output 3.2 | Indicator 3.2.1 |  |  |  |  |  |
|  | Indicator 3.2.2 |  |  |  |  |  |
| Output 3.3 | Indicator 3.3.1 |  |  |  |  |  |
|  | Indicator 3.3.2 |  |  |  |  |  |
| Outcome 4 CDNH is recognised as an effective institution for reducing community tensions in Myanmar and its continued existence is assured | Indicator 4.1 Additional funds are mobilised for CDNH | No other funds were mobilized. | Several donors engaging with and committing funds to CDNH as a result of its performance and reputation | Switzerland is now funding CDNH as well as funding from Norway and the Peace Support Fund (PSF). The Danish government will provide USD 700,000 starting in June 2016. |  |  |
|  | Indicator 4.2 Key government, non-state actors and third-party observers testify to value of CDNH to resolution of social conflict. | Many actors were unaware of the role of CDNH. | Key sectors of society increasingly value CDNH’s role and can cite concrete examples of its contribution to social coherence | As a result of dissemination of biweekly situation updates and weekly supplement by EW program, positive feedback was received and there is high demand to join the mailing list for situation updates. Dissemination has grown rapidly. |  | Norway has agreed to provide a new funding to CDNH. |
| Output 4.1 | Indicator 4.1.1 |  |  |  |  |  |
|  | Indicator 4.1.2 |  |  |  |  |  |
| Output 4.2 | Indicator 4.2.1 |  |  |  |  |  |
|  | Indicator 4.2.2 |  |  |  |  |  |
| Output 4.3 | Indicator 4.3.1 |  |  |  |  |  |
|  | Indicator 4.3.2 |  |  |  |  |  |

# Footnotes

Please note that where there are multiple agencies, only one consolidated project report should be submitted.

Approved budget is the amount transferred to Recipient Organisations.

# Funds committed are defined as the commitments made through legal contracts for services and works according to the financial regulations and procedures of the Recipient Organisations. Provide preliminary data only.

# 4 Actual payments (contracts, services, works) made on commitments.

5 PBF focus areas are:

PBF Focus Areas are:

1: Support the implementation of peace agreements and political dialogue (Priority Area 1):

(1.1) SSR, (1.2) RoL; (1.3) DDR; (1.4) Political Dialogue;

2: Promote coexistence and peaceful resolution of conflicts (Priority Area 2):

(2.1) National reconciliation; (2.2) Democratic Governance; (2.3) Conflict prevention/management;

3:Revitalise the economy and generate immediate peace dividends (Priority Area 3);

(3.1) Employment; (3.2) Equitable access to social services

4) (Re)-establish essential administrative services (Priority Area 4)

(4.1) Strengthening of essential national state capacity; (4.2) extension of state authority/local administration; (4.3) Governance of peacebuilding resources (including JSC/ PBF Secretariats)