| Project Number and Title: MCA06 #48 SLE Social Mobilization & Provision of WASH Services For Achieving & Sustaining a Resilient Zero | PROJECT START DATE: 06/11/2015 | AMOUNT ALLOCATED by MPTF (please indicate different tranches if applicable) $856,000 | RECIPIENT ORGANIZATION UNICEF |
| --- | --- | --- | --- |
| Project ID: 00096725 |  |  |  |
| Project Focal Point: Name: Sandra Lattouf E-mail: slattouf@unicef.org | EXTENSION DATE: Not applicable | FINANCIAL COMMITMENTS $28,337.66 |  |
| Strategic Objective (STEPP) SO3 – Ensure essential services | PROJECTED END DATE: 06/11/2016 | EXPENDITURES AS OF 14 March 2016 $89,468.02 due to the delay in project implementation | IMPLEMENTING PARTNER(S): Government, Ministry of Health and Sanitation, Ministry of Social Welfare, Gender and Children’s Affairs and NGOs |
| Mission Critical Action MCA06 – Access to basic services |  |  |  |
| Location: Sierra Leone | Sub-National Coverage Areas: Bombali, Kambia |
| MONTHLY PROGRESS REPORT RESULTS MATRIX OUTPUT INDICATORS Indicator Geographic Area Projected Target (as per results matrix) Quantitative results for the (one month) reporting period Cumulative results since project commencement (quantitative) Delivery Rate (cumulative % of projected total) as of date Description of the quantifiable indicator as set out in the approved project proposal COMMUNITY ENGAGEMENT 1. Number of chiefdoms /Wards with established and functional Rapid Response Teams Bombali, Kambia 75 chiefdoms MPTF funds were used to support the response to the EVD event in Kambia and Tonkolili. A total of 18 Chiefdoms were targeted in both the districts. MPTF funds were used to support the response to the EVD event in Kambia and Tonkolili. A total of 18 Chiefdoms were targeted in both the districts. 10.45% of allotted amount for the project used to support the EVD event in Tonkolili 2. Number of community structures including VDCs trained Bombali, Kambia TBD after mapping community structure While the process of VDC mapping is ongoing, Chiefdom Taskforces in both the districts were engaged to mobilize community stakeholders and influencers, including village headmen and religious leaders. While the process of VDC mapping is ongoing, Chiefdom Taskforces in both the districts were engaged to mobilize community stakeholders and influencers, including village headmen and religious leaders. 3. Number of VDCs that have developed Community Action Plans Bombali, Kambia 100% MPTF funds were used to support the response to the EVD event in Kambia and Tonkolili MPTF funds were used to support the response to the EVD event in Kambia and Tonkolili 4. Percentage of social mobilizers and youths trained in hotspot communities on key messages and participatory approaches Bombali, Kambia 100% MPTF funds were used to support the response to the EVD event in Kambia and Tonkolili. Over 370 social mobilizers were deployed in the two districts to engage communities during the response. MPTF funds were used to support the response to the EVD event in Kambia and Tonkolili. Over 370 social mobilizers were deployed in the two districts to engage communities during the response. WASH 1. Number of EVD care centres/ communities provided with comprehensive WASH services Bombali, Kambia TBD The MPTF funds was used to support EVD responsible in Tonkolili and Bombali districts. Water well was rehabilitated, 3 additional tap stands constructed to provide water to 50 quarantined households. A submersible pumps was also installed to provide adequate water to Masanga hospital. Under early recovery Programme, the MPTF funds will be used to support the improvement of 13 community water points targeting 3,800 people, in the two districts. The MPTF funds was used to support EVD responsible in Tonkolili district. One water well was rehabilitated, 3 additional tap stands constructed and submersible pumps installed to provide adequate water to the quarantined village The improvement of water points in the targeted communities has commenced and will be reported next month. 10.45% of allotted amount for the project used to support the EVD event in Tonkolili. 2. Number of Health care facilities supported Bombali, Kambia 7 Health facilities Seven health care facilities, serving a catchment population of 35,000 have been identified and will be provided with comprehensive WASH services The provision of WASH services in two health care facilities has commenced and the progress will be reported next month 3. Number of schools with WASH facilities as per Government of Sierra Leone guidelines Bombali, Kambia 10 Public schools 10 primary schools with an estimated 2,000 children have been identified and will be provided with comprehensive WASH during the grant period The provision of WASH services in three schools has commenced and the progress will be reported next month 4. Number of wastage management facilities constructed / installed in health and educational institutions Bombali, Kambia See above based on the need Wastage management facilities are in-cooperated in comprehensive WASH services provided in schools and health care facilities Wastage management facilities are in-cooperated in comprehensive WASH services provided in schools and health care facilities EFFECT INDICATORS (if available for the reporting period) |
| NARRATIVE Situation Update Sierra Leone is one of the West African countries worst affected by the Ebola virus disease. Since the onset of the outbreak in May 2014, the country had reported 8,704 confirmed cases of Ebola and 3,589 deaths, including women and children. 8,624 children that had lost one or both parents due to Ebola have been registered; and over two-thirds of those infected are in the economically active age group. On 7 November 2015, the World Health Organization declared the end of the outbreak in Sierra Leone but two new cases of Ebola were later confirmed in January 2016 in the district of Tonkolili. The new event resulted in quarantined communities across the districts of Tonkolili, Kambia, and Port Loko. |
| Key Achievements COMMUNITY ENGAGEMENT: Following the notification of two EVD cases in Tonkolili, the standard event response SOP for social mobilization and community engagement was immediately activated. As part of the protocol, the social mobilization pillar was activated at the national level within the first 24 hrs of the event notification and an updated messaging guide and response checklist was shared with the district immediately. In all prioritized districts, especially Tonkolili and Kambia, the key social mobilization partners were activated and basic mobilization interventions initiated on the second day of the response. UNICEF through MPTF funding supported the deployment of 250 and 121 social mobilizers in Tonkolili and Kambia respectively. In addition, 20 community stakeholders, four social mobilisers and one Ebola survivor were activated across all 11 chiefdoms in Tonkolili to strengthen community ownership and engagement. In both the districts, the social mobilization team, in close collaboration with the surveillance team raised awareness on importance of early live and death alerts, visits to health facilities for active case search and engaging communities. Extensive engagement of youth leaders was ensured to maintain the link between the communities and retain the trust and faith developed during the response. Intensified engagement was also carried out with the individuals in quarantined homes, their close relatives and friends/communities on preventing stigma and discrimination. As a result, over 51,534 people were reached through interpersonal communication efforts during the response. WASH: UNICEF will continue monitoring the functionality of WASH services in Tonkolili and Bombali districts and strengthening WASH sector coordination. MPTF funds will be used to improve 13 community water points and provide comprehensive WASH services in ten schools and seven health care facilities during the grant period. The identification of the targeted communities, the schools and health care facilities has been completed and the implementation of the activities has commenced. The Programme will report the status of the progress of the ongoing WASH in communities, schools and health care facilities on a monthly basis. |
| Delays or Deviations Based on epidemiological trends, the initial proposition was to utilize MPTF funds for an EVD response in Bombali and Kambia. In light of the EVD emergency, MPTF funds under the Social Mobilization component were utilized for the EVD response in Tonkolili and Kambia as the hot spot districts were shifted from Bombali and Kambia. Since the prediction of next EVD outbreak district is difficult, it is proposed that part of the funds be utilized for strengthening social mobilization pillars across 14 districts of Sierra Leone to develop EVD preparedness plans and the balance for any event response. The short delay in commencement of WASH services in the targeted communities, schools and health care facilities was due to the identification process and the approval by respective districts and stakeholders to ensure prioritization as well as avoiding duplications/overlaps. |
| Gender and Environmental Markers (Please provide disaggregated data, if applicable) No. of Beneficiaries Environmental Markers Women e.g. Medical and Bio Hazard Waste Girls e.g. Chemical Pollution Men Boys Total |
| Additional Information (Optional) |

# Footnotes

The date project funds were first transferred.