RUNO END PRF PROJECT REPORTING					TEMPLATE 4.5

PEACEBUILDING FUND (PBF)

END OF PROJECT report

COUNTRY: Liberia

REPORTING PERIOD: February 2012 - December 2016

| Programme Title & Project Number |  |
| --- | --- |
| Programme Title: Enhancing Access to Security and Justice at the Decentralized Level – Gbarnga Justice and Security Regional Hub, covering Bong, Lofa and Nimba Counties Programme Number (if applicable) PBF/LBR/B-1 MPTF Office Project Reference Number: PBF/00076699 |  |  |

| Recipient UN Organizations |  | Implementing Partners |
| --- | --- | --- |
| List the organizations that have received direct funding from the MPTF Office under this programme: UNDP & UNOPS |  | List the national counterparts (government, private, NGOs & others) and other International Organizations: The Liberian Judiciary and the Ministry of Justice and its law enforcement agencies, including Liberia National Police, Liberia Immigration Services, Solicitor General’s Office, Bureau for Corrections and Rehabilitation; Probation Program; Juvenile Diversion Program; SGBV Crimes Unit and the Independent National Commission on Human Rights |
| Programme/Project Budget (US$) |  | Programme Duration |
| PBF contribution (by RUNO) UNOPS: USD 3,490,000 USD 490,000 UNDP: USD 2,245,000 USD 610,000 |  |  | Overall Duration (months) 48 Months |  |
|  |  |  | Start Date (dd.mm.yyyy) February 7, 2012 |  |
| Government Contribution (if applicable) The Government of Liberia provided the land for the construction of the Hub as "in kind" contribution. Since the operationalization of the Hub in February 2013, the Government has contributed a total of US$2,443,000 for the operationalization of the Gbarnga Hub. In addition, salaries for recruited and trained justice and security actors have been absorbed into Institutions' core budget. |  |  | Original End Date (dd.mm.yyyy) | 31st December 2016 |
| Other Contributions (donors) (if applicable) JSTF: Australian AID USD 1,500,000 GIZ: Probation Program JSTF: Swedish Government (SGBV) - USD 112,500 |  |  | Final End date(dd.mm.yyyy) 31st December 2016 |  |
| TOTAL: | Above USD 10,890,000 |  |  |  |

| Programme Assessment/Review/Mid-Term Eval. |  | Report Submitted By |
| --- | --- | --- |
| Mid-Term Evaluation / Review - if applicable please attach Yes No Date: End of project Evaluation– if applicable please attach Yes No Date: |  | Name: Joyce G. Cassell Frankfort Title: Program Manager Participating Organization (Lead): UNDP & UNOPS and Ministry of Justice Email address: jfrankfort@gmail.com |

PART 1 – RESULTS PROGRESS

  - Assessment of the project implementation status and results

For PRF projects, please identify Priority Plan outcome and indicators to which this project has contributed:

Priority Plan Outcome to which the project has contributed. Outcome 1.1 Enhanced access to justice and community security at the regional and county levels in preparation for UNMIL transition.

Priority Plan Outcome indicator(s) to which project has contributed. 1.1 - % of justice and security services provided by the Gbarnga Regional Hub (disaggregated by Gbarnga, Harper and Zwedru). 1.2 - % of people who feel safe or very safe in their community (disaggregated by county in the Hub region). 1.3 - % of people who trust the court system (disaggregated by Hub region). 1.4 - % of criminal cases adjudicated per court term (disaggregated by type of case and by county). 1.5 - # of trials on SGBV cases held in the Hub regions (disaggregated by county and by court term). 1.6 - # of cases prosecuted by the SGBV CU.

For both IRF and PRF projects, please rate this project’s overall achievement of results to date:

For both IRF and PRF projects, outline progress against each project outcome, using the format below. The space in the template allows for up to four project outcomes.

Outcome Statement 1:  Enhanced access to justice and community security at the regional and county levels in preparation for UNMIL transition.

Rate the current status of the outcome:

Output progress at the end of project

List the key outputs achieved under this Outcome (1000 character limit).Outputs are the immediate deliverables for a project.

Construction of the Gbarnga Regional Hub was completed in 2014. The hub delivers a total of 15 services (see attachment) across three counties - Bong, Lofa and Nimba counties.

Since 2012, a total of 77 LNP PSU officers deployed in the region have supported local police 86 times in response to criminal events that may have curtailed peace, while protecting lives and properties. Officers conducted 93 patrols in 481 communities, improving security and trust in the police.

45 BIN/BPU strengthened border security by conducting 87 visits along Liberia's porous borders with Guinea and  Ivory Coast.

SGBV Crimes Unit processed 410 complaints through hotlines; handled 74 rape and SGBV related cases with merits, prosecuted 48, gaining 36 convictions and provided medical and psycho-social support to 218 victims and their families.

Since 2012, Public Outreach officers raised awareness in 390 communities reaching out to 45,127 residents (25829 Males, 19298 women) and referred 47 complaints.

Outcome progress at the end of project

Describe progress made toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers (3000 character limit)?

Through funding provided by the Government of Liberia, the Gbarnga Regional Hub was operationalised in 2013, construction completed in April 2014. The Ministry of Justice completed the construction of the Cheesemanburg Prison Administration Building in 2013.  With support from international partners and the Government, security institutions were operationally prepared and took over full security responsibilities on 30th June 2016.

The Kahnplay Magisterial Court, one of the four courts approved for construction by the JS Board was inaugurated on the 27th March 2017, improving access to justice for people of that district.

The service delivery component has positively progressed over the years, with 15 services continue to be provided on a regular and successful manner, making the true impact of the programme, the "secondary beneficiaries" - the communities and families that benefit from the improvement in the justice and security institutions in the region. To improve coordination and enhance communications in the sector, the installation of the communication network was completed in 2016.

As compared to 2011, before the Hub was established, and when officers were brought in from Monrovia to quell security instances, the LNP/PSU officers in the region have successfully controlled 86 security incidents that had the propensity to evolve into major conflict drivers.  LNP's ability to quell difficult situations speaks to citizens' confidence in the police in the region and also demonstrates that in the absence of UNMIL presence (UNMIL withdrew in 2013 from the region), LNP can maintain the peace.

The SGBV Crimes Unit, strenghtened by the recruitment, training and deployment of additional assistant county attorneys with focus on the prosecution of gender based violence cases has effectively prosecuted 48 cases over the period and handled 410 cases through their hotlines.  This increase in case load in the region is remarkable, as before the construction of the Hub, there were no trial or conviction of SGBV cases in the region.  This directly speaks to how effective funding provided through PBF encouraged donors such as Australia and the Swedish Governments to continue to provide support to the roll out of such services in other parts of the country.

Through the provision of awareness on hub services, as provided by public outreach officers in all three counties, the use of improved services by residents in the region has increased.  Over the period, through town hall meetings and community dialogues, public outreach officers visited 390 communities, reaching 45,127 participants, of which 19, 298 were female.  In addition , outreach on hub services were provided through radio talk shows, reaching a wider coverage, in which issues relating to the Hub, and referral to community services were discussed.

Several Acts were passed during this period - the Liberia National Police; the Liberia Immigration Services andthe Firearms and Ammunition Control.

Reasons for low achievement and rectifying measures

If sufficient progress was not made, what were the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How were they addressed (1500 character limit)?

During this period, most deliverables were met in a timely manner and did not suffer low achievement.  However, the ineffective water system affects the use of the Hub facilities by more than two hundred officers and criminal justice actors during the "dry season" when ground water level is low.  The JSC approved funds to resolve this problem, however, the disbursement of said funds was not realised.

Outcome Statement 2:

Rate the current status of the outcome:

Output progress at the end of project

List the key outputs achieved under this Outcome (1000 character limit).Outputs are the immediate deliverables for a project.

Outcome progress at the end of project

Describe progress made toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers (3000 character limit)?

Reasons for low achievement and rectifying measures

If sufficient progress was not made, what were the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How were they addressed (1500 character limit)?

Outcome Statement 3:

Rate the current status of the outcome:

Output progress at the end of project

List the key outputs achieved under this Outcome (1000 character limit).Outputs are the immediate deliverables for a project.

Outcome progress at the end of project

Describe progress made toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers (3000 character limit)?

Reasons for low achievement and rectifying measures

If sufficient progress was not made, what were the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How were they addressed (1500 character limit)?

Outcome Statement 4:

Rate the current status of the outcome:

Output progress at the end of project

List the key outputs achieved under this Outcome (1000 character limit).Outputs are the immediate deliverables for a project.

Outcome progress at the end of project

Describe progress made toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers (3000 character limit)?

Reasons for low achievement and rectifying measures

If sufficient progress was not made, what were the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How were they addressed (1500 character limit)?

  - Assessment of project evidence base, risk, catalytic effects, gender at the end of the project

| Evidence base: What was the evidence base for this report and for project progress? What consultation/validation process has taken place on this report (1000 character limit)? | Over the years perception surveys have been conducted to set the baseline for reports submitted. Additionally reports for the program are collected from Heads of criminal justice institutions working as key stakeholders in the program. These reports are then compared with consolidated reports of the Hub Manager and Public Service Outreach Coordinators for the region. Both of these officers are responsible to collect and report on activities of he various institutions for validation. Reports are then compiled by and updates provided to the Sector Finance Committee and the Justice and Security Policy Management Board. |
| --- | --- |
| Funding gaps: Did the project fill critical funding gaps in peacebuilding in the country? Briefly describe. (1500 character limit) | Although the Government of Liberia (GOL) still suffers from the negative financial impact of the Ebola Virus Disease of 2014, the GOL has been able to sustain projects and personnel to the tune of US$2,443,000 for the operationalization of the Hub; thereby filling in critical funding gaps in peace consolidation. Additionally, funding provided by the GOL and international partners to ensure institutions readiness for UNMIL Transition has significantly helped to fill in the critical gaps in the region, as officers were trained, logistically empowered and strategically deployed to ensure peace in the region and throughout Liberia. Giving the GOL Plan for Transition is three years, the GOL focus is still on security preparedness and peace consolidation, even after the deadline of 30th June 2016, recognising that there is still much to be done in reforming the justice and rule of law areas. |
| Catalytic effects: Did the project achieve any catalytic effects, either through attracting additional funding commitments or creating immediate conditions to unblock/ accelerate peace relevant processes? Briefly describe. (1500 character limit) | With support from the JSTF three main services were enhanced in the region - sexual gender based violence cases were effectively processed and survivors provided much needed support; sixty college graduates are currently undergoing a thirteen month training program to become professional magistrates and the infrastructural element of access to justice for the people of the region was improved, as two magisterial courts are being constructed - one fully completed. In supporting the GOL Plan for UNMIL Transition, several development partners provided both financial and professional support to the process. The US government in particular ensured the training of all police support unit and emergency response unit officers and provided US$5 million for the maintenance and expansion of the communications network. The Government of China and their UNMIL contingency in Liberia also supported the peace consolidation process by logistically capaciting security institutions; whilst the UN CT headed by UNMIL worked with institutions to support the development of key legislation and policies to professionalize these institutions. |
| Risk taking/ innovation: Did the project support any innovative or risky activities to achieve peacebuilding results? What were they and what was the result? (1500 character limit) | Providing food for 100 officers assigned at the Gbarnga Regional Hub was initially implemented by an external catering contractor. As it became extremely expensive to maintain, the Program Management Unit of the JSJP initiated an in-house catering service to reduce cost. Initiating this service was a total risk as PMU did not have the expertise to implement. This turned out to be an innovation as it has proven to work effectively and reduce the costs by approximately 60%. Also, the timebound nature of UNMIL turnover of security responsibilities to the GOL was another opportunity to become innovative and / risky, but which proved successful. The PMU was instructed to ensure implementation of the GOL Plan inorder to ensure institutions and officers readiness to take security responsibilities with effect from 1st July 2016. The effective management of projects and activities ensured government's timely takeover of all eight tasks. |
| Gender marker: How have gender considerations been mainstreamed in the project to the extent possible? Is the original gender marker for the project still the right one? Briefly justify. (1500 character limit) | Justice and Security institutions in Liberia have adopted mainstreaming gender in the security sector through a policy first introduced by the Liberia National Police. The Policy now adopted by other agencies, requires institutions to recruit at least 20% women in the sector to reduce the gender disparity between men and women and is proven to be effective in recent recruitments. Training provided for criminal justice actors in 2015/2016 recorded a significant population of women, For example of 104 LNP recruits trained 33 (31.7%) were women The practical gender consideration was seen in the approval of two Barracks being constructed in Yeala and Yekepa, which prioritized space and access to basic facilities for both men and women, taking into consideration the 20% minimum ratio of women to men in the security sector. |
| Other issues: Are there any other issues concerning project implementation that should be shared with PBSO? This can include any cross-cutting issues or other issues which have not been included in the report so far. (1500 character limit) | The Government of Liberia even with evidence of resource constraints has remained committed to sustaining the hub through the provision of recurrent cost through the annual budgets which has made the hub operationally effective over the years. However, the absence of running water during the "dry season" affects the use of the facilities by officers and staff stationed at the Hub. |

1.3 INDICATOR BASED PERFORMANCE ASSESSMENT: Using the Project Results Framework as per the approved project document- provide an update on the achievement of key indicators at both the outcome and output level in the table below. Where it has not been possible to collect data on indicators, state this and provide any explanation in the qualitative text above. (300 characters max per entry)

|  | Performance Indicators | Indicator Baseline | End of project Indicator Target | Current indicator progress | Reasons for Variance/ Delay (if any) | Adjustment of target (if any) |
| --- | --- | --- | --- | --- | --- | --- |
| Outcome 1 Enhanced access to justice and community security at the regional and county levels in preparation for UNMIL transition. | Indicator 1.1 ndicator 1.1 - % of justice and security services provided by the regional hubs (disaggregated by Gbarnga, Harper and Zwedru Hubs) Gbarnga: 15 | Gbarnga 2011: 0% Gbarnga 2014: 100% | December 2016: 100% | Gbarnga : December 2016= 100% |  |  |
|  | Indicator 1.2 % of people who feel safe in their community, disaggregated by county in the Hub region. | June 2012: 65% June 2014:80% (Nimba 85%, Bong 76%, Lofa 77%) | December 2016: % of people who feel safe increased. |  | No new perception survey was conducted after the 2014 survey however, PBO and LISGIS have concluded preparation for the conduct of end of project preception survey which will commence mid 2017. |  |
|  | Indicator 1.3 % of people who trust the court system (disaggregated by county in the Hub region) | Gbarnga Hub: Bong, Lofa and Nimba, June 2012: 37% June 2014: 45% (Bong 57%, Lofa 52, Nimba 32) | Target (December 2016) Increased in the percentage of people accessing the court system. |  | No new perception survey was conducted after the 2014 survey however, PBO and LISGIS have concluded preparation for the conduct for end of project preception survey which will commence mid 2017. |  |
| Output 1.1 Infrastructure, equipment, and systems critical for command, control and operational response put in place for the Regional Hub | Indicator 1.1.1 - % of facilities completed (disaggregated by Gbarnga, Harper and Zwedru Hub) | December 2013 – 97% completed facilities. | Gbarnga Hub December 2016 – 100% | December 2016: Gbarnga:100 |  |  |
|  | Indicator 1.1.2 % of shared regional command, control and communication structures and systems of LNP, BIN and BCR functional at the Gbarnga Regional Hub, disaggregated by 5 factors: 1. infrastructure to house the LNP and BIN regional commanders a | Gbarnga Regional Hub: Dec. 2013: 75% 1.Automated Record case management is at 75%.. 2.SOP for each agency 75% 3. Communications network 61%. 21 of 34 Cellcom GSM towels | December 2016: 100% | December 2016: Automated case management software completed at 100%. SOP for individual institution completed 100% Installation of communication equipment is completed 100% |  |  |
| Output 1.2 Justice and security service providers at the regional hubs level able to provide fair and accountable professional services | Indicator 1.2.1 - # of PSU officers deployed in the Hub regions (disaggregated by Hub) | Gbarnga Hub June 2014: 77 officers in the region based on a rotational or quarterly basis. Gbarnga Hub – 52 PSU officers Nimba – 10 PSU officers Lofa – 15 PSU officers |  | December 2016 Gbarnga : 77 PSU Officers 45 BIN/BPU Officers PSO: 3 officers SGBV: 4 Officers Human Rights Officers : 4 Offficers Prosecutors: 3 County Attorneys Public Defenders:4 |  |  |
|  | Indicator 1.2.2 # of confidence patrols undertaken by the PSU annually | December 2013: Gbarnga Hub region: 11 December 2014:18 |  | November 2016 Gbarnga Hub: 19 |  |  |
| Output 1.3 | Indicator 1.3.1 |  |  |  |  |  |
|  | Indicator 1.3.2 |  |  |  |  |  |
| Outcome 2 | Indicator 2.1 |  |  |  |  |  |
|  | Indicator 2.2 |  |  |  |  |  |
| Output 2.1 | Indicator 2.1.1 |  |  |  |  |  |
|  | Indicator 2.1.2 |  |  |  |  |  |
| Output 2.2 | Indicator 2.2.1 |  |  |  |  |  |
|  | Indicator 2.2.2 |  |  |  |  |  |
| Output 2.3 | Indicator 2.3.1 |  |  |  |  |  |
|  | Indicator 2.3.2 |  |  |  |  |  |
| Outcome 3 | Indicator 3.1 |  |  |  |  |  |
|  | Indicator 3.2 |  |  |  |  |  |
| Output 3.1 | Indicator 3.1.1 |  |  |  |  |  |
|  | Indicator 3.1.2 |  |  |  |  |  |
| Output 3.2 | Indicator 3.2.1 |  |  |  |  |  |
|  | Indicator 3.2.2 |  |  |  |  |  |
| Output 3.3 | Indicator 3.3.1 |  |  |  |  |  |
|  | Indicator 3.3.2 |  |  |  |  |  |
| Outcome 4 | Indicator 4.1 |  |  |  |  |  |
|  | Indicator 4.2 |  |  |  |  |  |
| Output 4.1 | Indicator 4.1.1 |  |  |  |  |  |
|  | Indicator 4.1.2 |  |  |  |  |  |
| Output 4.2 | Indicator 4.2.1 |  |  |  |  |  |
|  | Indicator 4.2.2 |  |  |  |  |  |
| Output 4.3 | Indicator 4.3.1 |  |  |  |  |  |
|  | Indicator 4.3.2 |  |  |  |  |  |

PART 2: LESSONS LEARNED AND SUCCESS STORY

2.1 Lessons learned

Provide at least three key lessons learned from the implementation of the project. These can include lessons on the themes supported by the project or the project processes and management.

| Lesson 1 (1000 character limit) | The use of the training facility at the Gbarnga Hub was not highlighted as a key output in most program reports however, this facility has provided a cost free space for conferences / seminars / workshops that the population to include CSOs, chiefs and other community actors can access to address peacebuilding and rule of law relatedissues. At the end of the program in 2016, 99 trainings / workshops organized by government and civil society organizations, including youth and women groups were held at the Gbarnga Regional Hub. |
| --- | --- |
| Lesson 2 (1000 character limit) | Implementation of activities of the justice and Security Joint Program was speedily implemented when the Justice and Security Policy Management Board met on a monthly. How ever the program was restructured for setting the Board meeting time quarterly. This delayed implementation as decisions and approvals that were required monthly for implementation were made quarterly. |
| Lesson 3 (1000 character limit) | The daily operation of the Gbarnga Justice and Security Regional Hub is an evolving and innovative process. One major lesson learned during this period is that 'access to justice' is not the exclusive responsibility of any one institution, but rather, requires the collaboration of all criminal justice actors working together to ensure that the criminal justice chain is unbroken. |
| Lesson 4 (1000 character limit) | The Gbarnga Hub was never envisaged to respond to a catastrophe, such as the outbreak of the Ebola virus. The financial preparedness of criminal justice actors to respond to such unknown natural and health catastrophies should be taken into consideration in the design and roll out of similar programs going forward. |
| Lesson 5 (1000 character limit) |  |

2.2 Success story (OPTIONAL)

Provide one success story from the project implementation which can be shared on the PBSO website and Newsletter as well as the Annual Report on Fund performance. Please include key facts and figures and any citations (3000 character limit).

PART 3 – FINANCIAL PROGRESS AND MANAGEMENT ARRANGEMENTS

  - Comments on the overall state of financial expenditure

Please rate whether project financial expenditures were on track, slightly delayed, or off track:

If expenditure was delayed or off track, please provide a brief explanation (500 characters maximum):

Please provide an overview of project expensed budget by outcome and output as per the table below.

| Output number | Output name | RUNOs | Approved budget | Expensed budget | Any remarks on expenditure |
| --- | --- | --- | --- | --- | --- |
| Outcome 1: |
| Output 1.1 |  |  |  |  |  |
| Output 1.2 |  |  |  |  |  |
| Output 1.3 |  |  |  |  |  |
| Outcome 2: |
| Output 2.1 |  |  |  |  |  |
| Output 2.2 |  |  |  |  |  |
| Output 2.3 |  |  |  |  |  |
| Outcome 3: |
| Output 3.1 |  |  |  |  |  |
| Output 3.2 |  |  |  |  |  |
| Output 3.3 |  |  |  |  |  |
| Outcome 4: |
| Output 4.1 |  |  |  |  |  |
| Output 4.2 |  |  |  |  |  |
| Output 4.3 |  |  |  |  |  |
| Total |  |  |  |  |  |

  - Comments on management and implementation arrangements

Please comment on the management and implementation arrangements for the project, such as: the effectiveness of the implementation partnerships, coordination/coherence with other projects, any South-South cooperation, the modalities of support, any capacity building aspect, the use of partner country systems if any, the support by the PBF Secretariat and oversight by the Joint Steering Committee (for PRF only). Please also mention if there have been any changes to the project (what kind and when) (2000 character maximum):

Funding for the Justice and Security Joint Program was provided through three funding mechanisms PBF, Trust Fund and GoL budget. Funding provided through the PBF and and the Trust Fund (by bilateral donors) was managed by UNDP and UNOPs with the activities managed either through UNDP's Direct Implementation Modality or the National Implementation Modality by UNDP or its national implementing partner. Funding from the Government of Liberia was managed directly by the Program Management Unit of the Justice and Security Joint Program.The Justice and Security Joint Program coordinated the agencies who were beneficiary of the program from the Government while constant coordination activities were held between UNDP and the Justice and Security Joint Program. The Justice and Security Policy Management Board played and oversight role of the project while working together with Joint Steering Committee for overall supervision of  Liberia's portfolio.

# Footnotes

The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to “Project ID” on the MPTF Office GATEWAY

The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY

As per approval of the original project document by the relevant decision-making body/Steering Committee.

If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed.

Please note that financial information is preliminary pending submission of annual financial report to the Administrative Agent.