| Project Number and Title: Accelerating Progress Towards Interruption of Ebola Response – Report #16: MCA1-Epidemiologist District Management Team | PROJECT START DATE: 19 Dec-2014 | AMOUNT ALLOCATED by MPTF WHO-$3,655,050 UNFPA-$4,549,552 UNDP-$3,398,610 Total: $11,603,212 | RECIPIENT ORGANIZATION WHO, UNDP, UNFPA |
| --- | --- | --- | --- |
| Project ID: 00093252 (Gateway ID) |  |  |  |
| Project Focal Point: Dr. Alex Gasasira (WHO) Sekou Toure, Mamba Point, Monrovia Telephone: +231 77528 1157 gasasiraa@who.int Dr. Remi Sogunro (UNFPA) Sekou Toure, Mamba Point, Monrovia +231 77000 40001 sogunro@unfpa.org Dr. Kamil Kamaluddeen (UNDP) Sekou Toure, Mamba Point, Monrovia +231 77000 4000 kamil.kamaluddeen@undp.org | EXTENSION DATE: 30-05-2015 | FINANCIAL COMMITMENTS WHO-$137,495 UNFPA-$132,170 |  |
| Strategic Objective (STEPP) SO1 – STOP the outbreak | PROJECTED END DATE: 31-12-2015 | EXPENDITURES as of [September 2015] WHO- $2,465,881 UNFPA- $3,000,000 | IMPLEMENTING PARTNER(S): Ministry of Health (MoH), 6 County Health and Social Welfare Teams, Africare, MERCI and Action Aid |
| Mission Critical Action MCA01 – Identify and trace people with Ebola |  |  |  |
| Location (Country or Regional): Liberia | Sub-National Coverage Areas: Bomi, Bong, Gbarpolu, Grand Cape Mount, Lofa, Montserrado, and Nimba Counties. |
| MONTHLY PROGRESS REPORT RESULTS MATRIX OUTPUT INDICATORS Indicator Geographic Area Projected Target (as per results matrix) Quantitative and results for the (one month) reporting period Cumulative results since project commencement (quantitative) Delivery Rate (cumulative % of projected total) as of September Prompt case investigation, identification of all potential contacts, effective data integration % of contacts that have been followed up daily Montserado, Bomi, Bong, Gbarpolu, Grand Cape Mount, Lofa and Nimba 100% No contacts to follow-up due to no new EVD cases N/A N/A Number of active case finders/contact tracers incentivized on time Montserado, Bomi, Bong, Gbarpolu, Grand Cape Mount, Lofa and Nimba 2,802 (August-Dec) Systems to incentivize active case finders are currently being put in place In progress, all contact tracers to be incentivized by October % of community deaths that have been swabbed Montserado, Bomi, Bong, Gbarpolu, Grand Cape Mount, Lofa and Nimba 100% 716 post-mortem swabs collected UNFPA, WHO, UNDP 21%* EFFECT INDICATORS (if available for the reporting period) Number of New EVD cases resulting from unknown transmission chain Montserado, Bomi, Bong, Gbarpolu, Grand Cape Mount, Lofa and Nimba 0 0 EVD cases have been reported during the reporting period 2 2 National strategy and operational plan developed by GoL to integrate EVD surveillance as part of comprehensive IDSR National 1 1 A 6 month IDSR plan has been for Liberia has been drafted. Will be effective Jan 2016 1 100% Proportion of counties with at least 90% of districts submitting weekly surveillance reports Montserado, Bomi, Bong, Gbarpolu, Grand Cape Mount, Lofa and Nimba 100% 100% 100% 100% Proportion of Counties with enhanced active surveillance operations Montserado ,Bomi, Bong, Gbarpolu, Grand Cape Mount, Lofa and Nimba 100% 100% 100% 100% |
| *21% of the projected total of deaths nationwide have been swabbed. Due to a lack of capacity to physically swab every community death in the country, teams have focused on population in high-risk areas and individuals that may be at higher risk at contracting EVD. Figure 1 below shows the actual number so those swabbed, and figure 2 shows the projected community deaths by county. Figure 1: September 2015 Oral Swab Collection Data Week 36 Week 37 Week 38 Week 39 Monthly Total County Aug 31 - Sept 6 Sept 7 - 14 Sept 14 - 20 Sept 21 - 27 Number of swabs collected % population deaths Number of swabs collected % population deaths Number of swabs collected % population deaths Number of swabs collected % population deaths Number of swabs collected % population deaths Bomi 3 15.86% 9 47.58% 9 10.98% 4 21.15% 25 30.50% Bong 2 2.67% 9 12.00% 14 4.31% 15 20.00% 40 12.31% Gbarpolu 0 0.00% 0 0.00% 1 1.23% 0 0.00% 1 1.23% Grand Bassa 5 10.03% 5 10.03% 18 8.33% 15 30.09% 43 19.91% Grand Cape Mount 4 14.00% 5 17.50% 7 5.65% 2 7.00% 18 14.54% Grand Gedeh 3 10.65% 3 10.65% 4 3.28% 6 21.30% 16 13.11% Grand Kru 1 7.68% 0 0.00% 1 1.77% 1 7.68% 3 5.32% Lofa 9 14.46% 17 27.31% 15 5.56% 7 11.24% 48 17.79% Margibi 6 12.71% 15 31.78% 19 9.29% 4 8.47% 44 21.51% Maryland 3 9.81% 3 9.81% 6 4.53% 0 0.00% 12 9.06% Montserrado 71 28.24% 105 41.76% 109 10.00% 87 34.60% 372 34.14% Nimba 14 13.48% 4 3.85% 11 2.44% 8 7.70% 37 8.22% River Cess 8 49.75% 1 6.22% 2 2.87% 2 12.44% 13 18.66% River Gee 14 93.22% 4 26.63% 4 6.15% 2 13.32% 24 36.88% Sinoe 10 43.43% 1 4.34% 6 6.01% 3 13.03% 20 20.05% TOTAL 153 19.57% 181 23.15% 226 6.67% 156 19.96% 716 21.14% Highlighted areas are counties with active project interventions. Figure 2: Project total of deaths by county County Pop. Expected Deaths July August Sept 2015 Month Bomi 99,352 76 28% 26% 30% Bong 393,873 300 4% 10% 22% Cape Mount 150,089 116 17% 19% 16% Gbarpolu 98,489 76 9% 3% 1% Grand Gedeh 147,942 112 9% 9% 15% Grand Bassa 261,840 200 25% 22% 22% Grand Kru 68,401 52 13% 15% 6% Lofa 327,001 248 18% 19% 19% Margibi 247,939 188 28% 22% 27% Maryland 160,556 124 15% 11% 9% Montserrado 1,320,748 1004 46% 32% 39% Nimba 545,696 416 7% 10% 8% River Cess 84,459 64 16% 8% 8% River Gee 78,884 60 20% 18% 18% Sinoe 120,933 92 22% 24% 15% National 4,108,217 3128 25% 21% 24% Figure 3: Dead Alerts per EPI NARRATIVE Situation Update (please describe critical changes, if any, in the situation that affect the project (1-2 paragraphs)) In June/July Liberia experienced resurgence in EVD with six new reported cases. On 3rd September the Ministry of Health (MOH) and WHO declared Liberia free of Ebola transmission in the human population after the country’s last laboratory-confirmed case completed treatment and was confirmed EVD negative. Liberia has subsequently entered a three-month period of heightened surveillance and as of the end of September had completed 28 days into that period. In response to the June/July 2015 outbreak, the implementing partners submitted a revised project extension proposal to MPTF with the objective of enhancing surveillance capacity in Montserrado country, where the majority of the country lives and had the most reported cases, and six additional counties in border areas, which remain at risk due to the continued presence of Guinea and Sierra Leone. The primary goal of the revised project is early case detection and rapid identification of the sick and dead, and their visitors. The extension was approved and the new listing of personnel i.e. contact tracers, supervisors, monitors and coordinators by county has been compiled in close consultation with the various county health teams (CHTs). Work plans for implementing partners has been completed and fund allocation and disbursement process is ongoing to ensure that counties receive support with telephone, internet connectivity and funds for coordination meetings etc. The project has been a collaborative effort between WHO, UNFPA and UNDP. UNDP support ended as of July, and WHO and UNFPA will continue project activities through December 2015. The activities for July- December 2015 include: Supporting outbreak response activities in Montserrado (active case finders, community engagement, cash incentive of response team and operational fund) UNDP supported the payment incentive for July for 4,171 active case finders in Montserrado, refresher training, community engagement and operational costs. WHO continues to support 2,146 active case finders (a 50% reduction from the original number) from Aug to Dec 2015. UNFPA supports the payment of incentive to 123 response teams in Montserrado and provides operational support. Support active case finding in six counties (Bomi, Bong, Gbarpolu, Grand Cape Mount, Lofa and Nimba) with UNFPA supporting incentives through December 2015. UNFPA will continue supporting the 6 mandated counties by incentivizing the 656 active case finders, 176 supervisors 42 monitors and 14 coordinators, as well as training and providing them with operational cost for the extension period July-December 2015. WHO is providing technical and financial support to the 15 counties by deployment of 44 international and national epidemiologists. The team works directly with County Health Teams (CHTs) and partners in the field, in addition to the national epidemiologist team, which works closely with National MOH team. UNFPA field personnel in the counties are supporting the CHTs in ensuring the close monitoring of surveillance and timely reporting. Counties are on course with the monitoring and regular review of contact tracing and active surveillance and timely reporting. Communicating the extension of the UNMEER contact tracing support to counties and planning of new activities were some of the main undertakings in September and all counties successfully submitted final listings of revised numbers for contact tracers as prescribed by the project extension targets. The decision to support Montserrado County Health human resource team was well received by the Ministry of Health and various planning meetings were held to prepare for the agreed activities. In more detail, all county health personnel names, titles and banking details were obtained and clarity was made that UNFPA would only pay allowances for five months beginning August retrospectively. UNFPA had earlier in the year entered a contractual agreement with EcoBank to manage payment of incentives and allowances to any field staff during the response as part of UNFPA’s obligation to the Ministry of Health; and in this regard, this arrangement was activated for the payments to Montserrado County health team. By end of the month, a full list of beneficiaries had been shared with the bank and transfer of payment to the bank had been effected. The bank committed to making full payments for August and September before end of second week of October. Despite the delay to pay incentives for the scaled down contact tracers in the six counties attributable to extension planning for new activities on community engagement and dialogues with counties on revised implementation modality; contact tracers, their supervisors, district monitors and county coordinators have continued to conduct disease surveillance in especially the porous border communities. We have continued to observe timely reporting to Ministry of Health and UNFPA field personnel have continued to support the CHTs in ensuring close monitoring of surveillance, coordination, reviews and timely reporting. Counties are on course with the monitoring and regular review of contact tracing and active surveillance. In addition, profiling of county community structures for the community engagement component of the extension has been completed in four out of the six counties within the month of September. |
| Key Achievements (please use this section to highlight your key achievements for the month, using bullet points if preferred): Continued coordination of contact tracing and monitoring of surveillance activities in the field, especially within border counties. CHVs continue to promote hand washing for prevention of EVD. WHO surveillance teams, in collaboration with CHTs, continued conducting rapid assessment of EVD surveillance performance by district to ensure heightened EVD surveillance. During September ,all 15 counties reported alive and dead alerts, as seen above in Figure 3. The 5-year IDSR Strategic Plan for Liberia 2016-2020 was drafted by the MoH, through the support of WHO AFRO and input from all main health partners. The strategic plan will be effective January 2016. WHO surveillance officers, in collaboration with MoH and CDC, conducted National TOT for IDSR to support county-level IDSR training and future IDSR mentorships. WHO supported training of 65 County Epi and Surveillance Officers from all the 15 counties (including one County Surveillance Officer (CSO) per county) on the Integrated Disease Surveillance and Response (IDSR) from 7-13 September in Buchanan, Grand Bassa County. The 15 CSOs are currently enrolled in the Field Epidemiology Training Program (FETP) supported by CDC/Emory University, where they are gaining theoretical knowledge during the didactic portion and practical skills during their fieldwork in their respective counties. MoH is currently hiring District Surveillance Officer (DSOs) and those that have been recruited are also participating in FETP. Toolkit for IDSR roll-out in counties has been finalized, including developed participants and facilitators guidelines, finalisation of information flow and associated forms- with MOH, CDC and IOM. An ISDR M&E plan is under review for completion shortly to monitor implementation and measure performance of IDSR compliance, including a baseline IDSR assessment at the county and district level an 25% of health facilities. In the final week of September, the baseline assessment of county teams was conducted by WHO and data analysis will be completed in early October. As part of efforts to support intensified surveillance efforts, WHO in collaboration with CDC and FIND supported the expansion of EVD Diagnostic capacity through supporting the training of lab technicians in the use of GeneXpert equipment and installation of this equipment at the ELWA ETU in Monrovia. Processing of payment covering August and September for Montserrado County Health team has been initiated. Mapping/profiling for community engagement was initiated and completed for 4/6 counties. Meetings were held in all six counties to communicate the project extension and obtain support for the community engagement approach as part of project exit. Contact tracing continues to be concentrated in high risk areas especially boarder communities and gCHVs (CT/ACS) are helping to identify and refer sexual and gender based violence and maternal health related cases in communities while promoting hand washing for prevention of EVD. Sustained timely reporting of suspected and probable EVD cases and other disease conditions as part of the disease surveillance on-going. |
| Delays or Deviations (if any, briefly describe the delays or changes in focus, approach or targets, and provide a short justification for the change (1-2 paragraphs)) There has been a change in our previous approach of a door-to-door search for suspected cases of EVD. Since there are no EVD cases currently in the county, the project focus is now reporting all dead bodies in the community to the County Health Team and ensuring they are swabbed. This is crucial, reflecting on our experience in the Margibi County outbreak which could have been more devastating had it not been detected early by the swab team. There was some lost implementation time as a result of harmonizing the various community engagement strategies used by the different UNFPA supported IPs implementing in the six counties. However this was necessary in order to ensure application of the best optimal strategy that would sustain disease surveillance in these counties. |
| Gender and Environmental Markers (Please provide disaggregated data, if applicable) County Number Of Contact Tracers Number Of Female Contact Tracers No. Of Supervisors No. Of Female Supervisors No. Of District Monitors No. Of Female Monitors No. Of County Coordinators Bomi 61 14 12 2 4 0 2 Bong 60 15 14 3 8 0 3 Gbarpolu 38 16 13 2 12 1 2 Grand Cape Mount 92 33 19 3 5 1 2 Lofa 106 10 66 17 7 1 3 Nimba 299 104 52 9 6 0 2 Totals 656 192 176 36 42 3 14 Please explain what strategies are being used to reach out to the most vulnerable sections of the population (women, children, etc) and how it is making a difference. In addition to initial community entry and engagement with relevant opinion leaders, the project community-based approach employs a regular meeting as a strategy in engaging and sensitizing community members on the need to allow bodies of their dead relatives to be swabbed. The community leaders make a regular visit in his community to encourage members of his community to report visitors whose name will be recorded in the visitor’s log book. This approach also facilitates the identification of people sick in the community, taking into consideration the priority diseases and linking to the nearest health facility. Cases identified will also be reported the Zonal Surveillance Officers for coordination and support to the County health Team. |
| Additional Information (Optional) WHO also provides surveillance by screening male survivors for the presence of EVD in semen, to help prevent EVD from being reintroduced through sexual contact with infected survivors. National IDSR Training in Buchanan, Grand Bahassa County in September WHO providing on-site mentorship to lab technicians in Monrovia |

# Footnotes

The date project funds were first transferred.

The Indicators should be disaggregated by gender, age and region as and where applicable