| Project Number and Title: #33- Restoring Midwifery Services in Ebola most-affected counties | PROJECT START DATE: 19-10-2015 | AMOUNT ALLOCATED by MPTF $1,000,000 | RECIPIENT ORGANIZATION United Nations Population Fund |
| --- | --- | --- | --- |
| Project ID: 00096703 (Gateway ID) |  |  |  |
| Project Focal Point: Name: Philderald E. Pratt E-mail:Pratt@unfpa.org gobeh@unfpa.org | EXTENSION DATE: dd-mm-yyyy | FINANCIAL COMMITMENTS $... |  |
| Strategic Objective RSO1 : Health, Nutrition, and Water, Sanitation and Hygiene (WASH) | PROJECTED END DATE: 15-09-2016 | EXPENDITURES as of [date] $. To be reported later | IMPLEMENTING PARTNER(S): Jhpiego (Sub contractee) Ministry of Health (sub contractee) |
| Mission Critical Action RSO1 |  |  |  |
| Location: Country or Regional Liberia/West Africa | Sub-National Coverage Areas: Full list of countries and/or districts Lofa County Gbarpolu County Grand Cape Mount County |
| MONTHLY PROGRESS REPORT RESULTS MATRIX OUTPUT INDICATORS Number of BEmONC facilities providing all signal functions Proportion of met need for EmONC per county Number of clients of family planning who access services from community based distributors of family planning commodities Number of maternal deaths reports and response conducted per county Number of diseases including EVD reported and investigated per county Indicator Geographic Area Projected Target (as per results matrix) Quantitative results for the (one month) reporting period Cumulative results since project commencement (quantitative) Delivery Rate (cumulative % of projected total) as of date Description of the quantifiable indicator as set out in the approved project proposal Output 1: Strengthened capacity of health systems to deliver emergency obstetric and newborn care including management of fistulae in selected health institutions for women and young people. Number of BEmONC facilities providing all signal functions Lofa Grand Cape Mount Gbarpolu 9 0/9 0/9 0% Proportion of met need for EmONC per county Lofa Grand Cape Mount Gbarpolu To be provided next quarter To be provided next quarter To be provided next quarter To be provided next quarter Sub output 1.1: Human Resource capacity is strengthened to ensure quality service delivery Number of international obstetric teams trained and deployed to provide Obstetrical and Gynecological services including medical and surgical services Lofa Grand Cape Mount Gbarpolu 2 0 0 0% Number of national midwives newly recruited, trained and deployed to provide services including Infection Prevention and control (IPC)procedures Lofa Grand Cape Mount Gbarpolu 15 6 6 40% Sub output 1.2: Health facility capacity to provide Maternal Health services including EmONC and family planning Services improved through training, supply of commodities and monitoring Number of BEmONC facilities supported to provide services with full IPC for infection prevention and all 7 signal functions 7days a week 24 hours Targets Lofa = 4 Gbarpolu= 2 GCM= 3 Lofa=1 Gbarpolu = 0 GCM= 0 Progress has been made with most facilities lacking only one or two functions compared to more at baseline 1 health facilities are fully BEmONC compliant while others have partially met with compliance 11% Proportion of Caesarean Sections conducted in CEmONC facilities per county Targets= 10% to 15% for all one hospital 27% of all deliveries during the quarter resulted to Caesarean Section 27% of all deliveries 27% Proportion of women attending four ANC visits per quarter Targets= Lofa and Gbarpolu 70% GCM = 75% Lofa 49%and Gbarpolu 29% GCM = 46% Lofa 49% Gbarpolu 29% GCM = 46% Lofa 49% Gbarpolu 29% GCM = 46% Output 2: Strengthened National Systems for Reproductive Health Commodity Security Number of clients of family planning who access services from community based distributors of family planning commodities Number of clients of family planning who access services from community based distributors of family planning commodities Lofa Grand Cape Mount Gbarpolu Targets= Lofa 80 Gbarpolu 50 GCM = 50 Lofa =0 Gbarpolu =0 GCM =0 Lofa =0 Gbarpolu =0 GCM = 0 0% CHW have been trained but no yet started distribution of FP commodities Proportion of Health facilities with no stock out of essential drugs and medicines Lofa Grand Cape Mount Gbarpolu Targets= 100% of all facilities per county Stock out of antibiotics is still a challenged for few facilities 3/9 facilities have reported no stock out of essential drugs such as antibiotics 33% Proportion of Health facilities with no stock out of at least five modern method of contraceptives Lofa Grand Cape Mount Gbarpolu Targets=100% of all facilities per county Some health facilities reported stock out of one or two Family Planning commodities including Injectable contraceptives and Implants 3/9 facilities have reported no stock out of essential drugs such as antibiotics 33% Number of active community health and development committees that are functional and support community delivery of maternal health services Targets = Lofa= 15 Gbarpolu =8 GCM = 10 Lofa= 6 Gbarpolu =4 GCM = 6 16 CHDC functional 48% Number of CHWs conducting surveillance activities related to ebola prevention and promotion of maternal and newborn health care in project locations Targets Lofa= 150 Gbarpolu = 80 GCM= 100 Quarter Achievements Lofa= 56 Gbarpolu = 34 GCM= 60 Achievements Lofa= 56 Gbarpolu = 34 GCM= 60 45% (The target may have been exaggerated) Number of Community Distributors for FP commodities in targeted Counties Targets Lofa = 80 Gbarpolu =50 GCM= 50 Quarter Achievements Lofa = 15 Gbarpolu =15 GCM= 15 Lofa = 15 Gbarpolu =15 GCM= 15 25%( they have been trained but not initiated distribution Output 3: Enhanced national capacity for Disease surveillance and data availability during humanitarian situation Output Indicators: Number of maternal deaths reports and response conducted per county Number of diseases including EVD reported and investigated per county Proportion of reportable events that occur in targeted communities that are reported and investigated as per protocol Targets= 100% per county Two maternal death and five neonatal deaths 2 maternal deaths and 5 newborn deaths 100% Number of Districts with functional maternal death surveillance and response systems in place Targets= Lofa= 60% Gbarpolu = 60% GCM= 70% All health districts in each county have MNDSR in place as evidenced by the presence of District Surveillance Officers All health districts in each county have MNDSR in place as evidenced by the presence of District Surveillance Officers 100% EFFECT INDICATORS (if available for the reporting period) |
| NARRATIVE Situation Update (please describe critical changes, if any, in the situation that affect the project (1-2 paragraphs)) The project has four main objectives namely; (1) Improve access to quality safe delivery by providing Emergency Obstetric and New born care services to all women in catchment communities of the target health facilities during post ebola period (2) Improve the application of universal precaution/Infection Prevention services in targeted health facilities through training and provision of supplies and lastly (3) increase community engagement and enhance the participation in community surveillance activities through outreach and promotional activities. Progress is being made in restoring routine health services following the EVD crisis as per the project goal. In 2015, most health facilities have reopened and are fully functional. In most EVD high stricken counties such as Lofa and Cape Mount, all heath facilities resumed full functionality. Nevertheless the impact of the EVD crisis on many health facilities still remain. In some instances staff who had abandoned their duties at health facilities for fear of contracting the virus have still have not returned. These health facilities continue to face the impact of staff shortage. Challenges of insufficient equipment and supplies that existed prior to the EVD outbreak still impact the work of health facilities today. Poor geographic access to targeted health facilities also hampers service utilization as in the case of most of facilities Gbarpolu and some parts of Lofa. This project supports health care facilities in situated in three border counties. UNFPA and the MoH are committed to ensuring that health facilities remain fully functional while improving the linkage between community and health facility surveillance activities as well as strengthening health and related services that support the collection and reporting of quality data on maternal deaths for informed decision making. This report provides detailed information on progress and performances of the facilities in selected counties from November 2015 to March 2016. It provides and overview of the assessment conducted in January (already reported in the summary report) and data on service utilization as well as information on various inputs up to date. |

Key Achievements (please use this section to highlight your key achievements for the month, using bullet points if preferred) Skill building: Several trainings of midwives and community health volunteers to improve maternal and newborn care outcomes formed part of interventions for the first quarter of the year as follow; A 5 day pre-deployment training on integrated RMNCAH services and infection prevention and control were conducted for 66 staff averaging 3 per facility in three counties. This was followed by the distribution of IPC supplies including soap, bleach, and hand sanitizer, bucket with faucets & without faucets to targeted health facilities. Identification, training and equipping of 70 Community Health Volunteers in identifying danger signs as well as conduct timely referrals of maternal and new born complication while strengthening the promotion and utilization of services at all levels of the continuum of care. Introduction of performance based reward at all health facilities to motivate care providers was also part of this period’s achievement Coordination and Monitoring During the period under review, other essential health system strengthening activities were implemented at county level as part of efforts to reactivate and strengthen routine health care support systems in each county. The following was achieved in all three counties; Reactivation of RMNCAH coordination in targeted counties including district, facility and community levels through regular meetings were initiated. This activity is geared towards ensuring coordination and ownership of SRMNAH services and interventions at county level. The establishment and nurturing of a mix committee comprising representatives from CHTs, health facilities and community leaderships including quarterly review meetings in targeted counties also formed part of this process to improve RMNCAH coordination. Meeting participants included community leaders from Liberia and Sierra Leone two major meetings were held to in two districts in Gbarpolu (Bopolu and Koungbor) Reactivation and support of monitoring and supervision as well as maternal health commodity distribution activities in three counties and facilities to improve quality of maternal care services including EmONC and family planning indicator(s). The Joint supportive supervision visits for the first quarter of the year was also conducted in all counties. During such visits the following was observed; The MCH monitoring chart, PMTCT ledger and family planning ledgers on the ward were found incomplete at 7 of the 9 health facilities Delivery room in the Gbarngay Clinic were poorly arranged and the Midwife assigned to the facility had been absent for nearly a month The hospital in Lofa had received and conducted 16 C-section cases referred by community health workers. All 16 pregnant women with maternal complications were referred to the referral hospital for surgery and all 16 had favorable outcomes. Storage problems at various health facilities due to increased stock of IPC supplies remains a challenge as spaces for patient care decreases Provision of additional logistical support to counties including communication cards and fuel for to support monitoring activities in each county also formed part of the inputs for the reporting period. The reactivation of existing maternal death surveillance and response mechanisms was also supported to ensure identification, notification, reviews and reporting of maternal /neonatal deaths in targeted communities including border towns between countries. The process included the conduct of meetings with communities and county management teams. This process is work in progress as it requires training of focal persons at various levels of implementation as well as continuous monitoring. Also as per the request of the donor, a joint monitoring activity involving UNFPA and The donor was conducted in Grand Cape Mount County to assess progress. Two health facilities including the Lofa Bridge and the Tienne Clinics were visited. Although the general functionality of the clinic was good, specific issues such as storage of health facility supplies including IPC materials, limited adherence to SOPs and protocols, need for refurbishment as well as some concerns with recording data and completion of ledgers were identified. These weaknesses and gaps will form part of the coming quarter priority areas of focus for improvement. Service Delivery Human Resource: The recruitment and deployment of national midwives has been initiated. Although there have been some challenges in fast tracking the process, 8 midwives have been recruited. Six have been deployed in targeted health facilities mainly in Grand Cape Mount Counties, while the other two are expected to be deployed to Lofa as soon as possible. At the Level of the MoH where the process of recruitment is being conducted, several meetings have been held with the Chief Nursing Officer and the Liberia board of Nursing and Midwifery to fast track the process of recruiting and deploying more midwives in Gbarpolu and Lofa Counties. The office of the Chief Nursing Officer has promised to identify and screen for additional staff for recruitment. In relations to the deployment of Obstetricians and other surgical team members, discussions with the MoH continued during this quarter. UNFPA working closely with the MoH to fast track the process of recruitment as soon as possible. It is worth noting that the process of recruitment is that of the MOH. Facility Utilization: Nine health facilities in three counties (Gbarpolu, Lofa and Grand Cape Mount Counties) have been assisted through various interventions and support as indicated in the detailed report at the level of the county as well as at the level of health delivery points/facilities. Health facility capacity improvement to provide safe maternal health services has been the focus of interventions and support during the reporting period. All 9 facilities received, various medical instruments/equipment and supplies including 25 Reproductive Health Kits of various types. Although most health facilities had some components of IPC supplies distributed to some of these facilities by the MoH, UNFPA and others prior to this project, as part of UNFPA’s commitment to ensuring that health facilities practice infection prevention and control in maternities, a total of 90,500 pieces of Obstetrics and gynecological gloves were procured and distributed to all nine facilities. In addition, 5 labor/delivery beds have been distributed to five of the nine health facilities with the most deplorable delivery beds during the baseline assessment. One operating table was also procured and delivered to the Foya Boma Hospital where the densely populated Foya district population as well as populations from neighboring both Guinea and Sierra Leone towns and villages access obstetric emergency maternal and newborn care services. This donation has increased the number of operating beds by at least one more. Four most deprived post-partum wards/rooms have also been equipped with eight hospital beds and four bed screens for privacy. These delivery rooms have also received assorted instruments and medical supplies including 20 Sphygmomanometer and stethoscope sets and safe /clean delivery kits to improve quality antenatal and post-natal care services. Additional equipment and medical supplies are being procured to ensure the full equipment of all facilities. At the moment, drugs and additional medical devices have arrived in country and a distribution plan has been completed to initiate distribution. All nine health facilities are fully functional, providing a wide range of maternal health services to women and girls in various catchment communities. With the combination of health promotion through various training including IPC, skills building to improve quality and involvement of community health works particularly the traditional birth attendants some health facilities have slightly increased their ANC and health facility deliveries with the exception of the two health facilities in Gbarpolu County. Five out of nine counties have above the national average of ANC 4 coverage as well as have increased their indicator for institutional delivery. With the training of CHWs to improve referral of women to health facilities as opposed to conducting health facility delivery, the number of deliveries conducted at all health facilities is likely to increase during subsequent quarterly update. Health promotion activities have also been initiated by CHWs. Family Planning services continued during this reporting period with a total of 27,838.6 Couple Years of Protection in all nine catchment communities. As the reactivation of maternal death reporting in the county and the health facility catchment community is reinforced the reporting of maternal and newborn deaths reports may see an increase due to more reporting of cases. During this period the Maternal, intrapartum and newborn deaths reported included the following; 6 still birth 2 maternal deaths 7 newborn death Most (80%) of the maternal and newborn deaths were reported by the Foya Boma hospital in Lofa. Below are tables illustrating the performance of health facilities in during the reporting period. Table 1: ANTENATAL & MATERNAL DATA County Facility Catchment Population Annual Expected deliveries Monthly expected pregnancies 1st Antenatal Care visit 4th Antenatal Care visit 2nd IPT Dose for Malaria Prevention Nov to Dec 2015 % Jan-Mar 2016 % Nov to Dec 2015 % Jan-Mar 2016 % Nov to Dec 2015 Jan-Mar 2016 Cape Mount Damballa 9759 488 41 50 61.5 86 70.5 71.00 58.2 71 87.3 41 65 Lofa Bridge 9686 484 40 67 83.0 94 77.6 99.00 81.8 82 67.7 24 66 Tienni 4682 234 20 56 143.5 71 121.3 48.00 82.0 59 100 24 50 Gbarpolu Kungbor 16089 804 67 26 19.4 34 16.9 22.00 10.9 35 17.4 21 34 Gbangay 10992 550 46 33 36.0 60 43.7 30.00 21.8 20 14.6 31 47 Lofa Foya Boma 15742 787 66 146 111.3 121 61.5 60.00 30.5 95 48.3 54 55 Foya Tengia 5989 299 25 49 98.2 39 52.1 77.00 102.9 73 97.5 57 55 Worsonga 4567 228 19 25 65.7 39 68.3 40.00 70.1 10 17.5 20 37 Mendikorma 5321 266 22 51 115.0 71 106.7 89.00 133.8 83 124.8 14 48 Table 3: FAMILY PLANNING SERVICES County Name of Health Facility Catchment Population Implants (Jadelle) oral contraceptives Injectable Contraception Nov- Dec 2015 Jan-Mar 2016 Total CYP Nov- Dec 2015 Jan-Mar 2016 Total oral C Total CYP for Oral C Nov- Dec 2015 Jan-Mar 2016 Total injectable Total CYP Cape Mount Damball 9759 0 2 7.6 68 74 142 2130 194 231 425 1700 Lofa Bridge 9686 1 9 34.2 12 10 22 330 30 36 66 264 Tienni 4682 0 0 0 6 4 10 150 12 18 30 120 Gbarpolu Kungbor 16089 1 2 7.6 93 95 188 2820 285 297 582 2328 Gbangay 10992 3 2 7.6 56 59 115 1725 177 122 299 1196 Lofa Foya Boma 15742 2 3 11.4 9 9 18 270 25 25 50 200 Foya Tengia 5989 8 2 7.6 153 83 236 3540 249 447 696 2784 Worsonga 4567 19 17 64.6 114 101 215 3225 303 450 753 3012 Mendikorma 5321 0 5 19 37 42 79 1185 96 79 175 700 159.6 15375 12304 Note: The cumulative expected deliveries for each period was calculated by multiplying the monthly expected number of deliveries by the total number of months in that period .eg: 41x 2months=82(this number is not mentioned in the table). The proportions were than calculated per period in the following manner, for example of Damballa 50/82*100=61.5% Antenatal visits for all health facilities in Lofa and Grand Cape Mount Counties show a gradual increase from November to March 2016.As shown in the table above the first antenatal visits for the Damballa health center has increased from 61.5 % to 70.5%, while women who attend 4 antennal visits have also increased from 58.2 to 87.3 over the reporting two periods. In the additional two health facilities in the county, although there appears to be a slight reduction in attendance the numbers still remains above the national indicators. In Lofa County, the proportion of women reported to have attended at least four antenatal visits also increased from 30.5 to 48.3% during the two periods assessed, this is an additional 18%. Foya Tengia and Mendikorma clinics have very high utilization of antenatal services (above 100% in some cases). This may be due to the fact that women outside of the catchment area including those residing across the border to Guinea or Sierra Leone also access health services in these facilities due to their proximity to these clinics. Therefore the need to ensure adequate drug and medical supplies to these health facilities remain important. The 17.5% reported for ANC4 visits at the Worsongai Clinic appears to be very low compared to previous months. This may be due to error in reporting or absence of the professional staff assigned to the facility. UNFPA will work with the Ministry of health to verify the information. In Gbarpolu County, the situation presents a rather different picture as all indicators are low (below the national level coverage) despite the current efforts and inputs at the two health facilities. Two factors that may have contribute to the low performance of the facilities, very poor community to clinic road access that is largely characterized by steep hills and makeshift bridges to facilities coupled with long distances from communities to facilities. Koungbor health clinic in Gbarpolu County, the only health facility in the Kongba District (one of the county’s health districts) is a good 5 hour drive from the Lofa Bridge health clinic situated in Grand Cape Mount County and approximately 8 to 9 hours from the referral hospital in Gbopolu city. A total of 70 bridges and more than 123 hills between Lofa Bridge and Koungbor make it nearly impossible for the population to access services due to poor road conditions. It is evident that a maternal waiting home for women move closer to the clinic a month or two prior to delivery or prior to hospital referral schedule remains an essential intervention. Similar to antenatal care visits health facility deliveries in most health facilities have increased. The table below illustrate progress from November 2015 to March 2016. This gradually increasing trend is seen in most health facilities in Grand Cape Mount and Lofa Counties. Six out of nine health facilities had an increase in health facility deliveries ranging from 1 % to 26%. Four of these facilities have proportions equal to or mostly higher than the national level of 56%. Next key actions going forward Discussions and implementation of Local and international procurement as well as delivery and distribution of medical supplies Refurbishment of health facilities with emphasis on maternities Printing and distribution of protocols and Job Aids to improve quality of services More recruitment of staff both local and international Increased monitoring and supportive supervision

Delays or Deviations (if any, briefly describe the delays or changes in focus, approach or targets, and provide a short justification for the change (1-2 paragraphs)) The project encountered some delays during the initial implementation, particularly towards the end of 2015 due to the following reasons; The MoH and Jhpiego are the main implementing partners working with UNFPA on this project. By the time funds were released to UNFPA Liberia funds for the last quarter of the year 2015 had already been released to the MoH and Jhpiego. Therefore UNFPA and partners agreed to focus on the baseline assessment, which was conducted in December 2015. In early 2016 additional delays resulted from various processes associated with the preparation of annual work planning and disbursement of funds to partners during the first quarter of the year. In addition, UNFPA is using the MoH in the recruitment process for the recruitment of local midwives and international Obstetricians which is largely controlled by the MoH with support from UNFPA. Various MoH departments involved in the recruitment process have made it difficult to complete in a timely fashion.

Gender and Environmental Markers (Please provide disaggregated data, if applicable) No. of Beneficiaries Environmental Markers Women 3810 e.g. Medical and Bio Hazard Waste Girls 1905 e.g. Chemical Pollution Men 0 Boys 0 Total 5715 The number of beneficiaries reported for this period were women and girls who accessed maternal health services only

Additional Information (Optional)

# Footnotes

The date project funds were first transferred.

Signal functions are a set of clinical interventions/care/ services that are required to be in place for a health facility to qualify as an Emergency Obstetric and New Born Care Facility and there are nine in total. A facility that provides 7/9 is considered Basic Emergency Obstetric and Newborn Care facility while a facility that provides 9/9 of the services is referred to as a Comprehensive Emergency Obstetric and Newborn Care facility

# Comments

It’s a recovery project that refers to RSO1

Discrepancy with the third I.R. (as of 31 Dec 2015) that reports 8 national midwives trained and deployed

There was an error in the reference report, only 4 midwives had been deployed in Grand Cape Mount County by the end of December. 2 additional once were added by the end of March

Please, provide information about the delays in the effective starting date as included in the NCE submission

# Text boxes

Coordination Meeting in Cape Mount County

DHO Facilitating CHW training on referral and health promotion

IPC supply and CHV Kits distribution

| Table 2: ANTENATAL & MATERNAL DATA 2 |
| --- |
| County | Name of Health Facility | Catchment Population | Annual Expected deliveries | Monthly expected pregnancies | Monthly expected deliveries@4.5% | Actual Health Facility Deliveries |
|  |  |  |  |  |  | Nov to Dec 2015 | % | Jan-Mar 2016 | % |
| Cape Mount | Damballa Health | 9759 | 488 | 41 | 37 | 52 | 47.4 | 67 | 61.0 |
|  | Lofa Bridge | 9686 | 484 | 40 | 36 | 48 | 44.0 | 54 | 49.6 |
|  | Tienni | 4682 | 234 | 20 | 18 | 30 | 57.0 | 44 | 83.5 |
| Gbarpolu County | Kungbor | 16089 | 804 | 67 | 60 | 22 | 12.2 | 18 | 9.9 |
|  | Gbangay | 10992 | 550 | 46 | 41 | 28 | 22.6 | 29 | 23.5 |
| Lofa | Foya Boma Hospital | 15742 | 787 | 66 | 59 | 82 | 46.3 | 102 | 57.6 |
|  | Foya Tengia | 5989 | 299 | 25 | 22 | 47 | 69.8 | 55 | 81.6 |
|  | Worsonga | 4567 | 228 | 19 | 22 | 37 | 54.9 | 33 | 49.0 |
|  | Mendikorma | 5321 | 266 | 22 | 20 | 34 | 56.8 | 28 | 46.8 |