| Project Number and Title: Upgrading water and sanitation systems incorporating skills-based training and employment for youth in Ebola-affected slum communities | PROJECT START DATE: 01-02-2016 | AMOUNT ALLOCATED by MPTF (please indicate different tranches if applicable) $1,000,000.00... | RECIPIENT ORGANIZATION UNICEF ILO UN HABITAT |
| --- | --- | --- | --- |
| Project ID: 00097566 (Gateway ID) |  |  |  |
| Project Focal Point: Name: Patrick Sijenyi E-mail: psijenyi@unicef.org | EXTENSION DATE: DD-MM-YYYY | FINANCIAL COMMITMENTS US$1,000,000 |  |
| Strategic Objective (STEPP) RSO1 - Health, Nutrition, and Water, Sanitation and Hygiene (WASH) | PROJECTED END DATE: 31-01-2017 | EXPENDITURES as of [date] UNICEF: US$207,602 ILO: US$120,000 UN-Habitat: US$23,822 Total US$351,424 | IMPLEMENTING PARTNER(S): Ministry of Public Works; Ministry of Health and Social Welfare; Ministry of Gender and Social Development; Liberia Water and Sewer Corporation; Monrovia City Corporation; Slum dwellers Association of Liberia (SLUMDAL); Ministry of Internal Affairs through local Commissioner. |
| Mission Critical Action MCAn - Description |  |  |  |
| Location: Country or Regional: Liberia | Sub-National Coverage Areas: Full list of countries and/or districts: Clara Town, Monrovia, Montserrado County, Liberia |
| QUARTERLY PROGRESS REPORT RESULTS MATRIX OUTPUT INDICATORS Indicator Geographic Area Baseline/Projected Target (as per results matrix) Quantitative results for the quarterly reporting period Cumulative results since project commencement (quantitative) Delivery Rate (cumulative % of projected total) as of date Description of the quantifiable indicator as set out in the approved project proposal 1(a). Percentage of target group accessing at least 20 liters of water/day/ person Clara Town Baseline: 77% Target: 85% - - 0% 1(b). Maximum distance from household to water point Clara Town Baseline: 500m Target: 200 m - - 0% 1(c). Maximum queuing time at water points Clara Town Baseline: 15min Target: 10 mins - - 0% 1(d). Number of latrines constructed and being used Clara Town Baseline: 11 Target: 20 - - 0% 2(a). Percentage of households gaining access to solid waste management services Clara Town Baseline: 35% Target: 50% To be determined To be determined Current figure to be determined by assessment 2(b). Number of youth groups trained on solid waste management entrepreneurship Clara Town Baseline: 0 Target – 20 5 5 25% 3(a). Number of youths directly engaged in construction of WASH facilities Clara Town Baseline: 0 Target: 2,500 - - 0% 3(b). Number of community groups (consisting of 20 to 50 members) established and trained on maintenance of WASH facilities Clara Town Baseline: 5 Target: 20 5 5 25% 5 community groups trained each consisting of 10 persons 3(c). Number of youths willing to pursue entrepreneurship mentored/trained Clara Town Baseline: 0 Target: 60 60 60 100% All 60 youths selected. Training process 40% done. 4(a). Number of public agencies whose staff is trained on water supply, sanitation and solid waste management Monrovia Baseline: 2 Target: 2 - - 0% EFFECT INDICATORS (if available for the reporting period) |
| NARRATIVE Situation Update (please describe critical changes, if any, in the situation that affect the project (1-2 paragraphs)) |
| Key Achievements (please use this section to highlight your key achievements for the month, using bullet points if preferred) Agreement has been finalised with the Liberia Water and Sewer Corporation (LWSC) for implementation of hardware component of this project. This followed a comprehensive technical assessment by the institution with clear scope and bills of quantities for all proposed civil works - extension of water supply pipeline, construction/ rehabilitation of water supply kiosks and public latrines for the Clara Town community. Discussions with PSI for implementation of sanitation marketing under this project is already at an advanced stage. It is expected that progress on this activity will be reported in next quarterly report. Terms of Reference as well as budget for join training of the five Community Based Organization (CBEs) and Community Management Teams (CMTs) has been drafted and to be finalized by ILO and UNICEF. CBEs are those community based enterprises that are involved in solid waste management. They were recruited and initially trained in solid waste management in May 2016 and have been issued assorted set of basic tools (50 wheel barrows, 50 shovels, 50 pairs of rain boots, 50 pieces of nose marks, 50 pieces of reflector jackets, 50 sweeping brooms, 50 pieces rakes, 50 pairs of hand gloves). Finalizing the procurement process for the purchasing of four (4) metro five-wheeler tricycles for CBEs and the Monrovia City Corporation (3 for CBEs and 1 for the MCC) In consultation with the local authorities/community leadership, the training of 60 youths is ongoing. Youths were selected from the 12 zones of Clara Town to undergo training in semi-skilled construction component of this project. A Technical and Vocational Training (TVET) institution was identified and contracted, through a competitive process, to carry out the training in carpentry, masonry and plumbing. Once trained, the youths are expected to be absorbed as part of the civil works under this project. Administrative modalities near completion for the provision of transportation allowance for the above mentioned students who are currently involved in the practical component of the skills training program. The objective is to ensure at least 85% retention rate. One joint programme monitoring visit conducted in the Clara Town community. The monitoring team consisted of UNICEF, ILO, Local Commissioner Office and office of the UN Mission’s Ebola Multi Partner Trust Fund which was represented by its Planning, Monitoring & Evaluation Officer. Discussions were held with all 5 selected CBEs on their ongoing work activities of solid waste collections, tools and funding received and actions being taken to ensure sustainability beyond project implementation period. |
| Delays or Deviations (if any, briefly describe the delays or changes in focus, approach or targets, and provide a short justification for the change (1-2 paragraphs)) The project initially experienced some delays with civil (construction) phase due to limited availability of experienced in-country partners capable of undertaking comprehensive WASH activities within an urban slum context. Torrential rains which inundated the low-lying community in the rainy season also limited access to the community for a detailed technical assessment by potential contractors. While an agreement was reached with the Liberia Water and Sewer Corporation (LWSC) for preparation of design and implementation of the civil works which entailed extension of water supply pipelines, construction/rehabilitation of waster kiosks/standposts and construction/rehabilitation of public latrines, the implementation start-up was also delayed due to the rains. Discussion is being finalised for implementation of the software element (sanitation marketing programme to raise awareness and enhance the effective demand for improved sanitation) of this project through a Programme Cooperation Agreement (PCA) with PSI, an NGO with tremendous experience in health promotion, sanitation marketing and promotion of household water treatment and storage (HWTS). The closure of the UN Habitat office in Monrovia (Liberia) also necessitated a revision of the programme document including a change to the ProDoc. Reimbursement from UN-Habitat is expected to be completed soon. |
| Gender and Environmental Markers (Targeted – from pro doc - Please provide disaggregated data, if applicable) No. of Beneficiaries 58,481 Environmental Markers Women 14,620 Flooding of some sections of the community due to heavy rainfall in last few weeks Girls 16,471 Men 11,210 Problems with sewerage system in community due to water logging. Boys 16,180 Total 58,481 |
| Additional Information (Optional) |

# Footnotes

The date project funds were first transferred.