# RUNO Half Yearly Reporting 					TEMPLATE 4.3

[COUNTRY: Bosnia and Herzegovina]

PROJECT HALF YEARLY PROGRESS UPDATE

PERIOD COVERED: JANUARY – JUNE 2016

| Project No & Title: | PBF/Dialogue for the Future: Promoting Coexistence and Diversity in Bosnia and Herzegovina |
| --- | --- |
| Recipient Organization(s): | UNDP, UNICEF, UNESCO |
| Implementing Partners (Government, UN agencies, NGOs etc): | Presidency of Bosnia and Herzegovina |
| Total Approved Budget : | 2000000 |
| Preliminary data on funds committed : | 73,046.01 | % of funds committed / total approved budget: | 3.65% |
| Expenditure: | 1,841,127.32 | % of expenditure / total budget: (Delivery rate) | 92.06% |
| Project Approval Date: | October 25, 2013 | Possible delay in operational closure date (Number of months) |  |
| Project Start Date: | 21 July 2014 |  |  |
| Expected Operational Project Closure Date: | 21 July 2016 |  |  |
| Project Outcomes: | To increase citizen engagement in peacebuilding and improve attitudes and perceptions towards coexistence, trust building and appreciation of diversity. |
| PBF Focus Area (select one of the Focus Areas listed below) | Promote coexistence and peaceful conflict resolution. |

# Qualitative assessment of progress

| For each intended outcome, provide evidence of progress during the reporting period. In addition, for each outcome include the outputs achieved. (1000 characters max per outcome.) | Outcome 1: By signing the Declaration and organizing 2 Dialogue Platform Conferences, Project highlighted peacebuilding (PB) efforts in the country (DFF as well as other initiatives), raised issues which impede PB efforts and made adequate recommendations. Representatives of government structures from all levels took active part. Coupled with 40 completed Grant Scheme PB projects,diversity-promoting 20 episodes of TV show "Jump Out", media campaign, capacity development of government partners, NGOs and the media on PB, Project reached out to over one million citizens. Recently, Project completed KAP Study which shows distinction between general youth population and Project beneficiaries relevant to PB. Project effects were highlighted at the meeting between the UNDP Administrator and the Chairman of the BiH Presidency on 20 May 2016, where the Project was specifically mentioned as an example of good practice with proposals for continuation and regional expansion. (http://goo.gl/1B47yC). Outcome 2: With a third round of local forums Project created a grassroot base of activists totaling 378 persons. By providing capacity development and opportunities to cooperate these individuals established links with strong PB results. Example is cooperation established between students of political science universities from Sarajevo, Banja Luka and Mostar. A highly charged topic was used as a PB tool where joint student teams published an anthology in which they researched and wrote about Dayton Peace Accords which stopped the 1992-1995 conflict and established modern-day BiH constitutional setup. Youth Forum Results are each time summarized, analyzed and channeled into Dialogue Platform Conference topics of which closely relate to identified priorities and vice versa. Questionnaires completed by participants indicate significant changes to perceptions of influence on imp.decisions. Outcome 3: All 11 education small-grants have been successfully finalized and post-surveys conducted. Positive changes in perceptions have been recorded in children and youth where, after having benefitted from education activities, many more agreed with the statement „Life in a multicultural society has more positive than negative aspects“ (I wave: 65% children & 74% youth: II wave: 79% children & 77% youth). The majority of expected outcomes and outputs have been exceeded by 50-100%: 5,097 children (of which 97 CwD), 2,197 youth (of which 251 vulnerable youth), 240 teachers, and 38 parents directly benefitted from small-scale projects and 254 trainings/ workshops which encompassed 42 primary and 83 secondary schools in over 70 communities in BiH and the region. Dialogue on peacebuilding in education has been further opened to the general public through 2 live TV dialogue forums which reached a wide audience (cc 500,000). VoY survey is currently underway and results are expected by July 2016. Outcome 4: All small-grants (18 in total) in the field of culture have been successfully implemented. In parallel to the implementation of grants evaluation and monitoring of the implemented activities is carried out. The report shows positive changes in the perception of people especially among beneficiaries of the grants. The diversity of BiH society is being seen as extremely positive aspect and level of appreciation to the life in a multicultural society has been increased for over than 12 %. In general, through the implementation of grants over than 140.000 direct and indirect beneficiaries were reached with DFF project. |
| --- | --- |
| Do you see evidence that the project is having a positive impact on peacebuilding? (1000 characters max.) | Extensive outreach via combination of outputs, with a strong PB message are indicative of Project's wide, positive impact especially at the grassroot level. By supporting dialogue platforms at local and national level,social cohesion between decision-makers and youth developed,exemplified by several new interventions extending beyond Project scope. Majority of Grant Projects reached to youth from ethnically varied parts,whose joint activities developed PB architecture evident to date from ongoing cooperation. Experience from education small-grants shows that after having benefited from individually targeted non-formal education programs, children and youth have become more appreciative of interculturality in BiH. Finally, as media campaign and TV Show reached out to over 1 million viewers, positive stories presented via TV and soc.media platform contributed to trust-building with additional educational effect of understanding differences throughout the country. |
| Were there catalytic effects from the project in the period reported, including additional funding commitments or unleashing/ unblocking of any peace relevant processes? (1000 characters max.) | Project's capacity development interventions ranging from PCM trainings, to youth forums and government Youth Officers and NGOs trainings have all contributed to enhancing the abilities of peacebuilding actors to take peacebuilding interventions at their respective grassroot levels further. A number of youth participants have joined up to develop own initiatives, and a number of NGO organizations reached out to the Project to inform us of their intended interventions in the peacebuilding arena. Projects broad reach is considered extremely usefully in disseminating information and gathering feedback on peacebulding and is thus considered of interest to a majority of peacebuilding actors in the country. Finally, considering its positive impact, the Presidency of BiH expressed interest in expanding DFF Project to a regional platform as part of a regional, peacebuilding Brdo-Brijuni process, which would catalyze Project's interventions to a much larger platform. |
| If progress has been slow or inadequate, provide main reasons and what is being done to address them. (1000 characters max.) | N/A, as the project is being implemented in accordance to the planned schedule. Whilst the Project progress was not slow or inadequate, nor were its effects, common, negative media portreyals, particularly emphasized cyclically, during election campaigns retract Project's peacebuilding effects significantly. Whilst noting freedom of expression as a human right, state lacks the ability to oversee and regulate the media space when it comes to messages which promote hatred and mistrust. Result is a flourishing market of biased, ethno-centric media, usually colluding with particular political party. Such media exists both at national as well as local levels and are hampering peacebuilding processes in the country significantly. |
| What are the main activities/expected results for the rest of the year? (1000 characters max.) | As of June 15, 2016 Project will focus on conducting the Third Dialogue Platform Conference with focus on identified peacebulding priorities stemming from the previous one. Additionally, Project is currently undertaing Voices of Youth Survey whose results will be available shortly, as well as the Final Project Evaluation which will be completed by the end of the Project, July 21, 2016. In addition, Project will continue its regular social media activities and scoping areas of intervention which could be utilized for the next Project phase. |
| Is there any need to adjust project strategies/ duration/budget etc.? (1000 characters max.) | There is no need to make any adjustments at the moment, but some eventual recommendations could be expected from the final evaluation report. |
| What is the project budget expenditure to date (percentage of allocated project budget expensed by the date of the report) – preliminary figures only? (1000 characters max.) | Project budget expenditure to date is 1,841,127.32 USD or 92.06%. |
| Any other information that the project needs to convey to PBSO (and JSC) at this stage? (1500 characters max.) | In general project achieved planned targets and all planned activities were implemented. RUNOs agreed to continue peacebuilding activities through their existent programme portfolios whilst at the same time continuing with development of the next phase of the Dialogue for the Future Project. Such assessment was made given the following: - Guiding Principle of Young People's Participation in Peacebuilding 1.4 indicating peacebuilding interventions should "Promote sustainable, long-term and collaborative initiatives for and with young people, including joint initiatives that build on existing efforts and interventions at scale. Avoid short term projects that will only benefit a few". - Adoption of the Security Council Resolution 2250 which inter alia calls on "measures that support local youth peace initiatives…". - As reiterated in the approved request for a six (6)-month non-cost extension of the Project, the Presidency at its 11th regular session on 20 August, 2015 reached a conclusion expressing its full support for the ongoing activities within the Project and provided support for continuation and extension of the Project’s activities. - Presidency remarks were reiterated during the meeting between the UNDP Administrator and the Chairman of the BiH Presidency on 20 May 2016, where the Project was specifically mentioned as an example of good peacebuilding practice in BiH with suggestions for continuation and regional expansion. (http://goo.gl/1B47yC). |

INDICATOR BASED PERFORMANCE ASSESSMENT: Using the Project Results Framework as per the approved project document- provide an update on the achievement of key indicators at both the outcome and output level in the table below. Where it has not been possible to collect data on indicators, state this and provide any explanation in the qualitative text above. (250 characters max per entry)

|  | Performance Indicators | Indicator Baseline | End of project Indicator Target | Current indicator progress | Reasons for Variance/ Delay (if any) | Adjustment of target (if any) |
| --- | --- | --- | --- | --- | --- | --- |
| Outcome 1 Established dialogue spaces for decision makers, civil society and citizens that enable country-wide peacebuilding process to promote coexistence, trust building and appreciation of diversity. | Indicator 1.1 Dialogue and Peacebuilding Platform developed. | 2014: No Dialogue Platform | 2015: All elements of the dialogue platform functioning. | Target reached. Third envisaged Dialogue Platform Conference is due to be held 27.06.2016 at the BiH Parliemantary Assembly. | No. | Target moved to 2016 as per approved non-cost extension. |
|  | Indicator 1.2 Number of articles/stories positively depicting peacebuilding, tolerance, multiculturalism and non-violent conflict resolution in select media outlets. | 2014: Number captured through baseline analysis at the start of the project. | 2015: Number increased by a least 10% by the end of the project. | 2014: (jan-apr) = 226. 2016: (jan-apr) = 700 Percentage change = 309% increase | No | Target moved to 2016 as per approved non-cost extension. Earlier reported number corresponded with number of reported stories through DFF project. |
|  | Indicator 1.3 |  |  |  |  |  |
| Output 1.1 Establishment of Dialogue and Peacebuilding Platform. | Indicator 1.1.1 MoU Signed | 2013: No MoU | 2014: Signed MoU | Target reached. MoU/Declaration signed between BiH Presidency and UN RC in April 2015. | No. | No. |
|  | Indicator 1.1.2 High-level conferences of the Dialogue Platform held. | 2014: No conferences held | 2015: 3 Conferences Held | On track. Two conferences held. Final conference to be held in July 2016. | No. | Target moved to 2016 as per approved non-cost extension. |
| Output 1.2 Small Projects and Grant Facility (GF) is established to support local and civic initatives promoting peaceful coexistence, trust building, intercultural dialogue and appreciation of diversity. | Indicator 1.2.1 No. of small projects implemented (500-50,000 USD) | 2014: Calls for proposals conducted in 2014 | 2015: At least 15 projects implemented | Target exceeded. 40 projects successfully completed activities. | No. | No. |
|  | Indicator 1.2.2 n/a |  |  |  |  |  |
| Output 1.3 Awareness raised and interest generated among the broader population for participation in the dialogue Platform and Grants Facility. | Indicator 1.3.1 TV Show produced and broadcasted nationwide | 2014: No TV Show | 2015: Up to 10 episodes of the TV show producted and broadcast nationwide. | Target exceeded. 20 episodes of the TV show aired in the period May - November 2015. | No. | No. |
|  | Indicator 1.3.2 Web Platform Developed | 2014: No Web Platform | 2015: Web Platform | Target reached. https://goo.gl/1llqyE | No. | No. |
| Outcome 2 Increased participation, awareness and influence of youth and youth civil society organizations in policy dialogue with decision makers on issues impacting BiH's development and reform agenda | Indicator 2.1 Strengthened youth participation in policy development and governmental initiatives. | 2014: Assessment of existing youth participatory mechanisms | 2015: At least 3 sessions/ conferences organized through platform for the duration of the programme; establish new or strengthen existing youth participation mechanisms with the government. | Target reached. 2 Dialogue Platform Conferences held. One capacity development exercise for governments' Youth Officers and NGOs held. | No. | No. |
|  | Indicator 2.2 Nation-wide youth network established dedicated to intercultural understanding and dialogue. | 2014: No dedicated youth network | 2015: Network members from all parts of the country, at least 3 intiatives instigated by the network for the duration project. | Target reached. Dialogue Platform (380+) conferences and local Youth Forums (378) bring together young people from across BiH. | No. | No. |
| Output 2.1 Work stream established within the Dialogue Platform for youth and youth civil society organizations that provides and opportunity to influence policy making in on all key development issues in the country and in relation to improving intercultural. | Indicator 2.1.1 Workshops and training sessions held/study trips organized | 2014: 0 | 2015: At least three trainings and workships conducted, at least two study trips conducted | Target reached. PCM training conducted in five BiH cities. Study trips organized. | No. | No. |
|  | Indicator 2.1.2 No. of projects per area of intervention supported. | 2014: N/A | 2015: At least one project per area of intervention supported | Target reached. The Grants Facility has supported multiple projects in all areas. | No. | No. |
| Output 2.2 | Indicator 2.2.1 |  |  |  |  |  |
|  | Indicator 2.2.2 |  |  |  |  |  |
| Output 2.3 | Indicator 2.3.1 |  |  |  |  |  |
|  | Indicator 2.3.2 |  |  |  |  |  |
| Outcome 3 Education and peacebuilding initiatives support greater social cohesion at national level and in targeted communities. | Indicator 3.1 No. of boys and girls and youth who benefited from implemented trainings and small- scale projects on quality inclusive intercultural education. | B 2014: 0 | T 2015: At least 3,000 children (in targeted schools) | Indicator exceeded- 5,097 (2158 M, 2939 F) children and 1,746 (668 M, 1078 F) youth benefited from 254 trainings/ workshops and 11 small-scale projects which were implemented in over 70 local communities in BiH and region | No | No |
|  | Indicator 3.2 Opinion of targeted children/youth towards interculturalism and tolerance improved. | B 2015: 65% children and 74% youth fully/ partially agrees that life in a multicultural community has more positive than negative effects. | T 2015: +10% change in opinion. | Indicator partially met: 79% children and 77% youth fully/partially agrees that life in a multicultural community has more positive than negative effects | Experience from education small-grants shows that the same type of activity had a stronger, more positive effect on children (<18) than on older youth and adults, who require longer interventions to yield more substantial changes in their opinions. | No. |
| Output 3.1 Policy-makers, education professionals, civil society and other relevant stakeholders at different levels have discussed the importance of peacebuilding, diversity and social cohesion in the field of education. | Indicator 3.1.1 No. of local forums held. | B 2014: no local forums. | T2015: 3 local forums held. | Indicator reached - 3 regional forums on inclusive, intercultural education held with 59 participants (M20, F39); the importance of peacebuilding and diversity in education discussed within 2 live TV dialogue forums with close to 500,000 viewers. | The chanelling of dialogue through live TV program resulted in participation and interest of wider general public in ongoing discourse on the importance of peacebuilding, diversity and social cohesion in the field of education. | No. |
|  | Indicator 3.1.2 No. of initiatives supported. | B 2014: no initiatives supported. | T 2015: at least 5 initiatives supported. | Indicator reached- 5 initiatives promoting inclusive, intercultural education have been implemented by 7 NGOs encompassing cc 200 children and youth. | No. | No. |
| Output 3.2 Educational institutions CSOs and other partners have collaborated to promote peacebuilding, diversity and social cohesion in the field of education. | Indicator 3.2.1 School based programmes implemented. | B 2014: n/a | T 2015: At least three school based programmes implemented. | Indicator exceeded-Through 11 education small-scale projects, cooperation was established with 42 primary and 83 secondary schools, mostly in BiH but also the region. | No. | No. |
|  | Indicator 3.2.2 Trainings and workshops organized. | B 2014: n/a | T 2015: At least 3 organized. | Indicator exceeded- through 11 education projects 254 trainings, workshops and seminars for 1506 children and youth, 183 teachers, 38 parents and 40 NGO staff members were successfully held. | Original target projections have been surpassed as a result of receiving a large number of quality applications through the small grants facility, allowing for a larger number of trainings for a larger, more diverse, target group. | No. |
| Output 3.3 Vulnerable groups strengthened their capacities to be equally included in the decision-making process at the municipal/local level. | Indicator 3.3.1 Workshops conducted. | T2014: n/a | B 2015: At least 5 workshops conducted | Indicator exceeded - 10 entrepreneurship workshops successfully held targeting Roma youth (176) and youth with disabilities (139) from 23 BiH municipalities. | Each vulnerable group has specific needs and requires a specific approach. To strengthen the capacities of 2 groups of vulnerable youth (Roma and youth with disabilities) workshops were separately held for each target group (5 workshops x 2 groups). | No |
|  | Indicator 3.3.2 Initiatives implemented. | T2014: n/a | B2015: At least three initiatives implemented | Indicator exceeded - Based on 146 entreprenuership inititiaves proposed through workshops, 10 have been selected and implemented benefitting 150 vulnerable youth. | No | No |
| Outcome 4 Citizens and communities promote culture, intercultural dialogue, trust building and appreciation of diversity to advance common peacebuilding goals. | Indicator 4.1 Culture issues addressed through the Platform conferences in support of UNESCO Universal Declaration on Cultural Diversity and 2005 Convention on the Protection and promotion of Diversity of Cultural Expressions. | B 2014: n/a. | T 2015: At least one session on culture issues in the Platform conferences. | Target exceeded, specific culture session took place and both conferences held so far. | NA | NA |
|  | Indicator 4.2 % change of citizens’ perceptions of the following. | B 2012/2013, List of 11 statements with percentage baseline indicators, as per original LF | T 2015: 5% positive change in responses of general population in comparison to values captured in 2013 research. | As per evaluation and monitoring reports, positive change has exceeded expected level of 5%. | NA | NA |
| Output 4.1 Enhancing intercultural dialogue and fostering the role of culture through the Dialogue Platform. | Indicator 4.1.1 Workshops conducted | B 2014: n/a | T 2015: At least three workshops conducted | Ten workshops, forums and round tables for youth and vulnerable groups have been held in Brcko, Banja Luka, Mostar, Tuzla, Derventa and Livno, as part of the approved projects, with participation of prominent social influencers. | NA | NA |
|  | Indicator 4.1.2 |  |  |  |  |  |
| Output 4.2 Increasing participation and engagement by citizens, civil society and leaders in intercultural dialogue activities and initiatives. | Indicator 4.2.1 Initiatives implemented. | B 2014: n/a | T2015: At least 5 initiatives implemented. | Target fully reached Mapping of relevant stakeholders and projects is completed in cooperation with DPA office and all grants implemented were addressing themes of diversity, trust-building and intercultural understanding. | NA | NA |
|  | Indicator 4.2.2 Research and analysis projects | B 2014: n/a | T 2015: At least three research and analysis projects. | Authorities mainstreamed in govt policies and grants promotion of civic and intercult. dialogue,trust-bdg and respect for diversity.8 grantees impl. projects on promotion of cultural heritage. Based on research 2 thematic documentaries recorded. | NA | NA |
| Output 4.3 Vulnerable groups empowered to promote social inclusion, diversity, gender equality and peacebuilding in the field of culture. | Indicator 4.3.1 CSOs representing vulnerable and marginalized groups participating at the Dialogue Platform conferences. | B 2014: n/a | T 2015: At least three CSOs. | This target has been fully achieved as two conferences held so far were attended by five CSOs representing marginalized groups. | NA | NA |
|  | Indicator 4.3.2 Initiatives implemented. | B 2014: n/a | T 2015: At least 3 implemented. | Three initiatives are implemented and two particular documentary films were made, promoting marginalized groups. | NA | NA |

# Footnotes

Please note that where there are multiple agencies, only one consolidated project report should be submitted.

Approved budget is the amount transferred to Recipient Organisations.

# Funds committed are defined as the commitments made through legal contracts for services and works according to the financial regulations and procedures of the Recipient Organisations. Provide preliminary data only.

# 4 Actual payments (contracts, services, works) made on commitments.

5 PBF focus areas are:

PBF Focus Areas are:

1: Support the implementation of peace agreements and political dialogue (Priority Area 1):

(1.1) SSR, (1.2) RoL; (1.3) DDR; (1.4) Political Dialogue;

2: Promote coexistence and peaceful resolution of conflicts (Priority Area 2):

(2.1) National reconciliation; (2.2) Democratic Governance; (2.3) Conflict prevention/management;

3:Revitalise the economy and generate immediate peace dividends (Priority Area 3);

(3.1) Employment; (3.2) Equitable access to social services

4) (Re)-establish essential administrative services (Priority Area 4)

(4.1) Strengthening of essential national state capacity; (4.2) extension of state authority/local administration; (4.3) Governance of peacebuilding resources (including JSC/ PBF Secretariats)