# RUNO Half Yearly Reporting 					TEMPLATE 4.3

[COUNTRY: KYRGYZSTAN]

PROJECT HALF YEARLY PROGRESS UPDATE

PERIOD COVERED: JANUARY – JUNE 2016

| Project No & Title: | PBF/Peace and reconciliation through strengthening the rule of law and human rights protection |
| --- | --- |
| Recipient Organization(s): | Regional Office for Central Asia of the UN High Commissioner for Human Rights (OHCHR ROCA) |
| Implementing Partners (Government, UN agencies, NGOs etc): | Department for Judicial Reform and Rule of Law of the Office of the President of the Kyrgyz Republic; Apparatus of the Government of the Kyrgyz Republic; Judicial Training Centres under the Supreme Court and the General Prosecutor's Office; National Mechanism for the Prevention of Torture; Coordination Council on Human Rights under the Government |
| Total Approved Budget : | 1065753 |
| Preliminary data on funds committed : | US $ 839.137,00 | % of funds committed / total approved budget: | 90,07 % |
| Expenditure: | US $ 839.137,00 | % of expenditure / total budget: (Delivery rate) | 90,07 % |
| Project Approval Date: | 20/12/2013 | Possible delay in operational closure date (Number of months) | N/A |
| Project Start Date: | 01/07/2014 |  |  |
| Expected Operational Project Closure Date: | 30/09/2016 |  |  |
| Project Outcomes: | Key legislation in the area of administration of justice is in line with international and constitutional human rights standards and the judiciary adjudicates several cases in line with these standards; Adequate functioning of national human rights mechanisms and civil society actors leads to effective protection of human rights and increased accountability for their violations, including through holistic follow up to UN HRM recommendations; Duty bearers and right holders engage in dialogue about the importance of addressing grave human rights violations committeed during and in the aftermath of June 2010 events |
| PBF Focus Area (select one of the Focus Areas listed below) | Promote coexistence and peaceful resolution of conflicts |

# Qualitative assessment of progress

| For each intended outcome, provide evidence of progress during the reporting period. In addition, for each outcome include the outputs achieved. (1000 characters max per outcome.) | Outcome 1: 1) As a result of OHCHR's technical and expert support to the Expert Working Groups and relevant Parliamentary Committees, seven draft laws (including the Criminal Procedure Code) have been approved in first and second reading in the Parliament and now incorporate human rights standards related to the administation of justice; 2) After delivering two Trainings of Trainers (ToTs) and six trainings for judges and prosecutors on international and national human rights standards, OHCHR is now consolidating the material used for the trainings into a human rights manual and course to be institutionalized within the training curricula by the Judicial Training Centre (JTC) and the Prosecutors Training Centre (PTC). Outcome 2: 1) The NPM is staffed, present in 7 provinces and operates in line with OPCAT guiding principles, having full access to places of deprivation of liberty. OHCHR supported the development of internal administrative instructions to harmonize the work of NPM departments. Authorities are aware of the mandate of the NPM and the NPM produced three annual reports that were approved by the Parliament; the Parliament dropped draft amendments to the Law on the NPM; 2) After having trained over 80 young lawyers on international human rights standards, who now reference international human rights provisions in their case-work, OHCHR is consolidating the material used for the trainings into a human rights manual and course to be institutionalized within the training curricula by the Lawyers Training Center and Bar Association; 3) OHCHR provided two grants to NGOs in southern Kyrgyzstan to monitor the human rights situation and emerging human rights trends. Outcome 3: OHCHR held preliminary discussions on transitional justice with key interlocutors, including the Ministry of Justice, the Office of General Prosecutor and the Presidential Administration. After these discussions, it became clear that at the moment State authorities are reluctant to launch initiatives aimed at restoring justice for victims and trust among communities. Therefore OHCHR decided to approach the topic by including sessions on transitional justice in the trainings to the judiciary, as well as building the capacity of judges and prosecutors to deal with and implement views of UN Human Rights Mechanisms, some of which are related to the 2010 events Outcome 4: |
| --- | --- |
| Do you see evidence that the project is having a positive impact on peacebuilding? (1000 characters max.) | 1) Seven draft laws incorporating human rights standards have been approved by the Parliament in second reading. CPC and CC have been harmonized; 2) The NPM submitted three comprehensive annual reports on monitoring places of detention, including data disaggregated by gender, ethnicity and locations, and recommendations for state authorities; 3) Beneficiaries of capacity building activities on human rights standards, in particular young lawyers in the south of Kyrgyzstan, judges and prosecutors expressed positive feedback on the contents of the training activities and the impact of human rights knowledge in their work and requested additional trainings; 4) Two NGOs received grants to monitor human rights developments in southern Kyrgyzstan; 5) NHRAP is being developed to implement 664 human rights recommendations received by Kyrgyzstan |
| Were there catalytic effects from the project in the period reported, including additional funding commitments or unleashing/ unblocking of any peace relevant processes? (1000 characters max.) | 1) By advocating with the Government for strenghtening the role of the Coordination Council on Human Rights in coordinating follow up to recommendations from UN HRMs and with donors for supporting the efforts of this mechanism, OHCHR was able to raise the profile of the inter-agency body and mobilize additional funding from various donors; 2) The training material developed by OHCHR for the trainings of lawyers, judges and prosecutors has been used to form the human rights curricula of the training centres. OHCHR was able to attract additional funding from other donors to replicate training sessions. |
| If progress has been slow or inadequate, provide main reasons and what is being done to address them. (1000 characters max.) | 1) Slow progress on output 2.2, draft stategic plan to ensure comprehensive follow up to recommendations by UN HRM, is due to low capacity of the Secretariat and the complexity of organizing the high amount of recommendations received. OHCHR has developed a Compendium of recommendations to help the authoritues cluster recommendations. It served as a starting point to develop a NHRAP; 2) Slow progress in output 3.1 is due to the reluctunce of State authorities to discuss transitional justice issues, fearing that the topic could steer resentment in the communities and inter-ethnic strife. OHCHR is addressing the challenge by adapting the activities to the context, focusing more on capacity building and awareness raising activities on transitional justice for the judiciary; 3) Output 1.2 adapted: the Supreme Court has a new Chairperson. OHCHR was informed that the SC is of the opinion that there are not enough cases related to torture to justify a resolution on unification by SC Plenum. |
| What are the main activities/expected results for the rest of the year? (1000 characters max.) | Main activities/results expected to take place before the end of the year: 1) Additional trainings on human rights for young lawyers, including on freedom of religion or belief and Housing Land and Property; 2) Additional trainings for judges and prosecutors on human rights, including FoRB; 3) Awareness raising activities on transitional justice, including workshops targeting state authorites and judges on implementation of views of the UN Human Rights Committees related to 2010 events; 4) Finalization of human rights manuals for lawyers, prosecutors and judges; 5) Implementation of grants by two NGOs to monitor and report on human rights situation in the south of Kyrgyzstan; 6) Public consultations with civil society on draft NHRAP. |
| Is there any need to adjust project strategies/ duration/budget etc.? (1000 characters max.) | For output 1.2, project strategy was amended as the Supreme Court formally communicated that there will be no unification of judicial practice on cases related to torture due to the low number of cases registered. For output 3.1, since State authorities are reluctant to discuss transitional justice issues, fearing that the topic could steer resentment in the communities and inter-ethnic strife, OHCHR adapted the strategy and the activities to the context, focusing more on capacity building and awareness raising activities on transitional justice for the judiciary |
| What is the project budget expenditure to date (percentage of allocated project budget expensed by the date of the report) – preliminary figures only? (1000 characters max.) | 90,07 % |
| Any other information that the project needs to convey to PBSO (and JSC) at this stage? (1500 characters max.) | N/A |

INDICATOR BASED PERFORMANCE ASSESSMENT: Using the Project Results Framework as per the approved project document- provide an update on the achievement of key indicators at both the outcome and output level in the table below. Where it has not been possible to collect data on indicators, state this and provide any explanation in the qualitative text above. (250 characters max per entry)

|  | Performance Indicators | Indicator Baseline | End of project Indicator Target | Current indicator progress | Reasons for Variance/ Delay (if any) | Adjustment of target (if any) |
| --- | --- | --- | --- | --- | --- | --- |
| Outcome 1 Key legislation in the area of administration of justice is in line with international and constitutional human rights standards and the judiciary adjudicates several cases in line with these standards | Indicator 1.1 Degree of compliance of key laws relating to the administration of justice with international and human rights standards | Current criminal procedure code and other key laws are not fully in compliance with international human rights standards | A new Criminal Procedure Code is adopted and the laws mentioned are amended, largely in compliance with international human rights standards by 2015 | Seven draft laws (including the Criminal Procedure Code) have been approved in first and second reading in the Parliament and now incorporate human rights standards related to the administration of justice |  |  |
|  | Indicator 1.2 |  |  |  |  |  |
| Output 1.1 Technical and expert support is provided to the Secretariat of the National Council on Judicial Reform and its Expert Working Groups on elaborating the key laws relating to the administration of justice in line with international human rights standar | Indicator 1.1.1 Number of key draft laws relating to the administration of justice elaborated by the EWGs and submitted for public discussions | Three draft laws were partially elaborated by EWGs in 2013 | Draft of key laws relating to the administration of justice are elaborated by EWG and submitted for public discussion - three by end 2014; three by end 2015 | Seven draft laws (including the Criminal Procedure Code) have been approved in first and second reading in the Parliament and now incorporate human rights standards related to the administration of justice |  |  |
|  | Indicator 1.1.2 |  |  |  |  |  |
| Output 1.2 Technical assistance and capacity building provided to the Supreme Courte judges and staff regarding unification of judicial practices in criminal cases | Indicator 1.2.1 Number of resolution adopted by the Supreme Court regarding unified judicial practice on criminal cases | No such resolution has thus far been adopted by the Supreme Court on criminal cases | One such resolution adopted by the Supreme Court by June 2016 | ROCA conducted a research on unification of judicial practice on cases related to torture. The summarized judicial practice for cases related to torture that occurred up to mid 2015. | In early 2016, the Supreme Court formally communicated that there will be no unification of judicial practice through a resolution of the Supreme Court Plenum on cases related to torture due to the low number of cases registered | OHCHR continues supporting the Supreme Court in analysing trends in cases related to torture and producing statistics, with disaggregated data, as well as with the implementation of medical documentation standards included in the Istanbul Protocol. |
|  | Indicator 1.2.2 |  |  |  |  |  |
| Output 1.3 A human rights training package is developed with Supreme Court's Judiciary training centre and Center for Professional Training of Prosecutors | Indicator 1.3.1 Extent to which human rights are institutionalized in the training curricula of JTC and CPTP | The training curricula do not currently included human rights and will have to be updated in line with the new legislation | By end 2016, the training curricula if JTC and CPTP are updated and institutionalize human rights | By mid-2016, ROCA developed a 4-day training on human rights in administration of justice and delivered ToTs to 25 judges of the JTC and 25 prosecutors of CPTP; six additional trainings for judges and prosecutors delivered | OHCHR is now consolidating the material used for the trainings into a human rights manual and course to be institutionalized within the training curricula by the Judicial Training Centre (JTC) and the Prosecutors Training Centre (PTC) |  |
|  | Indicator 1.3.2 |  |  |  |  |  |
| Outcome 2 Adequate functioning of national human rights mechanisms and civil society actors leads to effective protection of human rights and increased accountability for their violations, including through holistic follow up to UN HRM recommendations | Indicator 2.1 Extend to which targeted national human rights mechanisms (NPM and CCHR) function effectively in line with their respective mandates and international human rights standards | The NPM is in the process of being established following law adopted in 2012. The Government established CCHR in 2013 to follow up on recommendations of UN HRMs. | By 2016, both national mechanisms function in line with their mandates, good practices and international human rights standards. | The NPM is staffed and present in 7 provinces. It operated in line with OPCAT guiding principles; 3 annual reports approved by Parliament. Since beginning 2016, there has been slow progress with the CCHR and the development of the NHRAP. | Slow progress in drafting the NHRAP, meant to ensure follow up to recommendations, is due to low capacity of the Secretariat, the complexity of organizing the high amount of recommendations and the fact that CCHR heavily relies on OHCHR experts. |  |
|  | Indicator 2.2 Extend to which young lawyers and NGO carry out their casework and monitoring and reporting, with reference to international human rights standards | There is lack of young defense lawyers and NGOs carrying out monitoring which refers to international human rights standards |  | By mid-2016, ROCA trained around 90 young lawyers from the south and north and conducted eight trainings on international human rights standards, lawyers skills, and conflict mediation for young lawyers | OHCHR is now consolidating the material used for the trainings into a human rights manual and course to be institutionalized within the training curricula by the Lawyers Training Center and Bar Association |  |
| Output 2.1 Institutional support provided to the newly established NPM and capacity building on monitoting places of deprivation of liberty is provided to the staff and members of the Coordination Council | Indicator 2.1.1 Number of reports following monitoring visits are produced by the NPM | Zero reports as the NPM has yet to start functioning | By mid-2015 the NPM issues 4 reports following monitoring visits, by mid-2016 the NPM issues 4 reports following monitoring visits | By mid-2016, the NPM issued 3 annual reports including analysis of information gathered during the monitoring visits conducted in 2013, 2014 and 2015. | The NPM produces its annual report at the end of each year. Thus far, the NPM has produced three annual reports that were approved by the Parliament. |  |
|  | Indicator 2.1.2 |  |  |  |  |  |
| Output 2.2 Institutional support and capapcity building on human rights law and strategic planning is provided to the newly established inter-ministerial entity that will follow up on UN HRM recommendations | Indicator 2.2.1 Existence of a draft strategic plan to ensure a comprehensive follow up to recommendations from UN HRM | No such comprehensive strategic plan exist | A strategic plan to follow up on recommendations by UN HRM is drafted by June 2015 | The CCHR established two working groups: one to draft the national human rights action plan and one to develop procedures to implement views of UN Committees. Both WGs include civil society organizations, but progress has been slow so far | Slow progress with drafting NHRAP to ensure comprehensive follow up to recommendations is due to the low capacity of the Secretariat, complexity of organizing the high amount of recommendations and the fact that CCHR heavily relies on OHCHR experts | Draft national human rights action plan expected by end-2016 |
|  | Indicator 2.2.2 |  |  |  |  |  |
| Output 2.3 Capacity building for young defence lawyers from multi ethnic towns and districts of southern kyrgyzstan on protecting human rights in criminal proceedings Output 2.4 Technical support and grants provided to faciliate human rights monitoring repor | Indicator 2.3.1 Number of cases addressed by the trained young lawyers to national and international mechanisms on alleged human rights violations with reference to international and national human rights standards | Zero | 5 cases by June 2015 and 5 cases by June 2016 refer to international human rights standards | At least in five cases, young lawyers confirmed having used the knowledge and skills acquired in trainings in their work. A lawyer used knowledge on human rights standards to submit a report to UN HRM and others submitted individual complaints | OHCHR organized a specific training for lawyers and human rights defenders from the south on preparing and submitting human rights violations to UN Committees in May 2016 |  |
|  | Indicator 2.3.2 Indicator 2.4 Number of public reports produced by NGOs documenting cases of HR violations in the south | Not available | By June 2016, two public monitoring reports with specific recommendations for the Gvt are produced by NGOs on HR issues in the south | By mid-2016, two NGOs from southern Kyrgyzstan have been awarded grants to monitor emerging human rights trends in the south of Kyrgyzstan |  |  |
| Outcome 3 Duty bearers and right holders engage in dialogue about the importance of addressing grave human rights violations committeed during and in the aftermath of June 2010 events | Indicator 3.1 Extent of undersnading among duty bearers and right holders of the importance of effectively addressing human rights violations committeed during and in the aftermath of June 2010 violence | Currently, there is little understanding among duty beares and right holders on the concept of justice for the past and its tools | Increasing understanding of the importance of addressing human rights violations of June 2010 violence | By mid-2016, ROCA held discussions on transitional justice issues with the Ministry of Justice, the Office of General Prosecutor, the Presidential Administration and Supreme Court. |  |  |
|  | Indicator 3.2 |  |  |  |  |  |
| Output 3.1 Awareness raising and capacity building of duty bearers and right holders regarding justice for 2010 violence | Indicator 3.1.1 Number of duty bearers and right holders whose awareness is raised and capacity is strenghtened about mechanisms and tools to address human rights violations including those committeed in the past | Low awareness and capacity of duty bearers and right holders about mechanisms and tools to address human rights violations, including those committeed in the past | By 2016, awareness raising and capacity building of at least 50 duty bearers and 50 right holders on mechanisms and tools to address human rights violations, including those related to the past, are raised and strenghtened | By mid-2016, ROCA held discussions on transitional justice issues with the Ministry of Justice, the Office of General Prosecutor, the Presidential Administration and Supreme Court. | State authorities are reluctant to discuss transitional justice issues, fearing that the topic could steer resentment in the communities and inter-ethnic strife. | OHCHR is addressing the challenge by adapting the strategy and the activities to the context, focusing more on capacity building and awareness raising activities on transitional justice for the judiciary |
|  | Indicator 3.1.2 |  |  |  |  |  |
| Output 3.2 | Indicator 3.2.1 |  |  |  |  |  |
|  | Indicator 3.2.2 |  |  |  |  |  |
| Output 3.3 | Indicator 3.3.1 |  |  |  |  |  |
|  | Indicator 3.3.2 |  |  |  |  |  |
| Outcome 4 | Indicator 4.1 |  |  |  |  |  |
|  | Indicator 4.2 |  |  |  |  |  |
| Output 4.1 | Indicator 4.1.1 |  |  |  |  |  |
|  | Indicator 4.1.2 |  |  |  |  |  |
| Output 4.2 | Indicator 4.2.1 |  |  |  |  |  |
|  | Indicator 4.2.2 |  |  |  |  |  |
| Output 4.3 | Indicator 4.3.1 |  |  |  |  |  |
|  | Indicator 4.3.2 |  |  |  |  |  |

# Footnotes

Please note that where there are multiple agencies, only one consolidated project report should be submitted.

Approved budget is the amount transferred to Recipient Organisations.

# Funds committed are defined as the commitments made through legal contracts for services and works according to the financial regulations and procedures of the Recipient Organisations. Provide preliminary data only.

# 4 Actual payments (contracts, services, works) made on commitments.

5 PBF focus areas are:

PBF Focus Areas are:

1: Support the implementation of peace agreements and political dialogue (Priority Area 1):

(1.1) SSR, (1.2) RoL; (1.3) DDR; (1.4) Political Dialogue;

2: Promote coexistence and peaceful resolution of conflicts (Priority Area 2):

(2.1) National reconciliation; (2.2) Democratic Governance; (2.3) Conflict prevention/management;

3:Revitalise the economy and generate immediate peace dividends (Priority Area 3);

(3.1) Employment; (3.2) Equitable access to social services

4) (Re)-establish essential administrative services (Priority Area 4)

(4.1) Strengthening of essential national state capacity; (4.2) extension of state authority/local administration; (4.3) Governance of peacebuilding resources (including JSC/ PBF Secretariats)