# RUNO Half Yearly Reporting 					TEMPLATE 4.3

[COUNTRY: Kyrgyzstan]

PROJECT HALF YEARLY PROGRESS UPDATE

PERIOD COVERED: JANUARY – JUNE 2016

| Project No & Title: | PBF/KGZ/A-5; MPTF 00089448 "Youth for Peaceful Change" |
| --- | --- |
| Recipient Organization(s): | UNICEF; UNDP |
| Implementing Partners (Government, UN agencies, NGOs etc): | State Agency for Youth Affairs, Physical Culture and Sports (former Ministry of Labour Migration and Youth) , Ministry of Education and Science, Ministry of Social Development, Agency for Local Self-Governance and Interethnic Relations, State Commission on Religious Affairs of the Kyrgyz Republic, LSG bodies, Defense Council |
| Total Approved Budget : | 605,825 USD (UNICEF: 243,318; UNDP: 362,507) |
| Preliminary data on funds committed : | UNICEF: 3,860USD UNDP: 42,232 USD | % of funds committed / total approved budget: | UNICEF: 1.6% UNDP: 11.6% |
| Expenditure: | UNICEF: $239,458 UNDP: $320,275 | % of expenditure / total budget: (Delivery rate) | UNICEF: 98.4% UNDP: 88.4% |
| Project Approval Date: | December 12th, 2013 | Possible delay in operational closure date (Number of months) |  |
| Project Start Date: | March 7th, 2014 |  |  |
| Expected Operational Project Closure Date: | September, 30th, 2016 |  |  |
| Project Outcomes: | Outcome 2.9: Vulnerable young women and young men at-risk have better opportunities to acquire civic participation skills to positively engage in society and develop respect for diversity. Outcome 2.10: Vulnerable young women and young men at-risk express their concerns, participate in decision-making at various levels and have better access to economic opportunities to reduce the likelihood of youth involvement in violent conflict. |
| PBF Focus Area (select one of the Focus Areas listed below) | Priority Area 3. |

# Qualitative assessment of progress

| For each intended outcome, provide evidence of progress during the reporting period. In addition, for each outcome include the outputs achieved. (1000 characters max per outcome.) | Outcome 1: 37 people are attending the "State youth policy" course, which was added to the curriculum (per year 45 public servants can also attend). 17 local public servants have attended a 6-month professionalization program covering rights and freedoms, active citizenship, monitoring of services, forming interest groups and youth engagement in peacebuilding. 28 young leaders that completed the course in 2014 are cooperating with local represenatives from LSGs and have organized youth-led trustbuilding events that have been attended by 6616 young people. In 2016 17 LSGs allocated 114,903 USD for youth work. Project trainings conducted on leadership, development project proposals, street workout campaigns, gender and conflict sensitivity; 400 youth representatives participated, more than 36% were young girls from pilot communities. 16 grant proposals to support youth initiatives were funded in 2016 for an amount exceeding USD 66,176 and will create at least 80 jobs for local youth. Outcome 2: Ten plans for youth development in target communities were implemented with the help of local youth last year. But this year the plans received Local Governments approval and partial funding. In fact, these are young people who were directly involved in the management and decision-making processes at the local level. The youth action plans instituionalized with the guide for LSGs on “How to develop a local youth strategy” that has been issued. 4 LSGs have already developed their local youth strategy using this guide book. Outcome 3: Outcome 4: |
| --- | --- |
| Do you see evidence that the project is having a positive impact on peacebuilding? (1000 characters max.) | No violent conflicts involving youth are seen in target communities at the current stage. Supposedly, the project has a positive effect on peace and sustainability in target communities. By enriching the country’s educational system with specializations in youth work through the new "State youth policy" course , as well as by building professional capacity of local authorities, the project has contributed to the institutionalization of a system that is building a shared civic identity and enables new generations to escape societal divisions. |
| Were there catalytic effects from the project in the period reported, including additional funding commitments or unleashing/ unblocking of any peace relevant processes? (1000 characters max.) | The project prompted important system level changes, as youth work has also been introduced in the MA course on municipal and public service. In six of the pilot communities municipalities have created youth comittees as a specific department attached to them. 43,015 USD was allocated for youth committees in 2015. In 2016 17 LSGs have allocated 114,903USD for youth work. In 3 communities out of 10 where youth plans were supported, the funding provided by local authorities was direclty allocated to youth comitees for further independent plan implementation. This shows that local youth received access to local development management. The position of Specialist for work with youth was introduced in Aktash municipality in frames of LSG staffing structure. |
| If progress has been slow or inadequate, provide main reasons and what is being done to address them. (1000 characters max.) | n/a |
| What are the main activities/expected results for the rest of the year? (1000 characters max.) | The national youth strategy will be finalized and the roles to be established for governmental actors on youth issues will be discussed and clarified through law implementation. Support will be provided for the implementation of 16 youth grants, which will ensure the achievement of all goals and expected results. Finalize an assessment of project implementation will be finalized during the summer of 2016, particularly to interview local youth and partners, assess achieved results and to analyze the level of project impact on the peacebuilding processes. |
| Is there any need to adjust project strategies/ duration/budget etc.? (1000 characters max.) | An unforeseen governmental restructuring has occurred by abolishing the Ministry of Labor, Migration and Youth, dividing the youth sector into the policy development section under the Ministry of education and Science and the implementation part under the State Agency for Youth issues, Physical culture and Sport. Therefore, more time is needed to build the professional youth work into the system, both locally and nationally, that will have a lasting and sustainable impact on reducing youth’s sense of exclusion and marginalization. In order to match the project interventions with the new governmental structure of the youth sector and to achieve better results the project teams request a non-cost extension of the project for 3 months (until September 30) with no budget changes. |
| What is the project budget expenditure to date (percentage of allocated project budget expensed by the date of the report) – preliminary figures only? (1000 characters max.) | Allocated project budget expenditure: UNICEF: 98.4% UNDP: 88.4% UNFPA:100% |
| Any other information that the project needs to convey to PBSO (and JSC) at this stage? (1500 characters max.) | n/a |

INDICATOR BASED PERFORMANCE ASSESSMENT: Using the Project Results Framework as per the approved project document- provide an update on the achievement of key indicators at both the outcome and output level in the table below. Where it has not been possible to collect data on indicators, state this and provide any explanation in the qualitative text above. (250 characters max per entry)

|  | Performance Indicators | Indicator Baseline | End of project Indicator Target | Current indicator progress | Reasons for Variance/ Delay (if any) | Adjustment of target (if any) |
| --- | --- | --- | --- | --- | --- | --- |
| Outcome 1 Vulnerable young women and young men at-risk have better opportunities to acquire civic participation skills to positively engage in society and develop respect for diversity | Indicator 1.1 Number of youth in LSGs targeted by the project who advocate for equal access to services together with youth from other ethnic groups. | 61% | 20% increase in number over baseline by end of 2016 | on track |  |  |
|  | Indicator 1.2 |  |  |  |  |  |
|  | Indicator 1.3 |  |  |  |  |  |
| Output 1.1 | Indicator 1.1.1 |  |  |  |  |  |
|  | Indicator 1.1.2 |  |  |  |  |  |
| Output 1.2 | Indicator 1.2.1 |  |  |  |  |  |
|  | Indicator 1.2.2 |  |  |  |  |  |
| Output 1.3 | Indicator 1.3.1 |  |  |  |  |  |
|  | Indicator 1.3.2 |  |  |  |  |  |
| Outcome 2 Vulnerable young women and young men at-risk express their concerns, participate in decision-making at various levels and have better access to economic opportunities to reduce the likelihood of youth involvement in violent conflict | Indicator 2.1 % increase in constructive participation of youth in decision-making processes at all levels | Only 3 out of 14 LSGs has platforms for youth work and youth concerns mainstreamed into local development plans supported through local budget. Youth represent 11% of LSG staff and occupy mainly mid and low level positions (to consider LSGs as key de | 15% increase in number over baseline by end of 2016 | No violent conflicts involving youth are seen in target communities at the current stage. Supposingly, the project has a positive effect on peace and stability in target communities. |  |  |
|  | Indicator 2.2 % of vulnerable young women and young men that are optimistic (think positively) about their future (and their future opportunities) | 63% | 10% increase in number over baseline by end of 2016 | on track |  |  |
| Output 2.1 | Indicator 2.1.1 # of development strategies and policies with inclusion and guaranteed budgetary stipulation addressing needs and priorities of young men and young women | 3 | at least 13 local and national level | 10 plans for youth development received Local Governments approval and partial funding. 7 Youth development plans received nearly 28 000 USD as local budget support. |  |  |
|  | Indicator 2.1.2 |  |  |  |  |  |
| Output 2.2 | Indicator 2.2.1 |  |  |  |  |  |
|  | Indicator 2.2.2 |  |  |  |  |  |
| Output 2.3 | Indicator 2.3.1 |  |  |  |  |  |
|  | Indicator 2.3.2 |  |  |  |  |  |
| Outcome 3 | Indicator 3.1 |  |  |  |  |  |
|  | Indicator 3.2 |  |  |  |  |  |
| Output 3.1 | Indicator 3.1.1 |  |  |  |  |  |
|  | Indicator 3.1.2 |  |  |  |  |  |
| Output 3.2 | Indicator 3.2.1 |  |  |  |  |  |
|  | Indicator 3.2.2 |  |  |  |  |  |
| Output 3.3 | Indicator 3.3.1 |  |  |  |  |  |
|  | Indicator 3.3.2 |  |  |  |  |  |
| Outcome 4 | Indicator 4.1 |  |  |  |  |  |
|  | Indicator 4.2 |  |  |  |  |  |
| Output 4.1 | Indicator 4.1.1 |  |  |  |  |  |
|  | Indicator 4.1.2 |  |  |  |  |  |
| Output 4.2 | Indicator 4.2.1 |  |  |  |  |  |
|  | Indicator 4.2.2 |  |  |  |  |  |
| Output 4.3 | Indicator 4.3.1 |  |  |  |  |  |
|  | Indicator 4.3.2 |  |  |  |  |  |

# Footnotes

Please note that where there are multiple agencies, only one consolidated project report should be submitted.

Approved budget is the amount transferred to Recipient Organisations.

# Funds committed are defined as the commitments made through legal contracts for services and works according to the financial regulations and procedures of the Recipient Organisations. Provide preliminary data only.

# 4 Actual payments (contracts, services, works) made on commitments.

5 PBF focus areas are:

PBF Focus Areas are:

1: Support the implementation of peace agreements and political dialogue (Priority Area 1):

(1.1) SSR, (1.2) RoL; (1.3) DDR; (1.4) Political Dialogue;

2: Promote coexistence and peaceful resolution of conflicts (Priority Area 2):

(2.1) National reconciliation; (2.2) Democratic Governance; (2.3) Conflict prevention/management;

3:Revitalise the economy and generate immediate peace dividends (Priority Area 3);

(3.1) Employment; (3.2) Equitable access to social services

4) (Re)-establish essential administrative services (Priority Area 4)

(4.1) Strengthening of essential national state capacity; (4.2) extension of state authority/local administration; (4.3) Governance of peacebuilding resources (including JSC/ PBF Secretariats)