RUNO END PRF PROJECT REPORTING					TEMPLATE 4.5

PEACEBUILDING FUND (PBF)

END OF PROJECT report

COUNTRY: Kyrgyzstan

REPORTING PERIOD: 01.01.2015-31.12.2016

| Programme Title & Project Number |  |
| --- | --- |
| Programme Title: Women as Peaceful Voters&Women as Candidates. Programme Number (if applicable) MPTF Office Project Reference Number: ID00093224l |  |  |

| Recipient UN Organizations |  | Implementing Partners |
| --- | --- | --- |
| List the organizations that have received direct funding from the MPTF Office under this programme: UNDP, UNICEF (UNRCCA – strategic partner) |  | List the national counterparts (government, private, NGOs & others) and other International Organizations: National Council on Gender Equality under the Government of KR (coordinating body is a Gender Policy Department of Ministry of Social Development), Central Electoral Commission, NGOs |
| Programme/Project Budget (US$) |  | Programme Duration |
| PBF contribution (by RUNO) USD 985,000.00 |  |  | Overall Duration (months) 24 |  |
|  |  |  | Start Date (dd.mm.yyyy) 01.01.2015 |  |
| Government Contribution (if applicable) |  |  | Original End Date (dd.mm.yyyy) | 30.06.2016 |
| Other Contributions (donors) (if applicable) |  |  | Final End date(dd.mm.yyyy) 31.12.2016 |  |
| TOTAL: | USD 985,000.0 |  |  |  |

| Programme Assessment/Review/Mid-Term Eval. |  | Report Submitted By |
| --- | --- | --- |
| Mid-Term Evaluation / Review - if applicable please attach Yes No Date: End of project Evaluation– if applicable please attach Yes No Date: 31.12.2016 |  | Name: Elmira Shishkaraeva Title: Country Programme Gender Coordinator Participating Organization (Lead): UNDP UNICEF Email address: elmira.shishkaraeva@undp.org |

PART 1 – RESULTS PROGRESS

  - Assessment of the project implementation status and results

For PRF projects, please identify Priority Plan outcome and indicators to which this project has contributed:

Priority Plan Outcome to which the project has contributed.

Priority Plan Outcome indicator(s) to which project has contributed.

For both IRF and PRF projects, please rate this project’s overall achievement of results to date:

For both IRF and PRF projects, outline progress against each project outcome, using the format below. The space in the template allows for up to four project outcomes.

Outcome Statement 1:  Women in priority PRF areas, especially women from minorities, exercise their electoral rights and participate in voting during parliamentary and municipal elections in 2015-2016

Rate the current status of the outcome:

Output progress at the end of project

List the key outputs achieved under this Outcome (1000 character limit).Outputs are the immediate deliverables for a project.

The project in total has engaged 16 local women’s and youth NGOs, who developed the national raising awareness interventions on women’s and youth's active participation in elections. Several knowledge management and advocacy materials were released for a wide-range of target audiences. Formal and informal meetings with the public were conducted, covering around 88,588 people. A TV series was released to create a positive image of women deputies and women on decision- making positions, the Central Election Committee was supported in releasing the Public Service Announcements(PSAs) that call women for active and self-paced participation in the Parliamentary elections, well-known TED Talks with prominent women-candidates and women-parliamentarians was organized in Osh/Bishkek, messages on active women's participation was spread covering all the country. An innovative tool in approaching women-candidates was used in a format of a board game that became popular among beneficiaries.

Outcome progress at the end of project

Describe progress made toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers (3000 character limit)?

According to the OSCE official statements, the parliament elections in Kyrgyzstan were conducted in a transparent and democratic way. The local elections will take place on December 11, 2016. The project provided opportunities for women in pilot communities and especially for women from ethnic minorities to get access to information on upcoming elections and specificities of the election process. The project was launched by consultations with the government and the civil society in January 2015. As a result of public consultations, stakeholders agreed on and developed a strong ownership for the project approaches, strategies and activities to be carried out. In view of this, the decision was made to reach every woman-voter, and to make this happen non-traditional ways of approaching electorate were implemented (“political” discourse tea meetings, door-to-door visits, meetings with the female religious groups, side-events in the kindergardens and schools). In Kyrgyzstan women, particulary in rural communities, sometimes are not allowed to participate in community meetings due to different reasons that are common to partiarchal society norms. Women are withdrawn from possibilities of communication within such kind of meetings. This way the project covered a wide range of women, who usually are not active in social life and the information on importance of peace and non-conflict processes of the elections was spread. The close cooperation with the Central Election Committee was targeted to convincing women of different ages, ethnic groups to participate in the elections since their ability to vote correlates to legitimate and democratic processes.

Reasons for low achievement and rectifying measures

If sufficient progress was not made, what were the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How were they addressed (1500 character limit)?

Due to changes in electoral legislation (biometrics principles that require additional steps from the voters to participate in elections), the number of voters had decreased. This change was foreseen at risk matrix "Frequent reshuffling in and lack of coordination between government units". Unplanned biometrics introduction withdrew many voters, including women, from voters' list. The project addressed this challenge through the revision of awereness and media campaigns with purpose to explain voters, particularly at local level, the new procedures.

Outcome Statement 2:  Women and men in priority PRF areas, especially youth, actively promote peaceful elections and engage in electoral debates, including on issues relating to gender equality and gender-based violence

Rate the current status of the outcome:

Output progress at the end of project

List the key outputs achieved under this Outcome (1000 character limit).Outputs are the immediate deliverables for a project.

IP “Agency of Social Technologies” NGO has developed its’ own research methodology on Gender Rating of political parties. It is the system of public monitoring of political parties to evaluate the gender sensitivity for the certain period, based on four key measures. Public poll was conducted to reveal the level of gender credit of political parties. In order to wide-promote and discuss the results- media coverage, meetings and seminars as well as provision of the platform to initiate the discourse on the results of the gender rating system of political parties were put in place. .Informational campaign “Learn. Act. Decide” for youth was conducted in target communities with coverage of 1481 participants. Young people trained on electoral rights, on debate skills and on civic journalism to share their views and observations during elections. The knowledge on electoral right of young people increased.

Outcome progress at the end of project

Describe progress made toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers (3000 character limit)?

The Prime minister of the country confirmed that in all polling stations there were no incidents or other conflict related developments as of national parliament elections. This confirms that the elections in Kyrgyzstan went in a peaceful and democratic manner in autumn 2015 and spring 2016. The project provided its’ input into the smooth process by running activities in pilot areas and interacting with the political parties and candidates. In pilot areas, the project initiated the process of integrated risk evaluation on upcoming elections. The objective of the evaluation was to inform the communities on how to react to possible conflict situations. The informational-targeted activity on the specificities of the election process with the community groups, like youth, ethnic and religious groups, provided a basis to peaceful processes of election and understanding the situation better. One of the lessons learnt from the previous elections on the work of women’s organizations with the political parties was to strengthen the involvement of the latter in women’s empowerment, thus during the present elections, women’s NGOs generated the idea of the necessity of strengthening accountability and transparency of political parties’ election campaigns. This was done through pressure from civil society and mass media. “Gender Rating” research was targeted at political parties’ and candidates’ positions and actions to take on women’s and youth empowerment. It was communicated by the project to politicians that gender issues should be voiced in public and should stand central to electoral debates, in order for the political processes be more responsive to the needs of women and youth. The results of the gender rating were widely published in media to inform as many electoral as possible on policies and activities of the political parties. To increase the effect of the intervention, the implementing partner worked directly with the political parties to underline the importance of promoting gender aspects throughout the activities. The theory of change is still relevant. In addition, the UNDP BPPS funded several trainings based on Gender Raing results to increase capacities of political parties and their members

Reasons for low achievement and rectifying measures

If sufficient progress was not made, what were the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How were they addressed (1500 character limit)?

Outcome Statement 3:  Women in selected areas, especially women from minorities, run as candidates during municipal elections in 2016

Rate the current status of the outcome:

Output progress at the end of project

List the key outputs achieved under this Outcome (1000 character limit).Outputs are the immediate deliverables for a project.

Within this Outcome 5 Women's Leadership schools were organized to capacitate women from pilot areas to run for elections.They were engaged into understanding the general principles of women's empowerment as well as developing their election campaign. Not only women but their networks to support them in elections were engaged. To strengthen the links between the local candidates and the national Parliament, current MPs were invited to most of the events to support candidates and provide mentorship. At the same time legal support was available for women in case issues occur during the elections. The first elections to local councils were held in March and the second are foreseen for December 11. Women were engaged into advocacy platforms to establish 30% gender quota at local levels, initiated by a women MP. More than 10 000 signatures were collected together with women's movement and submitted to the President of KR. Two additional schools for women were conducted with OSCE

Outcome progress at the end of project

Describe progress made toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers (3000 character limit)?

The leadreship schools preparation demanded direct activities aimed at identifying active women candidates who were interested in local elections. Thus it was a direct synergy of the partners who carried out the informational campaign and handed over the potential women-candidates to the next activity. It contributed to positive environment in supporting women potential candidates to run for local elections, as well as for voters in their understanding of gender equality and justice. Provided link between the local and national level of parliament by the Project made it possible to understand grass-root issues and created a platform of their active interaction. MPs mentors voiced the needs of local women-candidates on parliament sessions which made it possible to promote the new draft law on 30% gender quota for local councils from first to second hearings.

Reasons for low achievement and rectifying measures

If sufficient progress was not made, what were the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How were they addressed (1500 character limit)?

New amendment to the election code (article 17, 2 paragraph) restricts participation of state employed management personnel  to participate in local elections as candidates which will decrease the number of women-candidates in elections. This cohort of women had more chances to be elected due to formal and informal leadership skills (secondary school principals, doctors etc.). The change in electoral legislation was not foreseen in the risk matrix, however the project focused the efforts in supporting the advocacy campaign on introdusing the 30% gender quota in local councils.

Outcome Statement 4:

Rate the current status of the outcome:

Output progress at the end of project

List the key outputs achieved under this Outcome (1000 character limit).Outputs are the immediate deliverables for a project.

Outcome progress at the end of project

Describe progress made toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers (3000 character limit)?

Reasons for low achievement and rectifying measures

If sufficient progress was not made, what were the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How were they addressed (1500 character limit)?

  - Assessment of project evidence base, risk, catalytic effects, gender at the end of the project

| Evidence base: What was the evidence base for this report and for project progress? What consultation/validation process has taken place on this report (1000 character limit)? | The parliamentary elections in Kyrgyzstan were held in autumn, 2015, local elections in spring 2016 and winter 2016. The project is still collecting reports of all partners, which include a confirmation of all the activities planned as part of a public campaign. The project has conducted the baseline assessment, as well started the final evaluation process. All partners of the projects are members of the Coordination Council, which held its regular meetings on a permanent basis. Additionally, the project presented the results of its activities for the Oversight Group of Joint Steering Committee, where all partners of the PBF projects of state agencies are represented. Thus, the results of the project on parliamentary elections were discussed with the civil society and government institutions. |
| --- | --- |
| Funding gaps: Did the project fill critical funding gaps in peacebuilding in the country? Briefly describe. (1500 character limit) | The Project managed to reach out to a critical mass of women and youth from multi-ethnic rural communities whom are often left out during electoral processes to participate in the elections. In this regards, a participatory methodology has been tested in several communities to assess potential conflicts related to the upcoming elections. In addition, this unique methodology allowed local communities to review the potential conflicts and prepare plan of actions in response to possible conflicts. Based on observations and feedback received, the project was acknowledged to be effective in 2 keys areas 1) mitigating the risk of electoral violence 2 ) ensuring the substantative participation of women in taking a lead in resolving the conflicts. |
| Catalytic effects: Did the project achieve any catalytic effects, either through attracting additional funding commitments or creating immediate conditions to unblock/ accelerate peace relevant processes? Briefly describe. (1500 character limit) | The project works in close collaboration with the Central Election Committee (CEC), making sure that state-run voters' information campaign will engage women, youth and ethnic minorities;CEC supported the free TV channel space to air the project related videos on enhancing women's participation in elections. The project's support to the National Women’s Forum and International Parliamentary Conference in the framework of Beijing+20 anniversary, has increased the understanding of stakeholders that women's political participation in upcoming elections requires a special focus. Both events were highly supported and funded by central and local governments, NGOs and other international agencies.The final recommendations of the National Women's Forum were included into the National Action Plan on Gender Equality (2015-2017). The project activity on engaging marginal women into the public campaign helped to understand the process of elections, thus giving the possibility to stay back from the provocative actions and potential conflicts in the communities during the elections. In addition, because of the Gender Rating unique research, the project was able to attract additional funds to capacitate political parties in understanding gender representation as well as attracted additional funds from OSCE in conducting leadership schools for women-candidates |
| Risk taking/ innovation: Did the project support any innovative or risky activities to achieve peacebuilding results? What were they and what was the result? (1500 character limit) | The project has decided to take a risk in supporting a very innovative approach in communicating the main message on women’s empowerment through a popular among general public channel- the TV series. The key challenge was to make the idea of gender equality popular in patriarchal and ill norms towards women society. As a result, the TV series received a very good feedback from the public, taking into account that the style was chosen to be a comedy sequential. Another channel of communication to population was social media, through which the Public Service Announcements, quest and the computer game on women’s empowerment in politics were released by the IP. A lot of positive feedbacks were received by sharing the posts and likes of the audience. |
| Gender marker: How have gender considerations been mainstreamed in the project to the extent possible? Is the original gender marker for the project still the right one? Briefly justify. (1500 character limit) | This project has gender equality as a principal objective(GEN3). The direct target group are vulnerable groups of women, who often do not have the opportunity to participate in social life of their communities. The project aims at increasing women's participation in election processes, including from minorities and youth groups, both as candidates and peaceful voters, using a variety of innovative methods to include them in the activities as much as possible. In addition, the project supports inclusion of young men to be well informed about gender issues in their communities and to be able to support the participation of women in elections both as candidates and voters. |
| Other issues: Are there any other issues concerning project implementation that should be shared with PBSO? This can include any cross-cutting issues or other issues which have not been included in the report so far. (1500 character limit) | The project aims to work with voters in the parliamentary election period (Fall 2015) and local elections (Spring-Winter 2016), and plans to prepare women candidates from pilot communities to participate in local elections in 2016. Thus, project stakeholders recommended to prolong the project until December of 2016. Thus the data indicated in this report is not fully reflected until the results of the winter December 11, 2016 elections are announced. |

1.3 INDICATOR BASED PERFORMANCE ASSESSMENT: Using the Project Results Framework as per the approved project document- provide an update on the achievement of key indicators at both the outcome and output level in the table below. Where it has not been possible to collect data on indicators, state this and provide any explanation in the qualitative text above. (300 characters max per entry)

|  | Performance Indicators | Indicator Baseline | End of project Indicator Target | Current indicator progress | Reasons for Variance/ Delay (if any) | Adjustment of target (if any) |
| --- | --- | --- | --- | --- | --- | --- |
| Outcome 1 Women in priority PRF areas, especially women from minorities, exercise their electoral rights and participate in voting during parliamentary and municipal elections in 2015-2016 | Indicator 1.1 % of women (disaggregated by age and ethnicity, if possible) in target LSGs voting in elections (compared with previous elections) | 69.2% women participated in previous municipal (41.8%) and parliament (27.5%) elections. Disaggregated by age and ethnicity: Age: 60% -18-30, 41.9%-31-40, 52% - 41-60; Ethnic groups: 60% -Kyrgyz ethnic group (migrants from other countries), 45.5% - Kyrgyz, 15.8% - other | not less than previous participation of women who have relevant access to voting during parliament and local elections. | Since the project did not yet finished, current indicator progress will be presented in the end of December | Due to changes in electoral legislation (biometrics principles that require additional steps from the voters to participate in elections), the number of voters decreased, at the same time the project goal is targeted to encourage women to participate, those eligible to vote. |  |
|  | Indicator 1.2 |  |  |  |  |  |
|  | Indicator 1.3 |  |  |  |  |  |
| Output 1.1 Voters in target communities are empowered to exercise electoral rights without fear | Indicator 1.1.1 % of residents of voting age (disaggregated by age, sex and ethnicity, if possible) are saying they know their electoral rights and exercise them without fear | 80,2% of women exercised their electoral rights based on their own choice and will – independently. -Results were segregated by Age: 76% -18-30, 85.7%-31-40, 77.4%-41-60; Ethnicity: ethnic kyrgyz (migrants) - 75%, local Kyrgyz - 79.2%, other ethnic groups - 93.3%. | the number of voters who are empowered to exercise electoral rights without fear is not less than in the previous elections, taking into account the introduction of new voting regulations | BA data collected in 2 communities. | The % is high, but according to the quality data the ethnic groups make choices influenced by the family members. Women from 18 to 20 told that the decision is made by their husbands. |  |
|  | Indicator 1.1.2 |  |  |  |  |  |
| Output 1.2 | Indicator 1.2.1 |  |  |  |  |  |
|  | Indicator 1.2.2 |  |  |  |  |  |
| Output 1.3 | Indicator 1.3.1 |  |  |  |  |  |
|  | Indicator 1.3.2 |  |  |  |  |  |
| Outcome 2 Women and men in selected areas, especially youth, actively promote peaceful elections and engage in electoral debates on issues related to gender equality and gender-based violence | Indicator 2.1 Women and men in selected areas, especially youth, have enhanced their knowledge and skills on participating in electoral debates and promoting peaceful elections. | Data on the 1 case (rural, northern community): - 13,6% of respondents have confirmed their ability and knowledge to promote democratic changes for the communities in peaceful manners Data on the 2 case (urban, southern community): - 28,2% of respondents have confirmed their ability | Not less than 50% of respondents: women, men and youth confirm that they have received knowledge and skills to participate in electoral debates and promote peaceful elections. | Baseline assessment; endline assessment | The suggested indicator has direct link with Outcome 2 and practical implementation of the project |  |
|  | Indicator 2.2 |  |  |  |  |  |
| Output 2.1 Political parties at local level mainstream gender into their electoral programmes and respect gender quota | Indicator 2.1.1 Rating of parties by ‘gender rating’ study provided by women NGOs | lack of monitoring mechanisms of political parties on gender equality policies. | develop and test methodology of gender rating system of political parties. 4 gender rating results are published and disseminated. | “Gender Rating” report will be published and disseminated among the political parties and media. The summary report of the implementer will be shared |  |  |
|  | Indicator 2.1.2 |  |  |  |  |  |
| Output 2.2 Public discourse developed and electoral commitments set with regard to political participation issues, including those faced by youth | Indicator 2.2.1 Extent to which media (traditional and new) covers political participations issues, including those related to gender equality. | traditional and non-traditional media cover women’s political participation without gender-sensitive focus and with minimum attention | Media released specific materials on women’s political participation prior to Parliament and local elections. A targeted media campaign on women’s and youth’s participation in elections developed | Media monitoring (articles and briefs). The summary report of the implementer |  |  |
|  | Indicator 2.2.2 |  |  |  |  |  |
| Output 2.3 | Indicator 2.3.1 |  |  |  |  |  |
|  | Indicator 2.3.2 |  |  |  |  |  |
| Outcome 3 Women in selected areas, especially women from minorities, run as candidates during local elections | Indicator 3.1 Number of women-candidates and number of women-council deputies (age and ethnicity disaggregated) at local elections in target geographic areas. | Women - council deputies - 40, which is 11.8% of the total number of deputies. | maintain the baseline data (given the consequences of the amendments to the electoral code) | Baseline assessment; endline assessment | New amendment to the election code (article 17, 2 paragraph) restricts participation of state employed management personnel to participate in local elections as candidates which will decrease the number of women-candidates in elections. |  |
|  | Indicator 3.2 |  |  |  |  |  |
| Output 3.1 Women-candidates in target communities, incl. young women and women from minorities, have skills to run for local elections | Indicator 3.1.1 # of women-candidates (age and ethnicity disaggregated) in target communities and supported by the project running for local elections | data will be collected in 2016 before local elections. | at least 40% of women who were capacitated by the project leadership schools participate in local elections as candidates (with representation of youth not less than 15% and ethnic minorities not less than 15%) | Reports of the implementer |  |  |
|  | Indicator 3.1.2 |  |  |  |  |  |
| Output 3.2 | Indicator 3.2.1 |  |  |  |  |  |
|  | Indicator 3.2.2 |  |  |  |  |  |
| Output 3.3 | Indicator 3.3.1 |  |  |  |  |  |
|  | Indicator 3.3.2 |  |  |  |  |  |
| Outcome 4 | Indicator 4.1 |  |  |  |  |  |
|  | Indicator 4.2 |  |  |  |  |  |
| Output 4.1 | Indicator 4.1.1 |  |  |  |  |  |
|  | Indicator 4.1.2 |  |  |  |  |  |
| Output 4.2 | Indicator 4.2.1 |  |  |  |  |  |
|  | Indicator 4.2.2 |  |  |  |  |  |
| Output 4.3 | Indicator 4.3.1 |  |  |  |  |  |
|  | Indicator 4.3.2 |  |  |  |  |  |

PART 2: LESSONS LEARNED AND SUCCESS STORY

2.1 Lessons learned

Provide at least three key lessons learned from the implementation of the project. These can include lessons on the themes supported by the project or the project processes and management.

| Lesson 1 (1000 character limit) | The project was designed with the focus on involvement of a wide range of civil society organizations as partners of the implementation of its activities. This strategy has been quite successful, as the NGOs working on the ground are well aware of the community in certain regions and have access to them. On the other hand the evidence has shown that there is a need to increase the capacity of these organizations on financial and administrative reporting. Therefore, throughout the length of the project potential partners worked through the Micro-capital grants to be able to strengthen their institutional capacity |
| --- | --- |
| Lesson 2 (1000 character limit) | One of the main strategy of the project was to involve as many women, as possible, thus the innovations used within the information campaigns were more than relevant. Door-to-door visits, board games, TV shows, debates, forum-theaters had a significant success in attracting communities. Many field volunteers of the project and implementing partners underline these techniques as the best ones in approaching the public -it is because of the innovations there was a possibility to attract women |
| Lesson 3 (1000 character limit) | Within the project output "Public platforms" the project managed to support ad-hoc important activites, such as campaigns on advocating draft law on gender quotas, 16 Days of activism against gender-based violence campaign- one of the main message of which is "From peace at home to peace in the world".There was a space to provide support to women's movement to participate in several Parliament Hearings regarding quota and draft law on domestic violence and organize meeting of local women-candidates with MPs in the South of the Country. |
| Lesson 4 (1000 character limit) | The project was able to attract additional funds from UNDP IRH in developing a case-study on political inequalities in Kyrgyzstan within the UNDP’s regional human development report "Inequalities in Eastern Europe and Central Asia—Progress at Risk" http://www.kg.undp.org/content/kyrgyzstan/en/home/library/womens_empowerment/-case-study-on-combating-gender-inequality-in-political-particip/. Thus we consider it as one of the important issues in contributing to knowledge management on the particular area, such as politics and women's participation |
| Lesson 5 (1000 character limit) |  |

2.2 Success story (OPTIONAL)

Provide one success story from the project implementation which can be shared on the PBSO website and Newsletter as well as the Annual Report on Fund performance. Please include key facts and figures and any citations (3000 character limit).

“Another day is over and we can’t quit playing the game ...”- can be heard in the households of “Baltagulov” Ayil Aimak

In Aiyl Aimak “Baltagulov”, Ala-Buka rayon of Jalal-Abad oblast, women are trained on exercising women’s rights. It is planned to coach more than 2,000 households.

The results exceeded all expectations of women. Even those who couldn’t participate in such gatherings (women with small children, women with disabilities, elderly women) come together to play the game “I am a voter”.

Participants enthusiastically discuss the whole process of gaming, compare situations they fall in with the moments in their own lives, rooting for a particular character. In the course of the game players and fans make conclusions that awaits them if they do not go to the polls for some reason, or “sell their votes”, exchange their votes for lottery tickets and etc.

“Participants not only gain in receiving information on women's rights - they discuss this particular theme together and communicate with each other more than ever before.  Men say they feel a bit neglected, since so much attention is paid to women, but they do not hesitate in joining the game,” – shares her opinion the citizen of AA “Baltagulov”.

“It's so interesting and useful”, “the entire village is playing this game and it is useful, since it teaches us our voting rights”, “It is necessary to participate in the upcoming elections, thy must be interesting” – are being heard in the villages.

Such campaigns were conducted in 2015, before parliamentary elections, and the locals already recognize volunteers-community members. They not only participate in the events but are eager to help with organization. If last year the volunteers went into the courtyard and talked to women individually, this year groups of 7-10 women come together and are being informed about the project and play the game – “I am a voter”.

This board game is a new, interactive method of conveying information to the public, it is very easy to use and seem to be quite fascinating.

This information work will also be carried out in several other villages and will cover more than 8000 residents of households.

Public Foundation "NGO Coordination Support Center", has trained about 20 local leaders and a team of volunteers to carry out such activities, which included door-to-door visits and dialogues.

PART 3 – FINANCIAL PROGRESS AND MANAGEMENT ARRANGEMENTS

  - Comments on the overall state of financial expenditure

Please rate whether project financial expenditures were on track, slightly delayed, or off track:

If expenditure was delayed or off track, please provide a brief explanation (500 characters maximum):

Please provide an overview of project expensed budget by outcome and output as per the table below.

| Output number | Output name | RUNOs | Approved budget | Expensed budget | Any remarks on expenditure |
| --- | --- | --- | --- | --- | --- |
| Outcome 1: Women in priority PRF areas, especially women from minorities, exercise their electoral rights and participate in voting during parliamentary and municipal elections in 2015-2016 |
| Output 1.1 | Voters in target communities are empowered to exercise electoral rights without fear |  | UNDP: 145,000 USD M&E budget 46,837 USD UNICEF: 77,450 USD | UNDP: 249,619 USD M&E budget 34, 777 USD UNICEF: 77,540 USD | for UNDP : including commitments; funds were re allocated from Output 2.1 |
| Output 1.2 |  |  |  |  |  |
| Output 1.3 |  |  |  |  |  |
| Outcome 2: Women and men in priority PRF areas, especially youth, actively promote peaceful elections and engage in electoral debates, including on issues relating to gender equality and gender-based violence |
| Output 2.1 | Political parties at local level include gender issues in their electoral programmes and respect gender quota |  | UNDP: 203, 275 USD UNICEF: 82,000 USD | UNDP: 134,948 USD UNICEF: 82,000 USD |  |
| Output 2.2 | Public discourse developed and electoral commitments set with regard to political participation issues, including those faced by youth |  | UNICEF: 120,000 USD | UNICEF: 118,000 USD |  |
| Output 2.3 |  |  |  |  |  |
| Outcome 3: Women in selected areas, especially women from minorities, run as candidates during municipal elections in 2016 |
| Output 3.1 | Women-candidates in target communities, incl. young women and women from minorities, have skills to run for local elections |  | UNDP: 75,000 USD UNICEF: 119,000 USD | UNDP: 80,000 USD UNICEF: 119,000 |  |
| Output 3.2 |  |  |  |  |  |
| Output 3.3 |  |  |  |  |  |
| Outcome 4: |
| Output 4.1 |  |  |  |  |  |
| Output 4.2 |  |  |  |  |  |
| Output 4.3 |  |  |  |  |  |
| Total |  |  | UNDP: 470,112 USD UNICEF: 398,450 USD | UNDP: 499, 344 USD UNICEF: 396,540 USD | UNDP:funds were re allocated from "Staff and other personal cost" line |

  - Comments on management and implementation arrangements

Please comment on the management and implementation arrangements for the project, such as: the effectiveness of the implementation partnerships, coordination/coherence with other projects, any South-South cooperation, the modalities of support, any capacity building aspect, the use of partner country systems if any, the support by the PBF Secretariat and oversight by the Joint Steering Committee (for PRF only). Please also mention if there have been any changes to the project (what kind and when) (2000 character maximum):

The Joint Steering Committee (JSC), established by the President’s order, oversees overall project implementation and guidance. Country Program Gender Coordinator is responsible for day to day management of UNDP part. UNICEF allocates two programme officers to manage the project. Essential part of activities are undertaken through NGO-implementation modality. 16 local NGOs were engaged as the project partners. The two agencies established internal project coordination body with the joint action plan and communication means; they lead monitoring and evaluation processes, ensure commitment, coordination and support to all implementing partners, etc.

# Footnotes

The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to “Project ID” on the MPTF Office GATEWAY

The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY

As per approval of the original project document by the relevant decision-making body/Steering Committee.

If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed.

Please note that financial information is preliminary pending submission of annual financial report to the Administrative Agent.