RUNO END PF PROJECT REPORTING		TEMPLATE 4.5

PEACEBUILDING FUND (PBF)

END OF PROJECT report

COUNTRY: Kyrgyzstan

REPORTING PERIOD: July 2014 - September 2016

| Programme Title & Project Number |  |
| --- | --- |
| Programme Title: “Peace and reconciliation through strengthening the rule of law and human rights protection” Programme Number (if applicable) KGZ/B4 MPTF Office Project Reference Number: 00089348 |  |  |

| Recipient UN Organizations |  | Implementing Partners |
| --- | --- | --- |
| List the organizations that have received direct funding from the MPTF Office under this programme: OHCHR |  | List the national counterparts (government, private, NGOs & others) and other International Organizations: Department for Judicial Reform and Rule of Law of the Office of the President of the Kyrgyz Republic; Apparatus of the Government of the Kyrgyz Republic; Judicial Training Centres under the Supreme Court and the General Prosecutor's Office; National Mechanism for the Prevention of Torture; Coordination Council on Human Rights under the Government |
| Programme/Project Budget (US$) |  | Programme Duration |
| PBF contribution (by RUNO) USD 1,065.753 |  |  | Overall Duration (months) 27 months |  |
|  |  |  | Start Date (dd.mm.yyyy) 01 July 2014 |  |
| Government Contribution (if applicable) |  |  | Original End Date (dd.mm.yyyy) | 30 June 2016 |
| Other Contributions (donors) (if applicable) |  |  | Final End date(dd.mm.yyyy) 30 September 2016 |  |
| TOTAL: | USD 1,065.753 |  |  |  |

| Programme Assessment/Review/Mid-Term Eval. |  | Report Submitted By |
| --- | --- | --- |
| Mid-Term Evaluation / Review - if applicable please attach Yes No Date: End of project Evaluation– if applicable please attach Yes No Date: |  | Name: Beatrix Ferenci Title: Deputy Regional Representative Participating Organization (Lead): OHCHR Regional Office for Central Asia Email address: bferenci@ohchr.org |

PART 1 – RESULTS PROGRESS

  - Assessment of the project implementation status and results

For PRF projects, please identify Priority Plan outcome and indicators to which this project has contributed:

Priority Plan Outcome to which the project has contributed. Outcome 1: Laws, policies, reforms and recommendations of human rights mechanisms, including UPR39, are implemented to uphold the rule of law, improve access to justice and respect, protect and fulfill human rights.

Priority Plan Outcome indicator(s) to which project has contributed. 1.1: Proportion of cases brought to human rights and justice institutions which are satisfactorily resolved; 1.2: Number of key policies and laws adopted or amended; 1.4: Citizens' trust in national state institutions is increased.

For both IRF and PRF projects, please rate this project’s overall achievement of results to date:

For both IRF and PRF projects, outline progress against each project outcome, using the format below. The space in the template allows for up to four project outcomes.

Outcome Statement 1:  Key legislation in the area of administration of justice is in line with international and constitutional human rights standards, and the judiciary adjudicates several cases in line with these standards

Rate the current status of the outcome:

| Indicator 1: Degree of compliance of key laws relating to the administration of justice with international and human rights standards Indicator 2: Indicator 3: | Baseline: Current Criminal Procedure Code and other key laws are not fully in compliance with international human rights standards Target: A new Criminal Procedure Code is adopted and the laws mentioned are amended, largely in compliance with international human rights standards by 2015 Progress:As a result of OHCHR's technical and expert support to the Expert Working Groups (EWG) and the relevant Parliamentary Committees, seven draft laws (including the Criminal Procedure Code - CPC) were tabled in the Parliament, discussed with civil society and experts in Bishkek and Osh, and passed by the Parliament in the first reading. The drafts approved by the Parliament incorporated some human rights standards related to the administation of justice. In order to ensure full compliance, OHCHR continued to support the EWG on harmonization of the Criminal Code and Criminal Procedure Code. The EWG reviewed the draft CPC article by article and improved its human rights compliance. The draft CPC passed the second Parliamentary hearing in June 2016 and is expected to undergo the third and final hearing in November 2016. A research on the unification of judicial practice in cases of torture was finalized; and 4 capacity building activities on documentation of torture and Istanbul Protocol delivered. Two Trainings of Trainers (ToTs) and ten trainings for judges and prosecutors were delievered on international and national human rights standards, including on FoRB and Istanbul Protocol. Material used for the trainings was consolidated into a human rights training curricula and manual for the Judicial Training Centre (JTC) and the Prosecutors Training Centre (PTC), Baseline: Target: Progress: Baseline: Target: Progress: |
| --- | --- |

Output progress at the end of project

List the key outputs achieved under this Outcome (1000 character limit).Outputs are the immediate deliverables for a project.

Judical reform: CPC incorporating some human rights standards drafted; discussions on CPC held with international and national experts, and civil society in Bishkek and Osh; the package of 7 new laws (including the CPC) tabled in the Parliament, reviewed and discussed within the relevant Parliamentary Committees and eventually approved in the second hearing in June 2016; a new EWG established and tasked to improve the human rights compliance of the CPC and harmonize it with the Criminal Code, following advocacy from OHCHR; review of CPC completed by EWG, with technical and expert support from OHCHR; human rights compliance of CPC increased.

Supreme court: a research on the unification of judicial practice in cases of torture was finalized; four trainings on Istanbul Protocol and documentation of torture implemented;

Trainings: Two ToTs and ten trainings for judges and prosecutors delievered on international and national human rights standards.

Outcome progress at the end of project

Describe progress made toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers (3000 character limit)?

1) Judicial reform: OHCHR's support to the judicial reform process in Kyrgyzstan in close coordination with UNDP, UNODC and other international organizations, and the Department for Judicial Reform of the President's Office resulted in the finalization of seven key draft laws in the area of administration of justice by the EWGs. The Criminal Code, Code on Misdemeanors, Criminal Procedure Code, Criminal Executive Code, Civil Procedure Code, Laws on enforcement proceedings and state guaranteed legal aid were finalized by the Expert Working Groups and submitted to the Parliament by end 2014.  With OHCHR' support, the drafts were subsequently discussed with civil society and experts in Bishkek and Osh, and passed by the Parliament in first reading in June 2015.

According to the analysis by a number of nation and international experts, the draft Criminal Procedure Code approved by the Parliament contains a number of progressive provisions which comply with international human rights standards, further reform the criminal justice system of Kyrgyzstan and provide a transition from the inquisitorial model to a more adversarial model. However, OHCHR also noted a number of shortcomings, ie lack of full compliance of some provisions with international human rights standards, including in relation to excessive use of pre-trial detention, lack of legal certainty, and controversial articles on the implementation of view. In order to ensure full compliance, OHCHR advocated for the establishment of an EWG tasked to ensure full compliance with human rights standards and harmonization between the Criminal Code and Criminal Procedure Code. The EWG was established and with OHCHR's technical and expert advice reviewed the draft CPC article by article and improved its human rights compliance. The final draft of the CPC passed the second reading in June 2016 and is expected for third and final reading in Nov 2016.

2) OHCHR conducted a research on unification of judicial practice on cases related to torture. In 2016, the Supreme Court formally communicated that there will be no unification of judicial practice through a resolution of the Supreme Court Plenum on cases related to torture due to the low number of cases registered. OHCHR continued supporting the SC through capacity building activities on the implementation of medical standards for the documentation of torture case and Istanbul Protocol

3) OHCHR delivered two 4-day ToTs for judges and prosecutors on international human rights standards. OHCHR also developed human rights manuals for lawyers, judges and prosecutors to ensure institutionalization of human rights curricula and further training of judges, lawyers and prosecutors. Moreover, OHCHR was able to attract additional funding from other donors to continue working with the JTC and PTC. Additional trainings for prosecutors and judges were conducted in November/December 2015, June/July/September 2016 through partnerships with other donors.

Reasons for low achievement and rectifying measures

If sufficient progress was not made, what were the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How were they addressed (1500 character limit)?

Due to parliamentary elections in October 2015, the process of judicial reform has been delayed, which on the other hand gave more time to the EWG to ensure mainstreaming of human rights standards. In June 2016, the CPC has passed it second reading in the Parliament. Third and final reading is expected for October-November 2016.

Outcome Statement 2:  Adequate functioning of national human rights mechanisms and civil society actors leads to effective protection of human rights and increased accountability for their violation, including through holistic follow-up on UN human rights mechanisms’ recommendations.

Rate the current status of the outcome:

| Indicator 1: Extend to which targeted national human rights mechanisms (NPM and CCHR) function effectively in line with their respective mandates and international human rights standards Indicator 2: Extend to which young lawyers and NGO carry out their casework and monitoring and reporting, with reference to international human rights standards Indicator 3: | Baseline: The NPM is in the process of being established following law adopted in 2012. The Government established Coordination Council on Human Rights (CCHR) in 2013 to follow up on recommendations of UN Human Rights Mechanisms (UN HRMs). Target: By 2016, both national mechanisms function in line with their mandates, good practices and international human rights standards. Progress:The NPM is fully staffed, present in 7 provinces and operates in line with OPCAT guiding principles, having full access to places of deprivation of liberty. Authorities are aware of the mandate of the NPM. The NPM produced three annual reports that were approved by the Parliament. The CCHR is also functioning and engaged with a number of UN HRMs (including various UN Committes: ICCPR, CRC, CEDAW, CMW, CESCR and the Human Rights Council for the Universal Period REview). OHCHR developed a Compendium of recommendations to support the CCHR in clustering all recommendations received (664) into thematic areas. The CCHR established two working groups (WGs): one to draft the National Human Rights Action Plan (NHRAP) and one to develop procedures to implement views of UN Committees. Both include civil society organizations. The CCHR also reviewing a degree that institutionalizes the role of Human Rights Focal Points within state bodies, that are members of the CCHR. NHRAP will be presented for public consultations during the Autumn and final by end 2016 Baseline: There is lack of young defense lawyers and NGOs carrying out monitoring which refers to international human rights standards Target: N/A Progress:OHCHR conducted ten trainings and one ToT targeting over 90 young lawyers from the north and south of Kyrgyzstan on international human rights standards. Lawyers are now able to use and reference international human rights provisions in their case-work, which happened in at least five cases. A database of trained lawyers who are willing to engage in human rights issues was created and shared with other international organizations and NGOs. In two cases, young lawyers, who had in the past failed the Bar exam, were able to pass the exam after attending OHCHR's training sessions aimed at preparing non-licenced lawyers with human rights knowledge for the exam. OHCHR awarded small grants to 2 civil society organizations to monitor the human rights situation and new trends in Jalalabad, Batken and Osh. Baseline: Target: Progress: |
| --- | --- |

Output progress at the end of project

List the key outputs achieved under this Outcome (1000 character limit).Outputs are the immediate deliverables for a project.

1) NPM: Training to NPM on monitoring places of deprivation of liberty, gathering and storing data, analysing the information, harmonizing reporting tools and preparing reports, as well as on strategic planning delivered; Visibility material (leaflets) produced;

2) CCHR: Expert support to the Secretariat provided throughtout the project; a compendium of recommendations issued by UN HRMs produced; expert support, including through training and mentoring on NHRAP drafting and indicators to the WGs drafting the NHRAP and the procedures to implement views of UN Committees provided;

3) Capacity building for lawyers: Ten trainings targeting over 90 young lawyers from the north and south of Kyrgyzstan on international human rights standards delivered, including on FoRB, HLP; database of lawyers produced and shared with other international organizations;

4) NGO grants: two civil society organizations awarded with small grants to monitor the human rights situation in south Kyrgyzstan.

Outcome progress at the end of project

Describe progress made toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers (3000 character limit)?

1) The NPM staff received on-the-job mentoring and training from OHCHR on monitoring places of deprivation of liberty, gathering and storing data, analysing the information, harmonizing reporting tools, preparing reports and developing their strategic plan for the upcoming 3-5 years. This enabled the NPM to produce three public reports, including recommendations for state authorities. The reports were approved by the Parliament in pleanary hearing. At the same time, OHCHR supported the NPM in increasing its visibility with the authorities and raising the awareness on its mandate (including through designing and printing leaflets), which led to the NPM being granted full, unhindered access to places of deprivation of liberty, as well as enhanced budgetary resources and an office space in the city center. Through its advocacy, OHCHR prevented the Parliament from passing amendments to the Law on the NPM, which would put its independence at risk, contributed to the approval of the National Action Plan to combat torture, and the establishment of a new department within the General Prosecutor's Office on human rights and activities of law enforcement agencies in pre-trial. OHCHR supported the NPM in its internal reorganization of departments and human resources.

2) As a result of OHCHR's technical and expert support, the CCHR coordinated the state engagement with and prepared reports to UN HRMs on occasion of the review of Kyrgyzstan by various UN committees including CEDAW, CMW, CESCR and by the Human Rights Council during the UPR. With a view to implementing all human rights recommendations received (664), the CCHR established WGs: one to draft the National Human Rights Action Plan (NHRAP) and one to develop procedures to implement views of UN Committees. Both WGs include civil society organizations. To support these efforts, OHCHR developed a Compendium of recommendations clustering all recommendations received into 25 thematic areas. The CCHR is using the Compendium as a basis for developing the NHRAP, expected for end 2016. The CCHR also drafted a degree that institutionalizes the role of Human Rights Focal Points within state bodies which are members of the CCHR.

3) OHCHR conducted ten trainings and one ToT targeting over 90 young lawyers from the north and south of Kyrgyzstan on international human rights standards. Laywers are now able to use and reference international human rights provisions in their case-work, which happened in at least 5 cases. A database of trained lawyers, who are willing to engage on human rights issues has been created and shared with other international organizations and NGOs. In two cases, young lawyers, who had in the past failed the Bar exam, were able to pass it after attending OHCHR's training aimed at preparing non-licenced lawyers with human rights knowledge for the exam.

4) OHCHR awarded 2 small grants to civil society organizations to monitor the human rights situation in south Kyrgyzstan.

Reasons for low achievement and rectifying measures

If sufficient progress was not made, what were the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How were they addressed (1500 character limit)?

N/A

Outcome Statement 3:  Duty bearers and right holders engage in dialogue about the importance of addressing grave human rights violations committeed during and in the aftermath of June 2010 events

Rate the current status of the outcome:

| Indicator 1: Extent of understanding among duty bearers and right holders of the importance of effectively addressing human rights violations committeed during and in the aftermath of June 2010 violence Indicator 2: Indicator 3: | Baseline: Currently, there is little understanding among duty beares and right holders on the concept of justice for the past and its tools Target: Increasing understanding of the importance of addressing human rights violations of June 2010 violence Progress: OHCHR held discussions/consultations on transitional justice issues with the Ministry of Justice, the Office of General Prosecutor and the Presidential Administration. Transitional justice modules were included in all capacity building activities for young lawyers, prosecutors and judges carried out in the second half of 2015 and 2016. Specific training for supreme court and constitutional judges, as well as for and second instance judges addressing issues relevant to transitional justice (e.g. implementation of views of the UN Committees, compensation, reparation and restoration of justice) took place in December 2015. Two additional training for newly appointed first instance judges took place in September 2016 in north and southern Kyrgyzstan. Baseline: Target: Progress: Baseline: Target: Progress: |
| --- | --- |

Output progress at the end of project

List the key outputs achieved under this Outcome (1000 character limit).Outputs are the immediate deliverables for a project.

OHCHR held advocacy meetings and consultations on transitional justice in Bishkek including with the Deputy Minister of Justice, and the Head of the Department of Judicial Reform and Role of Law under the Presidential Administration, as well as meetings in Osh with city Mayor’s office, the office of the Governor, and the Prosecutor’s office.

Outcome progress at the end of project

Describe progress made toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers (3000 character limit)?

OHCHR noted that State authorities are neither effectively addressing the root causes of 2010 conflict, nor are launching initiatives aimed at restoring justice for victims and trust among communities. Since authorities are rather reluctant to discuss transitional justice initiatives, adducing as main reason concerns that they could again steer inter-ethnic tensions, OHCHR decided to hold preliminary discussion on transitional justice with key interlocutors, including the Ministry of Justice, the Office of General Prosecutor and the Presidential Administration, and agreed to organize an expert working group of lawyers to discuss next steps and tools that could possibly be applicable in Kyrgyzstan. Since authorities were reluctant to appoint lawyers/focal points for such a meeting, the meeting was not conducted.

At the same time OHCHR ensured that justice for 2010 events remained on the agenda of the authorities by raising this issue in official meetings, and ensuring that the topic was included in the UPR consultations organized by the CCHR including for civil society organizations.

In addition to that, transitional justice modules have been included in all capacity building activities for young lawyers, prosecutors and judges carried out in the second half of 2015. Specific trainings for supreme court and constitutional judges, as well as for and second instance judges addressing issues relevant to transitional justice (e.g. implementation of views of the UN Committees, compensation, reparation and restoration of justice) took place in December 2015. Two additional training for newly appointed first instance judges took place in September 2016 in north and southern Kyrgyzstan.

Reasons for low achievement and rectifying measures

If sufficient progress was not made, what were the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How were they addressed (1500 character limit)?

N/A

Outcome Statement 4:

Rate the current status of the outcome:

| Indicator 1: Indicator 2: Indicator 3: | Baseline: Target: Progress: Baseline: Target: Progress: Baseline: Target: Progress: |
| --- | --- |

Output progress at the end of project

List the key outputs achieved under this Outcome (1000 character limit).Outputs are the immediate deliverables for a project.

Outcome progress at the end of project

Describe progress made toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers (3000 character limit)?

Reasons for low achievement and rectifying measures

If sufficient progress was not made, what were the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How were they addressed (1500 character limit)?

  - Assessment of project evidence base, risk, catalytic effects, gender at the end of the project

| Evidence base: What was the evidence base for this report and for project progress? What consultation/validation process has taken place on this report (1000 character limit)? | The evidence base for this report is: - ROCA's internal monthly reports submitted to the OHCHR Performance Monitoring System; - Drafts of the seven key laws in the area of administration of justice elaborated by the Expert Working Groups; - Kyrgyzstan's reports to UN HRMs, the compendium of recommendations, draft NHRAP; - Draft regulations/decrees issued by the CCHR and instructions by the Supreme Court; - All material prepared and disseminated during capacity building activities, mission reports, activity reports and evaluation forms from beneficiaries; - Number of promotional materials prepared and disseminated by ROCA within the project; - Internal talking points and internal minutes of advocacy meetings with the authorities conducted by ROCA within the project; - Reports from NGO grantees |
| --- | --- |
| Funding gaps: Did the project fill critical funding gaps in peacebuilding in the country? Briefly describe. (1500 character limit) | By seconding two Human Rights Experts to the Secretariat of the Coordination Council on Human Rights, the project is meeting the critical need of having full time staff working within the Secretariat of the Coordination Council to manage the workload. By supporting the Prosecutors Training Centre on capacity building activities in the area of international human rights standards, the project is filling a critical funding gap, as the Center does not have its own budget for training activities of prosecutors. By having deployed experts to support the Expert Working Group on the Criminal Procedure Code a critical funding gap was closed as no in-house capacity existed on aforementioned within state authorites and the parliament. |
| Catalytic effects: Did the project achieve any catalytic effects, either through attracting additional funding commitments or creating immediate conditions to unblock/ accelerate peace relevant processes? Briefly describe. (1500 character limit) | 1) By advocating with the Government for strenghtening the role of the Coordination Council on Human Rights in coordinating follow up to recommendations from UN HRMs and with donors for supporting the efforts of this mechanism, OHCHR was able to raise the profile of the inter-agency body and mobilize additional funding from various donors; 2) The training material developed by OHCHR for the trainings of lawyers, judges and prosecutors has been used to form the human rights curricula of the training centres. OHCHR was able to attract additional funding from other donors to replicate training sessions. |
| Risk taking/ innovation: Did the project support any innovative or risky activities to achieve peacebuilding results? What were they and what was the result? (1500 character limit) | With a view to raise awareness on international human rights standards and best practices, OHCHR conducted small-scale consultations and training sessions for young lawyers, judges and prosecutors on human rights issues considered sensitive in the context of Kyrgyzstan. Topics included transitional justice, restoration of justice after 2010 events, freedom of religion or belief, arbitrary arrest and detention in the context of counter-terrorism and violent extremism. |
| Gender marker: How have gender considerations been mainstreamed in the project to the extent possible? Is the original gender marker for the project still the right one? Briefly justify. (1500 character limit) | Balanced representation of women in OHCHR’s activities (both as participants and trainers) was ensured in the overall implementation of the project. Moreover, gender topics were mainstreamed in capacity building and awareness raising activities. Issues specifically related to women's rights and women's access to justice were addressed during the trainings with judges, prosecutors and young lawyers. OHCHR supported the Government in its engagement with CEDAW, as well as to incorporate CEDAW recommendations in the NHRAP - by dedicating a specific WG to this topic. On the other hand, the budget allocation to gender-related activities within the project amounts to 136,000 USD. OHCHR did not dedicate the full amount to activities directly related to gender issues, but OHCHR rather ensured that gender considerations were taken into account throughtout the implementation of regular project activities implemented with the aforemention budget allocation. |
| Other issues: Are there any other issues concerning project implementation that should be shared with PBSO? This can include any cross-cutting issues or other issues which have not been included in the report so far. (1500 character limit) | 1) Due to parliamentary elections in October 2015, which led to the Parliament not being operational for several months, the process of judicial reform experienced delays. The draft codes passed the second reading in the Parliament in June 2016 and are expected to undergo the third and final reading in November 2016. On the other hand, the delay allowed the EWG to again review the draft CPC and ensure human rights are fully mainstreamed in the legislation. 2) In early 2016, the Supreme Court formally communicated that there will be no unification of judicial practice through a resolution of the Supreme Court Plenum on cases related to torture due to the low number of cases registered. OHCHR adapted its strategy to continued supporting the Supreme Court in analysing trends related to torture cases, as well as with the implementation of medical documentation standards included in the Istanbul Protocol. 3) Slow progress with drafting NHRAP to ensure comprehensive follow up to recommendations is due to the low capacity of the Secretariat, complexity of organizing the high amount of recommendations and the fact that CCHR heavily relies on OHCHR experts. The WG on NHRAP resumed working in June 2016 and the position for 2 OHCHR experts to the CCHR were re-advertised in August 2016 though ultimately the CCHR informed OHCHR that no further support was required. It is expected that the draft NHRAP will be presented for public consultations during the Autumn and final by end 2016. |

1.3 INDICATOR BASED PERFORMANCE ASSESSMENT: Using the Project Results Framework as per the approved project document- provide an update on the achievement of key indicators at both the outcome and output level in the table below. Where it has not been possible to collect data on indicators, state this and provide any explanation in the qualitative text above. (250 characters max per entry)

|  | Performance Indicators | Indicator Baseline | End of project Indicator Target | Current indicator progress | Reasons for Variance/ Delay (if any) | Adjustment of target (if any) |
| --- | --- | --- | --- | --- | --- | --- |
| Outcome 1 Key legislation in the area of administration of justice is in line with international and constitutional human rights standards and the judiciary adjudicates several cases in line with these standards | Indicator 1.1 Degree of compliance of key laws relating to the administration of justice with international and human rights standards | Current criminal procedure code and other key laws are not fully in compliance with international human rights standards | A new Criminal Procedure Code is adopted and the laws mentioned are amended, largely in compliance with international human rights standards by 2015 | Seven draft laws (including the Criminal Procedure Code) have been approved in first and second reading in the Parliament and now incorporate human rights standards related to the administration of justice | The process of judicial reform has been slowed down by the Parliamentary elections in October 2015, which led to the Parliament not being operational for several months | The third and final reading of the draft codes is expected for November 2016 |
|  | Indicator 1.2 |  |  |  |  |  |
|  | Indicator 1.3 |  |  |  |  |  |
| Output 1.1 Technical and expert support is provided to the Secretariat of the National Council on Judicial Reform and its Expert Working Groups on elaborating the key laws relating to the administration of justice in line with international human rights standar | Indicator 1.1.1 Number of key draft laws relating to the administration of justice elaborated by the EWGs and submitted for public discussions | Three draft laws were partially elaborated by EWGs in 2013 | Draft of key laws relating to the administration of justice are elaborated by EWG and submitted for public discussion - three by end 2014; three by end 2015 | Seven draft laws (including the Criminal Procedure Code) have been approved in first and second reading in the Parliament and now incorporate human rights standards related to the administration of justice | The process of judicial reform has been slowed down by the Parliamentary elections in October 2015, which led to the Parliament not being operational for several months | The third and final reading of the draft codes is expected for November 2016 |
|  | Indicator 1.1.2 |  |  |  |  |  |
| Output 1.2 Technical assistance and capacity building provided to the Supreme Courte judges and staff regarding unification of judicial practices in criminal cases | Indicator 1.2.1 Number of resolution adopted by the Supreme Court regarding unified judicial practice on criminal cases | No such resolution has thus far been adopted by the Supreme Court on criminal cases | One such resolution adopted by the Supreme Court by June 2016 | OHCHR conducted a research on unification of judicial practice on cases related to torture. The summarized judicial practice for cases related to torture that occurred up to mid 2015 | In early 2016, the Supreme Court formally communicated that there will be no unification of judicial practice through a resolution of the Supreme Court Plenum on cases related to torture due to the low number of cases registered | OHCHR continued supporting the Supreme Court in analysing trends related to torture cases, as well as with the implementation of medical documentation standards included in the Istanbul Protocol (1 training for judges in Bishkek and 3 in the south) |
|  | Indicator 1.2.2 |  |  |  |  |  |
| Output 1.3 A human rights training package is developed with Supreme Court's Judiciary training centre and Center for Professional Training of Prosecutors | Indicator 1.3.1 Extent to which human rights are institutionalized in the training curricula of JTC and CPTP | The training curricula do not currently included human rights and will have to be updated in line with the new legislation | By end 2016, the training curricula if JTC and CPTP are updated and institutionalize human rights | By Sept 2016, OHCHR developed a 4-day training on human rights in administration of justice and delivered ToTs to 25 judges of the JTC and 25 prosecutors of CPTP; 10 additional trainings for judges and prosecutors delivered, also on FoRB and IP | OHCHR with JTC, PTC consolidated the material used for the trainings into comprehensive human rights manuals and courses to be institutionalized in the training curricula by the Judicial Training Centre (JTC) and the Prosecutors Training Centre (PTC) |  |
|  | Indicator 1.3.2 |  |  |  |  |  |
| Outcome 2 Adequate functioning of national human rights mechanisms and civil society actors leads to effective protection of human rights and increased accountability for their violations, including through holistic follow up to UN HRM recommendations | Indicator 2.1 Extend to which targeted national human rights mechanisms (NPM and CCHR) function effectively in line with their respective mandates and international human rights standards | The NPM is in the process of being established following law adopted in 2012. The Government established CCHR in 2013 to follow up on recommendations of UN HRMs. | By 2016, both national mechanisms function in line with their mandates, good practices and international human rights standards. | The NPM is staffed and present in 7 provinces. It operated in line with OPCAT guiding principles; 3 annual reports approved by Parliament. Since beginning 2016, there has been slow progress with the CCHR and the development of the NHRAP. | Slow progress in drafting the NHRAP, meant to ensure follow up to recommendations, is due to low capacity of the Secretariat, the complexity of organizing the high amount of recommendations and the fact that CCHR heavily relies on OHCHR experts. | The WG on NHRAP resumed working in June 2016 and the positions for 2 OHCHR experts to the CCHR have been re-advertised in August. It is expected that the draft NHRAP will be presented for public consultations during the Autumn and final by end 2016 |
|  | Indicator 2.2 Extend to which young lawyers and NGO carry out their casework and monitoring and reporting, with reference to international human rights standards | There is lack of young defense lawyers and NGOs carrying out monitoring which refers to international human rights standards |  | By Sept 2016, ROCA trained around 90 young lawyers from the south and north and conducted ten trainings on international human rights standards, lawyers skills, conflict mediation, FoRB and HLP standards, and conducted one ToT for young lawyers. | OHCHR has consolidated the material used for the trainings into a comprehensive human rights manual and course to be institutionalized within the training curricula by the Lawyers Training Center and Bar Association |  |
| Output 2.1 Institutional support provided to the newly established NPM and capacity building on monitoting places of deprivation of liberty is provided to the staff and members of the Coordination Council | Indicator 2.1.1 Number of reports following monitoring visits are produced by the NPM | Zero reports as the NPM has yet to start functioning | By mid-2015 the NPM issues 4 reports following monitoring visits, by mid-2016 the NPM issues 4 reports following monitoring visits | By Sept 2016, the NPM issued 3 annual reports including analysis of information gathered during the monitoring visits conducted in 2013, 2014 and 2015. | The NPM produces its annual report at the end of each year. Thus far, the NPM has produced three annual reports that were all approved by the Parliament. |  |
|  | Indicator 2.1.2 |  |  |  |  |  |
| Output 2.2 Institutional support and capapcity building on human rights law and strategic planning is provided to the newly established inter-ministerial entity that will follow up on UN HRM recommendations | Indicator 2.2.1 Existence of a draft strategic plan to ensure a comprehensive follow up to recommendations from UN HRM | No such comprehensive strategic plan exist | A strategic plan to follow up on recommendations by UN HRM is drafted by June 2015 | The CCHR established two working groups: one to draft the national human rights action plan and one to develop procedures to implement views of UN Committees. Both WGs include civil society organizations, but progress has been slow so far | Slow progress with drafting NHRAP to ensure comprehensive follow up to recommendations is due to the low capacity of the Secretariat, complexity of organizing the high amount of recommendations and the fact that CCHR heavily relies on OHCHR experts | The WG on NHRAP resumed working in June 2016 and the position for 2 OHCHR experts to the CCHR have been re-advertised in August. It is expected that the draft NHRAP will be presented for public consultations during the Autumn and final by end 2016 |
|  | Indicator 2.2.2 |  |  |  |  |  |
| Output 2.3 Capacity building for young defence lawyers from multi ethnic towns and districts of southern kyrgyzstan on protecting human rights in criminal proceedings Output 2.4 Technical support and grants provided to faciliate human rights monitoring repor | Indicator 2.3.1 Number of cases addressed by the trained young lawyers to national and international mechanisms on alleged human rights violations with reference to international and national human rights standards | Zero | 5 cases by June 2015 and 5 cases by June 2016 refer to international human rights standards | At least in five cases, young lawyers confirmed having used the knowledge and skills acquired in trainings in their work. A lawyer used knowledge on human rights standards to submit a report to UN HRM and 7 submitted individual complaints to UN HRM. | OHCHR organized a specific training for lawyers and human rights defenders from the south on preparing and submitting cases of allaged human rights violations to UN Committees in May 2016. | A training on litigation of cases using international standards related to FoRB was conducted in July 2016 |
|  | Indicator 2.3.2 Indicator 2.4 Number of public reports produced by NGOs documenting cases of HR violations in the south | Not available | By June 2016, two public monitoring reports with specific recommendations for the Gvt are produced by NGOs on HR issues in the south | By Sept 2016, two NGOs from southern Kyrgyzstan have been awarded grants to monitor emerging human rights trends in the south of Kyrgyzstan |  |  |
| Outcome 3 Duty bearers and right holders engage in dialogue about the importance of addressing grave human rights violations committeed during and in the aftermath of June 2010 events | Indicator 3.1 Extent of undersnading among duty bearers and right holders of the importance of effectively addressing human rights violations committeed during and in the aftermath of June 2010 violence | Currently, there is little understanding among duty beares and right holders on the concept of justice for the past and its tools | Increasing understanding of the importance of addressing human rights violations of June 2010 violence | By Sept 2016, ROCA held discussions on transitional justice issues with the Ministry of Justice, the Office of General Prosecutor, the Presidential Administration and Supreme Court. |  |  |
|  | Indicator 3.2 |  |  |  |  |  |
| Output 3.1 Awareness raising and capacity building of duty bearers and right holders regarding justice for 2010 violence | Indicator 3.1.1 Number of duty bearers and right holders whose awareness is raised and capacity is strenghtened about mechanisms and tools to address human rights violations including those committeed in the past | Low awareness and capacity of duty bearers and right holders about mechanisms and tools to address human rights violations, including those committeed in the past | By 2016, awareness raising and capacity building of at least 50 duty bearers and 50 right holders on mechanisms and tools to address human rights violations, including those related to the past, are raised and strenghtened | By Sept 2016, ROCA held discussions on transitional justice issues with the Ministry of Justice, the Office of General Prosecutor, the Presidential Administration and Supreme Court. | State authorities are reluctant to discuss transitional justice issues, fearing that the topic could steer resentment in the communities and inter-ethnic strife. | OHCHR is addressing the challenge by adapting the strategy and the activities to the context, focusing more on capacity building and awareness raising activities on transitional justice for the judiciary. |
|  | Indicator 3.1.2 |  |  |  |  |  |
| Output 3.2 | Indicator 3.2.1 |  |  |  |  |  |
|  | Indicator 3.2.2 |  |  |  |  |  |
| Output 3.3 | Indicator 3.3.1 |  |  |  |  |  |
|  | Indicator 3.3.2 |  |  |  |  |  |
| Outcome 4 | Indicator 4.1 |  |  |  |  |  |
|  | Indicator 4.2 |  |  |  |  |  |
| Output 4.1 | Indicator 4.1.1 |  |  |  |  |  |
|  | Indicator 4.1.2 |  |  |  |  |  |
| Output 4.2 | Indicator 4.2.1 |  |  |  |  |  |
|  | Indicator 4.2.2 |  |  |  |  |  |
| Output 4.3 | Indicator 4.3.1 |  |  |  |  |  |
|  | Indicator 4.3.2 |  |  |  |  |  |

PART 2: LESSONS LEARNED AND SUCCESS STORY

2.1 Lessons learned

Provide at least three key lessons learned from the implementation of the project. These can include lessons on the themes supported by the project or the project processes and management.

| Lesson 1 (1000 character limit) | Through the support provided to the Coordination Council on Human Rights (CCHR) the lesson learned is that the role of the the Vice Prime Minister as the Chair of the Coordination Council is crucial. Ministries have shown resistance in cooperation with each other, increasing the need for a strong Coordination Council as a body of coordination between ministries. Due to the need of having a person with greater leverage in solving coordination difficulties, the role of the Vice Prime Minister is central. Furthermore the role of the Deputy Minister of Justice, as the chair of the Secretariat of the CCHR is also essential in ensuring that the coordination function of the Secretariat is fully performed and that the support of OHCHR experts is meaningful. |
| --- | --- |
| Lesson 2 (1000 character limit) | The qualifications of the members of the Expert Working Groups (EWGs) are crucial in ensuring that the draft laws comply with international human rights standards. The lesson learned for ROCA is that more capacity building of the experts on international human rights standards related to criminal justice should have been provided, in order for the experts to ensure that these standards are fully incorporated into the new draft laws. |
| Lesson 3 (1000 character limit) | There was a large number of donors that were providing support to the National Center for Prevention of Torture (NPM) as well as to the Training Centers for Judges, Prosecutors and Lawyers. This, including the sometimes difficult cooperation among donors, has led to training fatigue of the beneficiaries. The lesson learned is the need for strong coordination among the donors and partners working with the NPM and the Training Centers to ensure the best possible results and impact. |
| Lesson 4 (1000 character limit) |  |
| Lesson 5 (1000 character limit) |  |

2.2 Success story (OPTIONAL)

Provide one success story from the project implementation which can be shared on the PBSO website and Newsletter as well as the Annual Report on Fund performance. Please include key facts and figures and any citations (3000 character limit).

OHCHR conducted a series of 6 trainings from February to September 2015 aimed at increasing the professional capacity of 68 selected young counselors and litigators from multi-ethnic districts and cities of the Osh, Jalalabad and Batken  regions (south Kyrgyzstan, that was hit by an inter-ethnic conflict in June 2010).  The trainings were conducted in cooperation with the Lawyers Training Centre and the Bar Association of the Kyrgyz Republic and supported by the Ministry of Justice of the Kyrgyz Republic within the framework of the UN Peacebuilding Fund project “Peace and reconciliation through strengthening the rule of law and protection of human rights,” and covered topics on the effective protection of human rights, advocacy skills and conflict resolution. As a result of these trainings, participants increased their knowledge and improved their skills on specific legal issues. This will help to achieve more effective results in representation and protection of interests of citizens, of human rights at local and international levels, and to overcome various conflict situations. “The knowledge and skills acquired by young lawyers will definitely help greatly in their future work. Such trainings are necessary and are in demand by all counselors and litigators. And the result is qualified and competent protection of the rights and freedoms of citizens of the Kyrgyz Republic", said Gulniza Kojomova, Chairman of the Bar Association.

In addition, participants received the opportunity to work on various projects in the south including on trial monitoring, protection of the right to adequate housing, and protection of the rights of children and vulnerable populations.

The program designed by OHCHR for young lawyers, has become the basis for further training courses on professional advancement of young lawyers of the country. On the basis of this series of trainings, a similar training program has now started for 30 young lawyers from the Chui, Naryn, Talas and Issyk-Kul regions. OHCHR was able to mobilize funds from other donors, such as UNDP  and GIZ . “It’s a wonderful opportunity to share knowledge, experience, practice, vision and points of view with one another. I hope to create an effective group of young lawyers with entirely new approaches to the protection of human rights”, stated Mr Akylbek Tashbulatov, lawyer and trainer.

PART 3 – FINANCIAL PROGRESS AND MANAGEMENT ARRANGEMENTS

  - Comments on the overall state of financial expenditure

Please rate whether project financial expenditures were on track, slightly delayed, or off track:

If expenditure was delayed or off track, please provide a brief explanation (500 characters maximum):

Please provide an overview of project expensed budget by outcome and output as per the table below.

| Output number | Output name | RUNOs | Approved budget | Expensed budget | Any remarks on expenditure |
| --- | --- | --- | --- | --- | --- |
| Outcome 1: Key legislation in the area of administration of justice is in line with international and constitutional human rights standards and the judiciary adjudicates several cases in line with these standards USD 136,500 |
| Output 1.1 | Technical and expert support is provided to the Secretariat of the National Council on Judicial Reform and its Expert Working Groups on elaborating the key laws relating to the administration of justice in line with international human rights standar | OHCHR | USD 95,800 | USD |  |
| Output 1.2 | Technical assistance and capacity building provided to the Supreme Courte judges and staff regarding unification of judicial practices in criminal cases | OHCHR | USD 24,400 | USD |  |
| Output 1.3 | A human rights training package is developed with Supreme Court's Judiciary training centre and Center for Professional Training of Prosecutors | OHCHR | USD 16,300 | USD |  |
| Outcome 2: Adequate functioning of national human rights mechanisms and civil society actors leads to effective protection of human rights and increased accountability for their violations, including through holistic follow up to UN HRM recommendations USD 236,890 |
| Output 2.1 | Institutional support provided to the newly established NPM and capacity building on monitoting places of deprivation of liberty is provided to the staff and members of the Coordination Council | OHCHR | USD 30,300 | USD 30,300 |  |
| Output 2.2 | Institutional support and capapcity building on human rights law and strategic planning is provided to the newly established inter-ministerial entity that will follow up on UN HRM recommendations | OHCHR | USD 52,800 | USD 52,800 |  |
| Output 2.3 | Capacity building for young defence lawyers from multi ethnic towns and districts of southern kyrgyzstan on protecting human rights in criminal proceedings Output 2.4 Technical support and grants provided to faciliate human rights monitoring repor | OHCHR | USD 69,490 USD 84,300 | USD 69,490 USD |  |
| Outcome 3: Duty bearers and right holders engage in dialogue about the importance of addressing grave human rights violations committeed during and in the aftermath of June 2010 events 104,500 USD |
| Output 3.1 | Awareness raising and capacity building of duty bearers and right holders regarding justice for 2010 violence | OHCHR | USD 104,500 | USD |  |
| Output 3.2 |  |  |  |  |  |
| Output 3.3 |  |  |  |  |  |
| Outcome 4: |
| Output 4.1 |  |  |  |  |  |
| Output 4.2 |  |  |  |  |  |
| Output 4.3 |  |  |  |  |  |
| Total |  |  |  |  |  |

  - Comments on management and implementation arrangements

Please comment on the management and implementation arrangements for the project, such as: the effectiveness of the implementation partnerships, coordination/coherence with other projects, any South-South cooperation, the modalities of support, any capacity building aspect, the use of partner country systems if any, the support by the PBF Secretariat and oversight by the Joint Steering Committee (for PRF only). Please also mention if there have been any changes to the project (what kind and when) (2000 character maximum):

N/A

# Footnotes

The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to “Project ID” on the MPTF Office GATEWAY

The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY

As per approval of the original project document by the relevant decision-making body/Steering Committee.

If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed.

Please note that financial information is preliminary pending submission of annual financial report to the Administrative Agent.