RUNO END PRF PROJECT REPORTING					TEMPLATE 4.5

PEACEBUILDING FUND (PBF)

END OF PROJECT report

COUNTRY: Sri Lanka

REPORTING PERIOD: 14 April 2016 to 31 December 2017

| Programme Title & Project Number |  |
| --- | --- |
| Programme Title: Support for Sri Lanka to design transitional justice mechanisms: Phase 1: National consultations and design of follow-up strategy. Programme Number (if applicable) PBF IRF 138 MPTF Office Project Reference Number: 0099958 |  |  |

| Recipient UN Organizations |  | Implementing Partners |
| --- | --- | --- |
| List the organizations that have received direct funding from the MPTF Office under this programme: OHCHR |  | List the national counterparts (government, private, NGOs & others) and other International Organizations: Ministry of Foreign Affairs, Secretariat for Coordinating and Reconciliation Mechanisms (SCRM), Ministry of Justice, Office of National Unity and Reconciliation (ONUR), other line ministries as appropriate, local civil society partners. |
| Programme/Project Budget (US$) |  | Programme Duration |
| PBF contribution (by RUNO) 1,000,000 |  |  | Overall Duration (months) 20,5 |  |
|  |  |  | Start Date (dd.mm.yyyy) 14 April 2016 |  |
| Government Contribution (if applicable) |  |  | Original End Date (dd.mm.yyyy) | 13 October 2017 |
| Other Contributions (donors) (if applicable) |  |  | Final End date(dd.mm.yyyy) 31 December 2017 (no cost extension granted in March 2017). |  |
| TOTAL: |  |  |  |  |

| Programme Assessment/Review/Mid-Term Eval. |  | Report Submitted By |
| --- | --- | --- |
| Mid-Term Evaluation / Review - if applicable please attach Yes No Date: End of project Evaluation– if applicable please attach Yes No Date: forthcoming (March 2018) |  | Name: Juan Fernandez Jardon Title: Senior Human Rights Adviser, Sri Lanka Participating Organization (Lead): OHCHR Email address: juan.fernandez@one.un.org |

PART 1 – RESULTS PROGRESS

  - Assessment of the project implementation status and results

For PRF projects, please identify Priority Plan outcome and indicators to which this project has contributed:

Priority Plan Outcome to which the project has contributed.

Priority Plan Outcome indicator(s) to which project has contributed.

For both IRF and PRF projects, please rate this project’s overall achievement of results to date:

For both IRF and PRF projects, outline progress against each project outcome, using the format below. The space in the template allows for up to four project outcomes.

Outcome Statement 1:  A National Consultation process that captures diverse views and opinions of different stakeholders of Sri Lankan society on mechanisms for the promotion of truth, justice, reparation and guarantees of non-recurrence.

Rate the current status of the outcome:

Output progress at the end of project

List the key outputs achieved under this Outcome (1000 character limit).Outputs are the immediate deliverables for a project.

A) Regarding consultations:

- Report of the Consultation Task Force on Reconciliation Mechanisms (CTF) published on 3 January 2017, containing over 7300 submission from 15 zones

- Report contains an Executive Summary with Recommendations and two Volumes (Final report; Zonal Task Forces Consolidated Report): http://www.scrm.gov.lk/documents-reports;

- Support of 100 public meetings, dozens of closed focus group discussions with special groups.

b) Regarding archiving (continued under the PBF):

- Preservation of all CTF records;

- Development of basic security procedures to ensure protection;

- Consolidation and filing of over 1100 written submissions and material;

- Consolidation and organisation of over 800 hours of audio from submissions made at public meetings, which constitute 4872 oral submissions;

- All submissions were tagged to faciliate access by future TJ mechanisms, and the public.

c) Continued leadership, advocacy and legal advice on TJ by two OHCHR senior level staff.

Outcome progress at the end of project

Describe progress made toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers (3000 character limit)?

A) Project contributed to embedding a process of broad based and inclusive National Consultations on Reconciliation Mechanisms throughout the country through the support provided to the Consultation Task Force (CTF), including to 15 Zonal Task Forces (ZTF). Enabled through this support, the CTF collected over 7300 submission from 15 zones around the country.

b) Published in January 2017, the CTF report was praised by the High Commissioner for Human Rights, requesting the Government to embrace the CTF's recommendations (A/HRC/34/20, paras. 13-15, 65a), which relate to the four elements of transitional justice, and additionally identify important aspects for reconcilation efforts, such as the need for psycho-social support structures etc. The Special Rapporteur on transitional justice has concluded that the CTF report "reflects the most thorough representation up to now of the voices of those affected ." (http://www.ohchr.org/EN/NewsEvents/Pages/DisplayNews.aspx?NewsID=22274&LangID=E)

c) With the translation of the full report into the local languages (Sinhala and Tamil), the report has had a broader readership beyond bigger agglomerations. Efforts are underway (under the PBF project) to reach an even broader audience with the CTF report being put in different formats that facilitate access.

d) Support to the archiving of the documents collected by the CTF report enabled to secure and preserve all records to prevent loss, damage, degradation and destruction. These archives will be an important source for all future transitional justice mechanisms in Sri Lanka. This is the first time that a concerted effort was made in Sri Lanka to preserve, store, tag records in such a way that the rights of the victims and the population to truth, justice, reparation and non-recurrence can be fullfilled.

e) Overall, the transitional justice process has progressed slowly during 2017, as noted by the March 2017 High Commissioner’s report. On the basis of this report, the Human Rights Council in March 2017 decided to grant two more years to Sri Lanka for the implementation of the commitments undertaken by the Government, which is to be monitored by the High Commissioner.

f) Despite this slow progress, the project is having a positive impact on peacebuilding:

The CTF Report includes a great number of solid recommendations pertaining to transitional justice and peacebuilding more widely. Despite some distance being placed between the Government and the report, its recommendations are being considered by the Working Groups responsible for design of the TJ mechanisms and related policy, and serves as a solid and strong advocacy tool for civil society and victims' groups.

With the CTF archiving being finalised, the PBF project is facilitating access to those  records, while protecting privacy rights.

Reasons for low achievement and rectifying measures

If sufficient progress was not made, what were the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How were they addressed (1500 character limit)?

The CTF project makes several key recommendations. Under the PBF project, efforts are being continued to encourage the Government to take these recommendations into account when progressing on the development of TJ mechanisms.

Outcome Statement 2:  Sri Lankan stakeholders obtain a basic knowledge and understanding of transitional justice processes that will put them in a position to implement Human Rights Council Resolution 30/1 of 2015 (linked to outcome 1).

Rate the current status of the outcome:

Output progress at the end of project

List the key outputs achieved under this Outcome (1000 character limit).Outputs are the immediate deliverables for a project.

A) About 50 awareness programme activities were conducted by civil society organisations funded with 10 small grants awarded by OHCHR as part of the project. These awareness raising activites targeted different stakeholders, which helped to increase the baseline understanding of the consultation process as well as different aspects of transitional justice.

b) These awareness programmes were reinforced by the work done at district level by the 15 Zonal Task Forces supported by the project.

c) As a result, these programmes enabled a broad-based participation of key stakeholders, enhancing inclusiveness and providing a voice to different vulnerable groups, which was critical for achieving a comprehensiveness National Consultations process.

Outcome progress at the end of project

Describe progress made toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers (3000 character limit)?

A) - Through the different project activities, particularly the awarness raising programmes and the support provided to the CTF and the ZTFs, the project has promoted implementation of Resolution 30/1 and enhanced understanding on transitional justice through high level advocacy, outreach to civil society and grassroot based programmes with victims groups.

b) - The project supported high level engagement between the UN and the Government, including  visits by different special procedures of the Human Rights Council, and in particular the continued engagement by the Special Rapporteur on transitional justice, to advocate for progressive and sustained transitional justice measures and reforms in line with non-recurrence.

c) -  Beyond eliciting views of the population, particularly victims, the consultation process, including the awareness raising activities, contributed to the broadening of  understanding on transitional justice among a range of civil society actors as well as various victims' groups. This has most recently been acknowledged by the Special Rapporteur on transitional justice, highlighting "a very steep learning curve regarding transitional justice issues" (http://www.ohchr.org/EN/NewsEvents/Pages/DisplayNews.aspx?NewsID=22274&LangID=E).

d) It also strengthened the role of civil society and victims groups in terms of advocacy, and provided space  to engage with the political leadership on a variety of different aspects pertaining to transitional justice and reconciliation. Consequently, the project has contributed to address a capacity deficit among different key actors. The capacity built through the different project activities, including the archiving of the CTF records, is contributing to a more sustainable and continuous advocacy process on transitional justice and reconciliation, preventing renewed violations.

Although this project has increased and widened stakeholder understanding of transitional justice and the provided key officers in both civil society and government with the conceptual underpinnings necessary to implement HRC 30/1, the knowledge gained has not yet translated into correspondingly substantive action on the ground in terms of progress by the government on advancing the transitional justice mechanisms. For civil society stakeholders this risks increasing frustrations at the speed of progress.

Reasons for low achievement and rectifying measures

If sufficient progress was not made, what were the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How were they addressed (1500 character limit)?

Although this project has increased and widened stakeholder understanding of transitional justice and the provided key officers in both civil society and government with the conceptual underpinnings necessary to implement HRC 30/1, the knowledge gained has not yet translated into correspondingly substantive action on the ground in terms progress on advancing the transitional justice mechanisms. For civil society stakeholders and progressive government officers, this risks increasing frustrations at the speed of progress.

With adoption of resolution 34/1 of 2017, the Human Rights Council provided two more years for the implementation of the commitments made by Sri Lanka. Activities, which continue and sustain the different programmes under this project, have been deviced under Pillar 1 on 'Transitional Justice' of the PBF project.

Outcome Statement 3:

Rate the current status of the outcome:

Output progress at the end of project

List the key outputs achieved under this Outcome (1000 character limit).Outputs are the immediate deliverables for a project.

Outcome progress at the end of project

Describe progress made toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers (3000 character limit)?

Reasons for low achievement and rectifying measures

If sufficient progress was not made, what were the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How were they addressed (1500 character limit)?

Outcome Statement 4:

Rate the current status of the outcome:

Output progress at the end of project

List the key outputs achieved under this Outcome (1000 character limit).Outputs are the immediate deliverables for a project.

Outcome progress at the end of project

Describe progress made toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers (3000 character limit)?

Reasons for low achievement and rectifying measures

If sufficient progress was not made, what were the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How were they addressed (1500 character limit)?

  - Assessment of project evidence base, risk, catalytic effects, gender at the end of the project

| Evidence base: What was the evidence base for this report and for project progress? What consultation/validation process has taken place on this report (1000 character limit)? | The departing point or baseline for the Transitional Justice process was the Report of the OHCHR Investigation on Sri Lanka together with Human Rights Council Resolution 30/1 that identified the needs of Sri Lanka in terms of promoting accountability, reconciliation and human rights. Both contained recommendations for the way forward and (with respect to HRC 30/1) included the commitments of the Government in terms of TJ and other human rights related reforms. The HRC tasked the High Commissioner for Human Rights to report back to the Council on progress on implementation of the Resolution in June 2016 (oral update), March 2017 (Report), and subsequently in March 2018 and March 2019 (through resolution 34/1). Observations of Special procedures mandate holders after their respective missions to Sri Lanka and those of the High Commissioner are also used for validation. |
| --- | --- |
| Funding gaps: Did the project fill critical funding gaps in peacebuilding in the country? Briefly describe. (1500 character limit) | In 2016, the project filled critical funding gaps in newly created structures dealing with transitional justice, in particular the Consultation Task Force on Reconciliation Mechanisms (CTF) and the Secretariat for the Coordination of Reconciliation Mechanisms (SCRM). At the end of the Consultations process (November 2016), SCRM had only just secured its Government budget (to begin from Dec 2016). Hence, it should be noted that without IRF/PBF support, the National Consultations process and the report's release in January 2017 could not have been conducted within the given timeframe. Furthermore, the project filled a funding gap by providing 7 months funding for the positions of the Senior Human Rights Adviser and the Transitional Justice Adviser, who were substantively advising on transitional justice and reconciliation issues as well as designing and implementing the IRF project and the Transitional Justice Pillar of the PBF project. |
| Catalytic effects: Did the project achieve any catalytic effects, either through attracting additional funding commitments or creating immediate conditions to unblock/ accelerate peace relevant processes? Briefly describe. (1500 character limit) | In 2017, the project continued to capitalize on its previous gains. A joint PBF project on TJ (with UNDP, OHCHR, IOM) and projects with development partners (EU, UK, Germany) have been designed partially as follow up of the Consultations and TJ processes kickstarted by this IRF project. Aside from PBF funds, OHCHR and the RCO have mobilised an additional $2.5m for transitional justice. In the second half of 2017, a number of potential donors approached the RCO and OHCHR to suggest funding proposals in the area of transitional justice. |
| Risk taking/ innovation: Did the project support any innovative or risky activities to achieve peacebuilding results? What were they and what was the result? (1500 character limit) | One of the innovative aspects of the project was the awarding of small scale grants to NGOs to undertake awareness raising programmes on TJ prior to and during the consultations. The grant selection assumed the risk of involving small grassroots groups with limited delivery capacity in order to achieve geographical coverage. The risk was mitigated through a stringent grants approval process, containing a quality check of those programmes. The grants enabled the NGOs to solidify their theoretical and practical TJ knowledge. As a result, beyond the awareness built among the vicitms and the population, the grants led to an empowernment of these NGOs, which is manifested by their strengthened advocacy and programming work around TJ and reconciliation. |
| Gender marker: How have gender considerations been mainstreamed in the project to the extent possible? Is the original gender marker for the project still the right one? Briefly justify. (1500 character limit) | Gender marker 2 Gender consideratios have continuously been taken into account in the implementation of the project, including through the support of specific focus meetings with women, undertaken by the CTF and the ZTFs. The composition itself of the CTF and its ZTFs reflected gender parity (and several members had specific background in gender rights) and the CTF report contains thorough analysis as to the gender-related impact of past violations. This, and other assessments, serve as a solid basis for the development of future gender specific projects, as conceived under the PBF and other funding sources (including in relation to work on reparation for conflict related sexual violence). |
| Other issues: Are there any other issues concerning project implementation that should be shared with PBSO? This can include any cross-cutting issues or other issues which have not been included in the report so far. (1500 character limit) | 1) The administrative burden was significantly heightened as the budget was first provided to OHCHR/Geneva, and then needed to be authorized in a cumbersome procedure to the Colombo OHCHR structure. Given that OHCHR has no country office in Sri Lanka, the management of similar projects should preferably be done through UNDP, while the OHCHR Senior Human Rights Adviser retains the leading role for the substantive implementation, guidance and possible re-adjustments of the project activities. Due to the complexity of the structure of the Consultation Task Force on Reconciliation Mechanisms (including their Zonal Task Forces) under the auspices of the Secretariat for the Coordination of Reconciliation Mechanisms, the provision of support had experienced challenges in its initial phase. These were mitigated through innovative interim administrative measures. |

1.3 INDICATOR BASED PERFORMANCE ASSESSMENT: Using the Project Results Framework as per the approved project document- provide an update on the achievement of key indicators at both the outcome and output level in the table below. Where it has not been possible to collect data on indicators, state this and provide any explanation in the qualitative text above. (300 characters max per entry)

|  | Performance Indicators | Indicator Baseline | End of project Indicator Target | Current indicator progress | Reasons for Variance/ Delay (if any) | Adjustment of target (if any) |
| --- | --- | --- | --- | --- | --- | --- |
| Outcome 1 A National Consultation process that captures diverse views and opinions of different stakeholders in SL society on truth, justice, reparation and guarantees of non-recurrence. | Indicator 1.1 Conflict affected groups are enabled through consultations to participate in an informed and effective manner in shaping a common vision for the establishment of credible and effective transitional justice mechanisms. | The government, victims, and civil society lack common grounds, and a timeline for national consultations Lack of an independent, credible and representative body to undertake national consultations | Consultations conducted. Final report on the findings of the National Consultation Process presented to the public | The National Consultations Task Force (CTF) received over 7300 written subissions from individuals, conducted interviews and had focus group sessions. (Feb - Sept 2016). The report was released on 3 January 2017. Different technical groups (including within SCRM) took CTF report's recommendations . |  | Achieved. |
|  | Indicator 1.2 Broad and inclusive participation of key stakeholders so as to provide voice for vulnerable groups. | Limited understanding of the consultation process and transitional justice at large among victim, other vulnerable groups and society at learge. | Capacity and knowledge of a significant number of vulnerable groups and victims' groups enhanced on TJ mechanisms so as to effectively feed into the consultations. Reports submitted by all ten CSOs in January 2017 on small grant awareness programmes. | CTF report reflects the inclusivity and the views of the breath of stakeholders, which benefitted from the awareness raising programmes (OHCHR provided for 10 small grants to CSOs to broaden the scope of those feeding into the consultations). |  | Achieved as reflected in the material of the CTF. |
|  | Indicator 1.3 |  |  |  |  |  |
| Output 1.1 Technical assistance provided by OHCHR to the Ministry of Foreign Affairs and relevant stakeholders to conduct National Consultations. | Indicator 1.1.1 Strengthening of OHCHR's capacity on TJ matters through the deployment of one international human rights officer to Colombo. | A HRO with TJ knowledge deployed to Office of Senior Human Rights Officer. | A HRO with TJ expertise accompanies the process throughout. | Further to the departure of the initially deployed HRO with TJ expertise, replacement was enabled through this project. Therefore SHRA accompanies the process continuously. |  | Achieved. |
|  | Indicator 1.1.2 Deployment of two National UNVs to assist SCRM and six UNVs to assist HRCSL with the support of Resident coordinator's office. | Capacity gaps in the CTF, SCRM and HRCSL. | SCRM, CTF and HRCSL have appropriate capacity to implement their mandate. | 3 UNVs to assist the MFA and the CTF and early support to the SCRM. The CTF requested and received additional researchers through this project, including for translation purposes. |  | Achieved |
| Output 1.2 Support provided to Government in designing and establishing a historical record managemnet system, which would support future accountability, truth, reparation and memorialization intitiatives (also under output 2.2.1.). | Indicator 1.2.1 Archived material is preserved in an appropriate manner, indexing of material allows for use in future TJ mechanisms, and access of the public to database strengthens knowledge about views expressed during the consultations and needs identified. | No archiving of the material collected during the national consultations. | Long-term preservation of all submissions made to the CTF and ZTFs at public meetings (including oral recordings), sectoral consultations, and received via post and email ensured; Tagging of all material and indexing for reference Searchable digital database developped. | Recruitment of three researchers, one coordinating officer and two senior officers (former CTF members) to undertake the archiving project. Support of a 5 days training programme to the newly recruited archiving team, conducted by external experts. |  | Preservation and tagging achieved. Database development ongoing. |
|  | Indicator 1.2.2 |  |  |  |  |  |
| Output 1.3 | Indicator 1.3.1 |  |  |  |  |  |
|  | Indicator 1.3.2 |  |  |  |  |  |
| Outcome 2 Sri Lankan stakeholders obtain knowledge and understanding of Transitional Justice process that will put them in a position to implement the Human Rights Council Resolution 30/1 of 2015 | Indicator 2.1 see below under output indicators. |  |  |  |  |  |
|  | Indicator 2.2 |  |  |  |  |  |
| Output 2.1 Strengthened capacity of key stakeholders on TJ principles and standards so as to faciliate broad based and informed participation in the process of establishing credible and effective mechanisms. | Indicator 2.1.1 Sensitisation and training sessions with Government. Number of officials reached. | No specialized or dedicated TJ knowledge in Government. No comprehensive framework. | A comprehensive TJ strategy/plan designed and implemented by dedicated Government experts. | Through continuous exchanges in preparation of HC report to the HRC in March 2017, and in follow-up of the report, awarness raised on the key deliverables among Government actors. The OHCHR team funded by IRF supported 6 visits by special procedures (4 Special Rapporteurs and 2 Working Groups) |  | Draft comprehensive strategy prepared, being examined by the executive. Delays ocurred in relation to the study of the comprehnsive strategy/plan by the executive. |
|  | Indicator 2.1.2 Continuing exchanges with victims and their representatives in relation to the commitments undertaken in HRC resolution 30/1 (now 34/1) so as to enable them to feed effectively into the process. | Limited knowledge and exposure to the process of monitoring by the High Commissioner through reports to the Human Rights Council. | Civil society and victims groups are organised in an advocacy umbrella to push for progress on TJ mechanisms, in particular the Office of Missing Persons. | Regular meetings with civil society and victims on the progress of the TJ mechanisms (including with RC) in North & East and Colombo. Continuing dissimination of OISL report and HRC resolution 30/1 to universities and libraries throughout Sri Lanka. |  | Continuing fragmentation of civil society hampers the building of a strong advicacy based around a few fundamental principles. Victims and their groups have come more regularly to capital to engage with authorities directly, which furthered the gazetting of the OMP. |
| Output 2.2 Relevant stakeholders are supported in their early brainstorming and conceptualization of TJ policies and measures that ensure accountability for human rights violations and provide effective redress, effective remedies and reparations to victims. | Indicator 2.2.1 Advice provided to Government. | Limited knowledge of TJ with respect to mapping, documentation and archiving. | Technical capacity to conduct specialised TJ work on mapping, documentation and archiving. | Recruitment of three researchers, one coordinating officer and two senior officers (former CTF members) to undertake the archiving project. Support of a 5 days training programme to the newly recruited archiving team, by experts (April 2017). |  | Technical capacity of about 45 stakeholders on importance of archiving in the context of TJ strengthened. Solid capacity of the archiving team of the CTF (7 individuals) built. Capacity building on documentation and mapping is ongoing. |
|  | Indicator 2.2.2 Legislation put in place on the TJ mechanisms. | Existing legislation inadequate to accompany a TJ process. | Legislation allows and facilitates the implementation of a comprehensive TJ strategy. | Cooperation with IOM on the scope of current reparations programmes undertaken in the country, together with representatives of the SCRM and the Rehabilitation of Persons, Properties and Industries Authority (REPPIA), 16-17 April 2017. |  | Only legislation of the OMP gazetted with effective start of functioning expected towards the end of 2017. Draft frameworks of the truth mechanism and the reparation office prepared, but still being studied by the executive (delays in relation to this). |
| Output 2.3 | Indicator 2.3.1 Advice provided to UNCT enables its members to take into account issues of TJ and accountability in their programming. | Limited knowledge about TJ among most members of the UNCT. | Knowledge among UNCT members on TJ and accountability issues significantly increased so as to contribute with the programming to implementation of HRC resolution 30/1 (now 34/1). | Targeted training undertaken by OHCHR staff funded by this project and international experts on the concept of TJ and the pupose of a comprehensive TJ strategy. TJ experts from Colombia presented TJ experience in Colombia and its possible challenges. |  | TJ knowledge on TJ among UNCT increased. Still need for follow-up training, both on basics of TJ as well as on case studies of other countries. |
|  | Indicator 2.3.2 |  |  |  |  |  |
| Outcome 3 | Indicator 3.1 |  |  |  |  |  |
|  | Indicator 3.2 |  |  |  |  |  |
| Output 3.1 | Indicator 3.1.1 |  |  |  |  |  |
|  | Indicator 3.1.2 |  |  |  |  |  |
| Output 3.2 | Indicator 3.2.1 |  |  |  |  |  |
|  | Indicator 3.2.2 |  |  |  |  |  |
| Output 3.3 | Indicator 3.3.1 |  |  |  |  |  |
|  | Indicator 3.3.2 |  |  |  |  |  |
| Outcome 4 | Indicator 4.1 |  |  |  |  |  |
|  | Indicator 4.2 |  |  |  |  |  |
| Output 4.1 | Indicator 4.1.1 |  |  |  |  |  |
|  | Indicator 4.1.2 |  |  |  |  |  |
| Output 4.2 | Indicator 4.2.1 |  |  |  |  |  |
|  | Indicator 4.2.2 |  |  |  |  |  |
| Output 4.3 | Indicator 4.3.1 |  |  |  |  |  |
|  | Indicator 4.3.2 |  |  |  |  |  |

PART 2: LESSONS LEARNED AND SUCCESS STORY

2.1 Lessons learned

Provide at least three key lessons learned from the implementation of the project. These can include lessons on the themes supported by the project or the project processes and management.

| Lesson 1 (1000 character limit) | The presence of two senior OHCHR Advisers (Senior Human Rights Adviser; Transitional Justice Adviser) accompanying the transitional justice has had signifanct impact on the sustainability of the project. These positions have advanced UN advocacy access, built local capacities for transitional justice, enabled the provision of targeted technical expertise, and created spaces for strategic decisions on the priorization of project activities. Their impact on securing robust archiving facilities establishes a valuable resource for future transitional justice mechanisms to access to records of the CTF. This impact and the high level relationships that the team has developed has underlined the need for the continuity of a senior presence tasked with handling advocacy, direct technical expertise and programming. Together with substantive knowledge of transitional justice this continuity is crtical to the potential for deriving significant peacebuilding impact from these positions. |
| --- | --- |
| Lesson 2 (1000 character limit) | Support to the consultation process contributed significantly to the building of trust between victims, civil society and, to a certain degree, relevant Government institutions. At the same time, the consultation process has created enhanced capacities within civil society and relevant government entities. It empowered civil society leaders to advocate strongly for a number of changes and inclusions related to transitional justice planning. |
| Lesson 3 (1000 character limit) | Given the Government's distanced reaction in relation to the report of the CTF, and its recommendations, it was crucial to support the report's translation into all three languages with a view to faciliate access and broaden the report's readership. At the same time, the archiving activities in relation to material of the CTF, guarantee on the one hand the preservation of records that might otherwise be at risk, and on the other the building on structures established by the CTF in order to faciliate a continuing dialogue. |
| Lesson 4 (1000 character limit) |  |
| Lesson 5 (1000 character limit) |  |

2.2 Success story (OPTIONAL)

Provide one success story from the project implementation which can be shared on the PBSO website and Newsletter as well as the Annual Report on Fund performance. Please include key facts and figures and any citations (3000 character limit).

During his country visit to Sri Lanka from 10 to 23 October 2017, the Special Rapporteur on the promotion of truth, justice, reparation and guarantees of non-recurrence met with over 120 victims and victims' representatives throughout the country. Several of the individuals he discussed with had acted as Zonal Task Force members for the Consultation Task Force on Reconciliation Mechanisms, established by the Government in January 2016.

The Special Rapporteur, who paid a first visit to the country in early 2015, highlighted a number of positive changes in that respect. First, he noted the "very steep learning curve" of  both civil society and parts of government regarding transitional justice issues. He further noted, that while still underutilized, Sri Lankan civil society is "making crucial contributions to transitional justice debates". Second, he highlighted the very important development  the work of the Consultations Task Force on Reconciliation Mechanisms (CTF), "displaying a degree of commitment that deserves to be celebrated." He further noted that "the CTF managed to establish its presence broadly and deeply in the country, including at the local level." He went on by underscoring that "up to this point, this is the most comprehensive effort to capture the views of victims and others on transitional justice questions." In conclusion, he stresses that "the report reflects the most thorough representation up to now of the voices of those affected."

Statement available at:

http://lk.one.un.org/news/full-statement-by-pablo-de-greiff-un-special-rapporteur-on-the-promotion-of-truth-justice-reparation-and-guarantees-of-non-recurrence-at-the-conclusion-of-his-official-visit/

PART 3 – FINANCIAL PROGRESS AND MANAGEMENT ARRANGEMENTS

  - Comments on the overall state of financial expenditure

Please rate whether project financial expenditures were on track, slightly delayed, or off track:

If expenditure was delayed or off track, please provide a brief explanation (500 characters maximum):

Please provide an overview of project expensed budget by outcome and output as per the table below.

| Output number | Output name | RUNOs | Approved budget | Expensed budget | Any remarks on expenditure |
| --- | --- | --- | --- | --- | --- |
| Outcome 1: A National Consultation process that captures diverse views and opinions of different stakeholders in SL society on truth, justice, reparation and guarantees of non-recurrence. |
| Output 1.1 | Technical assistance provided by OHCHR to the Ministry of Foreign Affairs and relevant stakeholders to conduct National Consultations. | OHCHR | N/A | 366,150 |  |
| Output 1.2 | Support provided to the Government in designing and establishing a historical record management system, which would support future accountability, truth, reparation and memorialization intitiatives (also under output 2.2.1.). | OHCHR | N/A | 58,536 |  |
| Output 1.3 |  |  |  |  |  |
| Outcome 2: Sri Lankan stakeholders obtain knowledge and understanding of Transitional Justice process that will put them in a position to implement the Human Rights Council Resolution 30/1 of 2015 |
| Output 2.1 | Strengthened capacity of key stakeholders on TJ principles and standards so as to faciliate broad based and informed participation in the process of establishing credible and effective mechanisms. | OHCHR | N/A | 167,508 |  |
| Output 2.2 | Relevant stakeholders are supported in their early brainstorming and conceptualization of TJ policies and measures that ensure accountability for human rights violations and provide effective redress, effective remedies and reparations to victims. | OHCHR | N/A | 167,508 |  |
| Output 2.3 |  |  |  |  |  |
| Outcome 3: |
| Output 3.1 |  |  |  |  |  |
| Output 3.2 |  |  |  |  |  |
| Output 3.3 |  |  |  |  |  |
| Outcome 4: |
| Output 4.1 |  |  |  |  |  |
| Output 4.2 |  |  |  |  |  |
| Output 4.3 |  |  |  |  |  |
| Total |  |  |  | 759,702 (as at 31/10/2017) expected 839,715 (as at 31/12/2017) | 76 % (as at 31/10/2017) expected 84 % (as at 31/12/2017) |

  - Comments on management and implementation arrangements

Please comment on the management and implementation arrangements for the project, such as: the effectiveness of the implementation partnerships, coordination/coherence with other projects, any South-South cooperation, the modalities of support, any capacity building aspect, the use of partner country systems if any, the support by the PBF Secretariat and oversight by the Joint Steering Committee (for PRF only). Please also mention if there have been any changes to the project (what kind and when) (2000 character maximum):

# Footnotes

The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to “Project ID” on the MPTF Office GATEWAY

The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY

As per approval of the original project document by the relevant decision-making body/Steering Committee.

If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed.

Please note that financial information is preliminary pending submission of annual financial report to the Administrative Agent.