| Project Number and Title: #33- Restoring Midwifery Services in Ebola most-affected counties | PROJECT START DATE: 19-10-2015 | AMOUNT ALLOCATED by MPTF (please indicate different tranches if applicable) $1,000,000 | RECIPIENT ORGANIZATION United Nations Populations Fund |
| --- | --- | --- | --- |
| Project ID: 00096703 (Gateway ID) |  |  |  |
| Project Focal Point: Name: Philderald E. Pratt E-mail:Pratt@unfpa.org gobeh@unfpa.org | EXTENSION DATE: dd-mm-yyyy | FINANCIAL COMMITMENTS $... |  |
| Strategic Objective (STEPP) RSO1 : Health, Nutrition, and Water, Sanitation and Hygiene (WASH) | PROJECTED END DATE: 15-09-2016 | EXPENDITURES as of [June 30,2016] $492,617.66 | IMPLEMENTING PARTNER(S): UNFPA Two other partners are as follow; Jhpiego (Sub contractee) Ministry of Health (sub contractee) |
| Mission Critical Action MCA6: Access to basic services |  |  |  |

| Location: Liberia – West Africa Country or Regional | Sub-National Coverage Areas: Full list of countries and/or districts Three Counties including : Lofa County Grand Cape Mount Gbarpolu County |
| --- | --- |

QUARTERLY PROGRESS REPORT RESULTS MATRIX OUTPUT INDICATORS Number of BEmONC facilities providing all signal functions Proportion of met need for EmONC per county Number of clients of family planning who access services from community based distributors of family planning commodities Number of maternal deaths reports and response conducted per county Number of diseases including EVD reported and investigated per county Indicator Geographic Area Projected Target (as per results matrix) Quantitative results for the quarterly reporting period Cumulative results since Project commencement (quantitative) Delivery Rate (cumulative % of projected total) as of date Description of the quantifiable indicator as set out in the approved project proposal Output 1: Strengthened capacity of health systems to deliver emergency obstetric and newborn care including management of fistulae in selected health institutions for women and young people. Number of BEmONC facilities providing all signal functions Lofa Grand Cape Mount Gbarpolu 9 4/9 5/9 55% Proportion of met need for EmONC per county Lofa Grand Cape Mount Gbarpolu To be provided next quarter To be provided next quarter To be provided next quarter To be provided next quarter Sub output 1.1: Human Resource capacity is strengthened to ensure quality service delivery Number of international obstetric teams trained and deployed to provide Obstetrical and Gynecological services including medical and surgical services Lofa Grand Cape Mount Gbarpolu 2 0 0 35% Number of national midwives newly recruited, trained and deployed to provide services including Infection Prevention and control (IPC)procedures Lofa Grand Cape Mount Gbarpolu 15 8 14 98% Sub output 1.2: Health facility capacity to provide Maternal Health services including EmONC and family planning Services improved through training, supply of commodities and monitoring Number of BEmONC facilities supported to provide services with full IPC for infection prevention and all 7 signal functions 7days a week 24 hours Targets Lofa = 4 Gbarpolu= 2 GCM= 3 Lofa=2 Gbarpolu = 0 GCM= 2 Progress has been made with most facilities lacking only one or two functions compared to more at baseline 4 health facilities are fully BEmONC compliant while others are partially compliant 44% Proportion of Caesarean Sections conducted in CEmONC facilities per county Targets= 10% to 15% for all one hospital 45% of all deliveries during the quarter resulted to Caesarean Section 31% of all deliveries 31% Proportion of women attending four ANC visits per quarter Targets= Lofa and Gbarpolu 70% GCM = 75% Lofa and Gbarpolu 70% GCM = 75% Lofa 59.2% Gbarpolu 24.4% GCM = 69.2% Lofa 57% Gbarpolu 31% GCM = 69% Output 2: Strengthened National Systems for Reproductive Health Commodity Security Number of clients of family planning who access services from community based distributors of family planning commodities Number of clients of family planning who access services from community based distributors of family planning commodities Lofa Grand Cape Mount Gbarpolu Targets= Lofa 80 Gbarpolu 50 GCM = 50 Lofa =0 Gbarpolu =0 GCM =0 Lofa =0 Gbarpolu =0 GCM = 0 0% CHW have been trained but no yet started distribution of FP commodities Proportion of Health facilities with no stock out of essential drugs and medicines Lofa Grand Cape Mount Gbarpolu Targets= 100% of all facilities per county Stock out of antibiotics is still a challenged for few facilities 7/9 facilities have reported no stock out of essential drugs such as antibiotics 78% Proportion of Health facilities with no stock out of at least five modern method of contraceptives Lofa Grand Cape Mount Gbarpolu Targets=100% of all facilities per county Some health facilities reported stock out of one or two Family Planning commodities including Injectable contraceptives and Implants 6/9 facilities have reported no stock out of essential drugs such as antibiotics 67% Number of active community health and development committees that are functional and support community delivery of maternal health services Targets = Lofa= 15 Gbarpolu =8 GCM = 10 Lofa= 6 Gbarpolu =2 GCM = 6 28 CHDC functional 84% Number of CHWs conducting surveillance activities related to ebola prevention and promotion of maternal and newborn health care in project locations Targets Lofa= 150 Gbarpolu = 80 GCM= 100 Quarter Achievements Lofa= 49 Gbarpolu = 14 GCM= 12 Achievements Lofa= 105 Gbarpolu = 48 GCM= 72 68% (The target may have been exaggerated) Number of Community Distributors for FP commodities in targeted Counties Targets Lofa = 80 Gbarpolu =50 GCM= 50 Quarter Achievements Lofa = 35 Gbarpolu =20 GCM= 20 Lofa = 50 Gbarpolu =35 GCM= 35 36% Output 3: Enhanced national capacity for Disease surveillance and data availability during humanitarian situation Output Indicators: Number of maternal deaths reports and response conducted per county Number of diseases including EVD reported and investigated per county Proportion of reportable events that occur in targeted communities that are reported and investigated as per protocol Targets= 100% per county two maternal deaths and eleven neonatal deaths 4 maternal deaths and 16 newborn deaths 6 maternal deaths and 27 neonatal deaths have occurred N/A Number of Districts with functional maternal death surveillance and response systems in place Targets= Lofa= 60% Gbarpolu = 60% GCM= 70% All health districts in each county have MNDSR in place as evidenced by the presence of District Surveillance Officers All health districts in each county have MNDSR in place as evidenced by the presence of District Surveillance Officers 100% EFFECT INDICATORS (if available for the reporting period) Proportion of Skilled Institutional Deliveries increased Couple Years Protection for Family Planning increased by 50%

NARRATIVE Situation Update (please describe critical changes, if any, in the situation that affect the project (1-2 paragraphs)) The project set out to address three main objectives including the following; (1) Improve access to quality safe delivery by providing Emergency Obstetric and New born care services to all women in catchment communities of the target health facilities during post ebola period (2) Improve the application of universal precaution/Infection Prevention services in targeted health facilities through training and provision of supplies and lastly (3) increase community engagement and enhance the participation in community surveillance activities through outreach and promotional activities. The duration of the project is 12 months and although it is in its 10th month of implementation, it was slightly delayed by two round months as a direct result of delays in the initiation of active implementation.” Three major outputs/results are expected to be achieved by all nine health facilities across 3 counties as described in the table above. A total of 35 health facility staff have received trainings in EmONC care services in all nine health facilities up to date. Recruitment and deployment of skilled birth attendants including local midwives and other skilled cadres is work in progress with more than 80% achievement. The project targeted a total of 15 midwives to be recruited. However based on the critical need in these facilities, 19 health workers have been identified for recruited and deployment. Currently 10 receive incentives through this project. Modalities for the disbursement of incentives to the remaining 9 health workers have been finalized pending execution. Using the MoH recruitment process the recruitment of international obstetricians has been initiated, interviews have been conducted pending deployment. It is expected that the MoH will deploy the international obstetricians by the end of September 2016. The Foya Borma Hospital which serves Lofa County and which is an expectant CEmONC services provider has been assessed and found to be compliant (i.e. providing all nine signal functions of Emergency Obstetric and Newborn Care Services including the following: Administration of Parenteral antibiotics; administration of uterotonics; administration of anticonvulsants; New born resuscitation; Assisted Deliveries; Removal of retained placentas; perform blood transfusion; perform cesarean section, and removal of retained products). The donation of various maternal health equipment including delivery beds and instruments, operation table and other medical supplies in addition to the training of care providers all contributed to ensuring that the hospital is CEmONC compliant. At the level of the clinics and health centers, compliance for Basic Emergency Obstetrics and New born Care (BEmONC) has improved though not all facilities are fully compliant. During the baseline assessment, clinics and health centers were missing 3 to 4 signal functions. During this reporting period, EmONC monitoring revealed that four BEmONC facilities have improved their EmONC status with only one signal function missing, while the remaining facilities have improved with only two signal functions missing compared to four during the baseline assessment. Sixty-six percent (6/9) of health facilities had no stock out of essential medicines during this period compared to the average baseline of 44%. Additional skilled providers deployed to health facilities has contributed to the increase of maternal newborn service utilization including Antenatal care, Labor and Delivery services including EmONC and Family Planning in all health facilities. The report illustrates progress using three main MoH indicators (ANC1, ANC4 and Skilled deliveries at health facilities) for maternal and newborn health. The tables below provide an illustration of progress comparing the previous quarter and the quarter under review. Progress in Antenatal Care Visits comparing two quarters and baseline Counties Name of Health Facility Quarterly expected pregnancies (targets per facility) 1st Antenatal Care visit Baseline Jan-Mar 2016 April to June 2016 Grand Cape Mount County Damballa Health Center 122 62 86 94 Lofa Bridge Clinic 121 43 94 91 Tienni Clinic 59 42 71 79 Gbarpolu County Kungbor Clinic 177 25 34 45 Gbangay Clinic 146 52 60 72 Lofa County Foya Boma Hospital 197 102 121 212 Foya Tengia Clinic 75 27 39 31 Worsonga Clinic 57 27 39 41 Mendikorma Clinic 67 51 71 49 Cumulative 431 615 703 As mentioned further above, the utilization of services by pregnant women has increased in most facilities during the quarter – May – July 2016.. According to national protocols, all pregnant women are expected to attend at least four antenatal visits during each pregnancy period. The Ministry of health has identified two main indicators (ANC1 and ANC4 visits) during antenatal care that health facilities are required to report against. All health facilities aim to achieve 75% to 80% of their expected coverage in ANC 1 and ANC4. The average ANC 1 coverage at national level is 70% with some facilities achieving more than 80% coverage). During this quarter, 67% of all targeted facilities achieved ANC1 coverage above the average national coverage. Two health facilities in Gbarpolu (Gbarngay and Kungbor) had the lowest ANC1 coverage, 49% and 25% respectively, from May to July 2016. And although these proportions are higher than the previous quarter, the difference is not significant. Gbarpolu County is noted for low coverage of health services due to poor geographic access to health facilities. This has been a major challenge that has not only contributed to challenges in getting supplies to health facilities but also challenges in accessing services by the population. Also, in Lofa one health facility, Foya Tengia also had a low coverage at 41% of the expected proportion of visits. Progress in Fourth Antenatal Care Visits Counties Name and Type of Health Facility Quarterly expected pregnancies targets per facility) 4th Antenatal Care visit 2nd IPT Dose for Malaria Prevention Baseline Jan-Mar 2016 April - June 2016 April -June 2016 April -June 2016 Grand Cape Mount Damballa Health Center 122 53 71 68 65 76 Lofa Bridge Clinic 121 48 82 103 66 72 Tienni Clinic 59 41 59 38 50 39 Gbarpolu Kungbor Clinic 177 27 35 41 34 74 Gbangay Clinic 146 15 20 38 47 39 Lofa Foya Tengia Clinic 75 51 73 66 55 45 Worsonga Clinic 57 11 10 28 37 33 Foya Borma Hospital 197 87 95 101 55 86 Mendikorma Clinic 67 49 83 66 48 48 National coverage of ANC4 is approximately 49%. This indicator has been difficult to achieve due to poor reporting as well as the fact that most women seek ANC in their later trimester of pregnancy. During this reporting period, six of the nine health facilities achieved ANC4 coverage above national coverage indicator. Unlike the six, three health facilities—two in Gbarpolu and one in Lofa—fell below national coverage as shown in table 1 above. Meanwhile, comparing individual facility achievements with their baselines, eight of the nine health facilities exceeded the baseline number of ANC4 visits during the quarter. Progress in Skilled Institutional Deliveries County Name of Health Facility Quarterly expected deliveries (Target per facility) Baseline Actual Health Facility Deliveries Jan-Mar 2016 April - June 2016 Cape Mount Damballa Health Center 110 48 67 82 Lofa Bridge Clinic 109 37 54 69 Tienni Clinic 53 27 44 36 Gbarpolu County Kungbor Clinic 159 12 18 40 Gbangay Clinic 131 14 29 41 Lofa Foya Boma Hospital 177 96 102 117 Foya Tengia Clinic 67 29 55 34 Worsonga Clinic 51 21 33 42 Mendikorma Clinic 60 19 28 47 Total 917 303 430 508 Gradual progress in skilled deliveries at targeted health facilities continued during the quarter. All health facilities exceeded their baseline indicators for institutional deliveries during the quarter. However institutional delivery data for eight health facilities increased compared to the previous quarter as shown in the figure below. It is assumed that as facility deliveries increase, home deliveries conversely decrease in targeted catchment communities. In Gbarpolu County, poor geographic access and sparsely distributed populations that are distant from health facilities and services continued to affect the utilization of delivery services at health facilities. Although progress has been made against the baseline, these facilities are still far from reaching the expected populations by even 50%. As reported during the last quarter, maternal waiting homes have been identified as a potential solution to the problem of limited access to services due to distance. Waiting homes will encourage women and girls to come closer to the health facilities before they reach term. UNFPA with funding from MPTF will continue to work with the Ministry of Health and relevant county health teams to advocate and raise awareness regarding the benefits of maternal and newborn health care.

Family Planning Name of Health Facility Implants (Jadelle) Oral Contraceptives Injectable contraceptive Male Condom Users Total Users Jan-Mar 2016 April -June 2016 Jan-Mar 2016 April -June 2016 Jan-Mar 2016 April -June 2016 April -June 2016 Jan - Mar 2016 April -June 2016 Damballa Health Center 2 0 74 91 231 92 107 307 290 Lofa Bridge Clinic 9 0 10 19 36 24 97 55 140 Tienni Clinic 0 0 4 10 18 22 48 22 80 Kungbor Clinic 2 0 95 35 297 92 32 394 159 Gbangay Clinic 2 0 59 29 122 94 29 183 152 Foya Boma Hospital 3 10 9 18 25 36 97 37 161 Mendikorma Clinic 2 0 83 88 447 98 47 532 233 Foya Tengia Clinic 17 0 101 86 450 76 64 568 226 Worsonga Clinic 5 0 42 69 79 73 21 126 163 Total clients per commodity 42 10 477 582 1705 864 542 2224 1604 Use of family planning services at health facilities are often enhanced by knowledge and information above the benefits of family planning and availability of commodities. During this quarter, stock out of implants and injectable contraceptives hampered access to services and commodities. Fewer women and girls as well as men and boys accessed commodities compared to the previous quarter. However the numbers reported for facilities in Gbarpolu County last quarter appeared to be exaggerated. The records will be reviewed and corrections made during the next reporting period. Key Achievements (please use this section to highlight your key achievements for the month, using bullet points if preferred) Additional Results Six skilled birth attendants have been recruited and deployed in all 4 health facilities in Lofa and 3 facilities in Grand Cape Mount Counties. The recruitment process of international obstetricians has been completed by 60 percent. Out of five candidates, three obstetricians have successfully completed the interview led by the Liberia Medical and Dental Council that is responsible for the accreditation of Medical Doctors in Liberia. The obstetricians are expected to be positioned by the October 2016. Based on assessment findings, the Health Facility Refurbishment for four health facilities have been initiated in Grand Cape Mount (Tienii, Lofa Bridge clinics and Dambala) health center and Gbarpolu (Kungbor Clinic) Counties. All Rehabilitation activities are expected to be completed by the end of September 2016. During the quarter under review, 5 delivery beds, 14 hospital beds, 8 infant weighing scales, 8 infusion stands, several assorted medical supplies including ONGYN gloves, intravenous kits, assorted maternal health drugs including antibiotics and various types of reproductive health kits were procured and distributed. Additional medical supplies and equipment have been procured; delivery and distribution are pending for the fourth quarter. A total of 42 cesarean sections were conducted in the Foya Boma District Hospital during this period, compared to 28 last quarter. This was perhaps due to the fact that one additional operation table and instruments were donated to the hospital in addition to the fact that one new local doctor has been deployed by the MoH. Reporting of maternal and newborn deaths have been low, inaccurate and untimely in both health facilities and communities. As part of the project objectives, training of health care workers and community health workers on the need to report all deaths are expected to improve. During this quarter, seven deaths (two maternal death and five neonatal) were reported by targeted health facilities and counties. This maternal death was reported by the Foya Borma Hospital in Lofa, while the neonatal deaths occurred in Grand Cape Mount (Damballa) and Lofa (Foya Boma). During the previous quarter a total of 13 deaths occurred including 11 newborn deaths and 2 maternal deaths. Shortly before the inception of this project postnatal visits within the recommended 6 weeks period after birth (i.e.babies born in health facilities) was generally low (around 30 to 40%) in most health facilities. As a result of awareness raising and health promotion using community health workers, including trained traditional birth attendants, postnatal visits increased from 68% during the previous quarter to 96% during the quarter under review. The way the project inputs supported the achievement of this result was by training and inserting community health workers in selected catchment communities.

Delays or Deviations (if any, briefly describe the delays or changes in focus, approach or targets, and provide a short justification for the change (1-2 paragraphs)) The recruitment of national and international health providers including midwives and obstetricians has been significantly delayed due to the complexities in the MoH recruitment process. This situation has contributed to the slow implementation of activities related to the deployment of the international staff. Subsequently, the budget utilization rate has also been relatively low. Nonetheless, progress is underway. Based on these constraints, UNFPA will recommend a no cost extension up to March 31st 2017.

Gender and Environmental Markers (Please provide disaggregated data, if applicable) No. of Beneficiaries Environmental Markers Women (age 20 to49 yrs) 2235 e.g. Medical and Bio Hazard Waste Girls (10 to 19 yrs) 1845 e.g. Chemical Pollution Men (20 years + ) 897 Boys (10 – 19yrs) 1509 Total 6486

These beneficiaries are direct beneficiaries based on the total number of Family Planning users, number of women and girls accessing services. The numbers of men and boys were calculated based on the number of men and boys (15 to 19 years) accessing male condoms particularly during outreach activities. Indirect beneficiaries have not been mentioned in the table above. Additional Information (Optional) As a result of delayed implement of the overall project and the slow implementation of activities focused on the recruitment of international obstetricians, funds that are expected to pay salaries and other remunerations to the obstetricians have not been paid. These funds are still available with UNFPA. UNFPA will submit a request and justification for no cost extension to MPTF from October to March 31st 2017.

# Footnotes

The date project funds were first transferred.

Signal functions are a set of clinical interventions/care/ services that are required to be in place for a health facility to qualify as an Emergency Obstetric and New Born Care Facility and there are nine in total. A facility that provides 7/9 is considered Basic Emergency Obstetric and Newborn Care facility while a facility that provides 9/9 of the services is referred to as a Comprehensive Emergency Obstetric and Newborn Care facility