RUNO END PRF PROJECT REPORTING					TEMPLATE 4.5

PEACEBUILDING FUND (PBF)

END OF PROJECT report

COUNTRY: Sri Lanka

REPORTING PERIOD: June 2016_November 2016

| Programme Title & Project Number |  |
| --- | --- |
| Programme Title: Support for Sri Lanka national reconciliation efforts by addressing grievances of the concerned sections of the population through targeted resettlement of conflict affected internally displaced persons. Programme Number (if applicable) 00095915 MPTF Office Project Reference Number: |  |  |

| Recipient UN Organizations |  | Implementing Partners |
| --- | --- | --- |
| List the organizations that have received direct funding from the MPTF Office under this programme: UNHCR and UNICEF |  | List the national counterparts (government, private, NGOs & others) and other International Organizations: Ministry of Resettlement, Resettlement Authority, Northern Provincial Government, Regional Director of Health Services, the Assistant Commissioner of Local Government, Local Government Body (Pradeshiya Sabha), National Water Supply and Drainage Board and the NGOs Rural Development Foundation (RDF), Sevalanka Foundation (SLF), SOND and EHED Caritas. |
| Programme/Project Budget (US$) |  | Programme Duration |
| PBF contribution (by RUNO) USD 1,470, 000 |  |  | Overall Duration (months) 18 |  |
|  |  |  | Start Date (dd.mm.yyyy) 15.6.2015 |  |
| Government Contribution (if applicable) Approximately $232,300 (U$92 per family) as resettlement grants and in-kind support |  |  | Original End Date (dd.mm.yyyy) | 14.12.2016 |
| Other Contributions (donors) (if applicable) |  |  | Final End date(dd.mm.yyyy) |  |
| TOTAL: | USD 1,470,000 |  |  |  |

| Programme Assessment/Review/Mid-Term Eval. |  | Report Submitted By |
| --- | --- | --- |
| Mid-Term Evaluation / Review - if applicable please attach Yes No Date: End of project Evaluation– if applicable please attach Yes No Date: |  | Name: Dushanthi Fernando Title: Participating Organization (Lead): UNHCR Email address: fernandd@unhcr.org |

PART 1 – RESULTS PROGRESS

  - Assessment of the project implementation status and results

For PRF projects, please identify Priority Plan outcome and indicators to which this project has contributed:

Priority Plan Outcome to which the project has contributed. N/A - IRF Project

Priority Plan Outcome indicator(s) to which project has contributed.

For both IRF and PRF projects, please rate this project’s overall achievement of results to date:

For both IRF and PRF projects, outline progress against each project outcome, using the format below. The space in the template allows for up to four project outcomes.

Outcome Statement 1:  Minority confidence in the government and the peace process is increased as a result of sustainable resettlement of remaining IDPs.

Rate the current status of the outcome:

Output progress at the end of project

List the key outputs achieved under this Outcome (1000 character limit).Outputs are the immediate deliverables for a project.

Returnees were monitored at the place of displacement and return to ensure voluntariness and informed decision making; 46 focus group discussions were held at community level to raise awareness and identify concerns of more than 574 returning individuals; 374 vulnerable families, including 75 female headed households, benefitted from transitional shelters and monetary relocation assistance; UNHCR also constructed 142 household latrines to complement the 529 units constructed by UNICEF. All target households have improved knowledge on good hygiene practices through hygiene awareness sessions; nearly 520 families gained access to improved water through the extension of existing piped borne water lines, construction of 10 tube wells and 50 dug wells; all returnees in the targeted areas benefitted from life-saving mine risk education and improved health services through the training of 400 health professionals and construction/equipping of three health centres and a maternity ward.

Outcome progress at the end of project

Describe progress made toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers (3000 character limit)?

Through this project UNHCR and UNICEF have assisted all IDP returning families in the target areas to return in safety and dignity. The project spearheaded the physical return of displaced families to restart their lives and rebuild their homes. The assistance rendered includes: monetary assistance for land clearance; housing; access to water and sanitation; protection; health and mine risk education. All the project activities contributed towards confidence building among the returning communities on the government process and overall peacebuilding efforts. Moreover, through this project, UNHCR and UNICEF were able to advocate among government stakeholders, other donors as well as development partners on behalf of the prevailing needs and challenges preventing sustainable return of IDPs.

Post return monitoring visits have indicated no major protection threats and no family has encountered re-displacement or return to their previous locations. Returnees have expressed their gratitude for the assistance and some have managed to restart their livelihoods. Positive outcomes have been documented such as reduced risks of water borne and common communicable diseases due to increased levels of knowledge on good hygiene practices and access to safe water and adequate facilities. Further, noticeable progress has been made in the health and nutrition status of returnees, particularly children under five, through the formation of mothers’ support groups, awareness raising at community level on health and nutrition and access to improved and uninterrupted preventive and curative health services by trained professionals. These health services have ensured 100 per cent coverage of vaccinations for and growth monitoring of children under five years. Additionally, all newborns were reported to have been deliverered in hospitals under the supervision of skilled personnel which contributed to no maternal and prenatal deaths during the reporting period.

The mine risk education provided to all returnees living in at-risk areas has reduced the number of mine/explosive remnants of war incidents by 50 per cent from 2015 and is contributing to building community confidence and trust in the Sri Lanka Army (SLA). This can be seen in increased community reporting on mines/explosive devices to the SLA and their timely response actions.

The IRF assistance fortified the renewed will expressed by the Government of Sri Lanka to assist the remaining displaced communities. It also encouraged the mobilization of additional resources to address needs of vulnerable returnees from donors such as European union, Norway and USA.

Reasons for low achievement and rectifying measures

If sufficient progress was not made, what were the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How were they addressed (1500 character limit)?

All project indicator targets have been met as planned.

Despite the sporadic release of land by the government, there were instances in which the returnees were reluctant to return due to the fear of mines and limited access to quality education, income generation activities and health services. UNHCR engaged in a dialogue with returnees and provided the much needed space for them to voice their concerns prior to their return. UNHCR together with relevant government and community leaders provided the necessary information for the returnees to ensure that they are aware of ground realities prior to return. Both UNHCR and UNICEF provided access to basic services and mine risk education to support the resettlement of those who were willing to return.

There is a continued need for strong coordination between the multiple stakeholders involved in the resettlement areas. This is particularly with regard to the design and quality of infrastructure and the package of services provided to avoid potential conflicts between returnees. UNHCR and UNICEF shared the construction plans with District Secretariat and other related government bodies prior to construction.

Outcome Statement 2:  N/A

Rate the current status of the outcome:

Output progress at the end of project

List the key outputs achieved under this Outcome (1000 character limit).Outputs are the immediate deliverables for a project.

Outcome progress at the end of project

Describe progress made toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers (3000 character limit)?

Reasons for low achievement and rectifying measures

If sufficient progress was not made, what were the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How were they addressed (1500 character limit)?

Outcome Statement 3:  N/A

Rate the current status of the outcome:

Output progress at the end of project

List the key outputs achieved under this Outcome (1000 character limit).Outputs are the immediate deliverables for a project.

Outcome progress at the end of project

Describe progress made toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers (3000 character limit)?

Reasons for low achievement and rectifying measures

If sufficient progress was not made, what were the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How were they addressed (1500 character limit)?

Outcome Statement 4:  N/A

Rate the current status of the outcome:

Output progress at the end of project

List the key outputs achieved under this Outcome (1000 character limit).Outputs are the immediate deliverables for a project.

Outcome progress at the end of project

Describe progress made toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers (3000 character limit)?

Reasons for low achievement and rectifying measures

If sufficient progress was not made, what were the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How were they addressed (1500 character limit)?

  - Assessment of project evidence base, risk, catalytic effects, gender at the end of the project

| Evidence base: What was the evidence base for this report and for project progress? What consultation/validation process has taken place on this report (1000 character limit)? | This report is based on the records of local government and sector authorities on key indicators; UNHCR/UNICEF field officer monitoring visit reports and community level consultations, including with mother's support groups and community leaders. Both UNHCR and UNICEF field officers directly monitor progress at resettlement sites. |
| --- | --- |
| Funding gaps: Did the project fill critical funding gaps in peacebuilding in the country? Briefly describe. (1500 character limit) | At the start of this project, government provided initial resettlement support only for land clearance and temporary shelter. At that time, the PBF fund filled a critical gap and was catalytic for other donors to render support for other basic services. Without the PBF support, return of these families would have been prolonged or they would have returned to very basic living conditions. The IRF funds have therefore enabled the immediate resettlement of vulnerable IDP returnees in the newly released areas at the time (Trincomalee and Jaffna), thus assisting the government in solidifying its quest in reconciliation and peacebuilding. At project end, it is evident that the need for basic services and livelihood opportunities (to maintain return) remains high. Additional land has been returned by the government enabling more families to return to their places of origin. |
| Catalytic effects: Did the project achieve any catalytic effects, either through attracting additional funding commitments or creating immediate conditions to unblock/ accelerate peace relevant processes? Briefly describe. (1500 character limit) | The IRF funds were one of the first of limited allocated funds to address the needs of the remaining conflict-affected IDPs in the North and East of Sri Lanka. Following these funds, other UN agencies, development partners and NGOs aligned their programmes to address some of the immediate, yet unmet, needs identified for the returning families. For example, WFP mobilised critical funding support from the United States to provide food and cash-for-work programmes that supported land clearance, water tank repair, and clearance of access roads. UNDP also mobilised support for basic livelihood assistance in the form of home gardening. While the government is addressing permanent housing assistance for the returning IDPs, the UN is partnering with the EU on issues of transitional justice; peaceful co-existence; trust building; and access to land and essential socio-economic services that help returnees rebuild their lives. |
| Risk taking/ innovation: Did the project support any innovative or risky activities to achieve peacebuilding results? What were they and what was the result? (1500 character limit) |  |
| Gender marker: How have gender considerations been mainstreamed in the project to the extent possible? Is the original gender marker for the project still the right one? Briefly justify. (1500 character limit) | UNHCR and UNICEF have ensured gender equality in assistance and participation. UNHCR prioritised vulnerable female headed households in the selection process for shelter. Out of the 374 selected families for shelter assistance, 75 are women headed families. The 46 focus group discussions conducted included both males and females from different age groups. MRE programs are also designed based on the different target group needs in the villages. Women are a key target group (despite a comparatively low causality rate amongst women) due to the fact that they are the primary care giver of children and play a key influential role in the family. Causality data is disaggregated by age and sex and identifies the activity the victim was engaged in at the time of the incident, which is critical for assessing risks and identifying patterns of risk-taking behaviours specific to a particular sex and age group, as well as designing more tailored MRE. In the WASH sector, female headed households are prioritised in the beneficiary selection process. In addition, improved access to water and sanitation facilities has additional benefits for mothers and adolescent girls who are typically tasked with fetching water over long distances, as well as require privacy, comfort and safety when using sanitation facilities. In the health sector, the formation of mothers' support groups have increased the knowledge and skills of mothers, empowering them to promote good nutrition practices. |
| Other issues: Are there any other issues concerning project implementation that should be shared with PBSO? This can include any cross-cutting issues or other issues which have not been included in the report so far. (1500 character limit) | Viability and sustainability of returns is at risk with insufficient access to livelihood/ income generation opportunities; As further land is released and government is providing permanent housing, there is a risk of returnees becoming disheartened in the overall process if they fail to receive adequate support. This could potentially create tensions at the local level, including with returnees in neighbouring areas that benefited from earlier PBF assistance. As such the UN is working closely with the Government to support the effective operationalisation of the new Durable Solutions Policy, and has secured funding for ongoing resettlement support from the EU's Instrument Contributing to Stability and Peace. |

1.3 INDICATOR BASED PERFORMANCE ASSESSMENT: Using the Project Results Framework as per the approved project document- provide an update on the achievement of key indicators at both the outcome and output level in the table below. Where it has not been possible to collect data on indicators, state this and provide any explanation in the qualitative text above. (300 characters max per entry)

|  | Performance Indicators | Indicator Baseline | End of project Indicator Target | Current indicator progress | Reasons for Variance/ Delay (if any) | Adjustment of target (if any) |
| --- | --- | --- | --- | --- | --- | --- |
| Outcome 1 Tamil confidence in the government and the peace process is increased as a result of sustainable resettlement of remaining IDPs | Indicator 1.1 No of families who return to their own land | 0 | 2,525 families | During 2015/2016, 4,009 acres of land has been released by the Government. 2,022 families have already returned to their places of origin. Remaining families are visiting their land on a regular basis | Sporadic release of land; findings of unexploded ordinances in the areas of return (created delays, as areas had to be screened/cleared again); lack of livelihood/income generation opportunities; |  |
|  | Indicator 1.2 Percentage of IDP families reporting satisfaction with the resettlement process and support received | 0 | 75% | 100% | Information from protection monitoring and focus group discussions as well as post return site visits |  |
|  | Indicator 1.3 Percentage of IDP families who become re-displaced or returned to the displacement camps or host families | 0 | <5% of the target 2,525 families | 0% | Out of the families who returned to their places of origin, none have been subjected to re-displacement. |  |
| Output 1.1 Land, housing and property assistance is provided for most vulnerable returnee families | Indicator 1.1.1 Number of vulnerable families provided with land, housing and property assistance through IPs | 0 | 360 Shelters ( Original target) | 374 completed |  | Increased outputs utilizing the variance in funds due as a result of changes in the project period from 18 months to 9 months_ UNHCR |
|  | Indicator 1.1.2 | 0 |  |  |  |  |
| Output 1.2 Protection needs of newly resettled families monitored | Indicator 1.2.1 Number of individuals monitored at places of displacement to ensure voluntariness of return and informed decision. | 0 | 50% | 287 families monitored at the place of displacement. |  |  |
|  | Indicator 1.2.2 Number of focus group discussions conducted at community level | 0 | 24 FGDs | 46 FGDs were conducted for different age and gender groups (22 in return location and 24 in the place of displacement). |  |  |
| Output 1.3 Essential Sanitation and health services provided for resettling families | Indicator 1.3.1 Numberof families benefitting from a latrine | 0 | 336 (186 in the North, and 150 in the East) | 529 (259 in North, 270 in East) | Estimated targets were based on standard construction rates. The use of partner's and stakeholder's own resources led to savings resulting in an increase of the total number of units constructed. |  |
|  | Indicator 1.3.2 Number of families with access to an improved water source | 0 | 420 (40 common wells benefitting 5 families each in the North, and 220 household water connections from the national grid in the East | 520 (50 dug wells and 10 tube wells in North with 5 families shared each, 220 household piped water connections in East) | Estimated targets were based on standard construction rates. The use of partner's and stakeholder's own resources led to savings resulting in an increase of the total number of units constructed. |  |
| Outcome 2 SHOULD BE 1.4 Returning population know how to identify mines and UXOs, and know what to do | Indicator 2.1 SHOULD BE 1.4.1 Returning population know how to identify mines and UXOs, and know what to do | 0 | 2,525 families | Mine risk education, designed for specific risk-taking population groups, including returnees, was provided for 1,647 resettled families in Jaffna and 906 families in Trincomalee. | The figures for MRE coverage is higher due to the fact that UNICEF also includes target families that are due to return, or could return etc. |  |
|  | Indicator 2.2 SHOULD BE 1.4.2 % increase of Mine/UXOs reported to authorities | 32 explosive devices from Jaffna and 3 from Traincomalee were reported by the community over 1 month | 10 per cent | 21.8 % increase (624) explosive devices reported by community members during 16 month sine May 2015). 105 % increase (74 explosive devices reported by community members during the 12 month period since November 2015 in Sampur) |  |  |
| Output 2.1 | Indicator 2.1.1 |  |  |  |  |  |
|  | Indicator 2.1.2 |  |  |  |  |  |
| Output 2.2 | Indicator 2.2.1 |  |  |  |  |  |
|  | Indicator 2.2.2 |  |  |  |  |  |
| Output 2.3 | Indicator 2.3.1 |  |  |  |  |  |
|  | Indicator 2.3.2 |  |  |  |  |  |
| Outcome 3 | Indicator 3.1 |  |  |  |  |  |
|  | Indicator 3.2 |  |  |  |  |  |
| Output 3.1 | Indicator 3.1.1 |  |  |  |  |  |
|  | Indicator 3.1.2 |  |  |  |  |  |
| Output 3.2 | Indicator 3.2.1 |  |  |  |  |  |
|  | Indicator 3.2.2 |  |  |  |  |  |
| Output 3.3 | Indicator 3.3.1 |  |  |  |  |  |
|  | Indicator 3.3.2 |  |  |  |  |  |
| Outcome 4 | Indicator 4.1 |  |  |  |  |  |
|  | Indicator 4.2 |  |  |  |  |  |
| Output 4.1 | Indicator 4.1.1 |  |  |  |  |  |
|  | Indicator 4.1.2 |  |  |  |  |  |
| Output 4.2 | Indicator 4.2.1 |  |  |  |  |  |
|  | Indicator 4.2.2 |  |  |  |  |  |
| Output 4.3 | Indicator 4.3.1 |  |  |  |  |  |
|  | Indicator 4.3.2 |  |  |  |  |  |

PART 2: LESSONS LEARNED AND SUCCESS STORY

2.1 Lessons learned

Provide at least three key lessons learned from the implementation of the project. These can include lessons on the themes supported by the project or the project processes and management.

| Lesson 1 (1000 character limit) | To address issues related to beneficiary selection (at the initial stages there were discrepancies between those that received shelter and latrines) coordination was improved between UNHCR and UNICEF, particularly at the field level. |
| --- | --- |
| Lesson 2 (1000 character limit) | Community level structures were strengthened to respond to threats from mines/explosive remnants of war through the establishment of three related Information Centres in the recently released villages of Tellipalai and Kopay divisions. These Information Centres have facilitated improved reporting by community members on explosive devises resulting in the identification of new mine fields in the villages. |
| Lesson 3 (1000 character limit) | During implementation, strong partnerships between UNICEF and mandated government Water, Sanitation and Hygiene (WASH) service providers (such as the National Water Supply and Drainage Board) have led to building shared accountabilities in providing basic WASH facilities to returnees. In addition, the engagement of other state actors in project implementation, such as skilled and unskilled labour from the Sri Lanka Navy and heavy machinery provided by Muttur local authorities, have had positive results in terms of increased human resources and expertise (especially on local contexts); improved relationships between the government and returnees with a clear understanding of roles and responsibilities; increased reach of returnees due to project cost-savings; and sustainability of WASH services. Overall, these results contribute towards trust building in government services and confidence in ongoing peacebuilding and reconciliation efforts. |
| Lesson 4 (1000 character limit) | While the PBF support caters to many of the initial needs, it does not include support for livelihoods which has been raised in almost all focus group discussions as a top priority. Without access to livelihoods, families are unable to return, or can only return in a partial way. Fortunately for this initiative, other partners such as WFP and UNDP have been able to move in and supplement the PBF support with livelihood assistance. However, in hindsight, a more holistic resettlement package would have enabled better targeting of support to the most vulnerable families, and potentially contributed to building greater confidence on the overall return process |
| Lesson 5 (1000 character limit) | Improved access to safe water and adequate sanitation facilities must be complemented with the promotion of good hygiene practices to ensure a healthy environment for returnees. This strategy has resulted in good hygiene practices amongst returnees that prevented open defecation and reduced the risks of communicable diseases, as well as made other positive impacts on the environment. |

2.2 Success story (OPTIONAL)

Provide one success story from the project implementation which can be shared on the PBSO website and Newsletter as well as the Annual Report on Fund performance. Please include key facts and figures and any citations (3000 character limit).

Let’s start at the very beginning… - Sudharmini’s story

Sivakumar Sudharmini was just ten yrs old when she and her family were displaced from their home in Jaffna . She remembers little about that time; not surprising as the year was 1990.

Today, Sudharmini and her family are back home in Urani, in the North of Sri Lanka, more than 25 years since they were displaced when their property became part of the military High Security Zones in the North. “It feels good to be back in one place,” she says. “We moved so many times since I was little.”

Her mother Devarani (53) is able to vividly remember those difficult days. “Moving so much with a young child was very hard,” she recalls.

Sudharmini also faced the same experience. Having married while in displacement, she had two children of her own and had to move a lot. “We had no money. When the children fell ill, getting treatment for them was a really difficult task,” she explains. She tried her best to ensure her children received their education even though they were so far away from home.

Now, the family is settling back on their land with the support of the Peacebuilding Fund which is providing temporary housing and latrines to returning families. With a funding base of $1.47 million,  the project is providing assistance to facilitate the safe and immediate resettlement of IDPs to land released by the Govt from former High Security Zones. The PBF is also supporting peacebuilding and reconciliation efforts of the current government, which was elected to office in January 2015.

To support her family, Sudharmini worked as a packer for a small coffee packing business. She still works there, although making ends meet is very difficult. Still, she has a home, for which she is very grateful.

“Once we moved back here, UNHCR facilitated the construction of our temporary home. It was a great help, as we could not afford to build anything for ourselves at that point. Each family even received latrines from UNICEF and soon we will have the water supply,” she says. Currently, the families are using the community water supply provided by the Govt.

Now, Sudharmini and her family are looking forward to the completion of their permanent house, which has been provided to the resettling families by the government together with other development partners. “It’s nice how little by little, our home is coming up. The main thing is that after all these years, we have a solid structure to live in.”

Once her permanent house is soon complete, Sudharmini plans to use her temporary house to start a small grocery shop. “It’s a good solid structure. I have many plans and one is to start a grocery in the place we lived in since we came back.”

She continues, ‘Even in displacement, the UN helped us so much, and they are still doing so. I am so grateful to the UN for helping us to settle back after so long.”

“I am no longer an IDP. That is the happiness.”

-----

(1 of 6 stories. Others available from PBF Secretariat)

PART 3 – FINANCIAL PROGRESS AND MANAGEMENT ARRANGEMENTS

  - Comments on the overall state of financial expenditure

Please rate whether project financial expenditures were on track, slightly delayed, or off track:

If expenditure was delayed or off track, please provide a brief explanation (500 characters maximum):

Please provide an overview of project expensed budget by outcome and output as per the table below.

| Output number | Output name | RUNOs | Approved budget | Expensed budget | Any remarks on expenditure |
| --- | --- | --- | --- | --- | --- |
| Outcome 1: |
| Output 1.1 | Land, housing and Property assistance | UNHCR | $549,200 | $549,200 | Fully Utilised Please note that output 1.1 included physical construction of transitional shelters, latrines as well as monetised resettlement assistance. |
| Output 1.2 | (Protection Monitoring of all returnees across new settlements | UNHCR | $97,034 | $97,034 | Fully utilised (savings under staffing was re-programmed to output 1.1) |
| Output 1.3 | WASH and Health | UNICEF | $669,536 | $529,747 | The balance funding will be fully utilised prior to the expiry of the grant in December 2016. |
| Outcome 2: |
| Output 2.1 | Output 1.4: Child Protection | UNICEF | $96,800 | $87,963 | The balance funding will be fully utilised prior to the expiry of the grant in December 2016. |
| Output 2.2 | Coordination and Monitoring | UNICEF and UNHCR | $57,430 | $34,157 | The balance funding will be fully utilised for the evaluation prior to the expiry of the grant in December 2016. Savings were reprogrammed to output 1.1. |
| Output 2.3 |  |  |  |  |  |
| Outcome 3: |
| Output 3.1 |  |  |  |  |  |
| Output 3.2 |  |  |  |  |  |
| Output 3.3 |  |  |  |  |  |
| Outcome 4: |
| Output 4.1 |  |  |  |  |  |
| Output 4.2 |  |  |  |  |  |
| Output 4.3 |  |  |  |  |  |
| Total |  |  | 1,470,000 | 1,298,101 |  |

  - Comments on management and implementation arrangements

Please comment on the management and implementation arrangements for the project, such as: the effectiveness of the implementation partnerships, coordination/coherence with other projects, any South-South cooperation, the modalities of support, any capacity building aspect, the use of partner country systems if any, the support by the PBF Secretariat and oversight by the Joint Steering Committee (for PRF only). Please also mention if there have been any changes to the project (what kind and when) (2000 character maximum):

In terms of implementation, certain services were implemented by government partners, such as water supply through the National Water Supply and Drainage Board. However, in areas such as shelter and MRE, the UN partnered with NGOs and CBOs. In conducting protection monitoring activities, UNHCR included the local government authorities, rural development and women development officers together with the implementing partners. This enabled the strengthening and awarenessraising on the needs identified by IDP returnees among the greater public service network.

UNICEF/ UNHCR worked closely with the Ministry of Resettlement to deliver the project. Coordination at the field level was carried out by the respective Divisional Secretariats with support from the UN Field Coordination Officers. UNICEF and UNHCR held regular coordination meetings, and at the same time, worked alongside each other to ensure sequenced targeting of support etc.

UNHCR completed all project activities by the end of February 2016. UNHCR initially intended to recruit protection staff under this project for protection monitoring activities in the field. Instead, UNHCR conducted these activities with existing staff. Likewise, the project evaluation costs were identified to be lower than expected. Therefore, funds allocated under output 1.2 and coordination and monitoring for UNHCR were re-programmed into output 1.1 to provide maximum benefits to the target population. These funds were allocated to build 14 additional shelters, 142 latrines and for monetary assistance to 14 families.

This project has been a positive initiative in terms of working towards a ‘one UN' approach and the experiences gained are contributing towards the framing of further joint resettlement initiatives. An external end of project review is currently being planned and will be conducted by the Center for Poverty Analysis between December 2016 and March 2017. The terms of reference has been designed in consultation with PBSO.

# Footnotes

The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to “Project ID” on the MPTF Office GATEWAY

The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY

As per approval of the original project document by the relevant decision-making body/Steering Committee.

If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed.

Please note that financial information is preliminary pending submission of annual financial report to the Administrative Agent.