## Outcomes
Expected Results | Indicators | Baseline | Overall Target | Q3 Target | Q3 Progress | Q4 Target | Q4 Progress | Q1 2020 Target | Q1 2020 Progress | Q2 2020 Progress | Q2 2020 Target
Outcome 1: Empowered military and war widows have sustainable livelihoods, and access social support services with dignity. | Outcome Indicator 1.1 % of military and war widows who are subjected to sexual bribery and sexual exploitation when accessing services. | 50% of military widows (from 2016 study) War widows: TBD | Reduced to 25% | survey ongoing to establish baseline
| Outcome Indicator 1.2 % of widow beneficiaries who have used the grant provided to establish or upscale an existing business venture disaggregated by widow type. | 0% | At least 50% of grant recipients | implementation ongoing- EE curriculum development |  | 30% of widow beneficiaries used the grant provided to establish or upscale an existing business by end of 4th quarter
Outcome 2: Increased commitment of public institutions to prevent and respond to sexual bribery and to protect military and war widows from sexual exploitation. | Outcome Indicator 2.1 # of Circulars/ guidelines/ policies which incorporate explicit commitment and/ or accountability measures within the public sector to prevent and respond to sexual bribery and exploitation. | 1 | 2 |  |  | 1 new circulars/guidelines/policies by end of 4th quarter
| Outcome Indicator 2.2 # of complaints received and action taken by the Anti- Sexual Harassment Committees | 0 | 5 |  |  |  |  | 5 complaints received and action taken by end of 5th quarter

## Output 1.1
Expected Results | Indicators | Baseline | Overall Target | Q3 Target | Q3 Progress | Q4 Target | Q4 Progress | Q1 2020 Target | Q1 2020 Progress | Q2 2020 Progress | Q2 2020 Target
Output 1.1 Military widows and war widows have increased knowledge of their rights and have access to complaint mechanisms on sexual bribery.
Activity 1.1.1 Create/ strengthen collectives of military and war widows with a focus on asserting their rights and eliminating all forms of abuse. | Output indicator 1.1.1 # of widows’ collectives formed/ strengthened. | 0 | 12 collectives created/ strengthened across 3 districts. | 9 | 54 created/ strengthened | 11 (?) | [5 empty] | UN Women | UNDP
1.1.1.1 Mapping existing self-help groups and collectives. | # of self-help groups identified across the 3 districts | 0 | 30 | 0 | 21 | 0
1.1.1.2 Form new widows’ collectives. | # of newly formed widows’ collectives | 0 | 12 collectives across 3 districts | 0 | 54 created/ strengthened | 11 (?)
1.1.1.3 District level capacity building sessions for reps of self-help groups and collectives. | # of self-help group reps capacitated | 0 | 6 district level sessions across 3 districts | 0 | 0 | 90
1.1.1.4 District level and capacity building sessions with widows’ collectives. | # of widows’ collectives capacitated | 0 | 15 sessions across 3 districts | 0 | 0 | 750
1.1.1.5 Develop/revise and disseminate trilingual advocacy materials. | # of publications disseminated at the programmes | 0 | 1500 copies disseminated | 0 | 0 | 0
Activity 1.1.2 Conduct community-wide awareness programmes on “breaking the taboo” in relation to sexual bribery and exploitation through participatory methods such as ‘puppetry’ and ‘forum theatre’. | Output indicator 1.1.2 # of widows that are members of collectives formed/ strengthened who have increased knowledge of their rights, disaggregated by type of widow | 0 | 750 across 3 Districts/ 6 awareness programme per district | 0 | 936 mobilized | 0 |  | At least 250 widows after 1 year of implementation
1.1.2.1 Awareness programmes in each district. | # of participants attending the awareness programmes | 0 | 750 | 0 | 0 | app. 1,300
1.1.2.2. District-level public events with govt officials & women CSOs on SB. | #of government officials and members of CSO/ women’s organizations attending the event | 0 | 100 | 0 | 0 | see above
1.1.2.3 Social media awareness raising. | # of responses through social media engagement | 0 | 50 | 0 | 0 | 0
1.1.2.4 Newspaper articles, advertisements and at online Articles in the mainstream media. | # of articles/ advertisements of SB published on mainstream media | 0 | 25 | 0 | 0 | 0
1.1.2.5 Say No to SB/SE production and airtime in three languages. | # of times productions aired in 3 languages | 0 | 30 | 0 | 0 | 0
1.1.2.6 Talk shows on national television in three languages. | # of talk shows completed | 0 | 3 | 0 | 0 | 0
Activity 1.1.3 Conduct legal aid and documentation mobile clinics in ‘safe spaces’ linking with CSOs and Women Development Officers of the MWCA for delivery and develop and disseminate an information brochure of service providers together with a SOP on accessing these services collectively | Output indicator 1.1.3 % of widows trained to access legal and other services, disaggregated by type of widow. | 0 | 70% of widows within collective trained | 0 | 0 | (25% of the widows within collectives trained by 4th quarter) |  | Delayed implementation due to government partner- "output to be achieved Q1"
1.1.3.1 Prepare and print user-friendly trilingual awareness raising material | # of trilingual awareness raising material printed and disseminated | 0 | 1500 | 0 | 0 | 0
1.1.3.2 district-level & national level workshops to raise awareness/ capacitate officials on SB/SE. | # of officers made aware and capacitated with knowledge of SB/SE. | 0 | 160 | 0 | 0 | 0
1.1.3.3 TOT for identified potential resource persons from the above workshops to conduct the sensitization programmes at district and divisional levels | # of potential resource persons trained | 0 | 30 | 0 | 0 | 0
1.1.3.4 Conduct district level mobile legal and documentation clinics for widows. | # of women provided with legal aid | 0 | 150 | 0 | 0 | 0
1.1.3.5 Follow up meetings with stake holders regarding issues raised and documented during the mobile clinics | # of issues raised followed up | 0 | 30 | 0 | 0 | 0
1.1.3.6 Consultations (in Colombo and districts) with CSOs and service providers providing legal support to factor in SB/SE into their mandate and services | # of CSO reps and service providers that participated in the consultations | 0 | 90 | 0 | 0 | 0
Activity 1.1.4 Develop a pilot complaint reporting platform to report incidents of sexual bribery and exploitation, available online, through a mobile application and offline via SMS messaging, with geo-tagging location features. | Output Indicator 1.1.4 # of users accessing the online /offline complaints reporting platform | 0 | 100 | 0 | 0 | 0 |  | Platform developed and launched by 5th quarter.
1.1.4.1 Identify and commission suitable telecommunication partner to provide technical support. | Telecommunication partner selected from identified service providers | 0 | 1 | 0 | 0 | 1
1.1.4.2 Conduct consultations with stakeholders to add value and for CIABOC to feed into their existing complaints systems and procedures | # of consultations held | 0 | 3 | 0 | 1 | 1
1.1.4.3 Developing the app & linking to the website | # of persons that access website an App | 0 | 50 | 0 | 0
1.1.4.4 Pilot testing with select collectives and front-line officials | # of widows and front line officials trained to use and respond to app complaints | 0 | 15 | 0 | 0
1.1.4.5 District level Capacity building/ gender sensitization sessions of relevant officers who will handle new systems | # of officers trained to handle information gathered through the new system | 0 | 60 | 0 | 0
1.1.4.6 Launch event/ integration of the systems into CIABOCs overall system. | Launch event held | 0 | 1 | 0 | 0
1.1.4.7 Dissemination of advocacy material of the APP | # of advocacy materials disseminated | 0 | 500 | 0 | 0
1.1.4.8 TOT's on the use of the application for public officials, civil society and SH Committees at SLIDA. | # of government officers trained to use the application | 0 | 150 | 0 | 0
Activity 1.1.5 Provide widows’ collectives with leadership and life skills training, and strengthen them through the formation of cross- regional alliances to build social cohesion and to cope with SB/SE. | # of widow’s collectives trained | 0 | 100 | 0 | 0 | 90
1.1.5.1 Structured Exchange visits for widows’ collectives to cope with SB/SE. | # of MWs and WWs taking part in the exchange visit | 0 | 90 | 0 | 0
1.1.5.2 Widows’ collectives (from 1.1.1) sharing of best practices of coping strategies at district level inter community common forum | # of MW and WW reps participating in the forum | 0 | 30 | 0 | 0
1.1.5.3 Compilation of district level coping strategies. | coping strategy compiled | 0 | 1 | 0 | 0
1.1.5.4 Support DS level village meetings to share the coping strategies with the women | # of women made aware of coping strategies | 0 | 150 | 0 | 0
1.1.5.1 (a) Conduct a perception survey on widows and their adolescent children/youth in all three district | completed survey | in progress
1.1.5.2 (b) Dialogues (based on the findings of the perception survey) with widows from each district to identify and achieve consensus on their role in peacebuilding. This would be succeeded by follow-up workshops at the end of the project. | # of dialogues/follow-up workshops # of participants | 0 | 0 | 0 | 0
1.1.5.3 (c) Trainings for widows' on leadership and life skills | # of trainings | 0 | 0 | 0 | 0
Activity 1.1.6 Provide guidance and strategies to widows’ collectives to identify and respond to at-risk or negative changes in the behaviour of young/ adolescent children (to break the intergenerational impact of conflict). | n/a
1.1.6.1 Train WDOs and child (rights) protection officers to provide guidance and strategies to widows’ collectives to identify and respond to at-risk or negative changes in the behaviour of young/ adolescent children. | # of WDOs and child (rights) protection officers trained to identify at-risk or negative changes in the behaviour of young/ adolescent children. | 0 | 60 | 0 | 0
1.1.6.2 Training the widows’ collectives on identifying at-risk behaviour of their children etc. | # of widows collectives trained to identify at-risk or negative changes in the behaviour of young/ adolescent children. | 0 | 30 | 0 | 0
1.1.6.3 Link MW and WW to support structures such as WIN, Shanthiham and counselors and child support organizations. | #of women referred to support services | 0 | 30 | 0 | 0
Note on F1: User: Based on CEJ Q3 report
Note on F4: User: JSAC 9 Viluthu 14 RPK 17 WRC 14
Note on G4: User: Based on October M&E meeting
Note on F5: User: CEJ Q1 & Q2 report
Note on G7: User: 30 per district
Note on G8: User: 250 collective members per district to receive training from 90 capacitated reps/CEJ/partners
Note on F10: User: War widows 155 Military widows 257 Military widows disabled 20 Other FHH 504
Note on G11: User: minimum of 800 individuals (including collective members) through the 12 puppet shows across Anuradhapura and Kurunegala minimum of 300 individuals via forum theatre in Kilinochchi
Note on F26: User: Design thinking workshop 24 September
Note on G26: User: Follow-up roundtable with CIABOC and HRCSL planned.
Note on G33: User: 30 reps of collectives per districts at phase 1 training noted in 1.1.1.3

## Activity 1.1
Output 1.1 Military widows and war widows have increased knowledge of their rights and have access to complaint mechanisms on sexual bribery. | ANURADHAPURA | [11 empty] | KURUNEGALA | [11 empty] | KILINOCHCHI
| OCTOBER |  |  |  |  | NOVEMBER |  |  | DECEMBER |  |  |  | OCTOBER |  |  |  |  | NOVEMBER |  |  | DECEMBER |  |  |  | OCTOBER |  |  |  |  | NOVEMBER |  |  | DECEMBER
| Date | Event Type | Target Beneficiaries | Completed? (Yes/No/ Rescheduled) | Date | Event Type | Target Beneficiaries | Completed? (Yes/No/ Rescheduled) | Date | Event Type | Target Beneficiaries | Completed? (Yes/No/ Rescheduled) | Date | Event Type | Target Beneficiaries | Completed? (Yes/No/ Rescheduled) | Date | Event Type | Target Beneficiaries | Completed? (Yes/No/ Rescheduled) | Date | Event Type | Target Beneficiaries | Completed? (Yes/No/ Rescheduled) | Date | Event Type | Target Beneficiaries | Completed? (Yes/No/ Rescheduled) | Date | Event Type | Target Beneficiaries | Completed? (Yes/No/ Rescheduled) | Date | Event Type | Target Beneficiaries | Completed? (Yes/No/ Rescheduled)
Activity 1.1.1 Create/ strengthen collectives of military and war widows with a focus on asserting their rights and eliminating all forms of abuse. | 1. 25 Oct 2. 26 Oct | 1. Training 2. FGD | 1. War widows in Collective X 2. Public sector officials | 1. Yes 2. Rescheduled due to election to 30 Oct | [8 empty] | 1. 25 Oct 2. 26 Oct | 1. Training 2. FGD | 1. War widows in Collective X 2. Public sector officials | 1. yes 2. Rescheduled due to election to 30 Oct | [8 empty] | 1. 25 Oct 2. 26 Oct | 1. Training 2. FGD | 1. War widows in Collective X 2. Public sector officials | 1. yes 2. Rescheduled due to election to 30 Oct
1.1.1.1 Mapping existing self-help groups and collectives.
1.1.1.2 Form new widows’ collectives.
1.1.1.3 District level capacity building sessions for reps of self-help groups and collectives.
1.1.1.4 District level and capacity building sessions with widows’ collectives.
1.1.1.5 Develop/revise and disseminate trilingual advocacy materials.
Activity 1.1.2 Conduct community-wide awareness programmes on “breaking the taboo” in relation to sexual bribery and exploitation through participatory methods such as ‘puppetry’ and ‘forum theatre’.
1.1.2.1 Awareness programmes in each district.
1.1.2.2. District-level public events with govt officials & women CSOs on SB.
1.1.2.3 Social media awareness raising.
1.1.2.4 Newspaper articles, advertisements and at online Articles in the mainstream media.
1.1.2.5 Say No to SB/SE production and airtime in three languages.
1.1.2.6 Talk shows on national television in three languages.
Activity 1.1.3 Conduct legal aid and documentation mobile clinics in ‘safe spaces’ linking with CSOs and Women Development Officers of the MWCA for delivery and develop and disseminate an information brochure of service providers together with a SOP on accessing these services collectively
1.1.3.1 Prepare and print user-friendly trilingual awareness raising material
1.1.3.2 district-level & national level workshops to raise awareness/ capacitate officials on SB/SE.
1.1.3.3 TOT for identified potential resource persons from the above workshops to conduct the sensitization programmes at district and divisional levels
1.1.3.4 Conduct district level mobile legal and documentation clinics for widows.
1.1.3.5 Follow up meetings with stake holders regarding issues raised and documented during the mobile clinics
1.1.3.6 Consultations (in Colombo and districts) with CSOs and service providers providing legal support to factor in SB/SE into their mandate and services
Activity 1.1.4 Develop a pilot complaint reporting platform to report incidents of sexual bribery and exploitation, available online, through a mobile application and offline via SMS messaging, with geo-tagging location features.
1.1.4.1 Identify and commission suitable telecommunication partner to provide technical support.
1.1.4.2 Conduct consultations with stakeholders to add value and for CIABOC to feed into their existing complaints systems and procedures
1.1.4.3 Developing the app & linking to the website
1.1.4.4 Pilot testing with select collectives and front-line officials
1.1.4.5 District level Capacity building/ gender sensitization sessions of relevant officers who will handle new systems
1.1.4.6 Launch event/ integration of the systems into CIABOCs overall system.
1.1.4.7 Dissemination of advocacy material of the APP
1.1.4.8 TOT's on the use of the application for public officials, civil society and SH Committees at SLIDA.
Activity 1.1.5 Provide widows’ collectives with leadership and life skills training, and strengthen them through the formation of cross- regional alliances to build social cohesion and to cope with SB/SE.
1.1.5.1 Structured Exchange visits for widows’ collectives to cope with SB/SE.
1.1.5.2 Widows’ collectives (from 1.1.1) sharing of best practices of coping strategies at district level inter community common forum
1.1.5.3 Compilation of district level coping strategies.
1.1.5.4 Support DS level village meetings to share the coping strategies with the women
1.1.5.1 (a) Conduct a perception survey on widows and their adolescent children/youth in all three district
1.1.5.2 (b) Dialogues (based on the findings of the perception survey) with widows from each district to identify and achieve consensus on their role in peacebuilding. This would be succeeded by follow-up workshops at the end of the project.
1.1.5.3 (c) Trainings for widows' on leadership and life skills
Activity 1.1.6 Provide guidance and strategies to widows’ collectives to identify and respond to at-risk or negative changes in the behaviour of young/ adolescent children (to break the intergenerational impact of conflict).
1.1.6.1 Train WDOs and child (rights) protection officers to provide guidance and strategies to widows’ collectives to identify and respond to at-risk or negative changes in the behaviour of young/ adolescent children.
1.1.6.2 Training the widows’ collectives on identifying at-risk behaviour of their children etc.
1.1.6.3 Link MW and WW to support structures such as WIN, Shanthiham and counselors and child support organizations.
Note on J1: Mona Damdinjav: JSAC & Viluthu

## Output 1.2
Expected Results | Indicators | Baseline | Overall Target | Q3 Target | Q3 Progress | Q4 Target | Q4 Progress | Q1 2020 Target | Q1 2020 Progress | Q2 2020 Progress | Q2 2020 Target
Output 1.2 Civil society Is strengthened to provide services for the protection of victims of sexual exploitation and sexual bribery
Activity 1.2.1 Capacity building of civil society actors to provide services, information and referrals to victim survivors of sexual bribery and exploitation | Output Indicator 1.2.1 # of civil society organizations who are increasingly providing services, information and referrals for war and military widows | 0 | 10 | 0 | 4 | 5
1.2.1.1 Three district level capacity building workshops to Civil Society organizations including women’s organizations partners | # of participants representing CSO and women’s organizations capacitated | 0 | 60 | 0 | 0 | 0
1.2.1.2 Technical support to partner organisations on enhancing provision of services to survivors (supporting the filing of cases, follow up, documentation etc | # of partner organizations provided with technical support to assist victim survivors of SB/SE | 0 | 4 | 0 | 0 | 0
Activity 1.2.2 Support civil society on lobbying and advocating with national institutions and independent commissions to institutionalize response to complaints of sexual bribery (through setting up of special complaints mechanisms, gender- sensitive policies and procedures to investigate and handle sexual bribery cases). | Output Indicator 1.2.2 # of widows provided with legal and other assistance through CSOs | 0 | 50 | 0 | 0 | 0 |  | 20 |  |  | 30
1.2.2.1 National and district level sensitization workshops for CSOs on SB/SE and response mechanisms | # of public officials sensitized on SB/SE | 0 | 150 | 0 | 0 | 0
1.2.2.2 Capacity building of CSOs on effective advocacy and campaigning/serving as a 'watchdog' mechanism on SB/SE and form an advocacy group | # of capacity building trainings; one advocacy group formed | 0 | 0 | 0 | 0
Activity 1.2.3 CSOs provide free legal aid to war and military widows who are willing to file a complaint. | Output Indicator 1.2.3 # of complaints filed by military and war widows | 0 | 20 | 0 | 0 |  |  | 5
1.2.3.1 Two CSOs in different districts provide legal assistance to widows (UNDP) | # of CSOs | 0 | 2 CSOs per district? | 0 | 0
Note on F3: User: 4 district-level partners

## Activity 1.2
Output 1.2 Civil society Is strengthened to provide services for the protection of victims of sexual exploitation and sexual bribery | ANURADHAPURA | [11 empty] | KURUNEGALA | [11 empty] | KILINOCHCHI
| OCTOBER |  |  |  |  | NOVEMBER |  |  | DECEMBER |  |  |  | OCTOBER |  |  |  |  | NOVEMBER |  |  | DECEMBER |  |  |  | OCTOBER |  |  |  |  | NOVEMBER |  |  | DECEMBER
| Date | Event Type | Target Beneficiaries | Completed? (Yes/No/ Rescheduled) | Date | Event Type | Target Beneficiaries | Completed? (Yes/No/ Rescheduled) | Date | Event Type | Target Beneficiaries | Completed? (Yes/No/ Rescheduled) | Date | Event Type | Target Beneficiaries | Completed? (Yes/No/ Rescheduled) | Date | Event Type | Target Beneficiaries | Completed? (Yes/No/ Rescheduled) | Date | Event Type | Target Beneficiaries | Completed? (Yes/No/ Rescheduled) | Date | Event Type | Target Beneficiaries | Completed? (Yes/No/ Rescheduled) | Date | Event Type | Target Beneficiaries | Completed? (Yes/No/ Rescheduled) | Date | Event Type | Target Beneficiaries | Completed? (Yes/No/ Rescheduled)
Activity 1.2.1 Capacity building of civil society actors to provide services, information and referrals to victim survivors of sexual bribery and exploitation | 1. 25 Oct 2. 26 Oct | 1. Training 2. FGD | 1. War widows in Collective X 2. Public sector officials | 1. Yes 2. Rescheduled due to election to 30 Oct | [8 empty] | 1. 25 Oct 2. 26 Oct | 1. Training 2. FGD | 1. War widows in Collective X 2. Public sector officials | 1. yes 2. Rescheduled due to election to 30 Oct | [8 empty] | 1. 25 Oct 2. 26 Oct | 1. Training 2. FGD | 1. War widows in Collective X 2. Public sector officials | 1. yes 2. Rescheduled due to election to 30 Oct
1.2.1.1 Three district level capacity building workshops to Civil Society organizations including women’s organizations partners
1.2.1.2 Technical support to partner organisations on enhancing provision of services to survivors (supporting the filing of cases, follow up, documentation etc
Activity 1.2.2 Support civil society on lobbying and advocating with national institutions and independent commissions to institutionalize response to complaints of sexual bribery (through setting up of special complaints mechanisms, gender- sensitive policies and procedures to investigate and handle sexual bribery cases).
1.2.2.1 National and district level sensitization workshops for CSOs on SB/SE and response mechanisms
1.2.2.2 Capacity building of CSOs on effective advocacy and campaigning/serving as a 'watchdog' mechanism on SB/SE and form an advocacy group
Activity 1.2.3 CSOs provide free legal aid to war and military widows who are willing to file a complaint.
1.2.3.1 Two CSOs in different districts provide legal assistance to widows (UNDP)
Note on B1: Mona Damdinjav: JSAC & Viluthu

## Output 1.3
Expected Results | Indicators | Baseline | Overall Target | Q3 Target | Q3 Progress | Q4 Target | Q4 Progress | Q1 2020 Target | Q1 2020 Progress | Q2 2020 Progress | Q2 2020 Target
Output 1.3 Military widows and war widows increase their entrepreneurial knowledge and skills
Activity 1.3.1 Conduct a needs assessment in targeted districts to understand gaps in skills and capacities of widows, and value chain analysis in identified sectors to understand market opportunities | Output Indicator 1.3.1 # of widows who are trained to commence a business/enterprise | TBD | 280 military and war widows |  |  | 140
1.3.1.1 Conduct needs assessment in 3 districts | completed needs assessment | in progress
1.3.1.2 Identify and conduct value chain analysis in 3 districts (in 2-3 sectors) | completed value chain analysis | in progress
1.3.1.3 Develop programme design for output 1.3 | developed programme
Activity 1.3.2 Provide skills training (product development and use of technology) and capacity building on business management (business planning, financial literacy and management, particularly information on accessing loans and linking with credible lending institutions, and marketing for widows in identified sectors. | Output Indicator 1.3.2 # of widows provided with grants, disaggregated by type of widow. | 0 | 200 military and war widows |  |  | 100 military widows and war widows have received special grants by end of 4th quarter
1.3.2.1 Training for widows on product development and use of technology related to specific sectors (3 workshops per district) | # of workshops | 0 | 9 (3 per district)
1.3.2.2 Training for front-line government officials (WDOs, EDO, Vidatha Officers) to provide business advisory services (12 divisions) | # of workshops | 0 | 12 divisions
1.3.2.3 Training on marketing (3 workshops per district) | # of workshops |  | 9 (3 per district)
1.3.2.4 Conduct 14 capacity building training programs (each 5 day duration) for widows on business management skills (business planning, financial literacy and management particularly information accessing loans and linking with credible linking institutions and markets) 20 widows each training | # of trainings | 0 | 14 (with 20 widows at each training)
1.3.2.5 Facilitation the preparation of viable new business proposals or proposals to upscale existing businesses of widows (during and post training) | n/a | 0 | 0
Activity 1.3.3 Support widows to access markets and points-of-sale by linking them to Ranaviru villages, cooperatives, 'Hela Bojun Hala'/'Ammaarchi' outlets in the target areas, potential private sectors and existing UNDP supported women's associations and producer groups. | Output Indicator 1.3.3 # of Diversity Market Fairs held. | 2 | Target: 4 - 1 in each project district and 1 in Colombo) |  |  | 2
1.3.3.1 Identify existing markets and points-of-sale including UNDP existing linkages | # of markets identified | 0 | 0
1.3.3.2 Conduct 3 workshops in the 3 districts | # of workshops | 0 | 3
Activity 1.3.4 Support entrepreneurship by setting up mentoring programmes linking widow collectives with successful women entrepreneurs, regional Chambers of Commerce and Women's Chambers of Commerce, together with the MWCA | n/a
1.3.4.1 Identify mentors through the Chambers of Commerce and other networks to link with widow collectives in the three districts +1 (UNW and UNDP) | # of mentors identified | 0 | 0
1.3.4.2 Six workshops at the district level connecting mentors and mentees to jointly design an action plan on how to support widows' enterprises (3 by UNW and 3 by UNDP) | # of workshops | 0 | 3
1.3.4.3 Follow-up workshop on progress | # of workshops | 0 | 0
1.3.4.1 Identify mentors through the Chambers of Commerce and other networks to link with widow collectives in the three districts +1 (UNW and UNDP) | # of mentors identified | 0 | 0
1.3.4.2 Six workshops at the district level connecting mentors and mentees to jointly design an action plan on how to support widows' enterprises (3 by UNW and 3 by UNDP) | # of workshops | 0 | 3
1.3.4.3 Follow-up workshop on progress | # of workshops | 0 | 0
Activity 1.3.5 Provide special grants to identified widows for a viable, innovative up-market business venture or scaling up of an existing venture (following the capacity building programmes) via a 'competitive challenge' exclusively for military and war widows where contenders will present business proposals which will be judged by an independent selection panel. | see output indicator 1.3.2
1.3.5.1 Follow-up on ensuring the submission of business proposals by widows. | # of business proposals | 0 | 0
1.3.5.2 Presentation of business proposals at district level forums (6 forums) | # of forums | 0 | 6
Activity 1.3.6 Conduct 'exposure visits' where widow entrepreneurs from the North and South showcase their products in "Diversity Market fairs" held on rotational basis in all project locations to foster cross-regional learning, build social cohesion and inter-linkages for peace (including ILO/WFP PTK Cooperative) | see output indicator 1.3.3
1.3.6.1 Conduct 3 diversity market fairs (one in each district) organised- inclusive of neighboring non-project districts- where successful entrepreneurs and project beneficiaries showcase best practices/success stories | # of fairs | 0 | 3
1.3.6.2 Conduct 3 district-level experience sharing sessions by a select number of widow entrepreneurs from different project districts (cross-regional learning)- include ILO/WFP PTK Cooperative | # of experience sharing sessions | 0 | 3
1.3.6.1 Conduct 3 diversity market fairs (one in each district) organised- inclusive of neighboring non-project districts- where successful entrepreneurs and project beneficiaries showcase best practices/success stories | # of fairs | 0 | 3
1.3.6.2 Conduct 3 district-level experience sharing sessions by a select number of widow entrepreneurs from different project districts (cross-regional learning)- include ILO/WFP PTK Cooperative | # of experience sharing sessions | 0 | 3

## Activity 1.3
Output 1.3 Military widows and war widows increase their entrepreneurial knowledge and skills | ANURADHAPURA | [11 empty] | KURUNEGALA | [11 empty] | KILINOCHCHI
| OCTOBER |  |  |  |  | NOVEMBER |  |  | DECEMBER |  |  |  | OCTOBER |  |  |  |  | NOVEMBER |  |  | DECEMBER |  |  |  | OCTOBER |  |  |  |  | NOVEMBER |  |  | DECEMBER
| Date | Event Type | Target Beneficiaries | Completed? (Yes/No/ Rescheduled) | Date | Event Type | Target Beneficiaries | Completed? (Yes/No/ Rescheduled) | Date | Event Type | Target Beneficiaries | Completed? (Yes/No/ Rescheduled) | Date | Event Type | Target Beneficiaries | Completed? (Yes/No/ Rescheduled) | Date | Event Type | Target Beneficiaries | Completed? (Yes/No/ Rescheduled) | Date | Event Type | Target Beneficiaries | Completed? (Yes/No/ Rescheduled) | Date | Event Type | Target Beneficiaries | Completed? (Yes/No/ Rescheduled) | Date | Event Type | Target Beneficiaries | Completed? (Yes/No/ Rescheduled) | Date | Event Type | Target Beneficiaries | Completed? (Yes/No/ Rescheduled)
Activity 1.3.1 Conduct a needs assessment in targeted districts to understand gaps in skills and capacities of widows, and value chain analysis in identified sectors to understand market opportunities | 1. 25 Oct 2. 26 Oct | 1. Training 2. FGD | 1. War widows in Collective X 2. Public sector officials | 1. Yes 2. Rescheduled due to election to 30 Oct | [8 empty] | 1. 25 Oct 2. 26 Oct | 1. Training 2. FGD | 1. War widows in Collective X 2. Public sector officials | 1. yes 2. Rescheduled due to election to 30 Oct | [8 empty] | 1. 25 Oct 2. 26 Oct | 1. Training 2. FGD | 1. War widows in Collective X 2. Public sector officials | 1. yes 2. Rescheduled due to election to 30 Oct
1.3.1.1 Conduct needs assessment in 3 districts
1.3.1.2 Identify and conduct value chain analysis in 3 districts (in 2-3 sectors)
1.3.1.3 Develop programme design for output 1.3
Activity 1.3.2 Provide skills training (product development and use of technology) and capacity building on business management (business planning, financial literacy and management, particularly information on accessing loans and linking with credible lending institutions, and marketing for widows in identified sectors.
1.3.2.1 Training for widows on product development and use of technology related to specific sectors (3 workshops per district)
1.3.2.2 Training for front-line government officials (WDOs, EDO, Vidatha Officers) to provide business advisory services (12 divisions)
1.3.2.3 Training on marketing (3 workshops per district)
1.3.2.4 Conduct 14 capacity building training programs (each 5 day duration) for widows on business management skills (business planning, financial literacy and management particularly information accessing loans and linking with credible linking institutions and markets) 20 widows each training
1.3.2.5 Facilitation the preparation of viable new business proposals or proposals to upscale existing businesses of widows (during and post training)
Activity 1.3.3 Support widows to access markets and points-of-sale by linking them to Ranaviru villages, cooperatives, 'Hela Bojun Hala'/'Ammaarchi' outlets in the target areas, potential private sectors and existing UNDP supported women's associations and producer groups.
1.3.3.1 Identify existing markets and points-of-sale including UNDP existing linkages
1.3.3.2 Conduct 3 workshops in the 3 districts
Activity 1.3.4 Support entrepreneurship by setting up mentoring programmes linking widow collectives with successful women entrepreneurs, regional Chambers of Commerce and Women's Chambers of Commerce, together with the MWCA
1.3.4.1 Identify mentors through the Chambers of Commerce and other networks to link with widow collectives in the three districts +1 (UNW and UNDP)
1.3.4.2 Six workshops at the district level connecting mentors and mentees to jointly design an action plan on how to support widows' enterprises (3 by UNW and 3 by UNDP)
1.3.4.3 Follow-up workshop on progress
1.3.4.1 Identify mentors through the Chambers of Commerce and other networks to link with widow collectives in the three districts +1 (UNW and UNDP)
1.3.4.2 Six workshops at the district level connecting mentors and mentees to jointly design an action plan on how to support widows' enterprises (3 by UNW and 3 by UNDP)
1.3.4.3 Follow-up workshop on progress
Activity 1.3.5 Provide special grants to identified widows for a viable, innovative up-market business venture or scaling up of an existing venture (following the capacity building programmes) via a 'competitive challenge' exclusively for military and war widows where contenders will present business proposals which will be judged by an independent selection panel.
1.3.5.1 Follow-up on ensuring the submission of business proposals by widows.
1.3.5.2 Presentation of business proposals at district level forums (6 forums)
Activity 1.3.6 Conduct 'exposure visits' where widow entrepreneurs from the North and South showcase their products in "Diversity Market fairs" held on rotational basis in all project locations to foster cross-regional learning, build social cohesion and inter-linkages for peace (including ILO/WFP PTK Cooperative)
1.3.6.1 Conduct 3 diversity market fairs (one in each district) organised- inclusive of neighboring non-project districts- where successful entrepreneurs and project beneficiaries showcase best practices/success stories
1.3.6.2 Conduct 3 district-level experience sharing sessions by a select number of widow entrepreneurs from different project districts (cross-regional learning)- include ILO/WFP PTK Cooperative
1.3.6.1 Conduct 3 diversity market fairs (one in each district) organised- inclusive of neighboring non-project districts- where successful entrepreneurs and project beneficiaries showcase best practices/success stories
1.3.6.2 Conduct 3 district-level experience sharing sessions by a select number of widow entrepreneurs from different project districts (cross-regional learning)- include ILO/WFP PTK Cooperative
Note on B1: Mona Damdinjav: JSAC & Viluthu

## Output 2.1
Expected Results | Indicators | Baseline | Overall Target | Q3 Target | Q3 Progress | Q4 Target | Q4 Progress | Q1 2020 Target | Q1 2020 Progress | Q2 2020 Progress | Q2 2020 Target
Output 2.1 The capacity of public institutions and officials are built to prevent and respond to sexual bribery and to protect military and war widows from sexual exploitation.
Activities 2.1.1 Sensitization of public officials on sexual bribery and sexual exploitation as crimes, using ‘puppetry’ and ‘forum theatre’ to communicate the message in a non-contentious manner. | Output Indicator 2.1.1 # of sensitization programmes held for public officials on sexual harassment policies, legal frameworks, guidelines on response mechanisms, and accountability measures. | 0 | 20 | 0 | 0 | 10
2.1.1.1 National and district /divisional level sensitization workshops for public officials. | # of workshops
2.1.1.1 National and district /divisional level sensitization workshops for public officials. | # of workshops
Activities 2.1.2 Development of a special training programme for Public officials on handling complaints of sexual Exploitation and sexual bribery, in consultation with public training Institutions such as SLIDA/SLFI. | Output Indicator 2.1.2 # of public officials who complete the course on handling bribery complaints, including sexual bribery, harassment and exploitation. | TBC | 50 | 0 | 0 | 20
2.1.2.1 Draft, share and finalize special training module in consultation with the relevant institutions. | # of institutions consulted to draft training module | 0 | 3
2.1.2.2 TOT for SLIDA/SLFI trainers | # of officers participated at the ToT session | 0 | 60
2.1.2.3 Residential training programmes for public officials and SH Committees | # of SH committee members trained | 0 | 50
Activities 2.1.3 Capacity of National Human Rights Institutions are enhanced to receive and respond to complaints. | Output Indicator 2.1.3 # of legal aid clinics conducted by capacitated local public officers on preliminary assistance to survivors on possible legal remedies. | 0 | At least 15 legal aid clinics |  |  | 15 officers capacitated by end of 4th quarter.
2.1.3.1 Initiate discussions with Commissioners of HRC | # of discussions | 0
2.1.3.2 Conduct training for HRC officers on SB & SE | # of trainings | 0
Activities 2.1.4 Capacities of MWCA are enhanced to provide legal assistance through Women Development Officers, Counselling Assistants (and other relevant officers) on sexual bribery and exploitation in safe spaces. | see output Indicator 2.1.3
2.1.4.1 Formulate a module on para legal assistance for field officers of MWCA in S/T/E | # of discussions | 0
2.1.4.2 Identify WDOs and Counselling Officers to follow a residential TOT on providing legal assistance as para-legal officers | # of trainings | 0
2.1.4.3 Conduct 7 legal clinics linking with CSOs in relevant divisions led by capacitated officers | # of trainings | 0 | 7

## Activity 2.1
Output 2.1 The capacity of public institutions and officials are built to prevent and respond to sexual bribery and to protect military and war widows from sexual exploitation. | ANURADHAPURA | [11 empty] | KURUNEGALA | [11 empty] | KILINOCHCHI
| OCTOBER |  |  |  |  | NOVEMBER |  |  | DECEMBER |  |  |  | OCTOBER |  |  |  |  | NOVEMBER |  |  | DECEMBER |  |  |  | OCTOBER |  |  |  |  | NOVEMBER |  |  | DECEMBER
| Date | Event Type | Target Beneficiaries | Completed? (Yes/No/ Rescheduled) | Date | Event Type | Target Beneficiaries | Completed? (Yes/No/ Rescheduled) | Date | Event Type | Target Beneficiaries | Completed? (Yes/No/ Rescheduled) | Date | Event Type | Target Beneficiaries | Completed? (Yes/No/ Rescheduled) | Date | Event Type | Target Beneficiaries | Completed? (Yes/No/ Rescheduled) | Date | Event Type | Target Beneficiaries | Completed? (Yes/No/ Rescheduled) | Date | Event Type | Target Beneficiaries | Completed? (Yes/No/ Rescheduled) | Date | Event Type | Target Beneficiaries | Completed? (Yes/No/ Rescheduled) | Date | Event Type | Target Beneficiaries | Completed? (Yes/No/ Rescheduled)
Activities 2.1.1 Sensitization of public officials on sexual bribery and sexual exploitation as crimes, using ‘puppetry’ and ‘forum theatre’ to communicate the message in a non-contentious manner. | 1. 25 Oct 2. 26 Oct | 1. Training 2. FGD | 1. War widows in Collective X 2. Public sector officials | 1. Yes 2. Rescheduled due to election to 30 Oct | [8 empty] | 1. 25 Oct 2. 26 Oct | 1. Training 2. FGD | 1. War widows in Collective X 2. Public sector officials | 1. yes 2. Rescheduled due to election to 30 Oct | [8 empty] | 1. 25 Oct 2. 26 Oct | 1. Training 2. FGD | 1. War widows in Collective X 2. Public sector officials | 1. yes 2. Rescheduled due to election to 30 Oct
2.1.1.1 National and district /divisional level sensitization workshops for public officials.
2.1.1.1 National and district /divisional level sensitization workshops for public officials.
Activities 2.1.2 Development of a special training programme for Public officials on handling complaints of sexual Exploitation and sexual bribery, in consultation with public training Institutions such as SLIDA/SLFI.
2.1.2.1 Draft, share and finalize special training module in consultation with the relevant institutions.
2.1.2.2 TOT for SLIDA/SLFI trainers
2.1.2.3 Residential training programmes for public officials and SH Committees
Activities 2.1.3 Capacity of National Human Rights Institutions are enhanced to receive and respond to complaints.
2.1.3.1 Initiate discussions with Commissioners of HRC
2.1.3.2 Conduct training for HRC officers on SB & SE
Activities 2.1.4 Capacities of MWCA are enhanced to provide legal assistance through Women Development Officers, Counselling Assistants (and other relevant officers) on sexual bribery and exploitation in safe spaces.
2.1.4.1 Formulate a module on para legal assistance for field officers of MWCA in S/T/E
2.1.4.2 Identify WDOs and Counselling Officers to follow a residential TOT on providing legal assistance as para-legal officers
2.1.4.3 Conduct 7 legal clinics linking with CSOs in relevant divisions led by capacitated officers
Note on B1: Mona Damdinjav: JSAC & Viluthu

## Output 2.2
Expected Results | Indicators | Baseline | Overall Target | Q3 Target | Q3 Progress | Q4 Target | Q4 Progress | Q1 2020 Target | Q1 2020 Progress | Q2 2020 Progress | Q2 2020 Target
Output 2.2 Strengthen existing accountability mechanisms to report and responsibility mechanisms to report and respond to sexual bribery and exploitation.
Activity 2.2.1 Technical support to the formation/ re- establishment of anti- sexual harassment committee in public institutions as per the recent directive issued by the Ministry of Women and Child Affairs. | Output indicator 2.2.1 # of public institutions with established and functioning Anti- Sexual Harassment Committees | 10 established though not functioning | 12 established and fully functioning |  |  | 5 anti-sexual harassment committees strengthened by 4th quarter
2.2.1.1 Policy Dialogue with Ministries and District Secretariats to re-establish/set-up anti-SH committees with special attention to stories of widows’ experiences and inclusion of SB/SE into existing guidelines of the public institution. | # of meetings with Ministries and District Secretariats to re-establish/set-up anti-SH committees | 0 | 4
2.2.1.2 Trainings to the SH Committees in Sinhala and Tamil | # of trainings provided to the SH committees | 0 | 4
2.2.1.2 Trainings to the SH Committees in Sinhala and Tamil | # of trainings provided to the SH committees | 0 | 4
2.2.1.3 Develop a gender sensitive code of conduct, which addresses SB/SE explicitly, for public officers in consultation with SH Committees | # of SH committees consulted to draft gender sensitive code of conduct | 0 | 3
2.2.1.4 Launch of the code of conduct with policy makers, govt officers and district level govt officials. | # of policy makers, govt officers and district level govt officials attending the launch | 0 | 50
2.2.1.5 Follow-up discussion sessions/assessments of activities pertaining to the strengthening of existing anti-sexual harassment committees | # of follow-up discussion sessions/assessments | 0 | 0
Activity 2.2.2 Provide technical support to the Ministry of Women and Children to advocate for gender-sensitive Anti-Bribery legislation. | Output indicator 2.2.2 # of state/ public sector institutions provided with technical support to integrate adopt measures on addressing sexual bribery and sexual exploitation | 0 | 4
2.2.2.1 Meetings with the reps of MoWA to lobby for gender sensitive anti- bribery legislation | # of meetings held with the relevant MoWA representatives. | 0 | 4
2.2.2.2 Convene high-level ministerial meetings (with MWCA as the lead) ministries to highlight the need for gender sensitive anti-bribery legislation including sexual bribery | # of meetings | 0 | 0
2.2.2.3 Local consultant to support MWCA and inter-ministerial discussions | n/a
Activity 2.2.3 Provide technical support to Ministries who are willing to protect war and MWs from SB to draft policies/ circulars/ guidelines | see outcome indicator 2.1a
2.2.3.1 Meetings with the representatives of relevant ministries to draft policies/ circulars and guidelines | # of policies/ circulars and guidelines drafted with the support of the relevant Ministries. | 0 | 2
2.2.3.2 Local consultant to support MWCA in discussions and consultations aimed at drafting policies/circulars/guidelines

## Activity 2.2
Output 2.2 Strengthen existing accountability mechanisms to report and responsibility mechanisms to report and respond to sexual bribery and exploitation. | ANURADHAPURA | [11 empty] | KURUNEGALA | [11 empty] | KILINOCHCHI
| OCTOBER |  |  |  |  | NOVEMBER |  |  | DECEMBER |  |  |  | OCTOBER |  |  |  |  | NOVEMBER |  |  | DECEMBER |  |  |  | OCTOBER |  |  |  |  | NOVEMBER |  |  | DECEMBER
| Date | Event Type | Target Beneficiaries | Completed? (Yes/No/ Rescheduled) | Date | Event Type | Target Beneficiaries | Completed? (Yes/No/ Rescheduled) | Date | Event Type | Target Beneficiaries | Completed? (Yes/No/ Rescheduled) | Date | Event Type | Target Beneficiaries | Completed? (Yes/No/ Rescheduled) | Date | Event Type | Target Beneficiaries | Completed? (Yes/No/ Rescheduled) | Date | Event Type | Target Beneficiaries | Completed? (Yes/No/ Rescheduled) | Date | Event Type | Target Beneficiaries | Completed? (Yes/No/ Rescheduled) | Date | Event Type | Target Beneficiaries | Completed? (Yes/No/ Rescheduled) | Date | Event Type | Target Beneficiaries | Completed? (Yes/No/ Rescheduled)
Activity 2.2.1 Technical support to the formation/ re- establishment of anti- sexual harassment committee in public institutions as per the recent directive issued by the Ministry of Women and Child Affairs. | 1. 25 Oct 2. 26 Oct | 1. Training 2. FGD | 1. War widows in Collective X 2. Public sector officials | 1. Yes 2. Rescheduled due to election to 30 Oct | [8 empty] | 1. 25 Oct 2. 26 Oct | 1. Training 2. FGD | 1. War widows in Collective X 2. Public sector officials | 1. yes 2. Rescheduled due to election to 30 Oct | [8 empty] | 1. 25 Oct 2. 26 Oct | 1. Training 2. FGD | 1. War widows in Collective X 2. Public sector officials | 1. yes 2. Rescheduled due to election to 30 Oct
2.2.1.1 Policy Dialogue with Ministries and District Secretariats to re-establish/set-up anti-SH committees with special attention to stories of widows’ experiences and inclusion of SB/SE into existing guidelines of the public institution.
2.2.1.1 Policy Dialogue with Ministries and District Secretariats to re-establish/set-up anti-SH committees with special attention to stories of widows’ experiences and inclusion of SB/SE into existing+B6 guidelines of the public institution.
2.2.1.2 Trainings to the SH Committees in Sinhala and Tamil
2.2.1.3 Develop a gender sensitive code of conduct, which addresses SB/SE explicitly, for public officers in consultation with SH Committees
2.2.1.4 Launch of the code of conduct with policy makers, govt officers and district level govt officials.
2.2.1.5 Follow-up discussion sessions/assessments of activities pertaining to the strengthening of existing anti-sexual harassment committees
Activity 2.2.2 Provide technical support to the Ministry of Women and Children to advocate for gender-sensitive Anti-Bribery legislation.
2.2.2.1 Meetings with the reps of MoWA to lobby for gender sensitive anti- bribery legislation
2.2.2.2 Convene high-level ministerial meetings (with MWCA as the lead) ministries to highlight the need for gender sensitive anti-bribery legislation including sexual bribery
2.2.2.3 Local consultant to support MWCA and inter-ministerial discussions
Activity 2.2.3 Provide technical support to Ministries who are willing to protect war and MWs from SB to draft policies/ circulars/ guidelines
2.2.3.1 Meetings with the representatives of relevant ministries to draft policies/ circulars and guidelines
2.2.3.2 Local consultant to support MWCA in discussions and consultations aimed at drafting policies/circulars/guidelines
Note on B1: Mona Damdinjav: JSAC & Viluthu