## Per Activity
Annex D - PBF project budget
Note: If this is a budget revision, insert extra columns to show budget changes.
Table 1 - PBF project budget by Outcome, output and activity
Outcome/ Output number | Outcome/ output/ activity formulation: | Budget by recipient organization in USD - Please add a new column for each recipient organization | Percent of budget for each output reserved for direct action on gender equality (if any): | Level of expenditure/ commitments in USD (to provide at time of project progress reporting): | Level of expenditure/commitment in % to date | Any remarks (e.g. on types of inputs provided or budget justification, for example if high TA or travel costs)
Outcome 1: Increased Leadership and Participation of Young Women and Men in Electoral and Post Electoral Mechanisms and Processes for Peacebuilding at all levels
Output 1.1: | Increased space for youth engagement, dialogue and civic participation to diffuse potential election prone conflict at community levels and significantly reduced number of reported incidents of electoral related violence in 15 counties. | 200255
Activity 1.1.1: | Conduct youth awareness campaign on electoral violence prevention and strengthen the national youth architecture for the 2017 youth engagement | 92255 |  | 91250 | 98.91%
Activity 1.1.2: | Youth Theatre in 15 counties across Liberia | 15000 |  | 15000 | 100%
Activity 1.1.3: | Regional Youth caravan and forums on prevention of gender based electoral violence and Sexual Reproductive Health and Rights (SRHR) | 93000 |  | 82950 | 89.19%
Output 1.2: | Promote Confidence and trust building between the different community youth groups, political party youth leagues, Liberia National Police, local institutions and civl society | 99961
Activity 1.2.1: | Dialogue and consultations between LNP, youth and traditional leaders | 75000 |  | 60450 | 80.6%
Activity 1.2.2: | Joint Cultural and Sporting events between youths and different community groups, including LNP, NEC | 24961 |  | 24960 | 100%
Output 1.3: | Support LNP at the county district level to enage with youth, particularly young women and girls, community policing, peacebuilding and linkages with the early warning and response mechanism | 45000
Activity 1.3.1: | Hold training sessions and worrkshops for the development of ICT engineers of LNP and Youth led Early Warning and Response system | 45000 |  | 34109.5 | 75.8%
Sub Total - Outcome 1: |  | 345216 | 0 | 308719.5
OUTCOME 2: Increased capacity and skills of young men and women to monitor, prevent and mitigate electoral and gender based violence
Output 2.1: | Strengthen capacity of youth led and youth focused organisations on peacebuilding including mapping of activities in peacebuilding | 208160
Activity 2.1.1: | Increased capacity of female and male-led youth focused organizations to engage in peaceful electoral processes and electoral conflict prevention. | 148160 |  | 158160 | 106.7%
Activity 2.1.2: | Training youth at community, schools and universities on the five key elements of SCR 2250 and 1325 on the importance of their role in peacebuilding through inter-generational, interfaith and inter-ethic dislogues and translating them into action. | 40000 |  | 45000 | 112.5%
Activity 2.1.3: | Train young female police officers on electoral gender based violence | 20000 |  | 20000 | 100%
Output 2.2: | Increase capacities of national, county and district level institutions to engage youth particularly young women and girls in peacebuilding and linkages with the early warning and response mechanism are created | 274000
Activity 2.2.1: | Strengthen existing youth networks, coalitions and Youth Peace Committees at county level with minimum of 40% femaile participation | 80000 |  | 94394.6 | 118%
Activity 2.2.2: | Conduct Violence Against Women Education (VAWE) for NEC female staff and police | 107340 |  | 126482.24 | 117.8%
Activity 2.2.3: | Support the Ministry of Youth and Sports and existing youth centers to provide government and community liaison services. | 35000 |  | 55000 | 157.1%
Activity 2.2.4 | Support existing community security and health structures for provision of electoral related SRHR services | 51660 |  | 71000 | 137.4%
Output 2.3: | Joint Community and High School Peacebuilding Campaigne with Targeted groups (including Pen Pen Riders, Messengers of Peace and Paramount Young Women Initiative) | 170800
Activity 2.3.1: | Support young female pen-pen riders to engage in street and community sensitization. | 70800 |  | 91591.54 | 129.4%
Activity 2.3.2: | Support Messengers of Peace Liberia Inc. (MoP) in training young people in mediation and dialogue | 20000 |  | 23438.15 | 117.2%
Activity 2.3.3: | Youth peace dialogue programme (YPD) | 70000 |  | 69500 | 99.29%
Activity 2.3.4 | Theater for Peace with Messerges of Peace (MoP) | 10000 |  | 10000 | 100%
Sub Total - Outcome 2: |  | 652960 |  | 764566.53
OUTCOME 3: Increased capacity of the peace-building secretariat to provide effective oversight, coordination, monitoring, reporting, evaluation and communication on the achievement of the PBF investment contributing to the implementation of the Liberian peace-building plan, including government pro-poor agenda and future IRF projects that support it.
Output 3.1: | The PBF Secretariat effectively provides oversight and coordinates the implementation of PBF supported projects as well as communicate to PBSO on the results of IRF projects supporting the implementation of the Peace-building Plan | 772582 |  | 733997.75 | 95.01%
Output 3.2: | Enhance the Liberia Social Cohesion and Reconcilaition Index (SCORE) in order to provide evidence based conflict, prevention and peacebuilding policies for the implementation of national frameworks that address the root causes of conflict | 100000 |  | 93000 | 93%
Output 3.3: | The Office of the President of the new administration is empowered to ensure immediate political and economic policy decisions informed by the required knowledge and analysis as well as ensuring strategic liaison between presidential transition team, UN Resident Cordinator and other stakeholders including IFIs and bilateral donors during the transition through the deployment of the Senior Advisor on Governance, Peace and Development | 120000 |  | 52120.83 | 43.43%
Sub Total - Outcome 3 |  | 992582 |  | 879118.58
Project personnel costs if not included in activities above
Project operational costs if not included in activities above
Project M&E budget
Project Direct Activity Budget (Activity 4) |  | 324999.94 |  | 236298.81 | 72.71%
SUB-TOTAL PROJECT BUDGET: |  | 2315757.94 |  | 2188703.42 | 94.51%
Indirect support costs (7%): |  | 162103.06 |  | 153209.2394 | 94.51%
TOTAL PROJECT BUDGET/COST: |  | 2477861 |  | 2341912.6594 | 94.51%

## Per Category
Table 2 - PBF project budget by UN cost category
Note: If this is a budget revision, insert extra columns to show budget changes.
Output 00105667 - Enhancing Youth Participation
CATEGORIES | Amount Recipient Agency - UNDP (LMPTF/PBF) | [5 empty] | Comment
| Tranche 1 | Tranche 2 | Total Amount Received | Total Expenses | Balance | Del. %
1. Staff and other personnel | 252238.7 | 427725.7 | 679964.4 | 631117.32 | 48847.08 | 92.82%
2. Supplies, Commodities, Materials | 17500 | 32500 | 50000 | 50000 | 0 | 100%
3. Equipment, Vehicles, and Furniture (including Depreciation) | 44100 | 58900 | 103000 | 103000 | 0 | 100%
4. Contractual services | 261212 | 241405.8 | 502617.8 | 465483.42 | 37134.38 | 92.61%
5.Travel | 17500 | 17500 | 35000 | 37861.66 | -2861.66 | 108.2%
6. Transfers and Grants to Counterparts | 612511.2 | 262504.8 | 875016 | 877208.6 | -2192.6 | 100.3%
7. General Operating and other Direct Costs | 8400 | 61759.72 | 70159.72 | 24032.42 | 46127.3 | 34.25%
Sub-Total Project Costs | 1213461.9 | 1102296.02 | 2315757.92 | 2188703.42 | 127054.5 | 94.51%
8. Indirect Support Costs (must be 7%) | 84942.333 | 77160.7214 | 162103.0544 | 153209.2394 | 8893.815 | 94.51%
TOTAL | 1298404.233 | 1179456.7414 | 2477860.9744 | 2341912.6594 | 135948.315 | 94.51%