## AWP 2018 2nd phase
JOINT RUNO'S ANNUAL WORK PLANS FOR AWP FOR 2018: CROSS-BORDER COOPERATION FOR SUSTAINABLE PEACE AND DEVELOPMENT 2nd Phase
Reporting period
| Indicators | Targets (Annualized for Activity level) | RUNO | BUDGET KG | BUDGET TJ | 2018-04-01 | 2018-05-01 | 2018-06-01 | 2018-07-01 | 2018-08-01 | 2018-09-01 | 2018-10-01 | 2018-11-01 | 2018-12-01 | 2019-01-01 | 2019-02-01 | 2019-03-01
Outcome 1: Cooperation and trust between communities increased to mitigate risks of renewed violence | a: % of community members from the 6 pilot village clusters who indicate an improvement in cross-border relations/cooperation with community members in the same village cluster on the other side of the border (disaggregated by gender, age, village cluster and country) | 10% increase over baseline
| b: # of violent incidents in pilot cluster is decreased | 20% decrease over baseline
| c: % of community members from the 6 pilot cross-border village clusters who would be ready to work together with community members in the same village cluster on the other side of the border to improve the lives of cross-border communities o n both sides (indicating increased trust as a prerequisite for addressing common problems) | 10% increase over baseline
| d: % of youth from the 6 pilot cross-border village clusters who demonstrate inter-ethnic tolerance (data disaggregated by gender, age, village cluster, and country) | 10% increase over baseline
| e: % of women playing an active role in the local affairs | 10% increase over baseline
Output1 : Improved linkages and cooperation between security providers, local authorities and communities to reduce violent incidents | 1. Number of interventions/ activities/ preventive actions that were implemented by security providers, local authorities and communities on one side of the border in the 6 pilot cross-border village clusters to improve information exchange and prevent security incidents (with information on how many of those were implemented with active participation of women and youth) | 10 interventions/ activities/ preventive actions that were jointly implemented by security providers, local authorities and communities on one side of the border in the 6 pilot cross-border village clusters to improve information exchange and prevent security incidents | UNICEF, UNDP, with support of UN Women
| 2. Number of interventions/ activities/ preventive actions that were jointly implemented involving security providers, local authorities and communities from both sides of the border in the 6 pilot cross-border village clusters to improve information exchange and prevent security incidents (with information on how many of those were implemented with active participation of women and youth) | 4 interventions/ activities/ preventive actions (2 in TJ and 2 in KG) that were jointly implemented involving security providers, local authorities and communities from both sides of the border in the 6 pilot cross-border village clusters to improve information exchange and prevent security incidents
| 3 Number of problem solving and complaints mechanisms – PSCM, (either cross-border or on one side of the border) established/improved that bring security providers, local authorities and communities together to address community grievances and reduce the likelihood of security incidents along the border (with information on how many of those include women and youth) | Maintain and improve 4 existing problem solving and complaints mechanisms - 2 in TJ and 2 in KG (either cross-border or on one side of the border)
Strategy 1.1. Raise awareness of population on cross-border crossing rules
Activity 1.1.1. Support law enforcement services to adapt information materials to reflect context of the target area (ensure gender sensitivity where necessary) | # of information materials; # of recipients who receive these information materials | 2 information for the 700 recipients including youth and women | UNDP | 4000 | 4000
Activity 1.1.2. Raise awareness of adolescents, parents and teachers on cross-border rules and child rights in cross-border schools | # of adolescents participated with disaggregation by gender; # of parents with disaggregation by gender; # of teachers with disaggregation by gender | Improved understanding by 50% | UNICEF |  | 40000
Activity 1.1.3. Support and cooperation with the existing platforms at the national/ regional /or district level on addressing the concerns of women, men, girls and boys related to the border | the project findings are submitted to existing (in-country) platforms/mechanisms at national, regional and district levels. | 2 meetings / linkages with 2 platforms established | UNDP | 10000 | 15000
Activity 1.1.4. Support of local initiatives on improving cooperation with the local authorities and law enforcement structures (ensure, among others, gender responsiveness). | # of local initiatives | to be defined on the basis of consultations | UNDP | 5000 | 5000
Strategy 1.2. To improve the complaints mechanism through cooperation with the Ombudsman Office and other relevant institutions
Activity 1.2.1. Organize community meetings with Ombudsman, law enforcement structures and authorities to ensure access of communities to the complaint mechanism (Ombudsman). Raise awareness of the communities on complaint mechanisms, including child rights. Empower women leaders to participate in community meetings. | # of community engagement events organized to raise awareness | 66 meetings (at least 40 beneficiaries in each meetings, out of them 30% are women)+10 meetings in KG | UNDP, UNICEF, UN Women | 4000 | 10000
Activity 1.2.2. Follow up meetings/action of Office of Ombudsman with the local government and respective state structures at district, regional and national level (to raise complaints and ensure that they are addressed) /Capacity building of the Ombudsman for Child Rights to strengthen complaint mechanisms at district and national level | # of complaints/concerns raised and discussed at district, regional and national levels # of Ombudsman staff with enhanced capacity to address complaints # of participants with disaggregation on gender | 3 (2 at district and 1 at regional level) | UNDP, UNICEF | 10000 | 10000
Activity 1.2.3. Improving cooperation between Ombudsman Offices of RT and KR | # of joint meetings | at least 2 meetings | UNDP | 500 | 1000
Strategy 1.3. Build capacity of law enforcement agencies on human rights and build linkages between citizens and duty bearers
Activity 1.3.1 Elaborate the cooperation plan with the Border Service and Police on strengthening the linkages between the law enforcement structures, local government and citizens (women, men, girls and boys) (and its further implementation) | # of joint plans and events supported by project | 2 plans with detailed activities | UNDP, UNICEF KG, and UN Women | 5000 | 6000
Activity 1.3.2. Ensure that concerns raised during community meetings are discussed during meetings of border guards of both countries and follow up actions are taken. Ensure gender balanced approach where necessary. | # of meetings of border guards of RT and KR (internal meetings) where concerns/complaints were presented/discussed | 3 meetings | UNDP
Activity 1.3.3. Capacity building events (or consultation meetings) provided by Ombudsman office for border guards and other law enforcement services. Capacity building will integrate human rights and gender perspectives | # of events, # of people participating in them | 3 round tables (2 at district and 1 at regional level), 75 participants | UNDP
Activity 1.3.4. Development of training modules and cascade training for border guards, custom service providers, local ombudsman’s office staff and authorities on child friendly procedures and referral mechanisms at cross border points (Kyrgyzstan only - to be confirmed) | # of training modules developed # of trainings conducted # of participants with disaggregation on gender % of participants who increased their knowledge on child friendly procedures and referral mechanisms | to be defined on the basis of consultations | UNICEF (KG only)
Activity 1.3.5. Analysis of the gaps in the legal framework on application of child-friendly procedures - to be confirmed | # of analysis conducted |  | UNICEF (KG only)
Activity 1.3.6. Presentation of findings at the RT at national level - to be confirmed | # of round table conducted # of participants with disaggregation on gender |  | UNICEF (KG only)
Activity 1.3.7. Modelling of child-friendly checkpoints - to be confirmed | # of child-friendly checkpoints established # of adolescents used the checkpoints |  | UNICEF (KG only)
Output2: Communities restore cross-border linkages and trust by jointly addressing interdependent needs/ challenges associated with community infrastructure and natural resources, as well as by establishing platforms of confidence-building and cooperation between various societal groups. | 1: Number of projects that were agreed by communities from both sides of the pilot cross-border village clusters and to address interdependent needs/ challenges associated with community infrastructure (with information on how many of those were implemented with active participation of women and youth) | At least 10 in Tajikistan that were jointly agreed and implemented by communities from both sides. | UNDP, FAO, WFP, UNICEF, UN Women
| 2: Number of youth (disaggregated data for young men/ boys and young women/ girls) that benefitted from training/ support or participated in; a) cross-border joint youth events, and b) in-country youth events that aim to promote inter-ethnic tolerance in pilot cross-border village clusters | a) 500 young people from Tajikistan participated in cross-border events; b) 400 young people in Tajikistan participated in in-country events
| 3: Number of joint cross-border initiatives responding to specific gender equality and women’s empowerment (GEWE) issues are implemented by women activists | At least 4 cross-border women’s initiatives (small projects) implemented by women
Strategy 2.1. Facilitate dialogues within and between communities as well as participatory decision-making process through implementation of community initiatives
Activity 2.1.1. Carry out contextualized in-depth joint situation assessment (review of legal framework, conflict sensitivity, gender and environmental risks, identifying geographical areas which require more attention, potential contentious issues, understanding local power dynamics in specific municipalities) - through the mechanisms of community dialogue and consultations, consultations with authorities and other channels, as per SOPs. | # of joint planning meetings; # of participants/disaggregated by gender; | no less than 10 meetings, with no less than 50 participants | UNDP, FAO, WFP (UN Women TBC)
Activity 2.1.2. Carry out Community Dialogue - joint participatory planning of priorities (risk-informed), to ensure inclusion of vulnerable groups (women, youth etc.) | # of community meetings; # of participants disaggregated by gender; | 8 community meetings with 300 participants and 2 meetings at district level | UNDP, FAO, WFP (UN Women TBC) | 2000 | 2000
Activity 2.1.3 Support of operation of various consultative platforms at jamoat/ayil okmotu and district level of RT and KR (including youth, women); Jamoat/Ayil Okmotu level Working Group, Women Councils, Head of municipalities of TJ and KG meetings, Technical Groups, Inter-district Steering Committee, Youth Contact Group (cross-border), key government stakeholders to ensure involvement of key stakeholders into project implementation. | # of platforms # of participants disaggregated by gender | 6 platforms at jamoat level with 120 participants, 2 inter-district meetings with participation of 60 people | UNDP (with participation of ALL RUNOs) | 5000 | 5000
Activity 2.1.4. Rehabilitation or building (through a community-led and inclusive approach) small-scale social or natural resource-related infrastructure with a high potential for reducing tensions. Streamline UN agencies joint approach in implementation of community projects. | # of community projects; # of beneficiaries disaggregated by gender; | 2 community projects, 1000 beneficiaries | UNDP, WFP, FAO | UNDP 120000 | UNDP 100000 +180000
Strategy 2.2. Enhance cooperation in natural resource management and increase the effectiveness and transparency of the use of the natural resources to reduce the likelihood of the conflict
Activity 2.2.1. In-depth analysis of pasture management and pasture-related conflict sensitivity as well as water management issues | # of analyses | 1 analysis | FAO
Based on results of the In-depth Analysis the following Activities will be considered for implementation and detailed Action Plan will be developed. FAO Kyrgyzstan will not focus on pasture management issues.
Activity 2.2.2. Build awareness and promote dialogue of stakeholders and communities on pasture management issues and water management issues (with ensuring participation of women). Undertake advocacy actions at local and national levels. | # of awareness raising events (consultations, meeting etc.); # of people involved | TBD on the basis of the analysis | FAO TJ
Activity 2.2.3. Build capacities of communities in pasture management and water management in WUAs (with ensuring empowerment of women). | # of consultation meetings (trainings); # of participants (gender disaggregated) | TBD on the basis of the analysis | FAO
Activity 2.2.4. Provide contextualized capacity building on water resources management for WUAs (supporting implementation of infrastructure projects under Strategy 1). Irrigation related constructions (Water distribution, water measuring facilities, drip irrigation systems and trainings, with balanced representation of men and women). | # of trainings for WUAs; # of participants, number of infrastructure projects | TBD on the basis of the analysis | FAO
Activity 2.2.5. Facilitate cross-country communication and cooperation (including field visits) between WUAs of Tajikistan and Kyrgyzstan | # of events and meetings for WUAs; # of participants | TBD on the basis of the analysis | FAO
Strategy 2.3. Enhance cross-border linkages between communities, especially women and youth through the support of the confidence building platforms
Activity 2.3.1. Carry out 3-level consultation process (jointly UNICEF and UNDP) - 1) in-country focus groups, 2) consultations between countries 3) discussion at wider community meetings (Activity 2.1.3) to identify priorities of adolescents and youth initiatives | # of consultations # of participants with disaggregation on gender # of issues of concerns to adolescents, youth and women identified | 6 consultations | UNICEF, UNDP | UNDP 3000 | 8000 (UNDP 3000)
Activity 2.3.2. Enhance cross-border linkages between adolescents, youth and community through joint cultural and time-extended initiatives/exchanges through Youth Contact Groups (UNDP), schools, student councils and local level dialogue platform (with authorities); including interest-based cross-border trainings for trust building. | # of participants with disaggregation on gender # of events (including long-standing) | 17 joint events and exchanges, 14 cross-border long-term youth initiatives | UNICEF, UNDP | UNDP 42000 | UNDP 42000 24000 (UNICEF?)
Activity 2.3.3. Support tolerance building initiatives by adolescents and youth, including across the border with small grants that aim to promote cross-border linkages | # of cross-border initiatives designed and led by adolescents # of participants with disaggregation on gender | 20 small grant projects by adolescents implemented | UNCEF |  | 40000
Activity 2.3.4. Training for the Local Self-Government representatives on youth/child -friendly local planning | # of trainings # of participants with disaggregation on gender | To be defined | UNICEF (KG only)
Strategy 2.4. Enhance peacebuilding skills of beneficiaries within countries (focus on youth and women)
Activity 2.4.1.Build capacities of women leaders - through in-country and cross-border events - on conflict analysis, mediation, natural resource management and ensure their contribution to conflict assessment and monitoring mechanisms, dialogue and consultation meetings; | # of trained women leaders # of trainings events; | to be defined | UN Women |  | 5000
Activity 2.4.2. Developing peacebuilding competencies of adolescents | # of trainings # of participants with disaggregation on gender # and % of adolescents who acquired peacebuilding competencies # and % of adolescents who acquired 21st century skills | 200 adolescents have improved peacebuilding competencies | UNICEF, UNDP |  | 38000
Activity 2.4.3. Outreach services are in place for adolescents to have access to youth-friendly psychological support and care | # of adolescents who have access to youth-friendly services | 700 adolescents have access | UNICEF |  | 30000
Activity 2.4.4 Advocate for adherence to minimum standards of gender equality and women empowerment in decision-making processes, community dialogues, conflict/disputes resolution. Ensure exchange of women at the events. | % of women, youth, vulnerable population participating at decision making levels; # of women leaders acting as a focal point in villages; # of new women leaders [men activists] coached on conflict prevention; # of community meetings/activities conducted to raise awareness of community members [vulnerable people]; | 35% women representation; 20 new women leaders have on-site coaching; 12 community meetings with at least 240 vulnerable/excluded women | UN Women |  | 45000
Activity 2.4.5 Capacitate women leaders on NAP 1325 to identify issues and good practices of women-led conflict resolution to feed into NAP 1325 and participate in consultative meetings for development of new UNSCR 1325 NAP | # of women leaders trained on NAP 1325 # women-led conflict resolutions detected in target areas to feed the NAP 1325; % of women representation in consultative meetings for development of NAP 1325 | 12 women leaders trained on NAP 1325; At least 40% of trained women participate in consultative meetings (targets are for UN Women TJ only) | UN Women |  | 6000
Activity 2.4.6 Support establishing the associations of women peacebuilders in Sughd region jointly with the National Committee for Women’s and Family Affairs that will include women leaders | # of associations of women peacebuilders created | 1 women's association of peacebuilders created in Sughd region | UN Women (TJ only) |  | 4000
Strategy 2.5. Promote economic ties between cross-border communities and harness employment-related activities to build bridges between people, especially youth and women
Activity 2.5.1 Build capacities of youth and women on business skills/entrepreneurship such as business planning, income generating activities | # of trainings; # of trained women | 4 trainings/consultations on innovative entrepreneurship, 40 women trained | UN Women, UNDP | UNDP 2000 | UN Women 15000 UNDP 2000
Activity 2.5.2. Support women business initiatives that build linkages between women of Tajikistan and Kyrgyzstan | # of business supported; # of beneficiaries (also income increase can be measured); # of trained women leaders | 8 business initiatives supported - of it, at least 2 joint ones | UN Women |  | 3000
Activity 2.5.3. Establish linkages between business associations of both countries (youth focused) and improve trade through supporting market linkages (support innovation for cross border business) in local markets. Innovations for cross-border business | # of cross-border events for associations; # of market initiatives; # of beneficiaries | 2 market initiatives, 2 cross-border events for business associations, 50 beneficiaries | UNDP, WFP TBC | 5000 | 5000
Activity 2.5.4. Supporting vocational skills and agricultural processing through activities related to employment and ties building for youth and women from conflict prone areas. Vocational training activities will be linked to actual business (theme related to agriculture, processing, handcraft) opportunities which help maintaining durable ties between neighbor communities. It will be followed up with joint events with participation of Kyrgyz and Tajik youth and women on increasing trust and tolerance by building up relations and solidarities. | # of trainings; # of beneficiaries disaggregated by gender | To be defined | WFP |  | 18000
Activity 2.5.5. Professional orientation and building social entrepreneurship skills among youth and adolescents | # of events # of participants with disaggregation on gender | To be defined after consultations | UNICEF