## Report on Outputs
Annex D - PBF project budget
Note: If this is a budget revision, insert extra columns to show budget changes.
Table 1 - PBF project budget by Outcome, output and activity
Outcome/ Output number | Outcome/ output/ activity formulation: | Budget by recipient organization in USD - UNDP | Budget by recipient organization in USD - UNOHCR | Percent of budget for each output reserved for direct action on gender eqaulity (if any): | Level of expenditure/ commitments in USD: UNDP | Level of expenditure/ commitments in USD UNOHCHR | % Utilization | Any remarks (e.g. on types of inputs provided or budget justification, for example if high TA or travel costs)
OUTCOME 1: Political dialogue, peace advocacy and violence prevention enhanced
Output 1.1: | Political Parties and Aspirants develop and commit to peaceful and violence-free elections | 328607 |  | N/A | 328031 |  | 99.82%
Activity 1.1.1: | Political parties and Aspirants Commit to Dialogue
Output 1.2: | Sustained non-violence campaigns conducted and messages on human rights and peaceful elections promoted across Sierra Leone | 492000 |  | N/A | 1006961 |  | 204.7% | Funds were reprogrammed for the Post Election Social Cohesion
Activity 1.2.1: | Peace Advocacy and peaceful communication
Output 1.3: | Access to justice for rights holders, including women and vulnerable groups who may become victims of election-related offences enhanced | 245000 |  | N/A | 33326 |  | 13.6%
Activity 1.3.1: | Access to Justice
TOTAL $ FOR OUTCOME 1: |  | 1065607 | 0 |  | 1368318 | 0 | 128.4%
OUTCOME 2: Public security, civil protection, human rights promotion, and peaceful response capacities sustained.
Output 2.1: | The National and Community based Early Warning and Response System strengthened | 490000 |  | N/A | 406790 |  | 83.02%
Activity 2.1.1: | Early Warning early response |  |  | N/A
Output 2.2: | Capacity of the Sierra Leone Police (SLP) for conflict prevention and, peaceful management of violence improved | 336800 |  | N/A | 159314 |  | 47.3% | Greater support was received from DfID and therefore the low delivery
Activity 2.2.1: | Election Security for Peaceful Response |  |  | N/A
TOTAL $ FOR OUTCOME 2: |  | 826800 | 0 |  | 566104 |  | 68.47%
Project personnel costs if not included in activities above |  | 370000 | 220000 | N/A | 336139 | 220000 | 94.26%
Project operational costs if not included in activities above |  | 191142.9 |  | N/A | 211572 |  | 110.7%
Project M&E budget |  | 130000 |  | N/A |  |  | 0%
SUB-TOTAL PROJECT BUDGET CP & M PROJECT: |  | 691142.9 | 220000 |  | 547711 | 220000
Indirect support costs (7%): |  | 180848.493 | 15400 |  | 173749.31 | 15400 | 96.38%
TOTAL PROJECT BUDGET - CP & M PROJECT: |  | 2764398.393 | 235400 |  | 2655882.31 | 235400 | 96.38%
Notes: - % Utilization for UNDP is calculated based on contribution received from 1st and 2nd tranches. - UNDP indicative figures were generated from Account Activity Analysis (AAA) report as of 31st May 2019 - UNDP personnel and staffing costs are NOT reported on from the Outputs

## Cost Allocations to RUNOs
Table 2 - PBF project budget by UN cost category
Note: If this is a budget revision, insert extra columns to show budget changes.
CATEGORIES | Amount Recipient Agency: UNDP |  | Amount Recipient Agency: OHCHR |  | Total tranche 1 | Total tranche 2 | PROJECT TOTAL
| Tranche 1 (70%) | Tranche 2 (30%) | Tranche 1 (100%) | Tranche 2 (0%)
1. Staff and other personnel | 329000 | 141000 | 220000 |  | 549000 | 141000 | 690000
2. Supplies, Commodities, Materials | 90160 | 38640 |  |  | 90160 | 38640 | 128800
3. Equipment, Vehicles, and Furniture (including Depreciation) | 88853.8 | 38080.2 |  |  | 88853.8 | 38080.2 | 126934
4. Contractual services | 267400 | 114600 |  |  | 267400 | 114600 | 382000
5.Travel | 191100 | 81900 |  |  | 191100 | 81900 | 273000
6. Transfers and Grants to Counterparts | 718900 | 308100 |  |  | 718900 | 308100 | 1027000
7. General Operating and other Direct Costs | 123071.0348 | 52744.7292 |  |  | 123071.0348 | 52744.7292 | 175815.764
Sub-Total Project Costs | 1808484.8348 | 775064.9292 | 220000 |  | 2028484.8348 | 775064.9292 | 2803549.764
8. Indirect Support Costs (must be 7%) | 126593.9384 | 54254.55 | 15400 |  | 141993.9384 | 54254.55 | 196248.4884
TOTAL | 1935078.7732 | 829319.4792 | 235400 | 0 | 2170478.7732 | 829319.4792 | 2999798.2524