SECRETARY-GENERAL’S PEACEBUILDING FUND

PBF PROJECT PROGRESS REPORT TEMPLATE

PBF PROJECT progress report

COUNTRY:  LIBERIA

TYPE OF REPORT: semi-annual, annual OR FINAL ANNUAL REPORT

date of report: 15 NOVEMBER 2018

| Project Title: Strengthening the Rule of Law in Liberia: Addressing Pre-Trial Detention and Rolling Out Community Policing Project Number from MPTF-O Gateway: |
| --- |
| PBF project modality: IRF PRF | If funding is disbursed into a national or regional trust fund: Country Trust Fund Regional Trust Fund Name of Recipient Fund: UNDP AND UN WOMEN |
| List all direct project recipient organizations (starting with Convening Agency), followed type of organization (UN, CSO etc): UNDP and UNWomen List additional implementing partners, Governmental and non-Governmental: Judiciary, Ministry of Justice, Ministry of Internal Affairs, Liberia National Police (LNP), Prosecution Department, Bureau of Corrections and Rehabilitation, Independent National Human Rights Commission, Liberia National Bar Association (LNBA), Louis Arthur School of Law, Kofi Annan Institute for Conflict Transformation, Association of Female Lawyers in Liberia (AFELL), International Development Law Organisation (IDLO), Ministry of Gender, Social and Children Protection, Women Legislative Caucus, Prison Fellowship International Liberia (PFL), Institute of Research and Democratic Development (IREDD) and other selected CSOs/CBOs. |
| Project commencement date: 9 January 2018 Project duration in months: 18 months |
| Does the project fall under one of the specific PBF priority windows below: Gender promotion initiative Youth promotion initiative Transition from UN or regional peacekeeping or special political missions Cross-border or regional project |
| Total PBF approved project budget* (by recipient organization): UNDP: $ 1.680,000.00 UN WOMEN:$ 1,000,000.00: $ : $ : $ : $ Total: 2,680,000.00 *The overall approved budget and the release of the second and any subsequent tranche are conditional and subject to PBSO’s approval and subject to availability of funds in the PBF account How many tranches have been received so far: Only first tranches have been received by UNDP and UNWomen respectively) |
| Report preparation: Project report prepared by: Samuel Goteh, M&E Analyst Project report approved by: Maarten Barends, UNDP's Chief Technical Advisor/Manager- Rule of Law Did PBF Secretariat clear the report: Yes Any comments from PBF Secretariat on the report: Yes Has the project undertaken any evaluation exercises? Please specify and attach: No |

NOTES FOR COMPLETING THE REPORT:

- Avoid acronyms and UN jargon, use general / common language.

- Be as concrete as possible. Avoid theoretical, vague or conceptual discourse.

- Ensure the analysis and project progress assessment is gender and age sensitive.

PART 1: RESULTS PROGRESS

  - Overall project progress to date

Briefly explain the status of the project in terms of its implementation cycle, including whether all preliminary/preparatory activities have been completed (1500 character limit):

During the reporting period, the project made significant progress across the different outcomes and outputs towards achieving desired results of the interventions. UNDP and UNWomen helped to strengthen the capacities of key justice and security institutions and provided grants to twelve (12) civil society organisations- mostly active in outlying counties to provide quality gender responsive legal aid and assistance to socially disadvantaged groups. In addition, strenghtened the capacity of the Women and Children Protection Section at the LNP, Sexual and Gender-Based Violence (SGBV) Crimes Unit at the Ministry of Justice as well as operationalized a division of Court E in Nimba county. Further, the project stepped up provision of free legal aid and assistance to survivors/victims of SGBV by supporting the arrest of a dozens alleged rape perpetrators; provided legal aid services to 304 pre-trial detainees; mediated 341 cases outside the formal justice system and assisted108 children in conflict with the law with the aim of reducing harm that may be caused by the justice and security system. The project also supported the operationalization of six regional county security councils’ offices and strengthened women peace committees/peace-huts in the county and districts. In addition, UNDP and UNWomen are supporting the LNP to raise awareness about community policing policy and promote service-oriented outreach activities and 106 LNP officers have been trained.

Given the recent/current political/peacebuilding/ transition situation/ needs in the country, has the project been/ does it continue to be relevant and well placed to address potential conflict factors/ sources of tensions/ risks to country’s sustaining peace progress? Please illustrate. If project is still ongoing, are any adjustments required? (1500 character limit)

In addition to strenghtening of key justice and security sector institutions as well as civil society actors, the project further scaled up interventions that continue to sustainably address Liberia's ongoing political, peacebuilding and security needs and mitigate potential factors/sources of insecurity and conflicts. During 2018, UNDP and UNWomen began engaging relevant legislative committees to ensure the adoption of a gender responsive legal aid policy, provided capacity support to community watch forums, women's peace-huts, trained 30 prison officers in gender sensitive correction service delivery and worked towards establishing an effective plea-bargaining system that is significantly helping to reduce pretrial detention rates. The four community justice mediation teams established in densely populated communities in Bong, Margibi and Montserrado have mediated 341 cases outside the formal justice system. These tailored interventions including capacity building of community watch forums continue to sustain the peace and enhnace state-society relations.

The reactivation and operationalisation of security councils in the counties and districts have contributed towards addressing Liberia's security needs and enhanced coordination between local communities and state authorities in mitigating community security needs and have further improved state-society relations and proper flow of information between the county security councils and national security council.

In a few sentences, summarize what is unique/ innovative/ interesting about what this project is trying/ has tried to achieve or its approach (rather than listing activity progress) (1500 character limit).

Aimed at increasing access to justice and equitable protection services for socially disadvantaged Liberians particularly women and girls, the project has engaged twelve (12) civil society and community-based organisations who are mostly active in the leeward counties. The Civil Society Initiative has stimulated the demand for improved justice and security services including pro-bono legal aid services for pre-trial detainees, survivors/victims of SGBV. As a result, 304 pre-trial detainees including 14 women received free legal aid services, while 108 children in conflict with the law including 36 girls were released from detention as to prevent harm they may experience in the justice system. UNDP and UNWomen are also in the process of engaging key legislative committees to ensure the adoption of a gender responsive legal aid policy not only to assist survivors/victims of SGBV to seek legal redress, but increase access to justice for other vulnerable groups and individuals.

In addition to improving the capacity of the SGBV Crimes Unit and WACPS, the project has supported the establishment of legal aid clinics in Grand Bassa and Montserrado, trained 30 correction/probation officers from the 15 counties, established four community justice mediation teams in three counties and six regional county/district security councils offices to strenghten linkages between the local security councils and National Security Council.

Considering the project’s implementation cycle, please rate this project’s overall progress towards results to date:

In a few sentences summarize major project peacebuilding progress/results (with evidence), which PBSO can use in public communications to highlight the project (1500 character limit):

The operationalisation of the six regional county security councils offices has helped to improve early warning and response mechanisms at the local level and ensured a proper flow of information between the local security councils and National Security Council and its Secretariat. During the reporting period, the county security councils held several meeetings and mediated two critical land disputes that would have otherwise led to serious national security threats. The project increased the participation of informal justice actors in peacebuilding and public safety initiatives through the women peace-huts, awareness raising, legal literacy and empowerment. The project is also addressing key triggers of conflict and provided free legal aid services to 304 pre-trial detainees, assited 108 children in conflict with the law to ensure that detention and imprisonment are used only as last resort. In early 2018, the county security councils resolved two critical land disputes between Bong and Gbarpolu counties in which both counties were claiming ownership over a piece of land endowed with large natural resource deposits; another dispute between residents of Bomi and Grand Cape Mount counties for a mineral riched parcel of land which the security councils intervened and resolved. The project will continue to strenghten the capacity of the formal and informal actors and institutions to sustainably address major security threats in the country.

In a few sentences, explain how the project has made real human impact, that is, how did it affect the lives of any people in the country – where possible, use direct quotes that PBSO can use in public communications to highlight the project (1500 character limit):

Although it maybe still early to clearly realise real human impacts of the project, a number of real time changes or impact are taking place in a modest manner. For instance, by empowering a dozen of civil society and community-based organisations, more vulnerable people especially disadvtanged women and grils are now accessing free justice and security services and demanding for their the protection of their rights. During the reporting period, the project supported the arrest of 298 alleged rape perpetrators across through its CSO and institutional partners across the country. In addition, tailored legal aid services were provided to 800 beneficiaries including 504 women and girls; 28,093 people across communities in 14 counties were reached with legal information and awareness raising campiagns which are leading local residents to begin invoking their rights and demanding accountability of duty-bearers. Further, through 684 monitoring visits to police station, courts and correctional/prison facilities, the Judiciary has been engaged on the courts' refusal refund bail-bond fees to non-guilty party ligitants. Furthermore, 88 informal justice actors trained on international human rights norms and standards.

If the project progress assessment is on-track, please explain what the key challenges (if any) have been and which measures were taken to address them (1500 character limit).

Early this year, Liberia experienced double transitions including the transfer of power from one democratically elected president to the next and UNMIL closure which delayed implementation of key activities as enshrined in the annual work plan. However, UNDP and UNWomen made achieved significant milestones by strategically engaging the new government for political buy-in of the project and identified areas of continued support and collaboration. In August 2018, the project held a steering committee meeting involving all key stakeholders to identify challenges and constraints affecting implementation which has accelerated delivery or achievements of key milestones. While delivery has increased following the steering committee meeting, the project will continue to work with all relevant institutional and civil society actors as well as local communities to ensure that the it achieves the desired results and that results can be felt at both local and national levels.

If the assessment is off-track, please list main reasons/ challenges and explain what impact this has had/will have on project duration or strategy and what measures have been taken/ will be taken to address the challenges/ rectify project progress (1500 character limit):

N/A

Please attach as a separate document(s) any materials highlighting or providing more evidence for project progress (for example: publications, photos, videos, monitoring reports, evaluation reports etc.). List below what has been attached to the report, including purpose and audience.

  - Result progress by project outcome

The space in the template allows for up to four project outcomes. If your project has more approved outcomes, contact PBSO for template modification.

Outcome 1:  More inclusive, accountable and gender responsive justice and security institutions increase communities' confidence in the justice system.

Rate the current status of the outcome progress:

Progress summary: Describe main progress under this Outcome made during the reporting period (for June reports: January-June; for November reports: January-November; for final reports: full project duration), including major output progress (not all individual activities). If the project is starting to make/ has made a difference at the outcome level, provide specific evidence for the progress (quantitative and qualitative) and explain how it impacts the broader political and peacebuilding context. Where possible, provide specific examples of change the project has supported/ contributed to as well as, where available and relevant, quotes from partners or beneficiaries about the project and their experience. (3000 character limit)?

Under this outcome, institutional capacities across the justice chain were strenghtened with a focus on reducing the still exceedingly high pre-trial detention rates across the country. As a result, the scaled up provision of free legal aid services to 304 pre-trial detainees including 14 women and represented other poor defendants who don’t have the financial means to hire private lawyers to represent their legal interests.

The Programme further strenghtened the investigation and prosecutorial capacity of the SGBV Crimes Unit at the Ministry of Justice by recruiting and deploying 10 staff (two SGBV Prosecutors, four city solicitors, four case liaison and victim support officers) in Lofa, Nimba, Bong and Montserrado. In addition to training 30 specialised police officers and 25 prosecutors from 10 counties in investigation and case file handling techniques, specialised gender sensitive training was provided for prison officers in the 15 counties which has improved their skills in providing gender sensitive correction services to female inmates. Further, WACPS offices across six counties were equiped with logistics and supplies. The specialised training and institutional capacity support has fostered a level of specialisation necessary to effectively and professionally investigate and handle often highly complex domestic violence or SGBV cases.

UNDP and UN Women are supporting the establishment and operationalisation of a division of Court E in Nimba, the first of its kind to be established since Court E opened its doors in December 2008. Although court E in Montserrado has faced challenges in dispensing effective justice in SGBV cases and while awaiting the appointment of a judge, the establishment of a second specialised court outside Monrovia represents an important breakthrough in the fight against SGBV. Working closely with its civil society partners, 298 cases of rape have been reported and the alleged perpetrators have been arrested awaiting the next terms of court for trial. Hence, Nimba as the second most populous county- it is pivotal that SGBV crimes are handled and indeed prioritised by a specialised court.

With a view to increasing legal aid services and assistance to socially disadvantaged groups, increasing legal education among communities and fostering accountability, UNDP and UNWomen have signed project cooperation agreements with 12 CSOs/CBOs, many of them active in outyling counties. These civil society partners are actively ensuring that survivors of SGBV, pretrial detainees, children in conflict with the law  and other vulnerable groups have access to effective and fair justice, security and protection services as well as strenghtening informal justice actors.

Outcome 2:  Public engagement on community safety and security related matters at the local level enhanced, notably by rolling out community policing.

Rate the current status of the outcome progress:

Progress summary: (see guiding questions under Outcome 1)

With the view of increasing grassroots participation in public safety and security and reinforcing the role of the security councils at county and district levels, the project teamed up with the Liberia Law National Enforcement Association (LINLEA) to operationalise six regional county security council offices that are playing significant role in addressing security matters at local level and strenghtening linkages not only with the National Security Council and its Secretariat, but also ECOWAS Early Warning office in Monrovia. In the course of 2018, the regional security councils offices held 20 and resolved two critical land disputes among local residents in Bong, Bomi, Gbarpolu and Grand Cape Mount. In addition, six specialised police personnel were deployed as regional coordinators to ensure effective coordination of activites at the CSC/DSCs, while logistical supplies, office furniture, equipment and internet access provided to enhance the daily operations of the regional offices. UNDP and UNWomen are also supporting the LNP in its effort to raise awareness about community policing policy and promote service-oriented community outreach approaches that include community participation in identifying and addressing community security needs. In the course of 2018, the project provided sustained capacity development support to the Community Services Section and has organised several trainings for both LNP officers/officials and members of the different community watch forums, community dialogue committees. The LNP has set up mechanisms to ensure that feedback from local communities is heard and acted upon. The community outreach and dialogue mechanisms being rolled out by the CSS and CWF have built trust between the LNP and local communities and increased inclusion of women led structures at local level in addressing community security needs. In September 2018, 105 officers of LNP were trained at the National Policy Tranining Academy in the Community Policing concepts and policy. This has capacitated CSS which has organised four community policing trainings and trained over 200 members of community watch forum across in Bong, Montserrado, Bomi, Grand Cape Mount, Nimba and Lofa counties.

In addition to providing gender sensitive trainings to 30 prison officers in the 15 counties, UNDP and UNWomen are in the process of reviewing the LNP's community policing policy manual to ensure it becomes more gender responsive and leverage the involvment of women led structures in community policing and community watch forum activities at local community level.

Outcome 3:

Rate the current status of the outcome progress:

Progress summary: (see guiding questions under Outcome 1)

Outcome 4:

Rate the current status of the outcome progress:

Progress summary: (see guiding questions under Outcome 1)

  - Cross-cutting issues

| National ownership: How has the national government demonstrated ownership/ commitment to the project results and activities? Give specific examples. (1500 character limit) | To ensure national ownership, commitment and sustainability of the project, key national justice and security sector institutions and civil society actors are being fully involved in all stages of implementation. The project steering committee met in August 2018 to review progress and ensure accountability and oversight as well as national ownership of the project. In addition, the work plan and progress of the project are reviewed by a joint technical justice and security sector working group periodically to provide strategic (re) direction and ensure that the project remains on track to meeting its objectives and desired results. |
| --- | --- |
| Monitoring: Is the project M&E plan on track? What monitoring methods and sources of evidence are being/ have been used? Please attach any monitoring-related reports for the reporting period. (1500 character limit)? | The project has a comprehensive and costed M&E plan which is well on track. Regular quarterly/monthly monitoring visitations and spot-checks are carried out to track progress, performance and results. Regular field monitoring reports, partners' quarterly reports are used to monitor progress and track results. |
| Evaluation: Provide an update on the preparations for the external evaluation for the project, especially if within last 6 months of implementation or final report. Confirm available budget for evaluation. (1500 character limit) | TBC. |
| Catalytic effects (financial): Did the project lead to any specific non-PBF funding commitments? If yes, from whom and how much? If not, have any specific attempts been made to attract additional financial contributions to the project and beyond? (1500 character limit) |  |
| Catalytic effects (non-financial): Did the project create favourable conditions for additional peacebuilding activities by Government/ other donors? If yes, please specify. (1500 character limit) | Following UNMIL's departure, local communities have become exposed to rising in-security threats which necessitated this innovative interventions. Although social cohesion and reconciliation level has improved over the years, Liberia's SCORE Index 2018 report and Peacebuilding Plan highlighted several factors or sources of insecurity and conflicts that if not sustainably addressed may lead to relapse of past conflict. Against this backdrop, the project continues to support series of innovative interventions to address security gaps and promote peacebuilding efforts. For instance, the project is supporting the operationalisation of the county and district security councils which has improved the capacity of local communities and law enforcement agencies to collectively identify, prevent and resolve common crimes/conflicts that have the propensity to escalate into violent conflicts. These grassroots approaches are helping to sustain peace and stability and improve state-society relations and public safety and security. The community justice mediation teams have mediated 341 cases outside the formal justice system without recidivism, while key institutional and civil society actors continue to provide free legal aid and assistance to indigent Liberians, especially in hard to reach and remote communities in Liberia. |
| Exit strategy/ sustainability: What steps have been taken to prepare for end of project and help ensure sustainability of the project results beyond PBF support for this project? (1500 character limit) | The project is time-bound, therefore, adequate preparation of national partners and exit mechanisms are being put in place to ensure sustainability of the project. Through sustained institutional capacity strengthening of justice and security institutions, civil society actors and by rolling out dialogues between communities and security agencies, as well as confidence and trust building in the formal justice system will be improved and sustained. |
| Risk taking: Describe how the project has responded to risks that threatened the achievement of results. Identify any new risks that have emerged since the last report. (1500 character limit) | While the political and security transitions affected timely implementation including delays from government partners to submit requests, the project held consultations and signed letters of agreement with all national counterparts and 12 civil society actors. To mitigate the delay in implementation and slow delivery challenge, the project held its second board meeting in August 2018 with all stakeholders to discuss lessons learned and developed stragegies to increase not only financial delivery but implementation of activities with focus on measuring development results. |
| Gender equality: In the reporting period, which activities have taken place with a specific focus on addressing issues of gender equality or women’s empowerment? (1500 character limit) | Gender sensitive and responsive interventions are core focus of the project. The project provided specialised gender sensitive training for 30 prison/correction officers in the 15 counties; improved the skills of crimes investigators at the Bureau of Correction and Rehabilitation (BCR); provided free legal aid services 120 family law cases including divorce, alimony, child support. In addition, UNDP and UNWomen along with their partners enhanced the capacity of 30 specialised police of the Women and Children Protection Section in LNP (all females) in effective investigation and filing of SGBV crimes; 10 prosecutors (6m, 4f) recruited and deployed to the SGBV Crimes Unit at Ministry of Justice to provide free legal representation for survivors/victims of sexual and gender-based violence offences. |
| Other: Are there any other issues concerning project implementation that you want to share, including any capacity needs of the recipient organizations? (1500 character limit) |  |

1.3 INDICATOR BASED PERFORMANCE ASSESSMENT: Using the Project Results Framework as per the approved project document or any amendments- provide an update on the achievement of key indicators at both the outcome and output level in the table below (if your project has more indicators than provided in the table, select the most relevant ones with most relevant progress to highlight). Where it has not been possible to collect data on indicators, state this and provide any explanation. Provide gender and age disaggregated data. (300 characters max per entry)

|  | Performance Indicators | Indicator Baseline | End of project Indicator Target | Current indicator progress | Reasons for Variance/ Delay (if any) | Adjustment of target (if any) |
| --- | --- | --- | --- | --- | --- | --- |
| Outcome 1 More inclusive, accountable and gender responsive justice and security institutions increase communities’ confidence in the justice system | Indicator 1.1 Number of complaints, investigations, prosecutions and adjudications handled, disaggregated by type, gender and location | No proper plea-bargaining system in place; | Overarching plea-bargaining system in place | A national legal consultant has been hired to support the Prosecution Department at Ministry of Justice to amend the Criminal Procedure Law that will establish an effective plea bargaining system to help sustainably reduce case backlogs and the high pretrial detention rates. |  |  |
|  | Indicator 1.2 Change in the percentage of pre-trial detention rates across the country | 64% pre-trial detention rates (2017) | 54% pre-trial detention rates; | In the course of 2018, there has being a modest reduction in pretrial detention across the country. The pretrial detention rate has reduced by 2% from 64% in November 2017 to 62% in March 2018. By October 2018, the sector experienced another two percent reduction. | Delay in signing agreements with Ministry of Justice to hire a consultant drive the establishment of a plea bargaining system to sustainably pretrial detention rates through amendment of the Criminal Procedures Law. |  |
|  | Indicator 1.3 Number of SGBV Crimes investigated, prosecuted and adjudicated | 52 SGBV crimes adjudicated and disposed of (2017) | 100 SGBV crimes adjudicated and disposed of | With sustained capacity support to the SGBV Crimes Unit, WACPS and civil society actors, 298 SGBV cases reported and trials ongoing. |  |  |
| Output 1.1 Institutional capacities across the entire justice ‘chain’ enhanced, with a focus on reducing pretrial detention rates across the country | Indicator 1.1.1 Number of judges, prosecutors, and public defenders, disaggregated by age, gender, educational attainment and location; | November 2017: 300 judges, 75 prosecutors and 30 public defenders | (June 2019): 350 judges, 75 prosecutors and 35 public defenders | 10 prosecutors recruited, trained and deployed supported by the project across the country (MOJ) | UNDP, UN Women along with the Bureau of Correction and Rehabilitation are in the process of recruting and deploying 25 probation officers to prison facilities in the 15 counties. |  |
|  | Indicator 1.1.2 Number of female pre-trial detainees with access to legal aid and assistance in all prison facilities in Liberia | (December 2017): 40 female detainees | (June 2019): 56 female detainees | 30 prison officials trained in gender responsive service delivery; by October 2018, 12 female detainees trained |  |  |
| Output 1.2 Civil Society Contributions to rule of law and community access to justice enhanced | Indicator 1.2.1 Number of CSOs/CBOs legal aid providers under the project, disaggregated by location and type of services | November 2017: 2 CSOs/CBOs legal aid providers; 10% community legal literacy rate per county | June 2019: 12 CSOs/CBOs legal providers; | October 2018: 12 CSOs/CBOs provided grants to provide legal aid services; two legal aid clinics established and operationalised in Montserrado and Grand Bassa counties | Although, the project will continue a wide range of civil society actors, this indicator target has been reached already. |  |
|  | Indicator 1.2.2 Community legal literacy rates per county, disaggregated by gender | November 2015: 10% community legal literacy rates per county | June 2019: 20% increase in community legal literacy rate per county | Although the 2018 Public Percetions Survey and justice and security data survey reports are not yet released, community legal literacy awareness and legal education campaigns have reached 28,093 community members in 14 counties of Liberia. | The 2018 Public Perceptions and Justice and Security Sector Data Surveys when released in November will provide the actual percentage of community legal literacy rates and community access to justice and security services |  |
| Output 1.3 Advocacy, social mobilisation and partnerships to provide gender responsive legal aid services and empowerment supported | Indicator 1.3.1 Number of legal aid beneficiaries of the project, disaggregated by gender, age and location | November 2017: None | June 2019: 200 beneficiaries | October 2018: 140 (100 females, 40 males) beneficiaries received legal aid services; | N/A |  |
|  | Indicator 1.3.2 Number of legal aid providers with capacity to provide specialized legal aid services for women | November 2017: 1 women focused legal aid provider | June 2019: 3 women focused legal aid providers | 3 legal aid providers, CSOs/CBOs capacitated/supported |  |  |
| Outcome 2 Public engagement on community safety and security related matters at the local level enhanced, notably by rolling out community policing | Indicator 2.1 Number of security ‘hot-spots and intra-community tensions/disputes reduced | November 2017: N/A | June 2019: 10 security hot-spots reduced | October 2018: two critical security hot-spots reduced and two land disputes between citizens of Bong, Gbarpolu, Bomi and Grand Cape Mount resolved |  |  |
|  | Indicator 2.2 Number of community policing action plans jointly developed between local police officers and community members | November 2017: N/A | June 2019: 15 CP action plans jointly developed | October 2018: 105 police officers and 80 members of community watch forums trained; five joint actions plans developed between the LNP and local community members |  |  |
|  | Indicator 2.3 |  |  |  |  |  |
| Output 2.1 Joint initiatives on security and safety issues between communities and security institutions undertaken, as per the LNP’s community policing policy | Indicator 2.1.1 Number of security councils established and operationalised at both county and district level | November 2017: 4 CSCs/DSCs established | June 2019: 15 county security councils established and operationalised | October 2018: 6 regional county security councils offices established and operationalized; operationalized 10 district security councils; supported monthly meetings of county security councils; recruited and deployed six specialised security personnel to manage and coordinate the regional offices |  |  |
|  | Indicator 2.1.2 |  |  |  |  |  |
| Output 2.2 Community policing structures effectively address women and girls’ justice and security needs, including by liaising with relevant government authorities | Indicator 2.2.1 Number of women from peace hots, peace committees and early warning structures that engage in community watch forums | November 2017: 0 | June 2019: 30 women and girls | October 2018: 13 women from peace-huts, peace committees and early structuring are involved in community watch forum activities | Delay in signing project cooperation agreements with institutional and civil society partners |  |
|  | Indicator 2.2.2 Number of cases referred to the police through community policing structures at the local level | November 2017: 25 | December 2018: 300 cases | None | Delay in signing project cooperation agreements with institutional and civil society partners |  |
| Output 2.3 | Indicator 2.3.1 |  |  |  |  |  |
|  | Indicator 2.3.2 |  |  |  |  |  |
| Outcome 3 | Indicator 3.1 |  |  |  |  |  |
|  | Indicator 3.2 |  |  |  |  |  |
|  | Indicator 3.3 |  |  |  |  |  |
| Output 3.1 | Indicator 3.1.1 |  |  |  |  |  |
|  | Indicator 3.1.2 |  |  |  |  |  |
| Output 3.2 | Indicator 3.2.1 |  |  |  |  |  |
|  | Indicator 3.2.2 |  |  |  |  |  |
| Output 3.3 | Indicator 3.3.1 |  |  |  |  |  |
|  | Indicator 3.3.2 |  |  |  |  |  |
| Outcome 4 | Indicator 4.1 |  |  |  |  |  |
|  | Indicator 4.2 |  |  |  |  |  |
|  | Indicator 4.3 |  |  |  |  |  |
| Output 4.1 | Indicator 4.1.1 |  |  |  |  |  |
|  | Indicator 4.1.2 |  |  |  |  |  |
| Output 4.2 | Indicator 4.2.1 |  |  |  |  |  |
|  | Indicator 4.2.2 |  |  |  |  |  |
| Output 4.3 | Indicator 4.3.1 |  |  |  |  |  |
|  | Indicator 4.3.2 |  |  |  |  |  |

PART 2: INDICATIVE PROJECT FINANCIAL PROGRESS

  - Comments on the overall state of financial expenditures

Please rate whether project financial expenditures are on track, delayed, or off track, vis-à-vis project plans and by recipient organization:

How many project budget tranches have been received to date and what is the overall level of expenditure against the total budget and against the tranche(s) received so far (500 characters limit): One budget tranche has been released. .

When do you expect to seek the next tranche, if any tranches are outstanding: N/A

If expenditure is delayed or off track, please provide a brief explanation (500 characters limit):

Please state what $ amount was planned (in the project document) to be allocated to activities focussed on gender equality or women’s empowerment and how much has been actually allocated to date: $1,000,000.00

Please fill out and attach Annex A on project financial progress with detail on expenditures/ commitments to date using the original project budget table in Excel, even though the $ amounts are indicative only.

# Footnotes

Note: commencement date will be the date of first funds transfer.

Maximum project duration for IRF projects is 18 months, for PRF projects – 36 months.