SECRETARY-GENERAL’S PEACEBUILDING FUND

PBF PROJECT PROGRESS REPORT TEMPLATE

PBF PROJECT progress report

COUNTRY:  LIBERIA

TYPE OF REPORT: semi-annual, annual OR FINAL FINAL REPORT

date of report: NOVEMBER 2019

| Project Title: Strengthening the Rule of Law in Liberia: Addressing Pre-Trial Detention and Rolling Out Community Policing Project Number from MPTF-O Gateway: 00108367 |
| --- |
| PBF project modality: IRF PRF | If funding is disbursed into a national or regional trust fund: Country Trust Fund Regional Trust Fund Name of Recipient Fund: UNDP AND UN WOMEN |
| List all direct project recipient organizations (starting with Convening Agency), followed type of organization (UN, CSO etc): UNDP and UNWomen List additional implementing partners, Governmental and non-Governmental: Judiciary, Ministry of Justice, Ministry of Internal Affairs, Liberia National Police Women and Children Protection Section (LNP - WACPS), Prosecution Department, Bureau of Corrections and Rehabilitation (BCR), Independent National Human Rights Commission, Liberia National Bar Association (LNBA), Louis Arthur School of Law, Kofi Annan Institute for Conflict Transformation, Association of Female Lawyers in Liberia (AFELL), International Development Law Organisation (IDLO), Ministry of Gender, Social and Children Protection, Women Legislative Caucus, Prison Fellowship International Liberia (PFL), Institute of Research and Democratic Development (IREDD) and other selected CSOs/CBOs. |
| Project commencement date: 1 January 2018 Project duration in months: 18 months |
| Does the project fall under one of the specific PBF priority windows below: Gender promotion initiative Youth promotion initiative Transition from UN or regional peacekeeping or special political missions Cross-border or regional project |
| Total PBF approved project budget* (by recipient organization): UNDP: $ 1,680,000.00 UN WOMEN: $ 1,000,000.00 : $ : $ : $ Total: 2,680,000.00 *The overall approved budget and the release of the second and any subsequent tranche are conditional and subject to PBSO’s approval and subject to availability of funds in the PBF account How many tranches have been received so far: First and second tranches have been received by UNDP and UNWomen respectively) |
| Report preparation: Project report prepared by: Alex Magal, UNDP/Kofi Ireland, UN Women Project report approved by: Violet Baffour, Deputy Resident Representative (Programmes) - UNDP Liberia Did PBF Secretariat clear the report: Yes Any comments from PBF Secretariat on the report: Yes Has the project undertaken any evaluation exercises? Please specify and attach: Yes, Evaluation Report attached. |

NOTES FOR COMPLETING THE REPORT:

- Avoid acronyms and UN jargon, use general / common language.

- Be as concrete as possible. Avoid theoretical, vague or conceptual discourse.

- Ensure the analysis and project progress assessment is gender and age sensitive.

PART 1: RESULTS PROGRESS

  - Overall project progress to date

Briefly explain the status of the project in terms of its implementation cycle, including whether all preliminary/preparatory activities have been completed (1500 character limit):

The implementation of all  project activities concluded with notable results. The project enhanced public engagement on community safety and security related matters at local level through the roll-out of gender responsive community policing. 15 County Security Councils (CSC)  were operationalised and all are active.  Also,  35 women from peace-huts were engaged in Community Watch Forums.

The  capacities of key justice and security institutions as well as 12 CSOs were strengthened to provide quality gender responsive legal aid and assistance to indigents and socially disadvantaged groups. Consequently, free legal aid  including representation was granted to  573 pre-trial detainees (232 women) resulting in the decrease of pre-trial detention by 3%.

The capacity of the Women and Child Protection Section (WACPS), Community Service Section of police and  the SGBV Crimes Unit were strengthened resulting to 320 cases being investigated.

The project supported strategic and policy development. The legal aid policy and community policing Standard Operating Procedures were adopted by justice and security institutions which resulted in integration and promotion of gender responsiveness in the sector.

Given the recent/current political/peacebuilding/ transition situation/ needs in the country, has the project been/ does it continue to be relevant and well placed to address potential conflict factors/ sources of tensions/ risks to country’s sustaining peace progress? Please illustrate. If project is still ongoing, are any adjustments required? (1500 character limit)

With the ongoing political fragility in Liberia, the evaluation of the project indicates that 87% of  key stakeholders attest that the project is highly relevant and has provided key interventions that sustainably address the country's peacebuilding and security needs, thereby assisting to mitigate potential sources of insecurity and conflict at grassroots level. The project has strengthened key justice and security actors and community structures including community watch forums and women's peace-huts that partner with the police to identify and solve community security-related needs.

Additionally, alternative dispute resolution mechanisms were established in local communities to address disputes thereby preventing their escalation, and sustaining peace and enhancing State-community relations. The operationalization of all the 15 County Security Councils in the counties  and districts have enhanced co-ordination and communication between local communities and state authorities.

Public confidence in the justice sector increased through enhanced access to justice. In addition to targeted legal aid services provided to pre-trial detainees referred above, 1,441 persons (912 female) also benefitted from legal aid services generally, including in respect of legal representation, inheritance, rape and meditation services.

In a few sentences, summarize what is unique/ innovative/ interesting about what this project is trying/ has tried to achieve or its approach (rather than listing activity progress) (1500 character limit).

According to the evaluation report, the project innovatively provided hotlines for community engagements and outreach activities, stakeholders consultative dialogues and promoting access to the Socio-Legal Defense Centers to increase the reportage of incidents to authorities.

The project for the first time provided legal representation through civil society organizations (CSOs) at the grassroot level to indigent and social disadvantaged groups especially women and girls as well as supporting the survivors of SGBV to appear for hearing or trial. This is in addition to support provided to police to visit crime scenes to conduct investigations.

The establishment of community watch forum represents an interesting preventive approach founded on police-community relations. The purpose is to prevent crime before it occurs, as opposed to the traditional policing method of investigating after the fact which is more costly.

Further, the project supported the drafting and adoption of gender responsive legal aid policy which recognizes the rights of citizens especially women and girls. This provides the basis for a legal architecture that sets out a comprehensive approach to the provision of legal aid in Liberia.

The establishment of community mediation centers and peace-huts as well as the operationalization of 15 County Security Councils has played a key role in maintaining peace and security at local and national levels, preventing conflict before they escalate.

Considering the project’s implementation cycle, please rate this project’s overall progress towards results to date:

In a few sentences summarize major project peacebuilding progress/results (with evidence), which PBSO can use in public communications to highlight the project (1500 character limit):

The operationalisation of the County Security Councils  in the 15 counties has contributed to  reduced violence. The County Security Councils which comprises of local authorities  mediated four critical land disputes that would have escalated into difficult security situations. For example, CSCs and joint security in Bong and Gbarpolu helped resolved a conflict over a rich gold mine situated between Bong and Gbarpolu counties.

In addition, enhanced coordination mechanisms between the community watch forums and local community leaders, resulted in increased regular patrol and monitoring across the counties by the security councils. This resulted in the identification and resolution of  triggers of conflicts, including family land disputes Grand Bassa; and tensions between the Vai and Gola tribes in Grand Cape Mount.

198 community watch forum members (including 45 women) and 250 police officers (including 30 women) drawn from 15 counties were trained on SGBV and  domestic violence resulted in increased demand for redress through the justice system. Consequently, active patrol of communities and increased trust in police-community relations have reportedly resulted in a reduction in mob violence.

In a few sentences, explain how the project has made real human impact, that is, how did it affect the lives of any people in the country – where possible, use direct quotes that PBSO can use in public communications to highlight the project (1500 character limit):

The project made significant impact in the  lives of its beneficiaries. Working closely with 12 civil society organisations and key justice institutions, 1,441 vulnerable/poor Liberians have been able to access free quality legal aid and assistance and 46,776 community residents in 14 counties benefitted from awareness raising and legal literacy interventions. In Grand Bassa, lawyers assisted Mary Sieh, a 73-year old woman whose sisters-in-law tried to evict from her deceased husband’s land and property. The lawyers filed a motion on Mary's behalf to dismiss the claim against her, on the basis that the amended Equal Rights of the Customary Marriage Law (1998) prohibits any restriction of a widow’s rights to her husband’s estate. During the court proceedings at the Magisterial Court in Buchanan, the judge dismissed the case and ruled in her favour.  …..“I am very grateful to all staff of the legal aid clinic for helping me to get my property back, because, after the death of my husband, all the family members turned against me and wanted to move me out of the land and house my husband constructed over 40 years ago”  she explained.

If the project progress assessment is on-track, please explain what the key challenges (if any) have been and which measures were taken to address them (1500 character limit).

Even though the transition from one democratically elected president to another took place more than a year ago, most officials were first time appointees, with  limited relevant technical capacity and experience to accelerate delivery and timely implementation of planned activities. Despite the delay caused by the transitions at the early stage of implementation including the UNMIL closure, the project  made significant achievements and ensured the necessary political buy-in leading to enhanced coordination and collaboration throughout the its lifespan. In this regard, the project successfully held two project board meetings in May 2018 and February 2019. Several technical coordination meetings were also held in August 2018, March 2019 and May 2019 respectively. During these meetings, key challenges and constraints affecting implementation and financial delivery were identified and solutions determined. The meetings also helped to remove barriers to delivery and scaled up implementation of planned activities.

If the assessment is off-track, please list main reasons/ challenges and explain what impact this has had/will have on project duration or strategy and what measures have been taken/ will be taken to address the challenges/ rectify project progress (1500 character limit):

N/A

Please attach as a separate document(s) any materials highlighting or providing more evidence for project progress (for example: publications, photos, videos, monitoring reports, evaluation reports etc.). List below what has been attached to the report, including purpose and audience.

Annex 1.1 Liberia National Police Gender Policy (Human Rights and Gender Administrative Instruction)

1.2  Liberia National Police Gender Responsive Community Policing Administrative Instruction

1.3 Liberia National Police -Women and Children Protection Services Standard Operating Procedure on SGBV

Annex 2. Legal Aid Policy

Annex 3. Liberia National Police -Women and Children Protection Services Quarterly Report

Annex 4 Prison Fellowship Liberia Report

Annex 5. Pictures of commodities sales at the prison

Annex 6. Assciation of Female Lawyers in Liberia Final Report

Annex 7. Links to publications on various activities

Annex 8. Community engagement photos

Annex 9: Evaluation Report

Annex 10: Selection of beneficiaries' testimonies

  - Result progress by project outcome

The space in the template allows for up to four project outcomes. If your project has more approved outcomes, contact PBSO for template modification.

Outcome 1:  More inclusive, accountable and gender responsive justice and security institutions increase communities' confidence in the justice system.

Rate the current status of the outcome progress:

Progress summary: Describe main progress under this Outcome made during the reporting period (for June reports: January-June; for November reports: January-November; for final reports: full project duration), including major output progress (not all individual activities). If the project is starting to make/ has made a difference at the outcome level, provide specific evidence for the progress (quantitative and qualitative) and explain how it impacts the broader political and peacebuilding context. Where possible, provide specific examples of change the project has supported/ contributed to as well as, where available and relevant, quotes from partners or beneficiaries about the project and their experience. (3000 character limit)?

The implementation of  project resulted in the strengthening of institutional capacities across the justice chain. In an effort to reduce overcrowding in prison facilities and pre-trial detention rate, 12 CSOs were empowered to provide legal aid services to ordinary citizens. This resulted in 573 pre-trial detainees (232 women); 163 children (61girls) in conflict with the law benefiting from  the free legal services.

Specialised training and institutional capacity support has fostered enhanced relevant skills required to effectively and professionally investigate and handle often highly complex cases of domestic violence and rape. In this regard, the project strengthened the investigation and prosecutorial capacity of the SGBV Crimes Unit at the Ministry of Justice through the recruitment and deployment of 10 staff (2 prosecutors, 4 city solicitors, 2 case liaisons and 2 victim support officers) in Lofa, Nimba, Bong and Montserrado counties. In addition, the project supported the training of 280 specialised police officers (100 females) and 25 prosecutors (10 females) from 10 counties in criminal investigation and case file handling techniques. As a result, out of 534 cases received, 188 cases were tried  and 172  convictions secured.

The project also supported the establishment and operationalisation  of Criminal Court E in Nimba  County. Although Court E in Montserrado has faced (and continues to face) challenges in dispensing effective justice in SGBV cases, the establishment of an additional specialised Court E outside Monrovia represents an important breakthrough in the fight against sexual offences in Liberia. Working closely with its civil society partners, police and the prosecutors  the project supported the prosecution of 320 SGBV cases through the provision of free legal aid and representation leading to 13 convictions.

Legal literacy and knowledge in local communities were increased through 40 awareness events and dialogues that fostered accountability and enabled public participation in governance.

Civil society partners worked to ensure that survivors of rape and domestic violence, pre-trial detainees, children in conflict with the law and other vulnerable groups had access to effective and fair justice, security and protection services. They interventions also contributed to the strengthening of informal justice actors as a result of capacity building.

Outcome 2:  Public engagement on community safety and security related matters at the local level enhanced, notably by rolling out community policing.

Rate the current status of the outcome progress:

Progress summary: (see guiding questions under Outcome 1)

Increased grassroots participation in public safety and security was achieved through the operationalisation of 15 county security council offices. These offices now play a critical role in addressing security matters at the local level and strengthening linkages not only with the National Security Council and its Secretariat, but also with the ECOWAS Early Warning office in Monrovia.

Throughout the project lifespan, the 15 county security councils held 20 meetings and resolved four critical land dispute cases among local residents in Bong, Bomi, Gbarpolu, Grand Cape Mount counties. In Sinoe, Grand Kru and Grand Gedeh, the security councils along with Liberia Immigration Service intervened and resolved the issues of illegal entry and use of forest land by foreign nationals from Ghana, Mali and Togo. Furthermore, specialised police personnel were deployed as regional coordinators to ensure effective coordination of critical security matters at the CSC/DSCs, while logistical supplies, office furniture, equipment and internet access were provided to improve the daily operations of the security council offices. The project also supported the police in effort to raise awareness about the community policing policy and promote service-oriented community outreach approaches.

In addition, the project enhanced the capacity of the Community Services Section at the Liberia National Police by training 400 police officers (100 women) and 1,072 members (595 women) of different community watch forums as well as community dialogue committees across the country. This has enabled the Liberia National Police set up mechanisms to ensure that feedback from local communities is heard and acted upon. For example, the property of M.L. Gold Mining Company in Bong county was vandalized and looted by unknown youth. Due to  trust and confidence in the police,  the communities cooperated with the police resulting in the arrest and charging of 84 persons. There was also an increased inclusion of women at the local level in addressing community security needs.

Moreover, the project supported the development of the National Legal Aid Policy and supported the recruitment and deployment of six additional public defenders to increase access to justice services and leverage the involvement of women led structures in community policing and community watch forum activities at local community level.

Outcome 3:

Rate the current status of the outcome progress:

Progress summary: (see guiding questions under Outcome 1)

Outcome 4:

Rate the current status of the outcome progress:

Progress summary: (see guiding questions under Outcome 1)

  - Cross-cutting issues

| National ownership: How has the national government demonstrated ownership/ commitment to the project results and activities? Give specific examples. (1500 character limit) | To ensure national ownership, commitment and sustainability of the project, key national justice and security sector institutions and civil society actors have been fully involved in all stages of implementation. They have been empowered and provided with the necessary institutional and technical development support to reduce the capacity gaps and deficits. Two successful Project Board meetings were held in 2018 and 2019 to ensure oversight and accountability, and review progress. In addition, several technical meetings were held with all stakeholders, including Government and civil society partners. Senior Government personnel demonstrated ownership through monitoring visits and presence during activities. For instance, the Prison Director in the Bureau of Corrections and Rehabilitation (BCR) at the Ministry of Justice, travelled to all locations and was present at training sessions for prison officers. Again, Heads of Sections of the LNP were trained and have taken up the responsibility of training officers within their respective units. Further, the work plan and progress of the project are reviewed by a joint technical justice and security sector working group periodically to provide strategic (re) direction and ensure that the project remains on track to meeting its objectives and desired results. |
| --- | --- |
| Monitoring: Is the project M&E plan on track? What monitoring methods and sources of evidence are being/ have been used? Please attach any monitoring-related reports for the reporting period. (1500 character limit)? | Yes, the project M&E plan was fully implemented. A combination of observation, informal interviews and focused group discussions were employed during the regular monthly/quarterly monitoring visits and spot checks, to closely track progress, performance and results. Regular field visits, monitoring reports and partners' quarterly reports were used to monitor progress, track results and strengthen or build capacities as well as build partnerships and address challenges from the field. Participants and beneficiaries' testimonies were gathered and documented. |
| Evaluation: Provide an update on the preparations for the external evaluation for the project, especially if within last 6 months of implementation or final report. Confirm available budget for evaluation. (1500 character limit) | The evaluation of the project has been completed, following the recruitment of an international and national consultant. The evaluation team worked with the PBF Secretariat, UNDP and UN women and employed a combination of qualitative and quantitative methods to access primary and secondary project information and data against the project objectives. The final evaluation report is attached. |
| Catalytic effects (financial): Did the project lead to any specific non-PBF funding commitments? If yes, from whom and how much? If not, have any specific attempts been made to attract additional financial contributions to the project and beyond? (1500 character limit) | The project made meaningful contribution to the Rule of Law Joint Programme in respect of which the Swedish and Irish Embassies provided funding to support similar interventions totalling $7,400,000 and $800,000 respectively. |
| Catalytic effects (non-financial): Did the project create favourable conditions for additional peacebuilding activities by Government/ other donors? If yes, please specify. (1500 character limit) | Following UNMIL's departure, local communities have become exposed to rising security risks/threats which necessitated this project. Although, social cohesion and reconciliation level has improved over the years, the SCORE Index 2018 report for Liberia and the Peacebuilding Plan highlighted several factors or sources of insecurity and conflict triggers. Against this backdrop, the project supported a series of interventions that aimed to support efforts to address security gaps and promote peacebuilding efforts. The operationalization of county and district security councils helped to sustain peace and stability at the grassroot level, improved police-community relations, and promoted public safety and security. The project increased the demand for legal aid and assistance including representation; and capacity building for informal justice actors to offer quality mediation services particularly on matters that require urgent attention to prevent the escalation of violence. |
| Exit strategy/ sustainability: What steps have been taken to prepare for end of project and help ensure sustainability of the project results beyond PBF support for this project? (1500 character limit) | The project worked closely with Government partners since inception to ensure ownership and maximise the extent to which Government contributions are efficient and effective, and identify areas for inherent sustainability wherever possible. Capacity building around the institutions and structures that were established ensures transfer of knowledge and sustainability through the skills and practices acquired. Further, the development of policy such as the Legal Aid Policy serves as a basis to drive the process of formulating a national legal aid scheme that will be fully funded by the Government. In addition, the proposed amendment of the criminal procedure law (currently before the House of Parliament) to allow the establishment of the plea bargaining system will further sustain the project. |
| Risk taking: Describe how the project has responded to risks that threatened the achievement of results. Identify any new risks that have emerged since the last report. (1500 character limit) | While the political and security transitions affected timely implementation including delays from Government partners to submit requests, the project held consultations and signed letters of agreement with all national counterparts and 12 civil society actors. To alleviate the risk of not having reliable data that will ensure credible results, the project conducted two surveys on justice and security institutions. The project also focused on decentralizing decision making and supported the proper delegation of authority to ensure quick decision making to avoid delays in implementing project activities. Another major risk to the project was delays in the payment of salaries for Government personnel which resulted in low morale and productivity, particularly in the justice and security sector. However, increased support from project staff in information sharing, planning and coordination was enhanced during the period. |
| Gender equality: In the reporting period, which activities have taken place with a specific focus on addressing issues of gender equality or women’s empowerment? (1500 character limit) | Gender sensitive and responsive interventions are a core focus of the project. The project supported the development of a gender sensitive community policing policy and action plan, a gender sensitive Standards of Procedure (SOPs) for the Women and Children Protection Section at Liberia National Police and a national legal aid policy. Importantly, the project provided legal aid services for 1,441 family law cases including divorce, alimony and child support. Furthermore, 232 female inmates were assisted with free legal aid and assistance which led to their release from pre-trial detention. In addition, UNDP and UNWomen along with their partners enhanced the capacity of 30 specialised police of the Women and Children Protection Section in Liberia National Police (all females) in effective investigation and filing of SGBV crimes; 2 prosecutors were recruited and deployed at the SGBV Court in Sanniquellie (Nimba) to support the survivors/victims of sexual and gender-based violence offences. |
| Other: Are there any other issues concerning project implementation that you want to share, including any capacity needs of the recipient organizations? (1500 character limit) |  |

1.3 INDICATOR BASED PERFORMANCE ASSESSMENT: Using the Project Results Framework as per the approved project document or any amendments- provide an update on the achievement of key indicators at both the outcome and output level in the table below (if your project has more indicators than provided in the table, select the most relevant ones with most relevant progress to highlight). Where it has not been possible to collect data on indicators, state this and provide any explanation. Provide gender and age disaggregated data. (300 characters max per entry)

|  | Performance Indicators | Indicator Baseline | End of project Indicator Target | Current indicator progress | Reasons for Variance/ Delay (if any) | Adjustment of target (if any) |
| --- | --- | --- | --- | --- | --- | --- |
| Outcome 1 More inclusive, accountable and gender responsive justice and security institutions increase communities' confidence in the justice system | Indicator 1.1 Number of complaints, investigations, prosecutions and adjudications handled, disaggregated by type, gender and location | No proper plea-bargaining system in place; | Overarching plea-bargaining system in place | With a view to establishing a proper plea bargaining system that would allow the complainant, prosecutors and defendants to reach an agreement to dispose of a case without going to trial, the project assisted with preparing the necessary amendments to the Criminal Procedure Law (1972) |  |  |
|  | Indicator 1.2 Change in the percentage of pre-trial detention rates across the country | 64% pre-trial detention rates (2017) | 54% pre-trial detention rates; | During the course of the project lifespan, there has been slow reduction in pretrial detention rates across the country. The pretrial detention rate has reduced by 3% from 64% in November 2017 to 61% in May 2019. | Due to fast track court at Monrovia central prison not sitting regularly causing delays in disposal of pre-trial cases. The sudden resignation of the public defender and general shortage of public defenders due to high turn over as personnel sought more lucrative positions in the private sector. |  |
|  | Indicator 1.3 Number of SGBV Crimes investigated, prosecuted and adjudicated | 52 SGBV crimes adjudicated and disposed of (2017) | 100 SGBV crimes adjudicated and disposed off | 320 survivors/victims of SGBV and other domestic violence csaes were adjudicated and disposed off. | The target was surpassed due to sustained support to SGBV crime unit, police and civil society organization. |  |
| Output 1.1 Institutional capacities across the entire justice ‘chain’ enhanced, with a focus on reducing pretrial detention rates across the country | Indicator 1.1.1 Number of judges, prosecutors, and public defenders, disaggregated by age, gender, educational attainment and location; | November 2017: 300 judges, 75 prosecutors and 30 public defenders | 350 judges 75 prosecutors and 35 public defenders | 60 additional magistrate level judges (including 12 women) recruited and deployed. 2 prosecutors to increase access to justice and protection services for survivors of SGBV. 6 additional public defenders (including 2 women) recruited and deployed; | Due to the sudden economic down turn, national rule of law institutions could not attract or retain personnel including judicial officers, prosecutors and public defenders who preferred the more lucrative private sector. |  |
|  | Indicator 1.1.2 Number of female pre-trial detainees with access to legal aid and assistance in all prison facilities in Liberia | (December 2017): 40 female detainees | 56 female detainees | 232 female detainees | Use of mediation services by legal aid providers in adddion to litigation. |  |
| Output 1.2 Civil Society Contributions to rule of law and community access to justice enhanced | Indicator 1.2.1 Number of CSOs/CBOs legal aid providers under the project, disaggregated by location and type of services | November 2017: 2 CSOs/CBOs legal aid providers; | CSOs/CBOs legal providers; | 12 CSOs/CBOs given grants to provide legal aid services; Indigents and disadvantaged groups have really benefitted from the provision of legal aid sevices, some have reclaimed their rights and economic empowernment |  |  |
|  | Indicator 1.2.2 Community legal literacy rates per county, disaggregated by gender | November 2015: 10% community legal literacy rates per county | 20% increase in community legal literacy rate per county | Where the ratio of women to men is 6:4, at least 30% of communities reached with awareness messages through radio, meetings and ICT materials. |  |  |
| Output 1.3 Advocacy, social mobilisation and partnerships to provide gender responsive legal aid services and empowerment supported | Indicator 1.3.1 Number of legal aid beneficiaries of the project, disaggregated by gender, age and location | November 2017: None | 200 beneficiaries | 1,411 (912 females) beneficiaries received legal aid services; |  |  |
|  | Indicator 1.3.2 Number of legal aid providers with capacity to provide specialized legal aid services for women | November 2017: 1 women focused legal aid provider | 3 women focused legal aid providers | Five legal aid providers capacited/supported. These are Rural Integrated Center for Community Empowerment; Foundation for Human Rights and Democracy; Alliance for Women Advancement; Association of Female Lawyers; Southeastern Women Development Association;,capacitated/supported |  |  |
| Outcome 2 Public engagement on community safety and security related matters at the local level enhanced, notably by rolling out community policing | Indicator 2.1 Number of security ‘hot-spots and intra-community tensions/disputes reduced | November 2017: 0 | 10 security hot-spots reduced | 12 security hot-spots reduced; 18 community watch forums established to reduce intra- community tentions/ disputes in Bong, Montserrado, Bomi, Nimba, Grand Cape Mount, and Lofa counties. |  |  |
|  | Indicator 2.2 Number of community policing action plans jointly developed between local police officers and community members | November 2017: 0 | 15 Community Policing action plans jointly developed | 5 joint action plans, and SOPs developed between LNP and local community members; 400 police officers and 1,072 members of community watch forums trained. | Limited capacity by communities and police. |  |
|  | Indicator 2.3 |  |  |  |  |  |
| Output 2.1 Joint initiatives on security and safety issues between communities and security institutions undertaken, as per the LNP’s community policing policy | Indicator 2.1.1 Number of security councils established and operationalised at both county and district level | November 2017: 4 CSCs/DSCs established | 15 County Security Councils established and operationalised | June 2019: 15 County Security Councils offices established and operationalized in the 15 counties; supported monthly meetings of County Security Councils; recruited and deployed six specialised security personnel to manage and coordinate the regional offices. |  |  |
|  | Indicator 2.1.2 |  |  |  |  |  |
| Output 2.2 Community policing structures effectively address women and girls’ justice and security needs, including by liaising with relevant government authorities | Indicator 2.2.1 Number of women from peace huts, peace committees and early warning structures that engage in community watch forums | November 2017: 0 | 30 women and girls | 87 women from peace-huts, peace committees and early structuring are now involved in community watch forums.This is due to the improved relationship between the police and community women structures |  |  |
|  | Indicator 2.2.2 Number of cases referred to the police through community policing structures at the local level | November 2017: 25 | June 2018: 300 cases | 316 cases referred.This is due to the improved relationship between the police and community women structures |  |  |
| Output 2.3 | Indicator 2.3.1 |  |  |  |  |  |
|  | Indicator 2.3.2 |  |  |  |  |  |
| Outcome 3 | Indicator 3.1 |  |  |  |  |  |
|  | Indicator 3.2 |  |  |  |  |  |
|  | Indicator 3.3 |  |  |  |  |  |
| Output 3.1 | Indicator 3.1.1 |  |  |  |  |  |
|  | Indicator 3.1.2 |  |  |  |  |  |
| Output 3.2 | Indicator 3.2.1 |  |  |  |  |  |
|  | Indicator 3.2.2 |  |  |  |  |  |
| Output 3.3 | Indicator 3.3.1 |  |  |  |  |  |
|  | Indicator 3.3.2 |  |  |  |  |  |
| Outcome 4 | Indicator 4.1 |  |  |  |  |  |
|  | Indicator 4.2 |  |  |  |  |  |
|  | Indicator 4.3 |  |  |  |  |  |
| Output 4.1 | Indicator 4.1.1 |  |  |  |  |  |
|  | Indicator 4.1.2 |  |  |  |  |  |
| Output 4.2 | Indicator 4.2.1 |  |  |  |  |  |
|  | Indicator 4.2.2 |  |  |  |  |  |
| Output 4.3 | Indicator 4.3.1 |  |  |  |  |  |
|  | Indicator 4.3.2 |  |  |  |  |  |

PART 2: INDICATIVE PROJECT FINANCIAL PROGRESS

  - Comments on the overall state of financial expenditures

Please rate whether project financial expenditures are on track, delayed, or off track, vis-à-vis project plans and by recipient organization:

How many project budget tranches have been received to date and what is the overall level of expenditure against the total budget and against the tranche(s) received so far (500 characters limit): All tranches have been released. .

When do you expect to seek the next tranche, if any tranches are outstanding: N/A

If expenditure is delayed or off track, please provide a brief explanation (500 characters limit):

Please state what $ amount was planned (in the project document) to be allocated to activities focussed on gender equality or women’s empowerment and how much has been actually allocated to date: $1,000,000.00

Please fill out and attach Annex A on project financial progress with detail on expenditures/ commitments to date using the original project budget table in Excel, even though the $ amounts are indicative only.

# Footnotes

Note: commencement date will be the date of first funds transfer.

Maximum project duration for IRF projects is 18 months, for PRF projects – 36 months.