## Result Framework
Project Title: Integrated Approach to Building Peace in Nigeria’s Farmer-Herder Crisis
Project Number from MPTF-O Gateway: | [6 empty] | Targeting Method: Cumulative
| Outcomes | Indicator level |  | Outputs | Indicators | Baseline | 2019 Q3 target | 2019 Q4 target | 2020 Q1 target | 2020 Q2 target | Final Target | Means of Verification (MoV) | 6 Month Indicator Milestones | 12 Month Indicator Milestones | Responsible Agency | Status | Remedial Steps Taken | Delayed | On going | Achieved
| Outcome 1: Effective and gender-sensitive infrastructure for peace in place at the state level to support conflict prevention | Outcome | 1 |  | Outcome Indicator 1 a 1. Number of peacebuilding structures established per state | 0 |  | 1 | 1 | 1 | 3 (1 per state) | Constitution and meeting minutes, PB structured reports | Agreements with governor’s offices on PB structures | PB structure constitution meeting held in each state | UNDP | On going
|  | Outcome | 2 |  | Outcome Indicator 1 a 2. Percentage of women and youth participating in these structures | 0 | 5 | 10 | 20 | 35 | 35% women/youth participation | Constitution and meeting minutes, PB structured reports | Agreements with governor’s offices on PB structures | PB structure constitution meeting held in each state | UN Women | Delayed
|  | Outcome | 3 |  | Outcome Indicator 1 b. Percentage of women and youth surveyed who perceive that peace infrastructure adequately reflects and addresses their concerns | TBD | Conduct assessment |  |  | 50 | 50% women/youth | Survey reports by monitoring CSO | Monitoring CSO baseline survey complete | 50% of gender sensitization workshops completed | UN Women | Achieved
|  | Outcome | 4 |  | Outcome Indicator 1c1. Percentage of conflicts reported through EWERs in project area | 0 | 0 | 0 | 10 | 50 | 50% | Monitoring CSO’s reports, EWERS data outputs | ICT component of EWERS complete | PB structures linked and sensitized to EWERS system | UNDP | On going
|  | Outcome | 5 |  | Outcome Indicator 1c2. Percentage of reports responded to by Peacebuilding structures | 0 |  |  | 20 | 25 | 25% | Monitoring CSO’s reports, EWERS data outputs | ICT component of EWERS complete | PB structures linked and sensitized to EWERS system | UNDP | Delayed
|  | Output | 1 | Output 1.1 Establishment of state-level agency/ commission/ structure to drive gender-sensitive peacebuilding agenda | Output Indicator 1.1.1 Number of agreements with state governors’ offices on supporting the establishment of agency /commission/structure | 0 | 0 | 1 | 2 | 3 | 3 | Signed agreements, law/or decree establishing the agency, public statements by state officials, press releases | 1 signed agreement for one state | 1 agreement/official document commencing the process/establishing the structure in each of the three states | UNDP | On going
|  | Output | 2 | Output 1.2 State peacebuilding Agency / Commission / structure supported to drive gender-sensitive response to farmers-herders crisis | Output Indicator 1.2.1 Number of institutions supported to drive gender sensitive response | 0 | 0 | 5 | 10 | 15 | 15 | Perception survey by monitoring CSOs, meeting/workshop minutes, letters of appreciation, interim monitoring reports provided to project partners and PB structures Note: at least 5 per state | Key institutions needing support identified | 50% of identified institutions have received needed support | UN Women | On going
|  | Output | 3 |  | Output Indicator 1.2.2 Number of mediation/dialogues led by peacebuilding structure | 0 | Dev. dialogue protocol | 0 | 2 | 5 | 5 | Dialogue records (documented dialogue interventions), local level agreements | Dialogue protocol for PB structures developed | Dialogue sensitization and support to PB structures initiated | UNDP | Delayed
|  | Output | 4 | Output 1.3 Gender-sensitive early warning and early response capacity developed, supported and improved | Output Indicator 1.3.1 Number of functional EWERS established | 0 | 0 | 1 | 2 | 3 | 3 | Procurement report of completion of EWERS, EWERS database for logged warnings, threats transmitted, and responses initiated Note: 1 EWERS per state receives warnings, processes data and communicates threat to appropriate offices to initiate response | ICT component of EWERS complete and rolled out in 1 state | EWERS generating reports and linked to PB structures in all three states | UNDP | On going
|  | Output | 5 | Output 1.4 Constructive dialogue promoted through inter-ethnic and inter-religious exchanges | Output Indicator 1.4.1 Number of verifiable peacebuilding activities achieved | 0 | 0 | 10 | 20 | 30 | 30 | CSO monthly assessments document progress | CSO baseline completed and activities agreed | 50% of activities delivered | UNDP | Delayed
|  | Output | 6 |  | Output Indicator 1.4.2 Number of relevant state institutions provided with validated outputs from open grazing consultations | 0 | 0 | 1 | 2 | 4 | 4 | Meeting declarations, Response letters from State institutions Note: at least 2 institutions in 2 states | Consultation protocol agreed with relevant state agencies | Initial round of consultations completed in 3 states | UNDP | On going
| Outcome 2: Strengthening Economic Interdependence between farmers and herders | Outcome | 6 |  | Outcome Indicator 2 a. No of new co-operative initiatives between farmers and herders demonstrating mutually beneficial economic interdependence. | 0 | 0 | 0 | 1 | 3 | 3 | Project report with pictures, Reports from Cooperative societies, independent press releases | Sensitization of planned assessments, pilots and project activities with key institutions, associations and private sector initiated | High level recommendations brief prepared to underpin advocacy | UNDP | Delayed
|  | Outcome | 7 |  | Outcome Indicator 2 b. No of target States that adopt concepts of pasture and alternative fodder system for scale-up | 0 | 0 | 0 | 0 | 2 | 2 | Project report, Letters from State and community leaders | Discussions on project livelihoods and economic project interventions held with relevant state agencies | Key recommendations arising from surveys, pilots and projects activity provided to relevant state agencies and workshops/roundtables planned | FAO | Delayed
|  | Outcome | 8 |  | Outcome Indicator 2 c. No of people benefiting from new market opportunities in project areas | 0 | 0 | 200 | 300 | 485 | 485 | Project report; Beneficiaries disaggregated by farmer-herder-male-female-youth Note: 485 direct beneficiaries and at least 50000 indirect beneficiaries (70% youth, 50% women) | M&E baseline clearly identifies project beneficiaries and potential target groups | Project pilots and trainings 50% completed | UNDP | On going
|  | Output | 7 | Output 2.1 Improved land, fodder/feedstock and water management to reduce competition over natural resources | Output Indicator 2.1.1 Survey reports provided to relevant State institutions and validated | 0 | 0 | 0 | 1 | 1 | 1 | State survey report | Survey protocol designed, field experts hired | Draft survey reports available | FAO | Delayed
|  | Output | 8 |  | Output Indicator 2.1.2 No of farmers and herders (disaggregated by gender and age) informed about alternative fodder/feedstock opportunities | 0 |  |  |  |  | 30000 | CSO assessment in 3 states, meeting minutes, logbooks of 60 extension workers trained (50% women) and deployed with assessment report information | Agreements with Agriculture Dept on content and timing of trainings | 100% of trainings completed, extension outreach initiated | FAO | On going
|  | Output | 9 | Output 2.2 Livelihood opportunities at agricultural/pastoral interface improved to incentivize farmer herder co-operation | Output Indicator 2.2.1 No. of persons trained on value chain development around livestock production and markets | 0 |  |  |  |  | 300 | Training report on value chain development around livestock production and markets Note: 300 disaggregated by men/women/youth and age | Target states and beneficiaries identified and trainings planned | Trainings 50% completed | UNDP | Delayed
|  | Output | 10 |  | Output Indicator 2.2.2 No of Platforms and CBOs reached with knowledge products, advisory services and sensitization activities | 0 |  |  |  |  | 6 | Project report with pictures Letters from co-operative platforms & CBOs acknowledging material and support received Note: at least 6 (2 per state) | Draft profiling report completed | At least 1 CBO/Platform engaged in each state | UNDP | Delayed
|  | Output | 11 |  | Output Indicator 2.2.3 No. of men/women/youths supported by vocational training | 0 |  |  |  |  | 125 | Training report | Training package devised, training planned, enrollment completed | Vocational training 100% completed | UNDP | On going
| Outcome 3: Enhanced accountability promotes increased effectiveness of response to the farmers-herders crisis | Outcome | 9 |  | Outcome Indicator 3 a. Number of states with a systematic monitoring of HR abuses | 1 |  |  |  |  | 1 | Reports from target CSOs, Reports from NCHR | NGO/CSO partner in one state contracted and trained on reporting | Regular reporting achieved | OHCHR | Achieved
|  | Outcome | 10 |  | Outcome Indicator 3 b. Percentage increase in awareness of SEA and SGBV in project area | low awareness |  |  |  |  | 50% of surveyed population state being aware of SEA/SGBV | Perception survey reports | Gender sensitization activities planned and agreed with security sector | Capacity building activities 100% complete | UN Women | On going
|  | Outcome | 11 |  | Outcome Indicator 3 c. Degree of improvement in HR responsiveness of military and security apparatus | 0 |  |  |  |  | 30% | Perception survey reports | HR sensitization activities planned and agreed with security sector | Documented regular engagements with security outfit - 50% complete. Social media and other news outlets releases, letters of commendation/acknowledgement from military and security apparatus | OHCHR | On going
|  | Output | 12 | Output 3.1 Capacity of monitoring, investigation and follow up on human rights offences enhanced | Output Indicator 3.1.1 No and quality of reports referencing documented HR abuses | Irregular reports of poor quality |  |  |  |  | Regular reporting that meets minimum standards | Trend analysis | CSO identified and active in pilot area | CSO submitting monthly reports | OHCHR | Achieved
|  | Output | 13 |  | Output Indicator 3.1.2 Percentage of reported HR abuses and violations that are investigated | Low |  |  |  |  | 50% improvement | Trend analysis | Assessment of pre-project HR reporting complete | Trend analysis shows improvement | OHCHR | On going
|  | Output | 14 | Output 3.2 Increased civil-military/security agencies cooperation and dialogue | Output Indicator 3.2.1 No of workshops and dialogue platforms supporting behavioral changes | 0 |  |  |  |  | 3 | Workshop statement/attendance sheets, Nigerian Army HR desk deployment reports | Workshops/platforms planned and initial consultations with HR desk of Nigerian Army held | Agreement on minimum standards achieved with security agencies | UNDP | On going
| Outcome 4: Improved understanding of the crisis encourages evidence-based advocacy, targeted investments and innovative solutions | Outcome | 12 |  | Outcome Indicator 4 a. Number of initiatives informed by Project-generated information and advocacy on farmers-herders crisis | 0 |  |  |  |  | 5 | CSO monitoring reports, organization’s letters of request, declarations arising from meeting, project documents Note: 5 (at least 2 target women/youth) | N/a | 2 initiatives proposed | UNDP | Delayed
|  | Outcome | 13 |  | Outcome Indicator 4 b. Number of references in national and state media to Project-generated information and analysis on farmers-herders crisis | 0 |  |  |  |  | 12 | Monitoring national and state media | Media monitoring system in place | Interim impact analysis complete | UN Women | Delayed
|  | Outcome | 14 |  | Outcome Indicator 4 c. Total value of additional funds leveraged to address farmer herder conflict | 0 |  |  |  |  | $5 million | Project documents, requests for information, donor agreements, state/federal commitments Note: at least $1 million targets women/youth | N/a | At least $1 million leveraged | UNDP | Delayed
|  | Output | 15 | Output 4.1 Information Management and Analysis Unit provides reliable and credible information on farmers-herders crisis | Output Indicator 4.1.1 Number of verified and objective information products based on the project’s sources of information | 0 |  |  |  |  | 3 Reports, 9 updates and 12 infographics produced | Database, GIS system, regular reporting from field partners, access to reports, updates and infographics Note: with gender and youth dis-aggregated data and analyses | GIS and media officer hired, software procured, initial update and infographics on project baseline data produced | 1 report, 3 updates and 6 infographics produced | UNDP | Delayed
|  | Output | 16 | Output 4.2 Objective and verified information on the crisis is made publicly available | Output Indicator 4.2.1 Number of Reports, briefs and infographics that reach a wide audience | 0 reached, 0 likes, 0 shares/ retweets |  |  |  |  | 100,000 reached, 1,000 likes, 1,000 shares /retweets | Social media analytics, press releases and public announcements by State Ministries of Information; State Ministry websites | N/a | Creation of social media pages, membership in key social media forums, MoUs signed with SMoIs on sharing of information | UN Women | Delayed
|  | Outcome | 14
|  | Output | 16
|  | Total | 30

## With Activities
Outcomes | Outputs | Indicators | Means of Verification/ frequency of collection | indicator milestones
Outcome 1: Effective and gender-sensitive infrastructure for peace in place at the state level to support conflict prevention |  | Outcome Indicator 1 a. Number of peacebuilding structures established per state and percentage of women and youth participating in these structures | Constitution and meeting minutes, PB structure reports | 6 months: Agreements with governor’s offices on PB structures
12 months: PB structure constitution meeting held in each state
Baseline: 0
Target: 3 (1 per state; 35% women/youth participation)
|  | Outcome Indicator 1 b. Percentage of women and youth surveyed who perceive that peace infrastructure | Survey reports by monitoring CSO | 6 months: Monitoring CSO baseline survey complete
|  | adequately reflects and addresses their concerns |  | 12 Months: 50% of gender sensitization workshops completed
Baseline: 0
Target: 50% women/youth
|  | Outcome Indicator 1c. Percentage of conflicts reported through EWERs in project area and percentage of reports responded to by Peacebuilding structures | Monitoring CSO’s reports, EWERS data outputs | 6 months: ICT component of EWERS complete
12 months: PB structures linked and sensitized to EWERS system
Baseline: 0
Target: 50% capture; 25% response
| Output 1.1 Establishment of state-level agency/commission/structure to drive gender-sensitive peacebuilding agenda | Output Indicator 1.1.1 Number of agreements with state governors’ offices on supporting the establishment of agency/commission/structure | Signed agreements, law/or decree establishing the agency, public statements by state officials, press releases | 6 months: 1 signed agreement for each state
12 months: n/a activity completed
Baseline: 0
| List of activities under this Output: | Target: 3 agreements
Mapping and review of State Agencies / Commission / structures, CSOs engaged in peace and security, and existing EWERS available in the states and make practical recommendations
Advocacy and provision of technical support to establish an Agency / Commission / structure
Inter-state exchange for learning and sharing of good practices
| Output 1.2 State peacebuilding Agency / Commission / structure supported to drive gender-sensitive response to farmers-herders crisis | Output Indicator 1.2.1 Number of institutions supported to drive gender sensitive response | Perception survey by monitoring CSOs, meeting/workshop minutes, letters of appreciation, interim monitoring reports provided to project partners and PB structures | 6 months: key institutions needing support identified
12 months: 50% of identified institutions have received needed support
Baseline: 0
| List of activities under this Output: | Target: 15 (at least 5 per state)
Support through facilitating coordination meetings with ministries, departments, CSOs/CBOs, traditional and religious institutions, and women and youth networks to promote coordination around peace
Targeted support to peacebuilding Agency / Commission / structure in operationalizing relevant elements of UNSCR 1325
Support to CSOs to engage in community monitoring activities on farmers-herders crisis and reporting to peacebuilding Agency / Commission / structure
Targeted support to enable early response from Agency / Commission / structure based on early warning signs to promote gender-sensitive dialogue and mediation as a first step to resolving a crisis
|  | Output Indicator 1.2.2 Number of mediation/dialogues led by peacebuilding structure | Dialogue records, local level agreements | 6 months: dialogue training protocol for PB structures developed
12 months: dialogue sensitization and support to PB structures initiated
Baseline: 0
Target: 5 documented dialogue interventions
Output 1.3 Gender-sensitive early warning and early response capacity developed, supported and improved
List of activities under this Output:
Develop and implement ICT-based EWERS
Capacity building and system strengthening to the EWER institutions in target states
Advocacy at national and state levels with top government officials and security agencies to enhance effective response to conflict early warnings
|  | Output Indicator 1.3.1 Number of functional EWERS established | Procurement report of completion of EWERS, EWERS database for logged warnings, threats transmitted, and responses initiated | 6 months: ICT component of EWERS complete 12 months: EWERS generating reports and linked to PB structures
Baseline: 0
Target: 3 (1 EWERS per state receives warnings, processes data and communicates threat to appropriate offices to initiate response)
| Output 1.4 Constructive dialogue promoted through inter-ethnic and inter-religious exchanges | Output Indicator 1.4.1 Number of verifiable peacebuilding activities achieved | CSO monthly assessments document progress | 6 months: CSO baseline completed and activities agreed 12 months: 50% of activities delivered
Baseline: 0
| List of activities under this Output: | Target: 30
Support one CSO to build capacity and raise awareness with traditional rulers and religious leaders on peaceful coexistence, strengthening local level conflict prevention mechanisms, convening town hall meetings, and providing safe spaces for dialogue to take place.
Consultative meetings with stakeholders on legislation around open grazing
Sensitization and awareness raising activities amongst pastoralists, crop farmers, and members of the public on the cost of conflict and economic benefits of peaceful coexistence
|  | Output Indicator 1.4.2 Number of relevant state institutions provided with validated outputs from open grazing consultations | Meeting declarations, Response letters from State institutions | 6 months: Consultation protocol agreed with relevant state agencies
12 months: Initial round of consultations completed in 3 states
Baseline: 0
Target: 4 (at least 2 institutions in 2 states)
Outcome 2: Strengthening Economic Interdependence between farmers and herders |  | Outcome Indicator 2 a. No of new co-operative initiatives between farmers and herders demonstrating mutually beneficial economic interdependence. | Project report with pictures | 6 months: Sensitization of planned assessments, pilots and project activities with key institutions, associations and private sector initiated
12 months: high level recommendations brief prepared to underpin advocacy
Baseline: 0
Target: 3 instances of new cooperation
|  | Outcome Indicator 2 b. No of target States that adopt concepts of pasture and alternative fodder system for scale-up | Project report | 6 months: Discussions on project livelihoods and economic project interventions held with relevant state agencies
12 months: Key recommendations arising from surveys, pilots and projects activity provided to relevant state agencies and workshops/roundtables planned
|  | Baseline: 0 | Letters from State and community leaders
Target: 2
|  | Outcome Indicator 2 c. No of people benefiting from new market opportunities in project areas | Project report | 6 months: M&E baseline clearly identifies project beneficiaries and potential target groups
|  |  | Beneficiaries disaggregated by farmer-herder-male-female-youth | 12 months: Project pilots and trainings 50% completed
Baseline: 0
Target: 485 direct beneficiaries and at least 50000 indirect beneficiaries (70% youth, 50% women)
| Output 2.1 Improved land, fodder/feedstock and water management to reduce competition over natural resources | Output Indicator 2.1.1 Survey reports provided to relevant State institutions and validated | State survey reports | 6 months: survey protocol designed, field experts hired
12 months: draft survey reports available
Baseline: 0
| List of activities under this Output: | Target: 1
Surveying of 5,000 Ha for one state in support of the National Livestock Development Plan
Pilot pasture development through land preparation, provision of water harvesting structures, pasture production, processing and conservation
Assessment of alternative fodder/feedstock opportunities and information disseminated to both farmers and herders
Training of 60 Agricultural extensions officers on alternative feedstocks and value chains
|  | Output Indicator 2.1.2 No of farmers and herders (disaggregated by gender and age) informed about alternative fodder/feedstock opportunities | CSO assessment in 3 states, meeting minutes, logbooks of 60 extension workers trained (50% women) and deployed with assessment report information | 6 months: Agreements with Agriculture Dept on content and timing of trainings
12 months: 100% of trainings completed, extension outreach initiated
Baseline: 0
Target:
| Output 2.2 Livelihood opportunities at agricultural/pastoral interface improved to incentivize farmer herder co-operation | Output Indicator 2.2.1 No. of persons trained on value chain development around livestock production and markets | Training report on value chain development around livestock production and markets | 6 months: Target states and beneficiaries identified and trainings planned
12 months: Trainings 50% completed
Baseline: 0
| List of activities under this Output: | Target: 300 disaggregated by men/women/youth and age
Profile farmers, pastoralists, CBOs, vocational training centers, women and youths, and conduct an assessment on livelihood opportunities
Supporting vocational training for farmers, herders, women, youth and victims of conflict
Providing startup kits for graduates of vocational training programmes
Strengthen existing cooperative platforms & CBOs through provision of knowledge products, advisory services and sensitization
Conduct capacity building for 300 conflict affected people on value chain development around livestock production and markets
Convene high-level meetings between private sector and state to raise awareness of fodder and feedstocks value chain and investment opportunities
| Provide catalytic support to alternative fodder production | Output Indicator 2.2.2 No of Platforms and CBOs reached with knowledge products, advisory services and sensitization activities | Project report with pictures | 6 months: Draft profiling report completed
12 months: at least 1 CBO/Platform engaged in each state
Letters from co-operative platforms & CBOs acknowledging material and support received
Baseline: 0
Target: at least 6 (2 per state)
|  | Output Indicator 2.2.3 No. of men/women/youths supported by vocational training | Training report | 6 months: Training package devised, training planned
12 months: vocational training 50% completed
Baseline: 0
Target: 125
Outcome 3: Enhanced accountability promotes increased effectiveness of response to the farmers-herders crisis |  | Outcome Indicator 3 a. Number of states with a systematic monitoring of HR abuses | Reports from target CSOs, Reports from NCHR | 6 months: NGO/CSO partner in one state contracted and trained on reporting
12 months: Regular reporting achieved
Baseline: 0
Target: 1
|  | Outcome Indicator 3 b. Percentage increase in awareness of SEA and SGBV in project area | Perception survey reports | 6 months: Gender sensitization activities planned and agreed with security sector
12 months: Capacity building activities 50% complete
Baseline: low awareness
Target: 50% of surveyed population state being aware of SEA/SGBV
|  | Outcome Indicator 3 c. Degree of improvement in HR responsiveness of military and security apparatus | Perception survey reports | 6 months: HR sensitization activities planned and agreed with security sector
12 months: Documented regular engagements with security outfit - 50% complete
Baseline: zero/low response
Target: 30% improvement
| Output 3.1 Capacity of monitoring, investigation and follow up on human rights offences enhanced | Output Indicator 3.1.1 No and quality of reports referencing documented HR abuses | Trend analysis | 6 months: CSO identified and active in pilot area
12 months: CSO submitting monthly reports
Baseline: irregular reports of poor quality
| List of activities under this Output: | Target: regular reporting that meets minimum standards
Pilot human rights monitoring and reporting mechanism through National Human Rights Commission (NHRC)/NGO/CSO partnership in one state
Support to NHRC in convening CSOs, CBOs involved in human rights monitoring in each state
Capacity building and awareness raising on sexual exploitation and abuse (SEA) and sexual and gender-based (SGBV) violence
|  | Output Indicator 3.1.2 Percentage of reported HR abuses and violations that are investigated | Trend analysis | 6 months: Assessment of pre-project HR reporting complete
12 months: Trend analysis shows improvement
Baseline: low
Target: 50% improvement
| Output 3.2 Increased civil-military/security agencies cooperation and dialogue | Output Indicator 3.2.1 No of workshops and dialogue platforms supporting behavioral changes | Workshop statement/attendance sheets, Nigerian Army HR desk deployment reports | 6 months: Workshops/platforms planned and initial consultations with HR desk of Nigerian Army held
|  | Baseline: 0 |  | 12 months: Agreement on minimum standards achieved with security agencies
| List of activities under this Output: | Target: 3
Capacity building and sensitization of security agencies on codes of conduct and rules of engagement
Advocacy to deploy human rights desk of Nigerian Army alongside any military deployment in the three states
Support local level platforms for dialogue and exchange with security agencies and informal security actors (i.e. vigilante groups)
Outcome 4: Improved understanding of the crisis encourages evidence-based advocacy, targeted investments and innovative solutions |  | Outcome Indicator 4 a. Number of initiatives informed by Project-generated information and advocacy on farmers-herders crisis | CSO monitoring reports, organization’s letters of request, declarations arising from meeting, project documents | 6 months: n/a
12 months: 2 initiatives proposed
Baseline: 0
Target: 5 (at least 2 target women/youth)
|  | Outcome Indicator 4 b. Number of references in national and state media to Project-generated information and analysis on farmers-herders crisis | Monitoring national and state media | 6 months: Media monitoring system in place
12 months: Interim impact analysis complete
Baseline: 0
Target: 12
|  | Outcome Indicator 4 c. Total value of additional funds leveraged to address farmer herder conflict | Project documents, requests for information, donor agreements, state/federal commitments | 6 months: n/a
12 months: at least $1 million leveraged
Baseline: 0
Target: $5 million (at least $1 million targets women/youth)
| Output 4.1 Information Management and Analysis Unit provides reliable and credible information on farmers-herders crisis | Output Indicator 4.1.1 Number of verified and objective information products based on the project’s sources of information | Database, GIS system, regular reporting from field partners, access to reports, updates and infographics | 6 months: GIS and media officer hired, software procured, initial update and infographics on project baseline data produced
12 months: 1 report, 3 updates and 6 infographics produced
Baseline: 0
| List of activities under this Output: | Target: 3 Reports, 9 updates and 12 infographics produced (with gender and youth dis-aggregated data and analyses)
Information management Protocol developed to ensure gender and youth dis-aggregated data is gathered to enable project gender and youth targeted interventions and broader advocacy
Information gathered under the project and through partners are collated and analyzed
GIS-mapping capabilities enable spatial plotting of attacks to inform trends in the crisis
Production of analytical briefs and updates on the crisis in the three states help provide partners with a nuanced and well-informed understanding of the crisis
| Output 4.2 Objective and verified information on the crisis is made publicly available | Output Indicator 4.2.1 Number of Reports, briefs and infographics that reach a wide audience | Social media analytics, press releases and public announcements by State Ministries of Information; State Ministry websites | 6 months: n/a
12 months: Creation of social media pages, membership in key social media forums, MoUs signed with SMoIs on sharing of information
Baseline: 0 reached, 0 likes, 0 shares/retweets
| List of activities under this Output: | Target: 100,000 reached, 1,000 likes, 1,000 shares/retweets
Publishing outputs on online repositories and websites for wide distribution and sharing with the public
Engagement with State Ministries of Information help ensure that state-level media houses are made aware of the information and analysis generated
Social media platforms disseminate reports, briefs and infographics widely