SECRETARY-GENERAL’S PEACEBUILDING FUND

PBF PROJECT PROGRESS REPORT TEMPLATE

PBF PROJECT progress report

COUNTRY: Tajikistan and Kyrgyzstan

TYPE OF REPORT: semi-annual, annual OR FINAL Annual

date of report: November 15, 2018

| Project Title: Cross-border Cooperation for Sustainable Peace and Development Project Number from MPTF-O Gateway: 00097384 and 00097385 |
| --- |
| PBF project modality: IRF PRF | If funding is disbursed into a national or regional trust fund: Country Trust Fund Regional Trust Fund Name of Recipient Fund: |
| List all direct project recipient organizations (starting with Convening Agency), followed type of organization (UN, CSO etc): UNDP Tajikistan, UNDP Kyrgyzstan, UNICEF Tajikistan, UNICEF Kyrgyzstan, WFP Tajikistan, WFP Kyrgyzstan, FAO Tajikistan, FAO Kyrgyzstan, UN Women Tajikistan, UN Women Kyrgyzstan (All UN) List additional implementing partners, Governmental and non-Governmental: 1. Tajikistan: Ministry of Foreign Affairs of Republic of Tajikistan (Co-chair of the Steering Committee), State Border Service, Office of Ombudsman, districts administration (local authoriees), Ministry of Education and Science, Committee on Youth Affairs and Sport, and Committee of Women and Family Affairs under the Government of Tajikistan 2. Kyrgyzstan: Office of the President of the Kyrgyz Republic (Co-chair of the PBF Steering Committee), Ministry of Foreign Affairs of Republic of Kyrgyzstan, Office of the Vice Prime Minister, LSGs, State border service, Ombudsman, Ministry of Education and Science, State Agency for LSG and Interethnic Relations, State Agency for Youth and Physical Training |
| Project commencement date: April 2018 Project duration in months: 18 |
| Does the project fall under one of the specific PBF priority windows below: Gender promotion initiative Youth promotion initiative Transition from UN or regional peacekeeping or special political missions Cross-border or regional project |
| Total PBF approved project budget* (by recipient organization): UNICEF Tajikistan: $ 200'000 UNICEF Kyrgyzstan : $ 170,000 WFP Tajikistan : $ 200'000 WFP Kyrgyzstan : $ 170'000 UN Women Tajikistan: $ 100'000 UN Women Kyrgyzstan: $ 140'000 FAO Tajikistan: $ 130,000 FAO Kyrgyzstan: $150,000 UNDP Tajikistan: $370,000 UNDP Kyrgyzstan: $ 370,000 Total: $ 2,000,000.00 *The overall approved budget and the release of the second and any subsequent tranche are conditional and subject to PBSO’s approval and subject to availability of funds in the PBF account How many tranches have been received so far: 1 (one) |
| Report preparation: Project report prepared by: The project team and reviewed by Peace and Development Advisers Project report approved by: Did PBF Secretariat clear the report: Any comments from PBF Secretariat on the report: Has the project undertaken any evaluation exercises? Please specify and attach: The lessons learnt exercise (LLE) was conducted in October-November 2017 by an independent expert seconded by the PeaceNexus Foundation. The LLE aimed to review results of the first phase of the project (December 2015-December 2017), as well as analyse relevance, effectiveness and efficiency of the project, including analysis of peacebuilding dividends of each intervention. The report of lessons learnt exercise was used to formulate and revise strategies for the second phase of the project. In addition, the internal lessons learnt exercise was conducted by the team, and finalized in July 2017. |

NOTES FOR COMPLETING THE REPORT:

- Avoid acronyms and UN jargon, use general / common language.

- Be as concrete as possible. Avoid theoretical, vague or conceptual discourse.

- Ensure the analysis and project progress assessment is gender and age sensitive.

PART 1: RESULTS PROGRESS

  - Overall project progress to date

Briefly explain the status of the project in terms of its implementation cycle, including whether all preliminary/preparatory activities have been completed (1500 character limit):

The project is off-track and refrains from infrastructure interventions and cross-border activities until the SOPs for infrastructure-related activities and the Workplan is approved by the KG Government. RUNOs in TJ after 4-month suspension commenced ‘soft’ in-country activities. Similar decision was taken by UN KG in October 2018. The situation is to be discussed at the Heads of Agencies meeting on 20 November 2018. Activities are mainly at planning or early implementation stage.

TJ: Community or public consultations in project areas conducted. The complaint mechanism supported. 40 women leaders improved knowledge and skills in conflict resolution, mediation and decision making, 4 women's business initiatives are being supported aiming at strengthening trust and cooperation between KG and TJ communities. The pasture management programming was discussed and consulted with TJ Government and pasture users; joint visits conducted. A roadmap of implementation of youth-related activities was developed. The peacebuilding competency curriculum for youth trainings developed; the handbook on border crossing rules is being revised. The Government mission visited TJ project area in September 2018.

KG: A series of strategic planning meetings to ensure governments support conducted by KG RUNOs and project AWP designed. Capacity building and consultative meetings for WUAs conducted and equipment distributed. Preliminary selection of WUAs projects has been completed..

Given the recent/current political/peacebuilding/ transition situation/ needs in the country, has the project been/ does it continue to be relevant and well placed to address potential conflict factors/ sources of tensions/ risks to country’s sustaining peace progress? Please illustrate. If project is still ongoing, are any adjustments required? (1500 character limit)

The project continues to be relevant and addresses key factors that trigger border community conflicts over resources, border crossing rules, as well as helps to overcome negative stereotypes between residents of TJ and KG. In 10 months of 2018, 20 incidents took place in targeted border areas, with most of them related to land resources and water. Project interventions contributed to mitigation of the risks of conflicts, and overall number of incidents dropped from 34 in 2015 to 20 in 10 months of 2018 (41% decrease - TRACTION data; results varied from year to year). Outcome results research (mid-line survey) is showing mixed results and slightly differs on two sides of the border: the overall improved perception of relations between Kyrgyz and Tajiks, with simultaneous growing social distance between these nationalities. As delimitation and demarcation talks between Kyrgyzstan and Tajikistan are not progressing, the project remains critical in mitigating the risk of community-level violence.

In a few sentences, summarize what is unique/ innovative/ interesting about what this project is trying/ has tried to achieve or its approach (rather than listing activity progress) (1500 character limit).

The current project is one of the few cross-border peacebuilding projects that is aimed at improving relations between the communities of different countries by implementing mirroring and joint cross-border activities on both sides of the border. Conflict sensitive and bottom-up approach ensures involvement of border residents and authorities in project implementation. The project comprehensively addresses key issues (water, social infrastructure, education, border crossing etc.) and groups (youth, women, water users, duty bearers etc.). Furthermore, the project consolidates the efforts of five different UN agencies on each side of the border, where each agency brings its comparative advantage to achieve common objectives by applying collaborative approach, strong joint M&E and shared accountability frameworks.

According TJ Governmental Monitoring Group representatives', the project is seen by the Government as the only effort (on Tajik side) which adresses conflict risks (and not just implementing development projects) in undetermined border area. The government acknowledges the importance of partcipatory and confidence building methodology complemented by resources for practical solution/mitigation or prevention of tension. Therefore, the project is given a special attention by the Government of TJ, particularly MFA and other institutions that are involved into the process and negotiation of border delimitation.

Considering the project’s implementation cycle, please rate this project’s overall progress towards results to date:

In a few sentences summarize major project peacebuilding progress/results (with evidence), which PBSO can use in public communications to highlight the project (1500 character limit):

Due to project’s off-track status, the progress achieved in this phase relates to the building capacity (knowledge and skills) of 40 women leaders in conflict resolution, mediation and decision making, 4 women's business initiatives are identified for financial support, and aim at strengthening trust and cooperation between KG and TJ communities. Also, the activities on strengthening complaint mechanism for addressing grievances which grow after unfriendly treatment by law enforcement institutions of the other country has been also operational –14 legal community consultations/meetings by Ombudsman office were conducted, and 2 of them with participation of Border Service and police. All other activities were of preparatory nature, including community consultations, consultations with authorities, identification of project sites, review of manuals and publications etc. If to consider the results of the first phase, the project strongly contributed to the improved inter-community dialogue, peaceful solution of disputes between Kyrgyz and Tajik residents, infrastructure, relationships between youth and law enforcement agencies.

In a few sentences, explain how the project has made real human impact, that is, how did it affect the lives of any people in the country – where possible, use direct quotes that PBSO can use in public communications to highlight the project (1500 character limit):

As majority of actions are at initial stage, no evidence of real human impact is available for the activities within 2nd phase of the project. In the first phase, the human impact was considerable as people in communities were able to stop conflicting over water and access to services, gain confidence about future in their village, and start perceiving their neighbors more positively. As showed above the number of incidents dropped by 41% from 2015, and over 7000 young people met and worked together with a counterpart(s) from the neighbouring country. The comparison of the mid-line survey results with those measured 3 years ago shows that the good neighborly relations in border villages of the KR have improved almost in all indicators, while the urgency of selected problems has decreased.

If the project progress assessment is on-track, please explain what the key challenges (if any) have been and which measures were taken to address them (1500 character limit).

If the assessment is off-track, please list main reasons/ challenges and explain what impact this has had/will have on project duration or strategy and what measures have been taken/ will be taken to address the challenges/ rectify project progress (1500 character limit):

The key obstacle to project implementation is the Kyrgyzstan Government reluctance to hold Steering Committee and approve the infrastructure projects algorithm (SOPs).The KG Government links the SOPs approval with the restoring the Kayirma canal to its previous condition, which is difficult due to political sensitivities. As a result, implementation of infrastructure and cross-border activities have been put on hold by both countries. The delayed implementation would, most likely, require an extension of the project.

UN RC/UNDP RR in Kyrgyzstan held regular consultations with the Ministry of Foreign Affairs, other relevant authorities at all levels, RUNOs, UNDP HQ, IRH and Tajikistan CO. Meetings at working and management level were held by RUNO in TJ to discuss implementation. TJ government was informed about the delay. The Heads of Agencies are to meet on 20 November in Dushanbe to discuss the mitigation measures that will allow to address some of risks (including extension, strategy for no SOP approval etc.). In the meantime RUNOs started implementation of in-country capacity building activities in both countries. Worth reminding, that the “algorithm” (SOPs for infrastructure sub-projects' design and implementation) ensures review/approval by and coordination with governments over infrastructure sub-projects, and aims to prevent the repetition of Kayirma canal case situation.

Please attach as a separate document(s) any materials highlighting or providing more evidence for project progress (for example: publications, photos, videos, monitoring reports, evaluation reports etc.). List below what has been attached to the report, including purpose and audience.

n/a

  - Result progress by project outcome

The space in the template allows for up to four project outcomes. If your project has more approved outcomes, contact PBSO for template modification.

Outcome 1:  Improved linkages and cooperation between security providers, local authorities and communities to reduce violent incidents

Rate the current status of the outcome progress:

Progress summary: Describe main progress under this Outcome made during the reporting period (for June reports: January-June; for November reports: January-November; for final reports: full project duration), including major output progress (not all individual activities). If the project is starting to make/ has made a difference at the outcome level, provide specific evidence for the progress (quantitative and qualitative) and explain how it impacts the broader political and peacebuilding context. Where possible, provide specific examples of change the project has supported/ contributed to as well as, where available and relevant, quotes from partners or beneficiaries about the project and their experience. (3000 character limit)?

The project has achieved very limited progress in the reported period (since April 2018), and most achievements are at activitiy level - trainings and workshops for women conducted as well as complaints system activities operational. Project cannot provide evidence of achieving results at output and outcome level due to delay in the launch of the project. The reasons are explained above in the explanation of the off-track status of the project (page 5).

Outcome 2:

Rate the current status of the outcome progress:

Progress summary: (see guiding questions under Outcome 1)

Outcome 3:  n/a

Rate the current status of the outcome progress:

Progress summary: (see guiding questions under Outcome 1)

Outcome 4:  n/a

Rate the current status of the outcome progress:

Progress summary: (see guiding questions under Outcome 1)

  - Cross-cutting issues

| National ownership: How has the national government demonstrated ownership/ commitment to the project results and activities? Give specific examples. (1500 character limit) | The national ownership is ensured through several mechanisms. At national level, the project strategy and its Workplan are approved by the inclusive Steering Committee (led by the Government and co-chaired by the RC). The Government in both countries closely monitors the project progress and results, often supporting RUNOs in overcoming political sensitivities around field interventions (the most recent visit of the monitoring group was held on 11-12 September in TJ). The focal points in the Government are being consulted and informed about project status on a regular basis. Some Agencies include project activities into the Joint Action Plans with their national counterparts (thereby strengthening commitment and ownership). At regional and district level inclusive consultation ensure buy-in of key local stakeholders and avoiding institutional intricacies during field work. Bottom-up approach enable to ensure community ownership of projects, and the first phase showed that project was addressing priorities identified by communities themselves. The project aligns itself to various government strategies and action plans, including e.g. Water Strategies, NAP 1325, Youth Strategies etc. As has been mentioned in the part on project uniqeness, the TJ government acknowledges the unique methodology of project implementation and its conflict-prevention focus. |
| --- | --- |
| Monitoring: Is the project M&E plan on track? What monitoring methods and sources of evidence are being/ have been used? Please attach any monitoring-related reports for the reporting period. (1500 character limit)? | The detailed M&E plan for Phase 2 has been discussed and drafted during the Coordination meeting on 16-17 May 2018. UNDP continues monitoring of situation in cross-border area (till the end of 2018).In-country coordination meeting in TJ was held in September 2018. UNICEF TJ has developed internal monitoring system to track project results at activity and output levels. The data collected through this system will contribute to the larger project M&E system. WFP has developed and introduced the Conflict-Sensitivity, Gender and Environmental Risk Screening Checklist to address the recommendations of the Lesson Learned Exercise. The purpose of the checklist is to enhance positive peacebuilding, gender and environmental opportunities as well as ensure that adverse risks and impacts are avoided, minimized, and mitigated in WFP interventions.The WFP Conflict-Sensitivity, Gender and Environmental Risk Screening Checklist was introduced as an integral part of regular monitoring checklist to be collected using mobile tools. |
| Evaluation: Provide an update on the preparations for the external evaluation for the project, especially if within last 6 months of implementation or final report. Confirm available budget for evaluation. (1500 character limit) | Lessons learnt exercise (mid-term evaluation) was conducted in October-November 2017 by an international consultant from PeaceNexus Foundation. The report has been shared earlier with PBSO. Both countries have finalized the mid-line report, which analyses changes in people's beliefs of residents, trust and perception of neighbours. Reports (separate for each country) serve as data source to provide proxy data on the effectiveness/impact of project interventions (considering the attribution issue, and understanding that there are multiple factors and changing dynamics with regard to people percetions in a concrete point of time). |
| Catalytic effects (financial): Did the project lead to any specific non-PBF funding commitments? If yes, from whom and how much? If not, have any specific attempts been made to attract additional financial contributions to the project and beyond? (1500 character limit) | UNDP is negotiating the new intervention with SDC. The workshop on programming with participation of SDC representatives was held in July 2018. Some municipal structures in Kyrgyz side began to invest their own funds for the implementation of infrastructure projects, in particular one of the municipalities invested more than $14,000 to rehabilitate the internal irrigation canals; the second example, another municipality has invested more than $11,000 for the street lighting of border villages. |
| Catalytic effects (non-financial): Did the project create favourable conditions for additional peacebuilding activities by Government/ other donors? If yes, please specify. (1500 character limit) | The project remains catalytic in terms of keeping government's and international donors' attention to continuing incidents at the border. DFID in TJ is supporting two projects in targeted areas and, although development-oriented, they are bringing peacebuilding effect through improving socio-economic situation and supporting youth in border areas. Many of implemented initiatives of the project serve as an example and a guide for local communities and LSGs. For example, projects on streets lighting, concreting inland water canals, sports and cultural events between border communities independently carred out by the efforts of the local communities themselves. Several women's social initiatives supported in Phase 1 are being continued by the women such as cultural visits, craftwork exchange of experience, etc. Besides, there are mutual memorundum of understanding between cross-border village clusters at municipal level that promotes cross-border cultural visits, for instance the celebration of River Day. Peacebuilding competency curriculum that has been developed within the PBF project by UNICEF has a potential for catalytic effect for broader competency building among adolescents and youth in the country with the focus on peacebuilding. |
| Exit strategy/ sustainability: What steps have been taken to prepare for end of project and help ensure sustainability of the project results beyond PBF support for this project? (1500 character limit) | The sustainability is ensured through alignment of project activities with government programmes and priorities. E.g. youth-friendly psychological support is a part of a large initiative and ended with establishing the new system of psychological support. Most of infrastructure projects are included into local develoment plans, and all assets within infrastructure projects, including equipment, are officially transferred to the books of local authorities - this guarrantees their operation and maintenance after project ends. Embedding actions in the existing community mechanisms, including e.g. women groups, youth contact groups, and water-users associations ensures that capacities built within the project will be sustained and applied beyond the project cycle. |
| Risk taking: Describe how the project has responded to risks that threatened the achievement of results. Identify any new risks that have emerged since the last report. (1500 character limit) | Taking into account the fact that AWP of project has not been approved by the Government of Kyrgyzstan, Implementing Agencies decided to postpone infrastructure related and cross-border activitities and focus on prepratory, analysis and monitoring and in-country activitities to prevent possible risks of disbalance of international support in target border area. The project continued monitoring of conflict risks through TRACTION and noted that although the overall number of incidents is decreasing, the intensity and participation of law enforcement in incidents created higher risks of further escalation. The border services signed a memorandum to refrain from the use of force in the incidents. Operational/programmatic risks relate to the lack of funding to maintain TRACTION in 2019 (TRACTION was funded from SDC, and the project ended, and new SDC funds are not yet available). If TRACTION is discontinued, the link between analysis and interventions will become weaker, and the project will lose an important effectiveness measurement tool. UNDP is analysing possible sources of continued funding for TRACTION. |
| Gender equality: In the reporting period, which activities have taken place with a specific focus on addressing issues of gender equality or women’s empowerment? (1500 character limit) | The Gender Mainstreaming Strategy is discussed and accepted by all RUNOs during the 2nd Coordination Meeting in November 2018. The joint Annual Workplan integrates gender through all the activities by mainstreaming gender activities and ensuring tracking of gender-specific targets. It is highlighting gender-balanced representation of women in all activities, including cross-country dialogues, complaint-resolution mechanism, addressing women insecurities in trainings provided to border-security guards, WUAs and local self-governments. Sex-disaggregated data collection for M&E purposes will be carried out. UN Women has conducted activities, specifically addressing women empowerment that has been reported earlier (40 women leaders received capacity building, 4 small-scale income generating initiatives). Further, an informal group of women-peacebuilders is created in TJ [with its regulations], which is anticipated to be transferred into regional association of women-peacebuilders by the end of project. In addition, during the Open Day for Peace in Kyrgyzstan, that took place on 21 September 2018 in Batken city, roundtable with women peace activists was organized, discussing the role of women in sustaining peace and preventing cross-border conflicts. This roundtable served as a platform to articulate women’s needs and highlight concerns, priorities and recommendations on key context-specific issues relating to peace and security to high-level UN and Government officials. |
| Other: Are there any other issues concerning project implementation that you want to share, including any capacity needs of the recipient organizations? (1500 character limit) |  |

1.3 INDICATOR BASED PERFORMANCE ASSESSMENT: Using the Project Results Framework as per the approved project document or any amendments- provide an update on the achievement of key indicators at both the outcome and output level in the table below (if your project has more indicators than provided in the table, select the most relevant ones with most relevant progress to highlight). Where it has not been possible to collect data on indicators, state this and provide any explanation. Provide gender and age disaggregated data. (300 characters max per entry)

|  | Performance Indicators | Indicator Baseline | End of project Indicator Target | Current indicator progress | Reasons for Variance/ Delay (if any) | Adjustment of target (if any) |
| --- | --- | --- | --- | --- | --- | --- |
| Outcome 1 Cooperation and trust between communities increased to mitigate risks of renewed violence | Indicator 1.1 a: % of community members from the 6 pilot village clusters who indicate an improvement in cross-border relations/cooperation with community members in the same village cluster on the other side of the border (disaggregated by gender, age, villa | 1. 35% of respondents described their relations with neighbors as bad/open conflict. 2. 60% of respondents think that relations will not be improved (data disaggregated by nationality, gender and age is available) | 10% increase over baseline | Midline Study: KG: score 4.5/5 (scales: 1-open conflict; 5-close cooperation) = 90% TJ: 87.6% of respondents described their relations as neutral or friendly (baseline 62.15%); conflictual relations pointed out 10.5% of respondents in midline survey |  |  |
|  | Indicator 1.2 b: # of violent incidents in pilot cluster is decreased | Kyrgyz Republic – 32 in 2014 Republic of Tajikistan - 26 incident cases in 2014 | 20% decrease over baseline | 20 incidents (for both countries) during Jan-Nov 2018 41% decrease (uniform 2015 baseline based on TRACTION) |  |  |
|  | Indicator 1.3 c: % of community members from the 6 pilot cross-border village clusters who would be ready to work together with community members in the same village cluster on the other side of the border to improve the lives of cross-border communities o n both | 37% of respondents do not want even to work with the neighbors and 74% do not accept keenship relations (data disaggregated by nationality, gender and age is available) | 10% increase over baseline | 49% of respondents in KG and 88.3% in RT who are fully or partially willing to cooperate with representatives of the neighboring village of Tajikistan to resolve personal or social problems. |  |  |
| Output 1.1 Improved linkages and cooperation between security providers, local authorities and communities to reduce violent incidents | Indicator 1.1.1 Number of interventions/ activities/ preventive actions that were implemented by security providers, local authorities and communities on one side of the border in the 6 pilot cross-border village clusters to improve information exchange and pr | 94 events in KG and TJ (in the Phase 1 by December 2017; the target was 8) | At least 20 (10 in TJ and 10 in KG) interventions/ activities/ preventive actions that were jointly implemented by security providers, local authorities and communities on one side of the border in the 6 pilot cross-border village clusters to improve information exchange and prevent security incide | 2 events at district and 5 at jamoat level are conducted in Tajikistan. Handbook on cross-border rules that will be used for awareness raising on crossing the border among adolescents, teachers and community members has been revised. |  |  |
|  | Indicator 1.1.2 1.1.3 Number of problem solving and complaints mechanisms – PSCM, (either cross-border or on one side of the border) established/improved that bring security providers, local authorities and communities together to address community grievances and re | 4 (2 in each country) (by December 2017) | Maintain and improve 4 existing problem solving and complaints mechanisms - 2 in TJ and 2 in KG (either cross-border or on one side of the border) | 2 mechanisms established within the 1st phase of project in TJ are functioning. In 2018 Office of Ombudsman in RT registered 92 grievances of border residents. Partnership has been built with CSO "Legal initiative" and Ombudsman office to improve complaint mechanism and lead awareness raising. |  |  |
| Output 1.2 Communities restore cross-border linkages and trust by jointly addressing interdependent needs/ challenges associated with community infrastructure and natural resources, as well as by establishing platforms of confidence-building and cooperation between various societal groups | Indicator 1.2.1 Number of projects that were agreed by communities from both sides of the pilot cross-border village clusters and to address interdependent needs/ challenges associated with community infrastructure (with information on how many of those were i | 83 * projects implemented in RT and KR, according to AR (*projects financed both by IRF and SDC) | 20 projects (10 TJ, 10 KG) jointly agreed/implemented by communities from both sides | 0 Presently, the foundation for the dialogue process within community and intercommunity dialogue on identification of projects addressing interdependent needs/challenges associated with community infrastructure is being established |  |  |
|  | Indicator 1.2.2 Number of youth (disaggregated data for young men/ boys and young women/ girls) that benefitted from training/ support or participated in; a) cross-border joint youth events, and b) in-country youth events that aim to promote inter-ethnic toler | a) 7,293 b) 7,311 | a) 1000 (500 from TJ and 500 from KG) b) 800 (400 from TJ and 400 from KG) (segregated data for young men/ boys and young women/ girls) that benefitted from training/ support or participated in joint cross-border youth events in pilot cross-border village clusters | 0 (due to delay of project implementation) | Due to delay of approving of Annual Work Plan in Kyrgyzstan the interventions had been postponed. Currently Implementing partner is contracted and activtites will started from November 2018. |  |
| Output 1.3 | Indicator 1.3.1 Indicator 1.2.3: Number of joint cross-border initiatives responding to specific gender equality and women’s empowerment (GEWE) issues are implemented by women activists | 7 social and business initiatives | At least 4 cross-border women’s initiatives (small projects) implemented by women | Three new business initiatives are selected and supported as well as one previous business initiatives is assessed and expanded to improve economic security of vulberable women in 4 village clusters | The supported women's initiatives are being realised in Tajikistan side with perspective of linkage with Kyrgyz women initiatives planned to start in 2019 while 4 joint small-scale initiatives planned for implementation. |  |
|  | Indicator 1.3.2 |  |  |  |  |  |
| Outcome 2 | Indicator 2.1 |  |  |  |  |  |
|  | Indicator 2.2 |  |  |  |  |  |
|  | Indicator 2.3 |  |  |  |  |  |
| Output 2.1 | Indicator 2.1.1 |  |  |  |  |  |
|  | Indicator 2.1.2 |  |  |  |  |  |
| Output 2.2 | Indicator 2.2.1 |  |  |  |  |  |
|  | Indicator 2.2.2 |  |  |  |  |  |
| Output 2.3 | Indicator 2.3.1 |  |  |  |  |  |
|  | Indicator 2.3.2 |  |  |  |  |  |
| Outcome 3 | Indicator 3.1 |  |  |  |  |  |
|  | Indicator 3.2 |  |  |  |  |  |
|  | Indicator 3.3 |  |  |  |  |  |
| Output 3.1 | Indicator 3.1.1 |  |  |  |  |  |
|  | Indicator 3.1.2 |  |  |  |  |  |
| Output 3.2 | Indicator 3.2.1 |  |  |  |  |  |
|  | Indicator 3.2.2 |  |  |  |  |  |
| Output 3.3 | Indicator 3.3.1 |  |  |  |  |  |
|  | Indicator 3.3.2 |  |  |  |  |  |
| Outcome 4 | Indicator 4.1 |  |  |  |  |  |
|  | Indicator 4.2 |  |  |  |  |  |
|  | Indicator 4.3 |  |  |  |  |  |
| Output 4.1 | Indicator 4.1.1 |  |  |  |  |  |
|  | Indicator 4.1.2 |  |  |  |  |  |
| Output 4.2 | Indicator 4.2.1 |  |  |  |  |  |
|  | Indicator 4.2.2 |  |  |  |  |  |
| Output 4.3 | Indicator 4.3.1 |  |  |  |  |  |
|  | Indicator 4.3.2 |  |  |  |  |  |

PART 2: INDICATIVE PROJECT FINANCIAL PROGRESS

  - Comments on the overall state of financial expenditures

Please rate whether project financial expenditures are on track, delayed, or off track, vis-à-vis project plans and by recipient organization:

How many project budget tranches have been received to date and what is the overall level of expenditure against the total budget and against the tranche(s) received so far (500 characters limit):

1. UNDP TJ received: $370,000; expenditure: $51,239

2 UNDP KG  received $370,000 expenditure $26,936

3. UN Women TJ received $100,000; expenditure: $97,753

4 UN Women KG  $140,00; $21,900

5. FAO TJ  received $130,000; expenditure $102,075

6. FAO KG received: $150,000 expenditure $61,691

7. WFP TJ received: $ 200,000; expenditure: $122,463

8. WFP KG received $200,000 expenditure $54,424

9. UNICEF TJ received $200,000 ; expenditure $17,048

10 UNICEF KG received: 170'000; expenditure:$15,031

When do you expect to seek the next tranche, if any tranches are outstanding:

N/a

If expenditure is delayed or off track, please provide a brief explanation (500 characters limit): The main challenge in the project implementation at Kyrgyz side is related to lack of approval of the Workplan by KG Government which links it to the resolution of Kayirma canal case - that caused temporary suspension of project acitivites in 2018. To resolve the issue the UN RC/UNDP RR in Kyrgystan held regular consultations with the Minsitry of Foreign Affairs, other relevant authorities at all levels, RUNOs,  UNDP HQ, IRH and Tajikistan CO.

Please state what $ amount was planned (in the project document) to be allocated to activities focussed on gender equality or women’s empowerment and how much has been actually allocated to date: In project document, up to 30% of project budget is aimed to be allocated for gender mainstreaming activities, following the guidliness of the PBSO and total $71,011.10 was spent for activities focused on GEWE. The Joint Annual Workplan, consolidated and agreed during the Coordination Workshop on 16-17 May 2018 highlighted number of activties and indicators aimed at promoting gender equality and women empowerement, yet budget estimates need finalisation.

Please fill out and attach Annex A on project financial progress with detail on expenditures/ commitments to date using the original project budget table in Excel, even though the $ amounts are indicative only.

# Footnotes

Note: commencement date will be the date of first funds transfer.

Maximum project duration for IRF projects is 18 months, for PRF projects – 36 months.