## Cost category
Table 2 - PBF project budget by UN cost category
Note: If this is a budget revision, insert extra columns to show budget changes.
| Contractual budget |  |  |  | Budget revision
CATEGORIES | Amount Recipient DRC-DDG |  |  | PROJECT TOTAL | Budget changes (Note to File - 15 Nov 2019) | Budget change % variation (within the 15% margin stipulated in the guidelines) | Estimated expenditures (01 Jan-15 Nov 2019)
| Tranche 1 (35%) | Tranche 2 (35%) | Tranche 3 (30%)
1. Staff and other personnel | 137720 | 137720 | 118045 | 393485 | 374320 | 4.871% | 144126.88
2. Supplies, Commodities, Materials | 26101 | 26101 | 22372 | 74574 | 80757.44 | -8.292% | 6297.07
3. Equipment, Vehicles, and Furniture (including Depreciation) | 19975 | 19975 | 17120 | 57070 | 55958 | 1.948% | 11511.86
4. Contractual services | 16383 | 16383 | 14042 | 46808 | 48394.5 | -3.389% | 31958.09
5.Travel | 15533 | 15533 | 13313 | 44379 | 47885 | -7.9% | 13107.6
6. Transfers and Grants to Counterparts | 0 | 0 | 0 | 0 | 0 | 0% | 0
7. General Operating and other Direct Costs | 193168 | 193168 | 165572 | 551908 | 556685.06 | -0.8656% | 123787
Sub-Total Project Costs | 408880 | 408880 | 350464 | 1168224 | 1164000 |  | 330788.5
8. Indirect Support Costs (must be 7%) | 28621.6 | 28621.6 | 24532 | 81776 | 86000 | -5.165%
TOTAL | 437501.6 | 437501.6 | 374996 | 1250000 | 1250000

## Project budget by outcome
Annex D - PBF project budget
Note: If this is a budget revision, insert extra columns to show budget changes.
Table 1 - PBF project budget by Outcome, output and activity
Outcome/ Output number | Outcome/ output/ activity formulation: | Budget DRC-DDG in USD $ | Budget changes (15 June 2019) | Budget changes (15 November 2019) | Percent of budget for each output reserved for direct action on gender equality (if any): | Level of expenditure/ commitments in USD (to provide at time of project progress reporting): | Any remarks (e.g. on types of inputs provided or budget justification, for example if high TA or travel costs)
OUTCOME 1: Young women and men of Masisi and Beni are integrated into the community democratic dialogue processes and actively participate in the reduction of violence and inter/intracommunity conflicts
Output 1.1: | Young women and men are engaged within their community and intergenerational and intercommunity trust is established and/or reinforced | 467669 |  |  | 50% | 128334.41 | Compte tenu des catégories fixes du format présent, les coûts ont été ventilés en fonction des activités en cours d'implémentation (coûts activités + coûts programmatiques globaux + coûts support globaux) et celles actuellement en phase préparatoire (coûts programmatiques globaux + coûts support globaux) - telles que détaillées dans les sections narratives du deuxième rapport de progrès annuel (15 Novembre 2019) Les coûts mentionnés dans la feuille "Cost category" offre une vision plus précise des dépenses et engagements en cours pour la période de Janvier à Novembre 2019.
Activity 1.1.1 | Establish a community democratic dialogue process that is inclusive of young women and men to discuss the role of youth in community governance and peacebuilding | 52847 |  |  | n/a | 14501.9 | 45.2% des participants femmes
Activity 1.1.2 | Raise community awareness on human and womens’ rights | 33672 |  |  | n/a | 9240.03 | 46.4% de participants femmes
Activity 1.1.3 | Revitalise and/or rehabilitate youth centres and/or community cultural centres to enable young women and men to benefit from a safe space for collaboration, debate, recreational and artistic activities | 381150 |  |  | n/a | 104592.48
Output 1.2 | Young women and men actively participate in the management, mediation and prevention of intra- and intercommunity conflicts | 69309 |  |  | 50% | 12467.13
Activity 1.2.1 | Train YPCs in civic education, non-violent communication, peaceful conflict resolution and management techniques | 24348 |  |  | n/a | 6681.41
Activity 1.2.2 | Organise community forums on the themes of gender roles, women’s empowerment and “positive masculinity” in connection to violence and conflict reduction | 21084 |  |  | n/a | 5785.72
Activity 1.2.3 | Support YPCs in dispensing training on peaceful conflict resolution and management techniques in schools of target locations | 23877 |  |  | n/a | 0
Output 1.3 | Young women and men fight against discourses of hate, and are able to critically analyse public political messages, and work together to advocate for violence prevention and reduction | 218125 |  |  | 40% | 34714.88
Activity 1.3.1 | Provide the tools and enhance young women and men’s capacity to critically analyse political and media messages conveying violence and/or racial or gender-based stigma and encourage YPC-YPC to undertake monthly collaborative analysis through meetings | 50234 |  |  | n/a | 0
Activity 1.3.2 | Provide training to young women and men on communication and advocacy techniques to promote positive peace messages and convey their priorities and demands at community, local and provincial levels | 41385 |  |  | n/a | 0
Activity 1.3.3 | Broadcast through Pole FM YPC interventions (sensitization messages, debates etc.) on youth’s key role in peacebuilding, reconciliation and their involvement in the management of conflicts in their communities | 126506 |  |  | n/a | 34714.88
TOTAL $ FOR OUTCOME 1: |  | 755103 |  |  |  | 175516.42
OUTCOME 2:Young women and men understand their economic and professional environments and are capable of identifying opportunities
Output 2.1 | Young women and men understand their economic and professional environments and are capable of identifying opportunities | 45219 |  |  | 40% | 0
Activity 2.1.1 | Conduct labour market assessments in Masisi and Beni | 15218 |  |  | n/a | 0
Activity 2.1.2 | Support young women and men in identifying areas of pertinent professional interest and assist in formulating individualised plans for economic resilience | 30001 |  |  | n/a | 0
Output 2.2 | Members of the YPCs implement their professional and/or training plans | 110427 |  |  | 40% | 0
Activity 2.2.1 | Support YPC members in the elaboration of their “economic resilience and empowerment” action plans | 798 |  |  | n/a | 0
Activity 2.2.2 | Assist in the organization of mutual aid and/or networking sessions through working groups and skills-sharing sessions | 36837 |  |  | n/a | 0
Activity 2.2.3 | Support YPC members in the implementation of their “economic resilience and empowerment” action plans through training activities, mentorship and apprenticeship opportunities | 72792 |  |  | n/a | 0
TOTAL $ FOR OUTCOME 2: | #VALUE! | 155646 |  |  |  | 0
TOTAL FOR ACTIVITIES |  | 910749 |  |  |  | 175516.42
Project personnel costs |  | 106437 | 109745 |  |  | 76681.82
DRC-DDG | Country Director | 7320 | 8000 |  |  | 8810.23
DRC-DDG | Head of Support Services | 7925 | 7500 |  |  | 8123.01
DRC-DDG | Safety Advisor | 5970 | 6200 |  |  | 5241.25
DRC-DDG | Area Manager Petit Nord Kivu (PNK) | 5960 | 0 |  |  | 0
DRC-DDG | Area Manager Grand Nord Kivu (GNK) | 5960 | 6500 |  |  | 751.11
DRC-DDG | Deputy Director - RO | 13000 | 13000 |  |  | 178.12
DRC-DDG | Security Advisor - RO | 10574 | 11000 |  |  | 110
DRC-DDG | Specialist Finance | 2100 | 3100 |  |  | 1518.16
DRC-DDG | Specialist Admin RH | 2100 | 3100 |  |  | 2110.66
DRC-DDG | Admin/HR Team Leader Base (Beni) | 1350 | 1700 |  |  | 625.83
DRC-DDG | Admin Assistant SMT (Kinshasa) | 1050 | 1000 |  |  | 763.48
DRC-DDG | Logistics Team Leader (Beni) | 1350 | 1700 |  |  | 578.62
DRC-DDG | Logistics Assistant (Beni) | 1080 | 950 |  |  | 609.35
DRC-DDG | Logistics Specialist CO | 2100 | 3100 |  |  | 2179.74
DRC-DDG | Admin/Finance Assistant (Goma) | 950 | 950 |  |  | 857.79
DRC-DDG | Logistics Team Leader (Goma) | 1250 | 1200 |  |  | 709.63
DRC-DDG | Safety Officer (Beni) | 1250 | 1700 |  |  | 750.68
DRC-DDG | Warehouse Assitant (Beni) | 1020 | 750 |  |  | 150
DRC-DDG | Drivers (Goma, Beni, Kinshasa) | 750 | 650 |  |  | 912.73
DRC-DDG | Support Staff for Office and Guesthouse (cleaners, gardners - Goma/Beni) | 450 | 450 |  |  | 420.75
DRC-DDG | Medical fees | 50 | 50 |  |  | 794.2
DRC-DDG | Monitoring, Evaluation, Learning and Communications Coordinator RO | 6611 | 6700 |  |  | 67
DRC-DDG | Grants Manager RO | 8061 | 7500 |  |  | 75
DRC-DDG | Deputy Head of Support Services RO | 7711 | 8000 |  |  | 80
DRC-DDG | Cook (Beni) | 650 | 0 |  |  | 0
Pole Institute | Directeur | 4900 | 4900 |  |  | 11760
Pole Institute | Chargé des Finances | 2027 | 2027 |  |  | 4864.8
Pole Institute | Assistant Finances | 1518 | 1518 |  |  | 4857.4
Pole Institute | Logistician | 1400 | 1400 |  |  | 5600
ASP | Secrétaire Exécutif (Directeur ASP) |  | 1500 |  |  | 4800
ASP | Administrateur Finances |  | 900 |  |  | 2880
SOFEPADI | Coordinatrice |  | 1200 |  |  | 2403.43
SOFEPADI | Administrateur Finances |  | 600 |  |  | 1201.25
SOFEPADI | Comptable |  | 500 |  |  | 1004.15
SOFEPADI | Caissière |  | 350 |  |  | 702.45
SOFEPADI | Frais Médicaux |  | 50 |  |  | 191
Project operational costs |  | 51448 |  |  | 0 | 48873.1 | 0
| Bank fees | 3150 |  |  |  | 9314.72 | Frais bancaires liés aux transferts et gestion de comptes de tous les partenaires.
| Legal fees | 965 |  |  |  | 0
| IT (software, internet, computers) | 3290 |  |  |  | 12293.98
| Telecommunications (phone, satellite, radio) | 21693 |  |  |  | 3665.69
| Rent (offices, sub-offices, guesthouse) | 21150 |  |  |  | 20698.71 | Loyers des bureaux et guesthouse de tous les partenaires incluant les services d'eau et d'électricité pour ces locaux.
| Private security (guards) | 1200 |  |  |  | 2900
M&E budget |  | 99590 | 98980 |  | 0 | 29717.17 | 0
| DRC-DDG Chef d'Equipe MEAL | 6750 | 9180 |  |  | 1837.31
| DRC-DDG UNPBF Assistant MEAL | 34200 | 17100 |  |  | 5899.32
| DRC-DDG Spécialiste Redevabilité CoC & CHS |  | 6480 |  |  | 1300.44
| DRC-DDG UNPBF Stagiaire MEAL |  |  | 2800 |  | 0 | Afin d'appuyer l'Assistant MEAL UNPBF de DRC-DDG dans le suivi des activités du projet, et particulièrement au niveau de la saisie des données des partenaires, il est prévu qu'un/e stagiaire soit recruté/e. Les fonds pour ce poste sont pris de la ligne budgétaire (catégorie de coût 1) relative au poste de Chargé Finance & Logistique, étant donné que le recrutement de ce dernier avait été retardé de plusieurs mois. L'attribution du montant de ce stage au chapitre MEAL (catégorie de coût 7) du budget n'impacte pas sur l'ensemble du budget, et créé une variation de moins de -1% du budget de la catégorie de coût initiale (c.f. feuille "Cost category" de cet Annexe Financier). Le salaire brut total prévu pour ce poste est d'un montant total de 2800$.
| Pole Institute Chargé MEAL | 8640 | 15120 |  |  | 6720
| ASP Chargé MEAL |  | 350 |  |  | 840
| M&E Outils de Collecte de Données |  | 750 |  |  | 731.1
| Beneficiary targeting process |  | 7000 |  |  | 6973.38 | Les montants ci-contre sont inclus à titre indicatifs de l'état des dépenses établies par les données financières disponibles jusqu'en date du rapport de progrès du 15 Novembre 2019, et ayant été précédemment sur la même ligne budgétaire (c.f. version contractuelle pour référence), la désagrégation des dépenses, et consolidation de certains coûts est encore en cours d'affinage.
| Project presentation and accountability towards beneficaries and communities |  | 3000 |  |  | 415.62
| Baseline Assessment | 5000 | 5000 |  |  | 5000
| Endline Evaluation | 5000 | 5000 |  |  | 0
| Independent Evaluation | 25000 | 15000 |  |  | 0
| Financial Audit | 15000 | 15000 |  |  | 0
Sub-total |  | 257475 |  |  | 0 | 155272.09 | 0
Indirect support costs (7%): |  | 81776 | 86000
TOTAL PROJECT BUDGET: |  | 1250000 |  |  | 0 | 330788.51 | 0

## Description of roles (hidden)
Postion Titles | % Contribution to Project | Description of Roles
Country Director - A8 | 12% | Overall representation with local and national authorities, representation in coordination mechanism to facilitate implementation - the Country Director shares time between programme and it is estimated that 12% of her time will be spent on this programme.
Head of Support Services - A10 | 12% | Oversees the quality and compliance of all support activities for implementing the programmes - the HoSS shares time between programme and it is estimated that 12% of his time will be spent on this programme.
Head of Programmes - A10 | 15% | Ensures that all programmes are implemented as planned, activities are implemented in line and compliant with sectors strategies, ensuring proper implementation as per DRC, CHS and SPHERE standards - We estimate that the HoP shares time between programme and it is estimated that 12% of her time will be past on this programme.
Area Manager Grand Nord Kivu - A14 | 15% | Leads area activities and create results which impacts the area, enables and oversees the implementation of policies or activities of short-term and operational nature within the area of operation and enables a productive and accountable relationship with beneficiaries, communities’ leaders/representatives, relevant governmental authorities, NGOs, and UN Agencies - The Area Manager shares his time between different projects
Peacebuilding Project Manager - A16 | 100% | Takes the leadership of the project in all aspect. This position is dedicated.
Livelihoods Coordinator - A14 | 30% | Responsible for developing context sensitive strategies and implementing the relevant project component of DRC's programs in the area and provides technical expertise on program development in all relevant projects - This position is share between project touching this specific sector. It is estimated that the Livelihood Coordinator will be working on 3 projects and will spend 30% of his/her time on this project.
Safety Advisor - A14 | 15% | Responsible for the development and implementation of the DRC Safety Risk Management System (SRMS), in close cooperation with Senior Management and Safety Focal Points - the SA works in collabortion with the Country Director and Area Manager to ensure proper understanding of the context, minimize risks and worsk on prevention/response of safety incident. The percentage of time his estimate in relation of the complexity and risks of the activities in the area.
Area Manager Petit Nord Kivu - A14 | 15% | Leads area activities and create results which impacts the area, enables and oversees the implementation of policies or activities of short-term and operational nature within the area of operation and enables a productive and accountable relationship with beneficiaries, communities’ leaders/representatives, relevant governmental authorities, NGOs, and UN Agencies as well as represents DRC in some coordination fora, in absence of the Country Director - The Area Manager shares his time between different projects
Programme Development and Quality Manager - A15 | 15% | contributes to leading, coordinating and supporting the design, development and implementation of all PDQM related activities in DRC - It is estimated that the PDQM will share 15% of her time on this particular project.
Admin-HR Officer Base Beni | 15% | Support all administrative tasks in regard to Administration and Human Resources - shares his time between different projects implemented in the area.
Admin Assistant SMT (Kin) | 15% | Support all administrative tasks in regard to Administration and Human Resources. This particular position his dedicated to the Senior Management Team.
Logistic Team Leader - Beni | 15% | Supervise all logistic acitvities in Beni territory (Fleets, purchase, warehouse) - shares his time between different projects implemented in the area.
Logistic Assistant Beni | 15% | Ensures fleet mangement and procurement - - shares his time between different projects implemented in the area.
Logistic Manager | 15% | Oversees all logistic activities in the country - - shares his time between different programme, it ihs estimated that he will share 15% of his time on this particular project
Admin Fin Assistant - Goma | 15% | Oversees all finance activities in the country - it is estimated that he will share 15% of his time on this particular project
Logistics Team Leader - Goma | 15% | Supervise all logistic acitvities in Massisi and Nyragongo territory (Fleets, purchase, warehouse) - shares his time between different projects implemented in the area.
Safety Officer - Beni | 15% | Analyses security and safety situation, provides information to the SA and advise the AM Beni. He is also work on access and acceptance with communities and armed groups - shares his time between different projects implemented in the area.
Warehouse Assistant - Béni | 15% | Does all necessary activties to ensure stocks management and compliancy - shares his time between different projects implemented in the area.
Drivers - Goma, Beni, Kin | 15% | Share their time between different projects implemented in the area, supporting both programme and support activties.
Cook Beni | 15% | Shares his time between different projects implemented in the area.
Supports Staff Office and Guest (cleaners, gardners - Goma/Beni) | 15% | Guest House and Offices cleaners, garders for both Béni, Goma and Country Office - shares his time between different projects implemented in the area.
3 M&E agents | 100% | Implement qualitative and quantitative monitoring of the projects, including partners project - They will be all dedicated to the project
10 Construction field agents (service contract for 45 days only) | 100% | Supervise cash for work activities.