PBF PROJECT progress report

COUNTRY: SUDAN

TYPE OF REPORT: annual

YEAR of report: November 2020

| Project Title: East Darfur: Assalaya-Sheiria-Yassin Triangle of Peace and Coexistence Project Number from MPTF-O Gateway: PRF 00119469 |
| --- |
| If funding is disbursed into a national or regional trust fund: Country Trust Fund Regional Trust Fund Name of Recipient Fund: PBF | Type and name of recipient organizations: RUNO UNDP (Convening Agency) RUNO UNICEF RUNO UNHCR RUNO FAO |
| Date of first transfer: 16 January 2020 Project end date: 31 December 2021 Is the current project end date within 6 months? No |
| Check if the project falls under one or more PBF priority windows: Gender promotion initiative Youth promotion initiative Transition from UN or regional peacekeeping or special political missions Cross-border or regional project |
| Total PBF approved project budget (by recipient organization): Recipient Organization Amount UNDP $1,565,022.65 UNHCR: $1,091, 400 UNICEF: $999,999.98 FAO: $1,095,972.41 Total: $4,752,395.04 Approximate implementation rate as percentage of total project budget: 18% *ATTACH PROJECT EXCEL BUDGET SHOWING CURRENT APPROXIMATE EXPENDITURE* Gender-responsive Budgeting: Indicate dollar amount from the project document to be allocated to activities focussed on gender equality or women’s empowerment: $1,531,711.11 Amount expended to date on activities focussed on gender equality or women’s empowerment: $250,664 |
| Project Gender Marker: GM2 Project Risk Marker: High Project PBF focus area: 2, 3 Conflict Prevention/Management |
| Report preparation: Project report prepared by: UNDP Project report approved by: RCO Did PBF Secretariat review the report: PBF Secretariat not yet in place. |

PART 1: OVERALL PROJECT PROGRESS

Briefly outline the status of the project in terms of implementation cycle, including whether preliminary/preparatory activities have been completed (i.e. contracting of partners, staff recruitment, etc.) (1500-character limit):

Despite challenges due to COVID-19, which saw activities come to a halt for over five months, implementation of the PBF project in East Darfur is now progressing under all three outcomes. All preliminary activities have been completed, including stakeholder engagement and sensitisation, coordination meetings with government officials, recruitment of project staff, and contracting of Implementing Partners (IPs). With the relaxation of COVID-19 restrictions in August 2020, project implementation commenced at an enhanced pace. The enumerator trainings for the baseline survey are completed and data collection will commence in the coming weeks. Coordination with FAO and UN-Habitat needs to be strengthened moving forward.

Aside from pandemic-related constraints, intercommunal clashes and tensions between farming and nomadic communities were prevalent in Yassin and Sheria localities. In March 2020, for example, members of the nomadic Reizegat tribe clashed with members of the sedentary Birgid at Esheraya village in Yassin locality over a land dispute. In retaliation, individuals aligned to the Reizegat tribe set fire to a local market. Government security forces intervened and managed to contain the situation from further escalation. In April 2020, in Sheria locality, farmers clashed with herders over crop destruction. The Sudan Armed Forces (SAF) intervened and diffused the tensions. These incidents demonstrate the need for community-level conflict resolution mechanisms in the target locations, which this project aims to address. The incidents also show the need for effective rule of law in areas with high levels of inter-communal hostility, which this project aims to strengthen through institutional and capacity building support to local police.

At the national level, on 03 October 2020, the Transitional Government of Sudan and the Sudan Revolutionary Front (which is a coalition of armed opposition groups, including the Sudan Liberation Front-Minni Minawi, or SLF-MM) signed the Juba Peace Agreement. The Agreement presents an opportunity to address longstanding grievances, including at the locality- and community-levels, through the transition process. Consisting of region-specific protocols, the Agreement is a chance to address prevalent conflict drivers and strengthen ongoing peacebuilding efforts in Darfur. Though the Sudan Liberation Front-Abdul Wahid (SLF-AW) has not signed the Juba Peace Agreement, the SLF-AW has minimal influence in East Darfur.

Please indicate any significant project-related events anticipated in the next six months, i.e. national dialogues, youth congresses, film screenings, etc.  (1000-character limit):

Baseline survey: IOM is conducting field missions to to Assalaya, Sheria, and Yassin localities for sensitisation and preparation of baseline data collection in the coming weeks. UNHCR has contracted the Joint IDP Profiling Service organisation (JIPS) under the Durable Solutions Information Management Working Group to assist with the development of tools for the baseline. UNDP has contracted the NGO, SUDIA, to conduct undertake qualitative data collection (i.e. key informant interviews (KIIS).

Peace conference: Locality- and state-level peace conferences will be held with the participation of community leaders, community-based resolution mechanisms (CBRMs), internally displaced persons (IDPs), nomads, rule of law actors, civil society, peacebuilding institutions, and federal-level peacebuilding entities.

Peace dialogues: Community- and locality-level peace dialogue forums will be held with the participation of community members, native administrations, rule of law actors, and other peacebuilding stakeholders in the locality.

FOR PROJECTS WITHIN SIX MONTHS OF COMPLETION: summarize the main structural, institutional or societal level change the project has contributed to. This is not anecdotal evidence or a list of individual outputs, but a description of progress made toward the main purpose of the project. (1500-character limit):

N/A

In a few sentences, explain whether the project has had a positive human impact. May include anecdotal stories about the project’s positive effect on the people’s lives. Include direct quotes where possible or weblinks to strategic communications pieces. (2000-character limit):

Since the project is in early stages of implementation, human impact will be assessed in the next reporting period.

PART II: RESULT PROGRESS BY PROJECT OUTCOME

Outcome 1: Durable solutions for the return of IDPs and refugees and the residents are made possible by peaceful resolution of land disputes, and sustainable land and natural resource management facilitates enhanced agricultural productivity, processing and value-chains to create jobs and improve livelihoods.

Rate the current status of the outcome progress: Off track

Progress summary: (3000-character limit)

UNDP signed an implementation agreement with the international NGO, ZOA Sudan, in East Darfur. ZOA Sudan will address land-related issues, which are key drivers of conflict in Assalaya, Sheria, and Yassin localities, by building government capacity to resolve land disputes at the locality level and developing a Locality Action Plans. ZOA Sudan will also implement activities to develop the vocational skills of at-risk youth and income generating activities for women, as well as support the development of natural resource management plans. Funds have been disbursed to the IP and implementation has commenced.

UNHCR has contracted ZOA Sudan, as well American Refugee Committee (ARC). Both IPs are making progress on conducting community consultations and forming community-based protection committees, with a 47 percent target of women members. The consultations have helped to raise community awareness on the planned activities and contributed to community anticipation of the project. Members of the community-based protection networks have been trained in protection principles and mechanisms, identification of vulnerable persons, referral pathways, and case management.

Though delayed, during the reporting period, progress was made on the baseline survey, which comprises a household survey (led by IOM) and key informant interviews (led by the NGO, SUDIA). The baseline survey is a key component of the five Darfur-wide PBF projects and will provide an evidence-base to inform and advance the work of PBF partners across Darfur. The conduct of the baseline survey was communicated to local authorities through the National Peace Commission and the Ministry of Federal Governance.

In the first week of October, the Joint IDP Profiling Service (JIPS), contracted by UNHCR, designed and facilitated a remote Training of Trainers for IOM team leaders who will lead data collection at the field-level. From 27 to 31 October 2020, IOM trained 105 enumerators, including 25 from East Darfur (10 women; 15 men). IOM is administering the household survey on a sample of 12,000 households selected from the eight localities targeted by PBF, representing a random sample of IDPs, nomads, returnees, and host communities. Initial analysis of this data by JIPS is due late December 2020 and will cover the baseline for the outcome indicators and the area-based durable solutions analysis.

Indicate any additional analysis on how Gender Equality and Women’s Empowerment and/or Youth Inclusion and Responsiveness has been ensured under this Outcome: (1000-character limit)

The project engaged national NGOs that are rooted in the local communities and have previously promoted gender equality and women’s empowerment in a limited capacity. In addition, in August 2020, UNDP recruited a PBF Gender Officer whose mandate include strengthening the gender component in the PBF project across all five Darfur states. At the operational level, this project takes into consideration gender issues in the context of land-based conflict, therefore including gender-inclusive land consultations. The project also includes entrepreneurial opportunities for both women and youth.

The project intends to ensure the inclusion of women, boys, and girls in all the planned activities including: data collection efforts that will inform the development of Locality Action Plans for durable solutions; the community support projects that will be implemented to enable peaceful co-existence and conflict resolution; the civil documentation services that will be delivered; and the community reconciliation committees that will be established, trained ,and technically supported. The project will also ensure age and gender disaggregated reporting. Furthermore, all community consultations, as well as the community-based protection networks that have been established, have involved women and youth to ensure both equality and inclusion.

With regards to data collection, IOM is in the process of hiring more female enumerators to lay the foundation for greater inclusion of gender sensitivity and gender equality throughout the project. The project will also build the capacity of male enumerators for gender responsiveness

Outcome 2: Good governance is instituted at locality level and confidence of people built: freedom of movement and physical security is taken for granted by men and women and the rule of law is perceived to be applied without fear or favour; quality basic services are accessible to all, and all feel a stakeholder to their provision

Rate the status of the outcome progress: Off track

Progress summary: (3000-character limit)

UNDP is in the early stages of promoting responsive security and justice institutions. During the reporting period, a bill of quantities (BoQ) was developed and designs for the civil works  (i.e. police posts and rural court) were formulated in consultation with the Sudan Police Force (SPF) and the local judiciary, including securing land ownership documents and end-user approvals. The procurement process for construction companies is at an advanced stage and work will start upon receipt of the second tranche of PBF funds.

Specific geographic locations have been identified to drill boreholes for improved drinking water supply and basic sanitation for IDPs, returnees, and local communities. Members of the different communities, including women and youth, have expressed willingness to support management of water supply, share knowledge on hygiene, and install services accessible for disabled individuals, thus allowing all groups to use the water and sanitation services.

Indicate any additional analysis on how Gender Equality and Women’s Empowerment and/or Youth Inclusion and Responsiveness has been ensured under this Outcome: (1000-character limit)

This project promotes the recruitment of women as police officers and social workers, inclusion of women in community governance structures as decision makers, training on gender equality, and diversity and gender-responsive policing in the curriculum of the Darfur Police Academy and training of police. UNDP has partnered with the national NGO, Relief and Mediation Corps (REMCO), which has extensive experience working with women and girls in East Darfur.

The water sources to be rehabilitated or established will involve inclusion of women in water user committees to manage the supply and distribution of water across the different community members.

Outcome 3: A culture of peace and rights is nurtured and sustained in Darfur by a vibrant civil society with the commitment and capacity to represent the interests of all stakeholders in the resolution of disputes, and in holding Government to account for maintenance of the social contract

Rate the current status of the outcome progress: Off track

Progress summary: (3000-character limit)

UNDP signed an implementation agreement with the national NGO, National Initiative Development Organization (NIDO), to improve the functionality of community-based reconciliation mechanisms (CBRMs), build CBRMs networks across Darfur, and link them to state and national-level peace architecture. This project will build on NIDO’s prior experience in this field with UNDP on other funding streams. Another IP, REMCO, was contracted to focus on strengthening civil society mechanisms for the protection of women and girls and empowerment of women. The partner has received funds and community engagements has started.

Through its implementing partners, American Refugee Committee and ZOA Sudan, UNHCR supported the establishment of six Community-based Protection Network (CBPN) in three East Darfur localities with 45 persons (21 women and 24 men) in Shanabla and Jakhara villages in Sharia locality; Al-Fado and Ma’ali villages in Asalaya locality and Om-elkhirat and Baraka villages in Yassin locality.

They have also been able to identify 150 vulnerable adults (81 female; 69 male), as well as 50 children (23 girls; 27 boys) who have been assisted in the birth registration process.

Members of the existing community-based child protection network prepared lists of services required in the villages to improve the education system, including school supplies and school construction and rehabilitation. They also identified schools in which to establish Parents Teacher Associations (PTAs) involving both men and women, and IDP communities in which to provide technical and vocational training.

Local labour will be encouraged, where possible, during the rehabilitation and construction of community infrastructure, such as schools and women centres. Women will also be supported to participate, with schedule adjustments made to accommodate their traditional household chores and to prevent from overburdening them.

Indicate any additional analysis on how Gender Equality and Women’s Empowerment and/or Youth Inclusion and Responsiveness has been ensured under this Outcome: (1000-character limit)

The project ensures women, girls, and boys are part of the decision-making processes in the CBRMs. In addition, women’s and youth organisations will be trained on human rights-based approaches. Women’s participation in Parents Teachers Associations (PTAs) will be supported, with special attention to advocating for and advancing their aspirations to leadership positions within these forums.

The protection committees set up by UNHCR include youth participants, as well as women.

PART III: CROSS-CUTTING ISSUES

| Monitoring: Please list monitoring activities undertaken in the reporting period (1000-character limit) | Do outcome indicators have baselines? NO Has the project launched perception surveys or other community-based data collection? NO A revised results framework for the project has been developed and shared with PBSO. A gender sensitive baseline survey is currently in progress with all the data collection tools now developed and over 60% of household respondents are expected to be women Data collection tools were completed. These tools included gender-related questions on current workload for women, impact of conflict on women and girls, access to land, education, protection (sexual and gender-based violence), economic opportunities and women rights. IOM will collect quantitative data while Sudanese Development Initiative (SUDIA), a national organisation contracted by UNDP, will collect qualitative data. Focus group discussions with women only will be constituted to discuss women related issues and the impact of the conflict on women including protection related issues. |
| --- | --- |
| Evaluation: Has an evaluation been conducted during the reporting period? No | Evaluation budget (response required): $70000.00 If project will end in next six months, describe the evaluation preparations (1500-character limit): N/A |
| Catalytic effects (financial): Indicate name of funding agent and amount of additional non-PBF funding support that has been leveraged by the project. | Name of funder: Amount: UNAMID/SLF $1,622,817 SLF focuses on 1) providing multisectoral support, including to traditional mechanisms to resolve communal conflicts as well as root causes of conflicts, 2) protect return areas and support for community-level conflict resolution and prevention platforms, 3) set up and operationalize the land management mechanism 4) supporting the re-establishment of the criminal justice institutions building the capacity of these institutions 5) to strengthen the capacity of the police, rural courts to address land disputes and other inter-communal conflict drivers, 6) Community-based protection, protection and returnee monitoring, awareness raising on protection and protection coordination; 7) institutional strengthening of Ministry of Social Welfare; 8) reintegration assistance for refugee returnees. CERF $915,579 CERF is laying a foundation and ensuring that durable solutions for the internally displaced persons and refugees are prioritized to enhance peace and social stability, and peaceful coexistence among the targeted communities. This includes setting land conflict management system in place to accommodate further influx of returnees or displaced people; help IDPs restore their lifestyle, as well as to support local communities to welcome new or returning members of the community. Implementation of micro-projects aimed at mitigating, preventing, and addressing conflict triggers between different communities and tribes to ensure peaceful co-existence; enhancing community-based protection focusing on durable solutions planning; community-based protection networks; support for persons with specific needs (case management & referral, paralegal aid, youth networks, micro-projects to address conflict triggers). |
| Other: Are there any other issues concerning project implementation that you want to share, including any capacity needs of the recipient organizations? (1500-character limit) | COVID-19 has delayed the implementation of activities under the project from March to August 2020 due to state government measures and directives in place that restricted movement between states and localities, banned all public gatherings making it difficult to conduct capacity building activities, and imposed curfews and granting of paid leave to all government employees except for those working in health and water sectors. However, the government has now relaxed COVID-19 restrictions and project activities have since commenced at an enhanced pace In addition, given the rainy season between the months of July and October, roads and communities were often inaccessible and sometimes flooded. Damaged and flooded roads have also led to a severe shortage of fuel, further hampering the ability of vehicles and staff to travel to the various localities to implement the activities. |

PART IV: COVID-19

Please respond to these questions if the project underwent any monetary or non-monetary adjustments due to the COVID-19 pandemic.

- Monetary adjustments: Please indicate the total amount in USD of adjustments due to COVID-19:

$0

- Non-monetary adjustments: Please indicate any adjustments to the project which did not have any financial implications:

None

- Please select all categories which describe the adjustments made to the project (and include details in general sections of this report):

☐ Reinforce crisis management capacities and communications

☐ Ensure inclusive and equitable response and recovery

☐ Strengthen inter-community social cohesion and border management

☐ Counter hate speech and stigmatization and address trauma

☐ Support the SG’s call for a global ceasefire

☒ Other (please describe): No adjustments done

If relevant, please share a COVID-19 success story of this project (i.e. how adjustments of this project made a difference and contributed to a positive response to the pandemic/prevented tensions or violence related to the pandemic etc.)

PART IV: INDICATOR BASED PERFORMANCE ASSESSMENT

Using the Project Results Framework as per the approved project document or any amendments- provide an update on the achievement of key indicators at both the outcome and output level in the table below (if your project has more indicators than provided in the table, select the most relevant ones with most relevant progress to highlight). Where it has not been possible to collect data on indicators, state this and provide any explanation. Provide gender and age disaggregated data. (300 characters max per entry)

|  | Performance Indicators | Indicator Baseline | End of project Indicator Target | Indicator Milestone | Current indicator progress | Reasons for Variance/ Delay (if any) |
| --- | --- | --- | --- | --- | --- | --- |
| Outcome 1 Durable solutions for the return of IDPs and refugees and the residents are made possible by peaceful resolution of land disputes, and sustainable land and natural resource management facilitates enhanced agricultural productivity, processing and value-chains to create jobs and improve livelihoods | Indicator 1.1 Percentage of community members reporting improved socio-economic conditions (social cohesion and economic opportunities) in their locality. Disaggregated by sex and age | TBD | TBD | None yet | The baseline survey has commenced with IOM and SUDIA conducting Enumerator trainings. Field missions to Assalaya, Sheria and Yassin localities will take place to prepare for the data collection commencing in the following weeks. IOM and UNHCR have engaged Joint IDP Profiling Service organisation (JIPS) under the Durable Solutions Information Management Working Group to assist with baseline tools development. UNDP-engaged SUDIA will undertake qualitative data collection. | COVID-19 pandemic government and UN Country Team restrictions |
|  | Indicator 1.2 Increase in the extent to which local communities support the return and/or peaceful integration and continued presence of forcibly displaced persons and report positive interactions. Disaggregated by sex and age | TBD | TBD | None yet | The baseline survey has commenced with IOM and SUDIA conducting Enumerator trainings. Field missions to Assalaya, Sheria and Yassin localities will take place to prepare for the data collection commencing in the following weeks. IOM and UNHCR have engaged Joint IDP Profiling Service organisation (JIPS) under the Durable Solutions Information Management Working Group to assist with baseline tools development. UNDP-engaged SUDIA will undertake qualitative data collection. | COVID-19 pandemic government and UN Country Team restrictions |
|  | Indicator 1.3 Percentage of community members across all groups in the target areas reporting improved access to legal documentation and livelihood opportunities disaggregated by sex and age | TBD | TBD | None yet | The baseline survey has commenced with IOM and SUDIA conducting Enumerator trainings. Field missions to Assalaya, Sheria and Yassin localities will take place to prepare for the data collection commencing in the following weeks. IOM and UNHCR have engaged Joint IDP Profiling Service organisation (JIPS) under the Durable Solutions Information Management Working Group to assist with baseline tools development. UNDP-engaged SUDIA will undertake qualitative data collection. | COVID-19 pandemic government and UN Country Team restrictions |
| Output 1.1 Government capacities built for resolution of land issues at Locality level, and Locality Action Plans produced | Indicator 1.1.1 Percentage of land institutions with improved arbitration, registration & sketch mapping capacities to deliver on their mandate | 15% | 60% | None yet | UNHABITAT will soon engage a national NGO to undertake activities under this output. Stakeholder engagements have been done and first staff workshops held in Al Fashir in October to improve understanding of the project. Engagement with communities and government has commenced. The participants were trained on STDM GIS, sketch Mapping and Land electronically registration. UNDP engaged an international NGO ZOA to undertake activities under this output and funds have been disbursed. | COVID-19 pandemic government and UN Country Team restrictions |
|  | Indicator 1.1.2 Number of inclusive stakeholder consultations on land reforms for drafting land legislation | 2 | 6 | None yet | An international NGO named ZOA was engaged to undertake activities under this output and funds have been disbursed. Stakeholder engagements have been done and first staff workshops held to improve understanding of the project. Engagement with communities and government has commenced. | COVID-19 pandemic government and UN Country Team restrictions |
| Output 1.2 Planning for durable solutions informs Locality Action Plans | Indicator 1.2.1 Number of inclusive locality Action Plan for durable solutions developed based on disaggregated data in target locations | 0 | 3 | None yet | Joint IDP Profiling Service organisation (JIPS) designed and facilitated a remote Training of Trainers targeting IOM team leaders. IOM conducted training for 25 enumerators (10 women; 15 men) in East Darfur. IOM will conduct field missions in the 3 localities sensitizing communities on the upcoming baseline data collection. JIPS will develop the action plans based on the DS analysis (it will be interagency/collaborative process) |  |
|  | Indicator 1.2.2 # of community support projects identified, implemented, and utilized by the community | 0 | 8 | None yet | UNHCR/ZOA conducted meeting with 46 members from the local community – local leaders, youth, men, women + elderly. Relations between pastoralists and agro-pastoralists are generally good, minimal conflicts during the rainy season. A local committee of farmers and nomads exist, that mitigate conflict to an effective degree. Improved access to drinking water was considered top priority for the people in Baraka and to encourage returnees to re-settle. |  |
| Output 1.3 Locality-level Land and Natural Resource Management Plans prepared on an inclusive and participatory basis | Indicator 1.3.1 Number of IDPs, returnees, host communities and nomads participating within community-based resolution mechanisms | 10 | 120 (20% female, 15% youth) 120 (20% female, 15% youth) | None yet | An international NGO ZOA was engaged to undertake activities under this output and funds have been disbursed. Stakeholder engagements have been done and first staff workshops held to improve understanding of the project. Engagement with communities and government has commenced. |  |
|  | Indicator 1.3.2 Number of community initiatives jointly planned by nomads and farmers, used and managed including livestock migratory routes, water resources and veterinary services | 0 | 3 community initiatives | None yet | An international NGO ZOA was engaged to undertake activities under this output and funds have been disbursed. Stakeholder engagements have been done and first staff workshops held to improve understanding of the project. Engagement with communities and government has commenced. |  |
| Outcome 2 Good governance is instituted at locality level and confidence of people built : freedom of movement and physical security is taken for granted by men and women and the rule of law is perceived to be applied without fear or favour; quality basic services are accessible to all, and all feel a stakeholder to their provision. | Indicator 2.1 Percentage of community members reporting a perceived decrease in levels of violence within and between communities and groups, including a decrease in GBV and violations of rights of the child. Disaggregated by sex and age | TBD | 40% | None yet | The baseline survey has commenced with IOM and SUDIA conducting Enumerator trainings. IOM and UNHCR have engaged Joint IDP Profiling Service organisation (JIPS) under the Durable Solutions Information Management Working Group to assist with baseline tools development. UNDP-engaged SUDIA will undertake qualitative data collection. |  |
|  | Indicator 2.2 Percentage of community members reporting increased satisfaction with informal and formal rule of law mechanisms/ initiatives. Disaggregated by sex and age | TBD | 40% | None yet | The baseline survey has commenced with IOM and SUDIA conducting Enumerator trainings. IOM and UNHCR have engaged Joint IDP Profiling Service organisation (JIPS) under the Durable Solutions Information Management Working Group to assist with baseline tools development. UNDP-engaged SUDIA will undertake qualitative data collection. |  |
|  | Indicator 2.3 Percentage of community members reporting satisfaction with equitable access to quality basic social services. Disaggregated by sex and age | TBD | 40% | None yet | The baseline survey has commenced with IOM and SUDIA conducting Enumerator trainings. IOM and UNHCR have engaged Joint IDP Profiling Service organisation (JIPS) under the Durable Solutions Information Management Working Group to assist with baseline tools development. UNDP-engaged SUDIA will undertake qualitative data collection. |  |
| Output 2.1 Governance system reinforced at the local level | Indicator 2.1.1 Percentage of functional local governance forums advocating for policy change, social accountability and inclusion of women and youth in leadership positions | 10% | 45% | None yet | Government institutions have been consulted for the establishment of functional governance forums which will include all groupings including women and youth with a 35% women target. The capacity and composition of these forums will be strengthened and reformulated respectively in the next reporting period |  |
|  | Indicator 2.1.2 Percentage of authorities adopting the developed guidelines for effective mandate delivery | 0% | 10% | None yet | Local government authorities were engaged, and a consultant will be contracted to work with the local government at state and locality level to develop the guidelines for effective mandate delivery |  |
| Output 2.2 Responsive security and justice institutions promoted through increasing their presence, capacities, and service-oriented culture | Indicator 2.2.1 Number of functional police posts established to increase SPF presence in target communities Number of functional police posts established to increase SPF presence in target communities | 4 | 6 | None yet | State-level Sudanese Police Force (SPF) engaged, villages identified, land documents and end-used approvals secured. Designs, bill of quantities, developed for the new Police post and approved by SPF. Procurement process has commenced for contractors to build the infrastructure. |  |
|  | Indicator 2.2.3 Number of paralegals CSO members and native administration members with improved capacity in legal awareness | 0 | 60 | None yet | Activity will commence in the next reporting period. |  |
| Output 2.3 Increased access to equitable quality basic services | Indicator 2.3.1 Percentage of out of schoolgirls, boys and adolescents across diverse target groups accessing formal and informal education with direct support from the project | TBD | 80% (50 % girls) | None yet | Target geographical locations and schools have been jointly selected in a bottom up participatory approach to provide quality and equitable education, alternative learning and life skills services to children and adolescent of IDPs, returnees and local communities with the participation of women and girls since they are affected most.. | COVID-19 pandemic government and UN Country Team restrictions |
|  | Indicator 2.3.2 Number of girls, boys, women and men from diverse community groups having access to safe drinking water and sanitation | TBD | 20,000 (as a % of the population) | None yet | Target geographical locations have been jointly selected by all population groups including women and youth in a bottom up participatory approach to provide equitable and sustainable access to improved drinking water facilities and basic sanitation facilities for IDPs, returnees and local communities. | COVID-19 pandemic government and UN Country Team restrictions |
| Output 2.4 Improved management and delivery of basic services in a responsive, accountable and inclusive way | Indicator 2.4.1 Number of Education officials and PTA members reporting a greater understanding of the theory and practice of conflict sensitivity and peacebuilding | 0 | 10 education officials, 200 PTA members (at least 40% female) | None yet | Ministry of Education has Teacher Training Institutions with full capacity to implement the capacity building for Teachers and PTA members. A defined number of education service providers and PTA members was identified for planning purposes to be trained on conflict sensitivity and peacebuilding. The actual members are yet to be selected by community members and school authorities | COVID-19 pandemic government and UN Country Team restrictions |
|  | Indicator 2.4.2 Percentage of community members (men and women) who perceive the water committees as an effective mechanism in resolving tensions and disputes about water | TBD | 70% (at least 40% women) | None yet | Discussions are being conducted with the community members including women, youth and government line ministries to enhance the capacity of water committees to play critical role in the process of resolving tensions and disputes about water and intensify awareness creations to the community about role of water committees mechanism. | COVID-19 pandemic government and UN Country Team restrictions |
| Outcome 3 A culture of peace and rights is nurtured and sustained in Darfur by a vibrant civil society with the commitment and capacity to represent the interests of all stakeholders in the resolution of disputes, and in holding Government to account for maintenance of the social contract | Indicator 3.1 % of disputes over land, water and other resources, identified by the community as affecting the return and integration of forcibly displaced persons, settled through peaceful means (e.g. CBRMs and committees) in target localities | TBD | TBD | None yet | The baseline survey has commenced with IOM and SUDIA conducting Enumerator trainings and data collection will start in the following week. UNHCR has engaged Joint IDP Profiling Service organisation (JIPS) under the Durable Solutions Information Management Working Group to assist with baseline tools development. UNDP-engaged SUDIA will undertake qualitative data collection. |  |
|  | Indicator 3.2 Numbers of key stakeholders – women, children and youth, returnees – with peacebuilding competencies and engaged in initiatives to effect meaningful change at the community level. | TBD | TBD | None yet | The baseline survey has commenced with IOM and SUDIA conducting Enumerator trainings and data collection will start in the following week. UNHCR has engaged Joint IDP Profiling Service organisation (JIPS) under the Durable Solutions Information Management Working Group to assist with baseline tools development. UNDP-engaged SUDIA will undertake qualitative data collection. |  |
|  | Indicator 3.3 Increase in the confidence of civil society and community members that opportunities exist for them to work with government to encourage greater accountability and collaboration. Disaggregated by sex and age | TBD | TBD | None yet | The baseline survey has commenced with IOM and SUDIA conducting Enumerator trainings and data collection will start in the following week. UNHCR has engaged Joint IDP Profiling Service organisation (JIPS) under the Durable Solutions Information Management Working Group to assist with baseline tools development. UNDP-engaged SUDIA will undertake qualitative data collection. |  |
| Output 3.1 Community-based reconciliation mechanisms (CBRMs) functioning, networked across Darfur, and linked to State and National-level peace architecture | Indicator 3.1.1 Number of functional community-based resolution mechanisms (CBRM) in place | 1 (90% Male, 10% youth) | 15 (of which 30% female and 30% male Youth) | None yet | Communities in the three localities have identified the need for strong community-based resolution mechanisms and the project is working towards that. Women and youth advocated for their inclusion in these community-based resolution mechanisms and this will be considered as the CBRMs are formed A national NGO named National Initiative Development Organization (NIDO) was engaged by UNDP as a partner for this output. They have received tranche 1 funds and implementation has commenced starting with identifying CBRMs and their composition |  |
|  | Indicator 3.1.2 Number of community members actively participating in different peace initiatives (dialogue & conference) disaggregated by gender and age | 0 | 210 community members (15% women; 20% youth) | None yet | Communities identified the need for peace initiatives and the project is working towards that. Women and youth will be included in community dialogues and conferences in the coming reporting period A national NGO named Relief and Mediation Corps (REMCO) was engaged by UNDP as a partner for this output. They have received tranche 1 funds and implementation has commenced | COVID-19 government restrictions |
| Output 3.2 Civil society mechanisms for protection of women and girls strengthened, and women empowered to claim rights and redress and participate equally in public affairs and community peacebuilding | Indicator 3.2.1 Number of community members sensitized on women’s rights (disaggregated by gender & age) | 0 | 210 (65% women; 40% youth) | None yet | Communities identified the need for peace initiatives and the project is working towards that. Women and youth will be included in community dialogues and conferences in the coming reporting period A national NGO named Relief and Mediation Corps (REMCO) was engaged by UNDP as a partner for this output. They have received tranche 1 funds and implementation has commenced | COVID-19 government restrictions |
|  | Indicator 3.2.2 Number of targeted community members in functional community schemes disaggregated by age and gender | 10 | 200 (60% women, 50% youth) | None yet | Communities identified the need for peace initiatives and the project is working towards that. Women and youth will be included in community dialogues and conferences in the coming reporting period A national NGO named Relief and Mediation Corps (REMCO) was engaged by UNDP as a partner for this output. They have received tranche 1 funds and implementation has commenced | COVID-19 government restrictions |
| Output 3.3 Protection and rights of children respected, and young people capacitated for advocacy and peacebuilding | Indicator 3.3.1 Percentage of children/youth in the youth center catchment area that have benefitted from the youth center services | 0 | 80% (40% girls/young females) Disaggregated by age/gender | None yet | The State Council for Child and social welfare office has been engaged and identified and agreed on youth center, and Family and Child Protection Units to be constructed from the targeted localities and the package of interventions set to benefit children and youth inside centres | Evolving COVID 19 pandemic and movement restriction |
|  | Indicator 3.3.2 Number of inclusive youth initiatives designed, and implementation plans developed that incorporate peacebuilding and conflict sensitivity approaches | 0 | 6 youth-led peacebuilding plans developed (2 led by female youth) | None yet | Engagement with youth and adolescents have been undertaken and agreed on interventions to contribute on peacebuilding, members of Community Based Child protection Networks, and youth committee at village level will be represented during project implementation. | Evolving COVID 19 pandemic and movement restriction |
| Output 3.4 IDP and returnee communities in Darfur enhance their capacities and mechanisms to secure their rights, strengthen their protection and engage in sustained peacebuilding. | Indicator 3.4.1 Number of functional community-based protection networks, including women networks, applying AGDM and human rights approaches | 0 | 9 | None yet | Six Community-based Protection Network (CBPN) were established in three East Darfur localities with 45 persons (21 women and 24 men) in Shanabla and Jakhara villages in Sharia locality; Al-Fado and Ma’ali villages in Asalaya locality and Om-elkhirat and Baraka villages in Yassin locality the CBPNs will be contributing and playing strong role in addressing some of the protection issues at the community level. In Yassin, UNHCR/ARC was able to identify 150 PSNs 81 women; 69 men) for assistance and 50 children (23 girls; 27 boys) for birth registration process |  |
|  | Indicator 3.4.2 % of individuals, disaggregated by age and gender, received paralegal assistance and referral mechanisms support | 0 | 5% of targeted population | None yet | UNICEF completed the selection of the implementing partner for the project. A program document is being developed by United Peace Organisation (UPO) and UNICEF with detailed project activities and timeframe referring to the PBF result framework. The implementation of the project activities will start soon in three targeted localities. Discussions are ongoing to implement some of the PBF activities through government line ministries to enhance the government's engagement |  |