## OVERALL REPORTING INSTRUCTIONS
OVERALL INSTRUCTIONS
1 | All questions/sections must be responded to before submitting to secretariat. Once the document is uploaded in the relevant folder (as per instruction below) please email the secretariat.
2 | To ensure high quality narrative and results reports please pay attention to the following details: a) Report must be a well-written, succinct summary about what was done during the reporting period and results achieved, prioritizing on concrete activities, beneficiaries reached, and achievements beyond processes; b) Report must be factual and evidence-based against the outcome and output indicators presented in the original project document; c) In case certain indicators are no longer relevant, report must provide an explanation therefor; d) Report must explicate how it is in line with the overall SERP joint workplan and its relation to the global-level SERP indicators; e) Report must indicate the relevant SERP monitoring framework global indicators that were contributed to as part of this project; f) Report must include a honest analysis of challenges faced, the responses to these challenges, and the extent to which these responses were successful or unsuccessful; g) Reporting must go beyond the generic, standard and well-documented features of successful project implementation when reflecting on innovation and focus on what is truly new for you and what could enable replication efforts.
3 | Please complete and submit this workbook by uploading it in the relevant Project Folder here (https://undp.sharepoint.com/:f:/r/sites/covid19mptfcall1/Shared%20Documents/2020-REPORT?csf=1&web=1&e=j3cc3J). If you are unsure of your project number, please refer to http://mptf.undp.org/factsheet/fund/COV00
A | ANNUAL REPORT
DEADLINE: 31st of January 2021
4 | Complete annual report must be submitted for ALL projects receiving funds in 2020. HOWEVER, if your project ends on the 31st of December 2020, your FINAL report is your annual report.
5 | If you received a no-cost extension for your project, please provide an annual report. You may update the annual report in a few months time to include activities to complete your end of project report.
6 | Please make sure you use the RBM framework for your report here as per your approved Prodoc.
B | END OF PROJECT - FINAL REPORT
DEADLINE: 31st of January 2021
7 | Complete annual report must be submitted for ALL projects receiving funds in 2020. HOWEVER, if your project ends on the 31st of December 2020, your FINAL report is your annual report.
8 | Please make sure you use the RBM framework for your report here as per your approved Prodoc.

## General Information-Annual
Programme Title & Project Number |  | Programme Duration
Programme Title: | Protecting People: Supporting the Government of Indonesia and Key Stakeholders to Scale Up Inclusive Social Protection Programmes in Response to COVID-19 | Overall Duration (months) | 10 months
Programme Number (if applicable) |  | Start Date (dd.mm.yyyy) | 01.05.2020
MPTF Office Project Reference Number: | 121443 | Original End Date (dd.mm.yyyy) | 31.12.2020
Country | Indonesia | Current End date(dd.mm.yyyy) | 31.03.2021
Recepient UN Organizations |  | Implementing Partners
Organizations receiving direct funding from the MPTF Office under this programme | UNICEF, UNDP, WFP, and UN WOMEN | National counterparts (government, private sector, NGOs, & others) and other International Organizations | BAPPENAS, Ministry of Social Affairs, Ministry of Agriculture, Ministry of Finance, Ministry of Women Empowerment and Child Protection, Ministry of Villages, Development of Disadvantaged Regions, and Transmigration, CARE Indonesia, University of Indonesia, University of Padjajaran, and Bogor Agriculture Institute
Report Cleared by
o Name: | Valerie Julliand
o Title: | Residence Coordinator
o Email address: | valerie.julliand@un.org
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the Secretary-General's Designate
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Annual
# | Questions | Guidance to Respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results as well as any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum). | From May to December 2020, under the leadership of UN Resident Coordinator, UNDP, UNICEF, WFP, and UN WOMEN are supporting the government in rolling out social protection programmes that are more effective (reaching the most vulnerable with limited inclusion and exclusion errors) and truly inclusive (leaving no one behind). There are at least four main strategic results that were achieved in 2020: First, the UN played the key roles behind the national programme namely Unified Database Update (UNICEF-UNDP). This database registers the bottom 40% of populations eligible for social protection programme in Indonesia. The UN advocated the registration of homeless people and/or people without formal registration to the database. The UN also promoted inclusive approach during the update of the database by involving the community in the nomination and validation of the beneficiaries for social protection programme. This initiative would ensure no one is left behind. The support has also facilitated the government to develop the Standard Operating Procedures (SOP) for the Grand Design of Socio-Economic Registration for Social Protection. This SOP will be the reference for the government to improve the coverage of social protection programme from 40% to 60%. Secondly, in other initiative, the UN strengthened the expenditure tracking mechanism both at national and sub-national levels by providing better information on the analysis of public funding for children–one of the population groups with the highest risk of exclusion from social protection. Thirdly, as part of the innovative data analysis, WFP strengthened the methodology of VAMPIRE, a cloud-based Platform of risk and vulnerability assessment related to climate hazard by combining near real-time evidence of vulnerability and socio-economic impact of the current and future pandemics. This would allow monitoring and analysis on the vulnerability and impact caused by the pandemic. Fourthly, the UN advocated to ensure that the social protection response during COVID-19 pandemic are gender responsive and responded to the need of women and children. UN Women has been playing a key role in using the data inovation combining big data and quantitative and qualitative surveys to produce a rapid assessment of COVID-19 impact on gender including impact on women-owned micro and small businesses during the panedmic. It has led a pilot initiative on gender-responsive cash for work programme targeting female beneficiaries who have been adversely impacted in the garment industry. UN Women supported the Ministry of Women Empowerment and Child Protection (MoWECP) as well as CSO engagement in strengthening essential services for women and children who experience violence during COVID-19 pandemic as part of the comprehensive social protection package under the UN COVID-19 MPTF. The project has been able to facilitate adaptation of service provision to the vulnerable populations especially children in context of COVID 19 pandemic and capacity building of frontline workers.
2 | Purpose (and Beneficiaries) | Please include the number of direct and indirect beneficiaries reached, and disaggregate the data by gender, age, and any other groups. | The programme has reached direct beneficiaries up to 433,776 individuals with the details as follow: (1) Mapping of vulnerable children in institutional care: 349,841 children (Girls:172,941; Boys: 171,397) (2) Identification of vulnerable children in West Nusa Tenggara: 171 children (G: 82; B: 89) (3) Gender-responsive cash for work programme: 300 women (4) Training on Case Management, Psychosocial Support, Self-Care, Ethical Dilemma for Social Workers: 852 individuals (F: 472; M: 380) (5) Training on Social Service Provision for Social Workers (psychological first aid and counselling, facilitation skills, ethics, case management, identification of vulnerable children and families, and Prevention of Sexual Exploitation and Abuse and Gender-Based Violence): 1,985 individuals (F: 1,241; M: 744) (7) Training for Parents and Caregivers on Good Parenting, PHBS, and Prevention of VAC: 1,930 individuals (F: 1337; M: 595) (8) Dissemination of Learning Kit for Public Communication by MoSA: 78,697 individuals The indirect beneficiaries of the programme are the beneficiaries of the current and expanded social protection programme for COVID-19, consisting of 10 million households of unconditional cash transfers (PKH); 20 million households of food assistance programmes (Kartu Sembako); and 11.6 million households of Village Cash Transfer.
3.1 | Results: Outcome Level | Please include outcome level results achieved. | The UN's intervention has contributed to the improvement of more effective and inclusive social protection programme in the country by reaching the most vulnerable populations (mapping and registration of children in the unregistered instititutional care, reaching women in garment industry that are deeply affected by the pandemic, advocating the enrollment of homeless people and/or people without formal registration to regular social protection programme, and advocating inclusive process during the update of unified database and improving the Unified Database of Social Protection. The programme has introduced innovative data analysis to better inform the socio-economic impact of the pandemic to the government through the use of big data in the assessment of socio-economic impact of pandemic on women. This also includes strengthening PRISM, a cloud-based platform to monitor and detect the socio-economic impact of the pandemic.
3.2 | Results: Output Level | Please include output level results achieved. | Overall, the JP has achieved three main outputs: (i) the government and key partners have enhanced policy and capacity to scale up and expand social protection coverage and fiscal space to include the affected and marginalised populations, particularly women and children from marginalised groups (ii) the COVID-19 Task Forces, volunteer mechanism operating under the Ministry of Social Affairs (MoSA) at the national and sub-national level, have increased capacity to plan, communicate, build partnerships, and deliver social protection response to COVID-19 crisis; and (iii) promoted the adoption of data analysis as well as financial and digital innovations to better inform the government on effective gender-responsive social protection. Specifically, the JP has achieved the following outputs: (1)The capacity of 4767 social workers for social protection delivery are strengthened (2) two integrated rights-based, equitable, and gender-responsive policy solutions are developed, including unbrella guideline and protocol for protecting the rights of women and girls during COVID-19 pandemic, and integration of GBV services into social protection policy and response (SOP on the Grand Design of Socioeconomic Registration for Social Protection, mapping of vulnerable children and women affected by COVID-19 pandemic, and link to access social support including that for children in institutional care/orphanages (there are 5,505 institutions, 1,804 of which are unregistered)). Total children identified: 349,841 (Girls:172,941; Boys: 171,397) (3) facilitating 2 nationwide surveys on socio-economic impact of COVID-19 pandemic as well as COVID-19 impact on gender (4) 300 beneficiaries in West Java have received cash for work programme that is focusing on value chain and entrepreneurship development programme (5) The capacity of COVID-19 task forces at the national and sub-national level are strengthened in Central Java, East Java and West Nusa Tenggara (6) strengthened the methodology of VAMPIRE, a cloud-based platform, namely by combining the near real-time evidence of additional vulnerability imposed by the socio-economic impact of the current and future pandemics. This platform ensures that said impacts are detected and monitored. (7) facilitated the government to adopt mobile data collection (mVAM) to assess and monitor food security in hard-to-reach areas, during pandemics and other crises (8) policy framework in the context of COVID-19 pandemic related to service provision for vulnerable children, especially children in institutions are improved (9) promoted the use of data innovation and technology to produce new evidence-based policy recommendations by conducting face to face survey, commencing Interactive Voice Response (IVR) Household survey on Socio-Economic Impact of COVID-19 with 17,000 respondents, launching COVID-19 impact on gender report by collaborating with INDOSAT Ooredoo (10) produced policy research, “Leveraging Digitalization to Cope with COVID-19 Pandemic: Indonesia Case Study on Women-owned Micro and Small Businesses” which contitutes an innovative initiative as it employed data and technologies that combine big data analysis as well as quantitative and qualitative surveys to assess the impact of COVID-19 pandemic on micro and small businesses from gender perspective. This report gives important insights into how Indonesia can leverage digitalization in supporting women entrepreneurs to survive the pandemic. It calls for the government stimulus packages to have greater focus on women-owned micro and small business in COVID-19 response and recovery.
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken. | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them. and changes introduced (any course of corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words). | Looking into the expectations of the programme and the time pressure of implementation, there were some challenges occuring during the achievement of COVID-19 MPTF outputs, namely: 1. Coordination has been proven to be challenging within the government i.e. between line ministries, from central to sub-national/local level governments. as well as among various partners outside of the government. The government's intention to expand the involvement of ministries and agencies in the programme has triggered questions not only among UN agencies but also within the newly appointed ministries in charge. At the initial stage, there were 8 ministries & agencies listed as government partners. In September, the UN received proposal from the government to incorporate additional 9 ministries and agencies into the programme. On one side, the UN appreciates the intention of National Development Agency (BAPPENAS)–as the coordinating ministry–to enrich the programme by engaging more ministries and agencies in the COVID-19 MPTF; however, this has triggered questions not only among the UN organizations but also the newly appointed ministries. Some ministries are questioning to what extent they could contribute to the programme. This concern is also shared by the agencies asking for more clarity on the expected engagement and contribution. In mitigating the risk, the UN and the government are planning to discuss in more detail the expectation and contribution of the additional 9 ministries to each of COVID-19 MPTF lower-level output. 2. Social protection response of the government traditionally focused on mitigating immediate income risks and poverty reduction. Addressing structural inequalities, particularly gender inequality, is generally not the primary objective of the social protection interventions. There are still challenges to ensure that eligibility criteria and the beneficiary selection/targeting process take into account other type of social vulnerabilities in the design and implementation of social protection response, which have gaps in inclusion and exclusion errors. The UN has been pushing for a more inclusive and gender-responsive social protection. It also requires stronger ownership and engagement from the government to continue to drive this agenda forward. 3. The COVID-19 pandemic is a force majeure which led to unprecedented measures. This pandemic has been affecting not only different life sectors but also the way people work. Due to precautionary measures such as travel restriction and large events cancelation, the programme is implemented virtually. As the consequence, some activities take longer than expected and the dominant intervention is focused on conducting studies and assessment.
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic, and/or operational lessons or findings from the programme that could inform similar responses at country or global level. Please focus on the knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) and include reflections on the implementation of gender markers and any impacts they have had on programming quality and results (up to 500 words). | The JP works to ensure the scale-up of inclusive social protection programme in response to COVID-19 pandemic in Indonesia. During the pandemic, the government expanded the social protection programme by redirecting and retargeting the existing social protection programme including launching different new programmes to provide safety net for the most affected populations. The JP aims to support the government by filling the gap due to the absence of updated unified database, lack of interlinkage with civil registration database, and minimum monitoring system as well as programme assessment for COVID-19 expanded social protection programme.  For the purpose of identifying the alternative/innovative schemes to augment GoI’s social protection, the JP has initiated the innovative financing study for social protection programme in two target provinces and undertaken further engagement with private sector as well as philanthropic and religion-based organizations to explore their potential contribution to strengthen the government’s social protection programme.  Specifically, through this programme, WFP strengthened the methodology of VAMPIRE, a cloud-based platform, by combining the near real-time evidence to detect and monitor the additional vulnerability incurred by socio-economic impact of the current and future pandemics, including for drought and floods. The programme also explored the feasibility of mobile data collection to assess and monitor food security in hard-to-reach areas, including during pandemics and other crises. Given gender equality is not necessarily the primary objective of the government’s social protection response, building strong linkages with the national priorities is imperative to gain the government’s attention. MPTF has made it possible for UN Women to leverage technologies and innovations to capture data and conduct analysis on gender and put a spotlight on the impact of the COVID-19 pandemic on women and children from marginalized groups, during the time in which in person data collection at the household level is improbable to do in Indonesia. This is critical to inform policy and strategies of GoI to integrate stronger gender dimensions into national economic recovery programme. Specific area in which progress has been made is related to the attempt to address GBV during the pandemic. In light of this, UN Women has led the support of MoWECP to issue both policy and programme interventions to ensure that violence is integrated into the social protection response and that GBV services continue to provide support for women and girls experiencing increased level of violence during the crisis. • JP managed to produce a simple web-based tool to identify vulnerable children, women, and the elderly (dubbed APEM KETAN). Realizing that the existing system used by the government in identifying individual at risk is mainly based on poverty level, the tool integrates disability, pregnancy, and female family heads into the vulnerability factors.
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative, and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. Further, explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words). | Partnership is an essential aspect that enables the JP create collective impact to support the government in enhancing policy and capacity to scale up and expand social protection coverage and fiscal space to include the affected and marginalized populations. For the partnership with the government, the JP's work has alligned and strengthened the government response to the pandemic. In different initiatives, the UN supported the government in enhancing policy, capacity. and data analysis for COVID-19 response. The work in the Unified Database for Social Protection (DTKS), strengthening of the budget monitoring & analysis for social protection programme both in the Ministry of Social Affairs, Ministry of Village and Disadvantage Regions, & Transmigration, as well as support provision in the development of four SOP and Guidelines in relatively short period (8 months) has clearly shown the trust and strong partnership between the government and the UN. Further, in the past seven months of implementation, the JP has been working with 10 implementing partners ranging from the university, Non-Government Organizations (NGOs), private sector, survey firm, and civil society organization. Jointly, our implementing partners have been supporting us in three different areas of work: (a) data analysis and financial and digital innovation (e.g., online applications and platform) (b) research/empirical evidence generation on the adequacy of social protection programmes provided by government (c) targeted advocacy and awareness raising. We marked the following three partnerships which served as significant catalysts for the programme outcome:  UN Women led the joint policy research together with Pulse Lab Jakarta with the support of GOJEK (multi-service tech platform) to provide evidence-based policy recommendations to the National Economic Recovery Programme (PEN) and government social protection strategy to ensure the provision of cash to micro/small enterprises targeting women entrepreneurs and women-owned micro/small businesses. GOJEK is the first on-demand tech platform in Indonesia. This partnership has leveraged the programme in two ways: (1) collaboration with private sector integrated gender equality into business practices and culture through the application of Women’s Empowerment Principles and enabled women entrepreneurs affected by COVID-19 pandemic to have increased access to markets and finance (2) the development of this report managed to involve the Coordinating Ministry of Economic Affairs. Leveraging partnerships with private sector such as with GOJEK and Indosat Ooredo, one of the major telecommunication companies in Indonesia, have made it possible to conduct a rapid assessment and provide the most comprehensive data and evidence on the impact of COVID-19 pandemic on gender through a survey on the socio-economic impact of the COVID-19 pandemic on women and men launched via SMS and web-link data collection during April and July 2020.  Our partnership with Indonesian Child Protection Body (Lembaga Perlindungan Anak Indonesia/LPAI)–an independent organization actively advocating for children rights and needs–has strengthened our work at the sub-national level. LPAI has trained community volunteers to identify vulnerable children and families and promote engagement with the multi-sector COVID-19 TASK Force by advocating prevention of violence against children through: enhancing dissemination of adolescents’ reproductive health services as well as incorporating this issue into the development of child friendly village/city.  The programme also worked with survey firm to provide data for the analysis of socio-economic impact of the pandemic. The survey we conducted is exceptional in which the face-to-face survey and Interactive Voice Response (IVR) household survey managed to reach 17.000 respondents which allow us to deliver reliable results.
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken. | 1. Report on the Grand Design of Socio-Economic Registration for Social Protection 2. Policy Brief on the Locally-funded Child-Sensitive Social Protection Programme in Papua Province (BANGGA Papua Program) 3. Face-to-face survey and Interactive Voice Response (IVR) Household survey on Socio-Economic Impact of COVID-19 Pandemic 4. Study on innovative social financing to better explore different schemes viable for the implementation of social protection in seven provinces 5.The Final Results Assessment for COVID-19 MPTF will be conducted from the 31st of January–31st of March 2021. The ToR has been shared to the Secretariat of COVID-19 MPTF and the revision thereof has been made based on the input from the Secretariat 6. Study on the budget monitoring and analysis at national and sub-national level 7. Study on the influence of Rumah Zakat programme to PKH beneficiary 8. Joint market assessment to examine the impacts of the pandemic on 12 critical market systems 9. Study on the budget monitoring and evaluation of Village Fund-Based Social Protection Programme 10. Assessment report on the effectiveness of the targeting mechanism for cash assistance from Village Fund 11. Policy Brief the role of CSO and women’s organisations and their engagement in social protection response to COVID-19 pandemic 12. Report on national economic recovery and government social protection strategy to provide cash to micro/small enterprises 13. Bulletin on the socio-economic and food security implications of the COVID-19 pandemic 14. Study on the use of mVAM to explore the feasibility of mobile data collection to assess and monitor food security in hard-to-reach areas, including during pandemics and other crises 15. Fill the Nutrient Gap report 16. Methodological review to strengthen the Food Security and Nutrition Surveillance System of BKP useful to monitor transitory food insecurity, during pandemics and other crises
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets, or key outcomes and outputs that took place. | The programme is extended until the 31st of March 2021 with no major adjustments in strategies, targets, outcomes, and outputs.
5 | Resources (Optional) | • Provide any information on financial management, procurement, and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners. | In implementing COVID-19 MPTF, the programme also mobilized resources from Joint SDG Fund which aims to support the GoI in transforming the existing social protection schemes into an Adaptive Social Protection system.

## RBM-Annual
| Achieved Indicator Targets | Reasons for Variance from Planned Target (if any) | Source of Verification
Outcome: By December 2020, Indonesia’s most vulnerable populations, particularly women and children from marginalised groups are protected and safeguarded from the adverse socio-economic impact of the COVID-19 crisis |  |  | MoSA institutional records on the Unified Database for Social Protection (Data Terpadu Kesejahteraan Sosial (DTKS))
Indicator 1 SDG 1.3.1 Proportion of population covered by social protection floors/systems, by sex, distinguishing children, unemployed persons, older persons, persons with disabilities, pregnant women, newborns, work-injury victims, and the poor and the vulnerable
Baseline: 38%
Planned Target: 57% | 40%
Indicator 2 SDG 1.5.4 - Proportion of local governments that adopt and implement local disaster risk reduction strategies in line with national disaster risk reduction strategies
Baseline: 173/514 local governments have a DRR plan, 90 of which are partly integrated with Sendai Framework |  |  | BNPB internal report per January 2021. Data have been shared to the UN upon official request.
Planned Target: 190/514 have a DRR plan at least partly integrated with Sendai Framework | 181/514
Indicator 3 SDG 2.1.1 Prevalence of undernourishment
Baseline: 6.7% |  |  | National Socio-Economic Survey (SUSENAS) per September 2020.
Planned Target: 6.4% | 7.66%
Output 1.1 The government and key partners have enhanced policy and capacity to scale up and expand social protection coverage and fiscal space to include the affected and marginalised populations, particularly women and children from marginalised groups |  |  | MoSA training reports, August 2020
Indicator 1.1.1. Number of social welfare workers/village cadres with increased capacity for social protection response
Baseline: 0
Planned Target: 750 | 4767 (F: 3050; M: 1719)
Indicator 1.1.2 Number of integrated rights-based, equitable, and gender-responsive policy solutions (including for food security and nutrition) creating an enabling environment for pandemic response that have been implemented |  |  | (1) National Agency for Development Planning (BAPPENAS) report, December 2020 (2) MoSA report, July 2020
Baseline: 0
Planned Target: 1 | 2
(1) SOP on the Grand Design of Socio-Economic Registration for Social Protection (2) Mapping of vulnerable children affected by COVID-19 pandemic and link to access social support including that for children in institutional care/orphanages (there are 5,505 institutions, 1,804 of which are unregistered). Total children identified: 349,841 (Girls:172,941; Boys: 171,397))
Output 1.2 COVID-19 task forces, at national and sub-national level, have increased capacity to plan, communicate, build partnerships, and deliver the social protection response to COVID-19 crisis in an inclusive and coordinated manner |  | The programme expanded the target beyond COVID-19 task forces, it also reached the volunteer mechanism operating under of the Ministry of Social Affairs (MoSA) by supporting the government in developing COVID-19 Risk Communication Learning Kit for: Disaster Response Team (39.004), Peace Pioneer (745), and Family Hope Program (38.948) | MoSA Report, August 2020
Indicator 1.2.1: Number of coordinating mechanisms established under the COVID-19 task forces (TF) with increased capacities
Baseline: 0
Planned Target: 5 | 4
Child Protection Working Group, Volunteer of Disaster Response Team, Peace Pioneer, and Family Hope Program
Indicator 1.2.2: Number of inter-agency SOPs for coordination on social protection services
Baseline: 0
Planned Target: 1 (national) & 5 (sub-national) | 2
| (1) Updated National Standard on Child Care (SNPA) in the context of COVID-19 pandemic (2) Guidelines on umbrella protocol for protecting the rights of women and children in COVID-19 response and recovery |  | (1) MoSA report, December 2020 (2) Ministry of Women Empowerement and Child Protection, 9th of December 2020
Output 1.3 Key institutions and partners have increased capacity to adopt data analysis as well as financial and digital innovations for effect
Indicator 1.3.1. Number of data analysis as well as financial and digital innovation (e.g., online applications and platform) that support social protection response to COVID-19 crisis that is inclusive and gender-sensitive
Baseline: 0
Planned Target: 5 | 6 | (a)Household survey on Socio-Economic Impact COVID-19 (b) Socio-Economic Impact of COVID-19 on women and men including vulnerable groups (c) Web application “Apem Ketan” in Central Java (d) M-vam mobile data collection to assess and monitor food security in hard-to-reach areas (e) Fill the Nutrient Gap report) (f) Bulletin on the socioeconomic and food security implications of the COVID-19 pandemic | Programme Report, December 2020
Indicator 1.3.2. Number of women in informal and vulnerable employment, female-headed households, and single mothers supported through financial and digital innovations
Baseline: 0
Planned Target: 10.000.000 (indicative) | 4002323 |  | Programme Report, December 2020
(1) For the indirect beneficiaries of women supported through financial and digital innovation - particularly the rapid assessment of the gender impact of COVID19 as well as the impact of COVID19 on women-owned micro and small business, we can estimated about 4 million that have been reached through survey, information sharing/knowledge products.
(2) UN Women WeLearn Platform has supported 2,023 women entrepreneurs in response to COVID for online training, coaching and mentoring
(3) Leveraging MPTF and Japan support, UN Women provided initial model for cash for work support also to 300 women in the garment industry that are affected by the pandemic
Please inlcude all three: Baseline, Planned Targets, and Achieved Targets.
[1] Note: Outcomes, outputs, indicators, and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3, etc.
Note on A36: hp: Incomplete sentence, more context required.

## Communication-Annual
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supported progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as applicable. To share the video as well picture material, please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
Cash-For-work Program Empowers Women To Regain Dignity The garment sector is often associated with hard working women. It is the world’s largest expanding industry, growing at an annual rate of over 8 percent per year. Indonesia is among four countries producing a sizable amount in garment exports. In Indonesia, the majority (83 percent) of the sector’s workers are women. Therefore, when the COVID-19 pandemic hit the garment sector, Indonesia’s significant female workforce were at risk of being impacted. In Indonesia, it is common for female factory workers to live in marginalized communities with weak civic facilities, placing economic and physical pressure on women to be able to access services as well as resolve domestic related issues. Ibu Icoh, a middle-aged woman who lives in Pondok Kaso village, Sukabumi, recently lost her husband - a tragic loss for the family. Her living conditions pre pandemic were already difficult. For example, she struggled to complete payment for her two children’s education by working as a washer worker in a home industry. With an income of less than half a million rupiah (US$ 35.62) per month and unstable income from her late husband, the family struggled to generate a stable income. Now that she has become a single parent, her economic future feels uncertain. A similar challenge was faced by Ibu Eni, in the same village. As the main provider for her family, including her parents that she lives with, her ability to generate income was crucial to the family’s livelihood and wellbeing. With the pandemic, she was forced to leaver her job at the garment factory due to its closure. Today, she is without a job and therefore does not earn any income. To make matters more challenging, both her and her mother are undergoing medical treatment, and as they are not yet registered to universal healthcare (BPJS), are paying out of their own pocket, creating unnecessary economic burden. These two are among garment workers that are the most marginalized, as they and their families bear the brunt of the negative effects of the pandemic - such as facing health risks, reduction and loss of income and related gendered impacts too - such as increased risk of gender-based violence, increased unpaid care work and barriers to sexual and reproductive healthcare (SRH). To respond to the situation, UN Women and Yayasan CARE Peduli (YCP) have supported groups of women garment workers in Kabupaten Sukabumi and Purwakarta, in the West Java Province (where many garment workers are located). They have done this through providing cash for work and cash transfers programming helping women create and obtain a source of income. Both organizations are targeting women that have lost their jobs or income and are entitled to receive the government safety net programming to meet daily basic needs. The connected training program for women repurposes their existing skills for mask production. Since December 2019, the program has provided various capacity building activities to empower 60 women of masks producers and 240 women of masks marketers, especially to build their leadership and negotiation skills, useful for their working and living environments. Organized in groups, the women will work under the program within the next three months, during which time they will also receive cash for their monthly work. Women workers, like Ibu Icoh and Ibu Eni, are thankful for the program, as they can regain their source of income, and moreover, become more independent, confident, and obtain a wider network of friends and relatives to support them. The program has obtained support and endorsements from the local government of the Sukabumi district, providing local encouragement of women’s engagement in the implementation of the project and the frameworks to continue interventions once the project ends. The function of local authorities is also to provide an enabling environment for women and youth entrepreneurs to grow. “We are optimistic with the program as it has become a solution of income for these women, and an opportunity for our society to recover from the COVID-19 crisis. The program is also aligned with our own program to increase the capacity of the community,” said Feriana Rahman, village secretary officials of Desa Pondok Kaso, Sukabumi.
Through the cash for work program, it is estimated that women will be further empowered and enabled to protect themselves from the impacts of vulnerable situations and re-gain economic independence to meet basic household needs. “We provide women with access to life-saving information, resources, services and skills that will reduce the spread and negative socio-economic impact of COVID-19. Moreover, we give them the opportunity to restore their dignity,” explains Rika, officer of Yayasan Care Peduli
Link for Gender Responsive Cash for Work Programmes project visits:
https://drive.google.com/drive/folders/13e1FkT4_lttFpi9066bK5uaBSRGS_Y4w?usp=sharing
Link for high resolution footage from Cash Based Assistance (CBA) project in Lombok:
https://drive.google.com/drive/u/1/folders/1ATaVBvm6tw4YzF6JJ_9zbfWXNhrdhU5M
Please provide links to any videos that have been produced during implementation.
https://drive.google.com/drive/u/1/folders/1ATaVBvm6tw4YzF6JJ_9zbfWXNhrdhU5M
Please produce and share a social media card(s). See an example below and visit our Trello Board.
https://drive.google.com/drive/u/1/folders/1ATaVBvm6tw4YzF6JJ_9zbfWXNhrdhU5M
See - Fund's Trello Board

## General Information-Final
Programme Title & Project Number | Programme Duration
Programme Title: | Overall Duration (months)
Programme Number (if applicable) | Start Date (dd.mm.yyyy)
MPTF Office Project Reference Number: | Original End Date (dd.mm.yyyy)
Country | Current End date(dd.mm.yyyy)
Recepient UN Organizations | Implementing Partners
Organizations receiving direct funding from the MPTF Office under this programme | National counterparts (government, private sector, NGOs, & others) and other International Organizations
Report Cleared by
o Name:
o Title:
o Email address:
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY.
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY.
Report shall be in line with the approval of the original project document by the relevant decisionmaking body/Steering Committee.
If there has been an extension, then the revised and approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date, which is when all activities for which a Participating Organization is responsible under an approved MPTF/JP have been completed. As per the MoU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Final
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results as well as any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum).
2 | Purpose (and Beneficiaries) | Please include the number of direct and indirect beneficiaries reached, and disaggregate the data by gender, age, and any other groups.
3.1 | Results: Outcome Level | Please include outcome level results achieved.
3.2 | Results: Output Level | Please include output level results achieved.
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them. and changes introduced (any course of corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words).
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic, and/or operational lessons or findings from the programme that could inform similar responses at country or global level. Please focus on the knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) and include reflections on the implementation of gender markers and any impacts they have had on programming quality and results (up to 500 words).
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative, and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. Further, explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words).
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken.
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place
5 | Resources (Optional) | • Provide any information on financial management, procurement, and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners.

## RBM-Final
| Achieved Indicator Targets | Reasons for Variance from Planned Target (if any) | Source of Verification
Outcome 1[1]
Indicator:
Baseline:
Planned Target:
Output 1.1
Indicator 1.1.1:
Baseline:
Planned Target:
Indicator 1.1.2:
Baseline:
Planned Target:
Output 1.2
Indicator 1.2.1:
Baseline:
Planned Target:
Indicator 1.2.2:
Baseline:
Planned Target:
Please inlcude all three: Baseline, Planned Target, and Achieved Target.
[1] Note: Outcomes, outputs, indicators, and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3, etc.

## Communication-Final
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supported progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as applicable. To share the video as well picture material, please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
2. Upload here: Communications and Visibility (OPTIONAL)
To share the video as well picture material, please make sure you include all credits and upload them in high resolution Call1 countries.
Submit photographs. Please provide photographs that capture the programme in action with captions and in high resolution. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
The COVID-19 MPTF Branding Guidelines mentioned two types of photographs submission: high resolution and raw/untreated footage. The JP has prepared two types of the photographs qualities: