CENTRAL AFRICAN FOREST INITIATIVE

MPTF OFfice GENERIC ANNUAL programme NARRATIVE progress report

REPORTING PERIOD: 1 JANUARY – 31 December, 2020

| Programme Title & Project Number |  | Country, Locality(s), Priority Area(s) / Strategic Results |
| --- | --- | --- |
| Central African Forest Initiative Implementation Single-Donor Trust Fund (TF072553) MPTF Office Project Reference Numbers:102312 (Cameroon); 102121 (CAR); 102120 (RoC); 103850 (DRC - Mai-Ndombe); 105031 (DRC - Sud Ubangi); 102312 (DRC - Indigenous Peoples) |  | Country: Cameroon, Central African Republic, Republic of Congo, and the Democratic Republic of Congo Priority Area: REDD+ National Investment Framework (NIF) |
| Participating Organization(s) |  | Implementing Partners |
| World Bank Group (WB) |  | Cameroon: Ministry of Economy, Planning and Regional Development (MINEPAT); Ministry of Finance (MINFI); Ministry of Environment, Protection of Nature and Sustainable Development (MINEPDED); Ministry of Forestry and Wildlife (MINFOF) Central African Republic: Ministry of the Environment and Sustainable Development (MEEDD) Republic of Congo: Ministry of Forest Economy and Sustainable Development, with coordination from the National REDD+ Committee (CONA-REDD) Democratic Republic of Congo: FONAREDD, Ministry of the Environment and Tourism, Ministry of Agriculture, Livestock, and Fisheries and Caritas Congo Asbl. |
| Programme/Project Cost (US$) |  | Programme Duration |
| Total approved budget as per project document: $28,240,000 |  | Duration (months) | Start Date (dd/mm/yyyy) | Original End Date | Current End Date |
| Cameroon Investment Plan Preparation | $ 542,000 |  | Cameroon: | 09/23/2016 | 01/23/2018 | 12/31/2019 |
| CAR Investment Plan Preparation | $ 1,000,000 |  | CAR | 09/23/2016 | 03/23/2018 | 06/30/2020 |
| DRC - Mai Ndombe Investment Plan Preparation | $ 20,000,000 |  | DRC - Mai Ndombe | 03/01/2017 | 05/28/2022 | 05/28/2022 |
| DRC - Sud Ubangi Investment Plan Preparation | $ 4,000,000 |  | DRC - Sud Ubangi | 05/18/2018 | 02/28/2021 | 06/18/2021 |
| DRC - Indigenous Peoples Investment Plan Preparation | $ 2,000,000 |  | DRC - Indigenous Peoples | 03/01/2017 | 07/31/2022 | 07/31/2022 |
| RoC Investment Plan Preparation | $ 698,000 |  | RoC | 09/23/2016 | 05/23/2017 | 12/31/2018 |
| Programme Assessment/Mid-Term Eval. |  | Report Submitted By |
| Assessment/Review - if applicable please attach No: Mid-Term Evaluation Report No |  | Name: Loïc Braune Title: Senior Natural Resources Management Specialist Participating Organization (Lead): World Bank Email address: lbraune@worldbank.org |

# EXECUTIVE SUMMARY

On October 6, 2016, the World Bank (WB) received a Central African Forest Initiative (CAFI) grant package of US$ 2,240,000 for programming in Cameroon, Central African Republic (CAR) and the Republic of Congo (RoC), with a view to help these countries develop and implement a single, comprehensive and broadly supported multi-sector REDD+ National Investment Framework (NIF) to achieve significant results at a large scale. In 2017, the World Bank (WB) received an additional contribution to support three projects in Democratic Republic of Congo (DRC), following the acceptance of proposals by DRC’s National Fund for REDD+ (FONAREDD).

Overall progress:

In CAR, RoC and Cameroon, the activities were implemented jointly with other programs, such as the Forest Carbon Partnership Facility (FCPF) and the Forest Investment Program (FIP).

Cameroon:

The grant closed on December 31, 2019. There had been no actions in 2020.

Central African Republic:

Both the CAFI and FCPF grant agreements were signed in April 2017.  Key REDD+ Readiness institutional arrangements were established in 2018, including the National REDD+ Coordination, the National REDD+ Committee and two Inter-Prefectural Committees (CIP by its local acronym). Principal activities in support of the development of REDD+ instruments – such as NIF, National REDD+ Strategy and Strategic Environmental and Social Assessment (SESA) – were launched in early 2019 after several fiduciary issues were addressed. The development of the NIF started in March 2019. In the absence of a national REDD+ strategy (currently under development), a set of priority measures has been identified based on existing analyses of the drivers of deforestation and forest degradation, the national development vision and sectoral policies and country’s development priorities. NIF implementation approaches have been defined at both the national and subnational levels. The Government of CAR presented a progress report of the 2020-2025 NIF process during the 14th CAFI Board meeting on October 15-16, 2019. A no-cost extension of the grant closing date to June 30, 2020 was articulated to provide additional time to engage with high-level political decisionmakers, conduct an independent evaluation of the NIF, and support the government to address related feedback. The Government of CAR submitted the NIF to the CAFI Secretariat in April 2020 and presented a progress report of the 2020-2025 NIF process during the 16th CAFI Board meeting, which was held in June 2020. After which, the grants closed.

Republic of Congo:

The grants closed before 2020 and there were no activities this year.

Democratic Republic of Congo:

Three proposals were approved by the National Fund for REDD+ (FONAREDD) in late 2016 or early 2017 (PIREDD Sud Ubangi, PIREDD Mai Ndombe, and Indigenous Peoples). Two operations (PIREDD Sud Ubangi and PIREDD Mai Ndombe) have been approved by the Bank and became effective in 2018.

For PIREDD Mai Ndombe, project implementation progressed in 2020 although COVID-19 put a strain on activities between March and September. As of December 2020, activities are on-going: 235 Local Development Committees (LDC) have been created or dynamized and are functional (out of the 600 expected) with 271 Natural Resources Management Plans (NRMP) validated. About 819 hectares of agroforestry plantations (acacia) have been implemented (out of the 1650 ha planned), 16 ha of oil palm (out of the 1,650 ha planned), 4 Agricultural and Rural Management Councils (CARG) and 14 CART (territory level) have been revitalized and are functional. Furthermore, about US$ 930,000 in Payment for Ecosystem Services (PES) has been paid to communities. Twenty-three concessioner farmers (including 1 woman and 2 Indigenous Peoples) and 3536 farmers (including 1482 women and 143 Indigenous Peoples) are direct beneficiaries of the project. An “Acceleration Plan” was developed in August to respond to the implementation delay facing the project.

For the Sud Ubangi operation, the Grant Agreement between the Bank and Government of DRC was signed in April 2017, with the operation declared effective in February 2018 along with the PARRSA project to which it is attached. After the arrival and installation of the program team in October 2019, a series of activities were planned and carried out to launch the program, including: i) elaboration of terms of reference for the studies (NWFP, ESIA); ii) preparation of training modules; iii) organization of the training of trainers, facilitators and local cartographers, as well as customary and traditional authorities; and iv) missions to identify sites in the territories of Budjala, Gemena, Kungu and Libenge, in collaboration with local administrative authorities and stakeholders. In 2020, the Plan de Travail et Budget Annuel (PTBA) and the PIREDD + 2020 procurement plan were prepared and submitted to the WB for its non-objection. The Provincial Coordination and Monitoring Committee of Sud Ubangi’s CPCS project held its first meeting on March 21, 2020, during which the PTBA 2020 was presented and validated, in the presence of the National Fund for REDD+ (FONAREDD) Monitoring and Evaluation Officer.

Regarding the operation related to Indigenous Peoples (IPs): The CAFI proposal aims at expanding the Forest-dependent Community Support Project to include additional activities with the aim of (i) strengthening the participation of IPs in the land tenure and land use planning reforms and (ii) developing innovative activities to support forest management by the communities. While the additional CAFI grant has not been signed for administrative reasons, the project budget and activity plan were revised to include and start procuring the new activities. These new resources helped the project launch new activities that resulted in (i) a greater participation of IPs in the land tenure reform process; (ii) the identification of forest-related micro-projects and their launching in November 2020; and (iii) the identification and delimitation of four areas to be registered as forest concessions for the local communities. The agreement is expected to be signed by April 2021 with a retroactive financing clause that will accelerate the disbursement.

# Background

The Central African Forest Initiative (CAFI) Trust Fund was launched during the United Nations (UN) General Assembly in New York on September 29, 2015 through the official signing of the Joint Declaration. It is hosted by the Multi-Partner Trust Fund Office (MPTF-O) of the United Nations Development Programme and offers a coordination mechanism to donors who are part of CAFI by harmonizing approval, disbursement, and monitoring and reporting processes.

The objective of the CAFI program is to assist with the development of sound land and forest management policies, programs and projects in African countries as part of their low-emission development strategies. Its aim is to support African countries to define their REDD+ investment strategies, and financing policy development, investment programs and projects related to REDD+ in Africa. The main expected outcome of the program is the development of a single, comprehensive, broadly supported, multi-sector REDD+ National Investment Framework (NIF) in each of the recipient countries.

On September 13, 2016, an Administration Agreement was signed between the World Bank (WB) and MPTF-O, marking the first occasion for a UN Multi-Donor Trust Fund to transfer funds directly to the WB as an implementing organization. Beyond the practical terms, this agreement illustrates how the WB and UN are strengthening their cooperation to effectively support sustainable development investments.

In accordance with the requirements of the MPTF-O and the CAFI Governance Body, this annual report represents a status update on CAFI implementation in CY 2020 in countries that received CAFI preparation grants through the WB. They are:

Cameroon, Central African Republic (CAR) and Republic of Congo (RoC):

On October 5, 2016, a CAFI grant package in an amount of US$ 2,240,000 was transferred to the WB and allocated for programming in Cameroon, CAR and RoC with a view to assist them with the development and implementation of their REDD+ NIF in order to achieve significant results at a large scale.

Democratic Republic of the Congo (DRC):

Following the signing of the Letter of Commitment between the DRC and the CAFI Executive Board in April 2016, the National Fund for REDD+ (FONAREDD) launched a series of Calls for Proposal starting in May 2016. After several stages of technical reviews and multiple revisions, the WB was selected as the Implementing Agency in three of them, namely the Mai-Ndombe REDD+ Integrated Project (October 20, 2016), Sud Ubangi REDD+ Integrated Project (February 8, 2017), and Support to the participation of Indigenous Peoples (October 20, 2016).

Financial overview as of December 31, 2020

*

# Country Updates

- Central African Republic

- Narrative reporting on results:

The process to develop the NIF was initiated in March 2019, following the competitive selection of a consortium led by Terre Environnement Aménagement (TEREA) and comprised of the Institut de recherches et d’applications des méthodes de développement (IRAM), Laboratoire d’Economie Rurale et de Sécurité Alimentaire (LERSA), and Centre de coopération internationale en recherche agronomique pour le Développement (CIRAD). As a result of the delays in the procurement process, the terms of reference and proposal by the TEREA-IRAM-LERSA-CIRAD were updated in agreement with CN-REDD, WB and the CAFI Secretariat.

After several rounds of national stakeholder consultations and workshops, the final NIF was completed in December 2019. It identified 27 priority measures that contribute to achieving the following six results: i) integrated and inclusive land-use planning and increased land security; ii) sustainable management of forest ecosystems and restoration of degraded landscapes; iii) reduction of non-sustainable woodfuel consumption; iv) development of productive and sustainable agriculture with zero-deforestation; v) adoption of good practices in the management of environmental and social impacts in mining operations; and vi) increased access to "green" finance in the Land-use Change and Forestry (LULUCF) sector. The Prime Minister officially submitted the NIF to the CAFI Secretariat in April 2020.

Consultations with the various sectoral ministries on their involvement in the implementation of the financing of CAFI, as well as to develop a work plan, took place in May 2020. The specific objectives of this was to: i) evaluate and prioritize the measures identified in the NIF; ii) present the impact each sector has on NIF implementation; and iii) ensure that there is a common understanding amongst stakeholders of the objectives and approach laid out in the NIF and how responding to national and sectoral priorities can help to achieve the NIF objectives.

The Government of CAR presented a progress report of the 2020-2025 NIF process during the 16th CAFI Board meeting, which was held in June 2020, and was commended for sharing a long-term, ambitious national vision for the sustainable management of its lands and natural resources. Now that the CAFI grant has closed, the team continues to work with the Government of CAR and other technical partners to support REDD+ readiness in CAR (FCPF grant), which will, in turn, help enhance the institutional arrangements to support the execution, supervision, monitoring and evaluation of the NIF.

- Indicator Based Performance Assessment

|  | Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification |
| --- | --- | --- | --- |
| Outcome 1 Central African Republic has developed a comprehensive multi-sector NIF that consolidates national financing priorities through a broad consultative process. Indicator: REDD+ NIF Baseline: REDD+ NIF not yet prepared, consulted on or endorsed. Planned Target: REDD+ NIF that has been consulted and endorsed by relevant stakeholders. | The final version of the NIF was transmitted to the CAFI Secretariat in April 2020. |  | CAFI Board minutes |
| Output 1.1 Identification of priority investments and reforms in various sectors identified in the National REDD+ Strategy Indicator 1.1.1 Baseline: None Planned Target: Consolidate Strategic Options to address D+D with priorities for CAFI, First version End October 2017 | 27 priority measures were identified and contribute to 6 main effects. NIF implementation at the central level includes: Political dialogue on reforms on land use planning and tenure; Support intersectoral coordination to finalize laws of land tenure, set up an NLUP and revise the LUP policy, and identify and implement a DFP to protect HCS/HVC. At the local level, NIF implementation include political dialogue on forest preservation commitments in HCS/HCV forests / “green area” and implementation of integrated approach at a subnational scale in 3 priority areas. | In the absence of a national REDD+ strategy to date (under development), the set of priority measures were identified based on existing analyzes of drivers of deforestation and forest degradation, the national development vision and sectoral policies and country’s development priorities. | Final NIF |
| Output 1.2 Facilitation of multi-sector coordination and support for a National REDD+ Strategy and NIF to enable adoption by the government Indicator 1.2.1 Baseline: None Planned Target: Institutional arrangements for consultation defined (although consultations will be carried out as needed before finalization), December 2017 | Workshops were organized in the context of the Regional REDD+ platforms (Comités Inter-Préfectoraux-CIPs) in the prefectures of Ombella M’poko, Kemo et Ouaka and M’Baiki. and one specifically. CN-REDD has participated in numerous events, workshops, and discussions organized by sectoral and non-sectoral Ministries to promote the REDD+ agenda and raise awareness of multiple sectors and identify opportunities for collaboration and support. The NIF development process relied on extensive consultations in four phases: i) Awareness and identification of policies, regulations and initiatives; ii) Thematical consultations; iii) Assessment of priority measures; and iv) Validation (October 2019). 224 people were met from 94 organizations including government, civil society, private sector, donors, project entities, public agencies. | 2 out of the 3 CIPs initially planned were effectively established. The National REDD+ Committee was established in 2018 (Prime Minister) but has not yet convened (planned for 2020). A Ministerial-level seminary, chaired by the Prime Minister, is also planned to take place in February/March 2020 to present the NIF. REDD+ consultations specific to indigenous populations (REPALCA) will take place in 2020 leveraging the results of NIF, Strategy and SESA. | Final workshop reports |
| Output 1.3 Preparation and consolidation of analytical studies on key drivers of deforestation and forest degradation and relevant baseline studies Indicator 1.3.1 Baseline: None Planned Target: Key studies launched (to be defined) by end September 2017, with results to feed into national strategy and NIF design. | NIF identified a set of priority measures based on existing analyzes of drivers of deforestation and forest degradation, including agriculture, forest exploitation (industrial and artisanal logging, wood energy) and mining (direct drivers) as well as political instability, conflicts, poverty, lack of intersectoral coordination on land use planning and rights and lack of State budget (indirect drivers). NIF analyses each driver and formulate concrete adapted measures to address them. |  |  |
| Output 1.4 Consultations with key stakeholders at the national and sub-national levels on REDD+ investment priorities (including a sustainable consultation framework founded on a consultation methodology and plan) Indicator 1.4.1 Baseline: None Planned Target: Consultation plan drafted by end September 2017 (with consultations ongoing through National strategy design, SESA etc. thereafter). | As mentioned above under 1.2., NIF development relied on extensive consultations including government, civil society, private sector, donors, project entities, public agencies. The NIF defines a stakeholder communication plan for the implementation phase. The on-going work and consultations under the SESA process and National Strategy design are also using the NIF’s identified priority measures and implementation approach as a basis for REDD+ implementation in CAR. |  | Final workshop reports |
| Output 1.5 Design and reinforcement of institutional arrangements to support the execution, supervision, monitoring and evaluation of the NIF (including NIF Monitoring and Evaluation Framework) Indicator 1.5.1 Baseline: None Planned Target: NIF execution plan and M&E framework drafted along with capacity building needs December 2017, finalized by June 2018. | NIF defines institutional and implementation framework with current arrangements and improvement needs. Main blocks for NIF Monitoring and Evaluation Framework are defined. NIF execution plan is defined with associated investment budget and operational costs. |  | Final NIF |
| Output 1.6 Knowledge sharing and communication activities related to the National REDD+ Strategy and the NIF Indicator 1.6.1 Baseline: None Planned Target: National REDD+ Strategy and NIF shared, consulted upon and distributed. | General knowledge sharing activities on REDD+ have taken place since project start in 2017 (incl. CIP workshops in 4 prefectures etc.). Knowledge sharing and communication efforts significantly intensified in 2019 in the context of the development of NIF, SESA, and National Strategy with specific consultations and capacity building activities. | Several workshops and communication events are planned in the first half of 2020 (before project closing) to validation and/or disseminate results of the REDD Readiness Process (NIF, SESA, Strategy). | Final workshop reports |

- Republic of Congo (CLOSED)

- Narrative reporting on results:

In the Republic of Congo (RoC), the investment planning process for CAFI and the FIP has been jointly prepared in accordance with the investment plan design. After initial delays, the CAFI Preparation Fund Grant Agreement was signed on March 23, 2017.

Since then, diagnoses of agroforestry value chains, fuel wood production, legal and political context, and co-benefits were completed in early 2017. On the basis of its national REDD+ strategy, the Government of RoC produced its investment plan with the support of an international consulting firm. The Government organized extensive consultations during the preparation period, including two sets of consultation events spanning the entire country (33 events in total), gathering approximately 1,036 stakeholders, and a national validation workshop. The Government presented a first draft to the CAFI EB on October 10, 2017, and the CAFI EB provided written comments on November 22, 2017. The FIP Sub-Committee endorsed the investment plan on December 13, 2017. The Government submitted version 7 of the Investment Plan on 28 August 2018, for a second independent review. The recommendations of the second independent review of the Investment Framework were submitted on September 4, 2018; the final version of the investment plan was conditionally adopted, subject to a final review of the Investment Plan on October 29, 2018 by the CAFI EB.

The grant executed by the Government closed on December 31, 2018, and the Bank supervision ended on March 31, 2019. As both child Trust Funds have been legally closed, the financial figures related to this operation are final. Both grants were fully disbursed.

- Indicator Based Performance Assessment

|  | Achieved Indicator Targets | Reasons for Variance | Source of Verification |
| --- | --- | --- | --- |
| Outcome 1 Republic of Congo has developed and implemented a single, comprehensive, broadly supported, multi-sector REDD+ NIF to achieve significant results at a large scale. Indicator: REDD+ NIF Baseline: REDD+ NIF not yet prepared, consulted on or endorsed. Planned Target: Single REDD+ NIF that has been consulted and endorsed by development partners, relevant government departments, CSOs and IPs. | Final version conditionally approved on October 2018. |  | The submission of version 7a of the NIF. Decision EB.2018.13. |
| Output 1.1 Consultancy to take stock of the existing REDD+ documentation, draft, consolidate and produce the NIF Indicator 1.1.1 – Final report delivered Baseline: No Planned Target: Yes | Submission of version 6.a of the NIF to the CAFI Secretariat on 7 May 2018. Two independent reviews of the NIF version 6.a sent by the CAFI Secretariat to the Government 22 May 2018. Submission of version 6B of the National Investment Plan for a second independent review. Recommendations of the second independent review of the Investment Framework transmitted on 4 September 2018 |  | NIF |
| Output 1.2 Consultancy to incorporate the final set of strategic options that address key drivers of deforestation and forest degradation in the National REDD+ Strategy, and extend the sectoral economic analyses as needed (i.e. industrial agriculture sector, mining sector, others) Indicator 1.2.1 – Final report delivered Baseline: No Planned Target: Yes | Submission of version 6.a of the NIF to the CAFI Secretariat on 7 May 2018. Two independent reviews of the NIF version 6.a sent by the CAFI Secretariat to the Government 22 May 2018. Submission of version 6B of the National Investment Plan for a second independent review. Recommendations of the second independent review of the Investment Framework transmitted on 4 September 2018 |  | NIF |
| Output 1.3 Facilitation of cross-sectoral coordination and broad multi-sectoral consensus-building workshops to support the NIF in alignment with the National REDD+ Strategy, with involvement of CONA-REDD and relevant key ministries Indicator 1.3.1 – Workshops held Baseline: No Planned Target: yes | Multiple rounds of broad-based consultations and coordination workshops were held. Creation of a Task Force under Prime minister to help facilitate cross sectoral coordination |  | Activity reports. Nomination Order |
| Output 1.4 Consultation workshops on the NIF, with involvement of private sector, CSOs, local communities and IPs, at both the national level (in Brazzaville) and at the departmental level Indicator 1.4.1 – Workshops held Baseline: No Planned Target: Yes | 33 consultation workshops held. Specific platforms have also been created: - Private Sector Platform - Government/Donors Platform |  | Workshop minutes. |
| Output 1.5 Consultancy to design the institutional arrangements in support of the execution, supervision, monitoring and evaluation of the NIF, including a manual for implementation and necessary trainings for the concerned institutions Indicator 1.5.1 – Final report delivered Baseline: No Planned Target: Yes | Creation of a Task Force so that NIF’s implementation is supervised by Prime Minister |  |  |
| Output 1.6 Communications and knowledge activities, such as consultancies, dissemination events, production of printed materials, and the production of a communications plan for the implementation phase Indicator 1.6.1 – Communications plan delivered Baseline: No Planned Target: Yes | Outreach workshops have been organized on both NIF and LOI. |  |  |

- Democratic Republic of Congo – PIREDD Sud Ubangi

- Narrative reporting on results:

Following the approval of the proposal by the National Fund for REDD+ (FONAREDD) in February 2017, the WB began preparation of the additional financing (US$ 78.64 million, including US$ 3.64 million from FONAREDD/CAFI) for the on-going Agriculture Rehabilitation and Recovery Support Project (PARRSA - US$ 120 million).

The additional financing was approved by the WB Board on March 22, 2017 and the related Grant Agreement with the DRC was signed on April 19, 2017. Unfortunately, program implementation was delayed due to the timing of the Government’s decree recognizing the CAFI grant.

Following effectiveness, the PARRSA team prepared the implementation plan for the entire project, including the CAFI activities. The Terms of Reference (ToR) for the PIREDD team working on REDD+ were finalized in October 2018, allowing the procurement process to be launched. An initial advance was provided in November to procure material and seeds for farmers (perennial crops like coffee and cocoa).

After the arrival and installation of the program team in October 2019, a series of activities were planned and carried out, including: i) elaboration of ToRs for the studies (NWFP, ESIA); ii) preparation of training modules; iii) organization of the training of trainers, facilitators and local cartographers, as well as customary and traditional authorities; and iv) missions to launch the PIREDD Sud Ubangi (activities to be carried out, implementation challenges) and to identify sites in the territories of Budjala, Gemena, Kungu and Libenge, in collaboration with local administrative authorities and stakeholders (Provincial Government, Agriculture, Land Management, Environment, Rural Development, Health, NGDOs, GTCRR and Private Sector).

In 2020, the Plan de Travail et Budget Annuel (PTBA) and the PIREDD+ 2020 procurement plan were prepared and submitted to the WB for its non-objection. The Provincial Coordination and Monitoring Committee of Sud Ubangi’s CPCS project held its first meeting on March 21, 2020, during which the PTBA 2020 was presented and validated, in the presence of the FONAREDD Monitoring and Evaluation Officer. The main activities retained are:

- Capacity building of state and private actors;

- Sensitization and information to the political-administrative and customary authorities;

- Acquisition of field work equipment and offices;

- Sensitization of women on the importance of forests and contraception for sustainable forest management;

- Local governance through the creation of Local Development Committees for the communities in the territories of Budjala, Gemena, Kungu and Libenge;

- Call for sub-projects for the continued establishment of coffee and cocoa plantations, but also fruit and other crops;

- Strengthening the capacities of the provincial departments of Environment and Sustainable Development (EDD) and Land Management (AT);

- Realization of studies and surveys (Environmental Screening, Non-Timber Forest Products, drivers of deforestation, etc.);

- Geo-referencing of coffee and cocoa plantations installed in 2019;

- Signature of agreements with 34 selected nurseries;

- Installation of plots of coffee, cocoa and fruit trees, to a lesser extent caterpillar and fast-growing trees, for the benefit of the CLDs in the Budjala, Gemena and Kungu territories, as well as the Libenge and Zongo POs where the CLDs had not yet been installed;

- Preparation for the implementation of the land-use planning process through the acquisition of the various spatial exploitation tools including GIS and remote sensing software, basic data and the field implementation schedule;

- Updating and harmonization of concepts related to land-use planning through participation in the harmonization workshop of the Methodological Guide on participatory zoning of community lands and legends of simple land-use plan maps;

- Visit and exchange of experiences with small agroforestry enterprises and development of environmental projects (Miluna, CDI Bwamanda and INERA Boketa) and projects for payment for environmental services;

- Selection of 18 environmental sub-projects (in the territories of Budjala, Gemena, Kungu and Libenge) and three small agroforestry enterprises (Miluna, CDI Bwamanda and INERA Boketa);

- A network of 60 cartographic facilitators, socioeconomic investigators and agronomists are trained and available for the elaboration of plans in the terroirs.

- Visits to the sites of 18 environmental sub-projects and three small agroforestry enterprises for environmental and social screening to define the nature of the specific safeguard documents to be produced;

- Launching of the land-use planning process in the Gemena territory, Banga Kungu sector by supporting the communities of the Bobiton, Bokode, Bominenge, Boyambi and Kalanda groups in the production of simple land-use plans for their terroirs; and information available for the elaboration of 5 land-use management plans for 5 groups, successful pilot test.

- A PIREDD magazine is organized twice a week (Wednesday at 7:30 pm and Sunday at 7:30 am), in partnership with Radio de Développement de l'Ubangi (RDU), which allows the staff to reach the largest number of beneficiaries throughout the province.

- Indicator Based Performance Assessment

|  | Achieved Indicator Targets | Reasons for Variance | Source of Verification |
| --- | --- | --- | --- |
| Outcome 1 Forest-friendly agricultural investments that improve the livelihoods of rural people, including vulnerable and marginalized people. |  |  |  |
| Output 1.1 Forest area under sustainable management or rehabilitated Indicator 1.1.1 – ha Baseline: TBD Planned Target: Yes | Project activities related to agroforestry and forest management have been implemented. The target is 2000 Ha, of which 330 Ha are for agroforestry and 1670 Ha for perennial crops (coffee, cocoa, fruit and caterpillar trees), the defence of savannah, etc. The project has a target area of 2000 Ha. - 330 hectares of agroforestry carried out by small agroforestry enterprises including Miluna: 150 hectares, CDI (collaboration with experts on technical leave) Bwamanda: 50 hectares and INERA Boketa: 30 hectares and 96 hectares by villages under the supervision of CDI Bwamanda agents. - 85 Hectares for environmental sub-projects | Disruptions, accessibility, calendar dysfunction, low capacity of workforce mobilization, unconsciousness and low motivation of state agents, etc. | Micro-grants progress report - PV of selections - Activity report of sub-projects - Reports of internal commissions and external commissions - Mission reports of the members of the commissions set up |
| Output 1.2 Development of sustainable value chains Indicator 1.2.1 – Area planted with perennial crops, under forest cover or agroforestry cultivation Baseline: TBD Planned Target: Yes | In 2020, coffee, cocoa, caterpillar trees and fruit trees have been successfully propagated; the available in nurseries, planned to be planted in September until November 2020, cover today, - 197 hectares of coffee - 230 hectares of cocoa - 48 hectares of caterpillar trees - 181 hectares of fruit trees - 30 hectares of fast-growing trees - 432.15 hectares of agroforestry (330 ha for small agroforestry enterprises, 102.15 ha for community lands) - 85 hectares for environmental sub-projects - 60 hectares sown for IPs throughout the Province. |  | Micro-grants progress report - Report of distribution and supervision missions - CLD plantations |
| Output 1.3 Savannah area under sustainable management or rehabilitated Indicator 1.2.1 – ha Baseline: TBD Planned Target: Yes | The activities are carried out through environmental sub-projects covering 85 hectares as well as small agro-forestry enterprise activities in the degraded savannah areas of the Province. |  | Micro-grants progress report - Activity report of sub-projects |
| Outcome 5 Human activities are better planned to optimize the use of space and reduce their impact on forests. | After the study conducted by OSFAC on the diagnosis of the PIREDD+ intervention zone in 2019 which produced a synoptic view of the biophysical environment and a detailed diagnosis of the South Ubangi province in terms of agriculture, livestock, forestry, rural development, environment and land use planning. In 2020, by addressing several activities of different pillars of the program, the project team also worked on the launch of the process of land use planning or spatial planning of the province by the: Elaboration of the terms of reference for the mission of the firm that was to develop the Spatial Planning Plan of the South Ubangi Province; Acquisition of various spatial exploitation tools including GIS and remote sensing software, basic data and the schedule for the execution of the fieldwork; Capacity building for 55 government officials involved and members of civil society (GTCRR) on GIS and participatory mapping, socio-economic surveys (guide produced by FONAREDD and PIREDD+) and farm surveys; and Beginning of the process of land use planning in the territory of Gemena, Banga Kungu Sector by accompanying the communities of the Bobiton, Bokode, Bominenge, Boyambi and Kalanda groups in the elaboration of PSAT of their lands in collaboration with their neighbors. | The launch of the project was delayed by Covid-19. | CARG meetings Communities of Bobiton, Bokode, Bominenge, Boyambi and Kaland |
| Output 5.1 Number of administrative sectors, territories and provinces with a land use plan Indicator 5.1.1 – Number Baseline: No Planned Target: Yes | Following the production of provincial and territorial land management plans, communities will produce their own land management plans and associated land use and development plans. - Beginning of the land-use planning process in the Gemena Territory, Banga Kungu Sector. Accompaniment of the communities of the Bobiton, Bokode, Bominenge, Boyambi and Kalanda Groups in the production of PSATs from their lands. | The launch of the project was delayed due to the complexity of the implementation schedule and insufficient preparation | CARG Meetings Minutes of the restitution meetings with the State services at Gemena |
| Outcome 8 Good governance ensured through effective, cross-cutting and integrated, transparent, equitable and sustainable implementation of REDD +, based on results, and integrating information, consultation, participation and ownership of all stakeholders, equitably between women and men. | Important meetings and workshops were held to ensure transparent and integrated implementation: (1) PTBA meeting in March 2020 (Budget and schedule) installation of the team program and evaluation of activities (2) March - April 2020, technical working sessions, with FONAREDD's Monitoring and Evaluation Officer. (3) A Provincial Coordination and Monitoring Committee (CPCS) whose mission will be to ensure the implementation, monitoring and evaluation of project activities has been set up with the support of the provincial authorities. (4) April 2020, organization of the CPCS meeting where the PTBA of PIREDD+ SU 2020 activities was presented and validated in the presence of the FONAREDD Monitoring and Evaluation Officer. (5) May 2020. Organize the information and sensitization meeting of the political-administrative authorities, the technical services of the State involved in PIREDD+ SU and the civil society (GTCRR) on the activities of PIREDD+ SU based more on those of the land-use planning pillar. (6) Partnership contracts have been signed with rural radio stations in the province to sensitize stakeholders on climate change and REDD+, environmental education, sustainable management of natural resources, family planning, taking into account gender aspects, etc. (7) Magazine PIREDD+ SU is organized twice a week in partnership with Radio de Développement de l'Ubangi (RDU), which allows the staff to reach the largest number of beneficiaries throughout the province. (8) Organization of capacity building meetings with different stakeholders held in Gemena and in the territories with state actors, civil society, community and territorial representatives on agroforestry and sustainable forest management. (9) Training and sensitization of about 100 women from women's associations, churches, NGOs in the cities of Gemena and Zongo, the territories of Budjala, Gemena, Kungu and Libenge on family planning and women and forests. (10) Organization of working sessions with the CARGs, inspectors and agricultural supervisors on the distribution of seedlings and support to the CLDs in the establishment of seedlings in their community plantations. (11) Organization of the second meeting of the CPCS organized at the end of the supervision mission (monitoring and evaluation) carried out by the FONARED Monitoring and Evaluation Officer. | Project launching was delayed. | CARG Meetings |
| Output 8.1 Number of government institutions strengthened or established and operational Indicator 8.1.1 – Number Baseline: No Planned Target: Yes | For 2019, 4 CARGs have been created, 66 Unions of Producer Organizations (UOPs) and 534 Peasant Organizations (POs) have been created in the territories of Gemena and Budjala. In 2020, the capacities of 4 CARGs have been strengthened in agroforestry and sustainable forest management. Also, they were involved in the creation and installation of 98 CLDs in the territories of Budjala (34), Gemena (18), Kungu (33) and Libenge (13) and the distribution of seedlings to CLDs, FOs, PAs and individuals. For a rational management of the lands of the community terroirs, PIREDD+ SU in collaboration with all the stakeholders involved at the provincial and territorial levels had proceeded to the structuring of the communities of the groups drawn from the Local Development Committees (LDCs) in the 4 territories (Budjala, Gemena, Kungu and Libenge) of the province apart from the two cities (Gemena and Zongo). A total of 98 LDCs have been created and installed in the 98 groups in Southern Ubangi out of 201 in the province. | The objective was largely exceeded. 98 CLDs out of the 54 planned | Minutes of meetings with CARGs - CLD structuring report - Minutes of the appointment of members of the organs of the CLDs |

- Democratic Republic of Congo – PIREDD Mai-Ndombe

- Narrative reporting on results:

The “PIREDD Mai-Ndombe” project aims to extend to the Mai Ndombe District (Inongo, Kiri, Kutu and Oshwe Territories), the sectoral and enabling investments that are implemented under component 1 of the Improved Forested Landscape Management Project (PGAPF) in the Territories of the former Plateaux District (PIREDD Plateaux). Its overall objectives are to improve people's livelihoods and forest landscape management to reduce emissions from deforestation and forest degradation. After the approval of the project proposal in October 2016, the WB prepared the additional financing (US$ 18.22 million) to the on-going PGAPF (US$ 36.9 million). The Grant Agreement between the WB and the Government was declared effective on May 16, 2018. Between approval and effectiveness, the project recruited competitively the Delegating Implementing Agency (DIA) in charge of the implementation of the Mai-Ndombe PIREDD. The delegated project management contract between Ministry of Environment and DIA (consortium FRMi/WWC) was signed on the day of the grant's effectiveness date.

Project implementation has progressed in 2020 although COVID-19 put a strain on activities between March and September. The COVID-19 crisis and related measures by national authorities have indeed impacted main activities of PIREDD Mai Ndombe, including the structuring of Local Development Committees (LDC) due to the impossibility of gathering several people in the same place, establishing nurseries and oil palm plantations due to the closure of borders, contracting of PES which requires village assemblies. Restrictions on domestic travels (Kinshasa-Nioki flights) did not allow the Kinshasa based PIU to carry out supervision missions between March and September 2020. However, the project, through its DIA (1 HQ in Nioki and 4 satellite bases) and NGO service providers established in Mai Ndombe Province, maintained field presence to engage with communities, with due precautions, on awareness-raising and dialogue related to LCDs, nurseries, and PES.with the application of both governmental and project-related measures. The project prepared a “COVID-19 Prevention Plan” issued in June 2020. The Prevention Plan provides: 1) key measures taken at the level of the PIU in line with Governmental ones (e.g. designation of a COVID focal point, home-based work with office rotations, suspension of field missions, sanitary aspects, etc.); 2) an assessment of risks in the field (incl. in relation to health services, reticent local communities, etc.); 3) main objectives and audiences of the Plan; 4) implementation strategy of the Plan; 5) Measures to be taken at the level of the central PIU, DIA in the field, NGO partners, firms and Local Development Committees; 6) Process for managing suspected or confirmed cases; and 7) Mechanism for the Monitoring and Evaluation of the Plan.

As of December 2020, activities are on-going: 235 LDCs have been created or dynamized and are functional (out of the 600 expected) with 271 Natural Resources Management Plans (NRMP) validated. About 819 hectares of agroforestry plantations (acacia) have been implemented (out of the 1650 ha planned), 16 hectares (ha) of oil palm (out of the 1,650 ha planned), four Agricultural and Rural Management Councils (CARG) and 14 CART (territory level) have been revitalized and are functional, and about $930,000 in Payment for Ecosystem Services (PES) has been paid to communities. Twenty-three concessioner farmers (including 1 woman and 2 Indigenous Peoples) and 3536 farmers (including 1482 women and 143 Indigenous Peoples) are direct beneficiaries of the project. An “Acceleration Plan” was developed in August to respond to the implementation delay facing the project. The Acceleration Plan takes stock of on-going activities and those which have not yet started, committed and available budgets across components, implementation timeframe, key constraints facing the project, and options for acceleration including increasing HR resources, leveraging sub-contractors and local technical services, enhanced contract monitoring, and increasing cash availability field (e.g. direct payments from PIU to DIA’s contractors). Regarding overall project governance, the Annual Steering Committee of the project which was initially planned in March 2020 was held in December through virtual means and limited participation and chaired by the Governor of Mai Ndombe.

- Indicator Based Performance Assessment

|  | Achieved Indicator Targets | Reasons for Variance | Source of Verification |
| --- | --- | --- | --- |
| Outcome 1 Forest-friendly agricultural investments that improve the livelihoods of rural people, including vulnerable and marginalized people | In September 2018, PIREDD agronomists carried out the agricultural diagnosis of the Kutu Territory by identifying the main farming practices, the schedule of activities as well as the difficulties (related to agriculture and livestock farming) encountered by the inhabitants of this area. Territory. The agricultural diagnosis is attached to the report. |  | Methodology in preparation. |
| Output 1.1 Area of forests under sustainable management or rehabilitated Indicator 1.1.1 – ha Baseline: No Planned Target: Yes | 60 | Most activities to be implemented on the 1st quarter of 2021 | Agroforestry scorecard |
| Output 1.2 Area of savannah under sustainable management or rehabilitated Indicator 1.2.1 – ha Baseline: No Planned Target: Yes | 204 | 300ha are planned to be added during season B 2021 | Activities Tracking Sheet |
| Outcome 2 Reduction of non-sustainable wood energy |  |  |  |
| Output 2.1 Increase in the amount of wood energy produced by agroforestry plantations and the establishment of protected areas. Indicator 2.1.1 – ha Baseline: No Planned Target: Yes | 899 | Target for the first phase of the project is 1650 ha. Strong progress expected with the implementation of nearly 627 ha during season A 2020. | Agroforestry scorecard Activities Report |
| Outcome 3 Deforestation and degradation from logging are reduced through sustainable management. |  |  |  |
| Output 3.1 Increase in the number of communities and ETDs supported to implement community forestry Indicator 3.1.1 – Number and ha Baseline: No Planned Target: Yes | 188 / 0 | Over 202 the project has pre-identified nearly 6,000 ha that will be the subject of community forestry. | Management plans Activities Report |
| Outcome 4 Human activities are better planned to optimize the use of space and reduce their impact on forests |  |  |  |
| Output 4.1 Number of administrative sectors, territories and provinces with a land use plan Indicator 4.1.1 – Number Baseline: No Planned Target: Yes | 20 |  | Sustainable Development Plan |
| Outcome 5 Land rights enable sustainable development of forestry and agriculture |  |  |  |
| Output 5.1 Provincial land edicts developed in a participatory manner Indicator 5.1.1 Number Baseline: No Planned Target: No | 0 | A technical version of the edict has been prepared and discussed with the provincial authorities. Awaiting opening of the provincial assembly. | Edict |
| Output 5.2 Functional land coordination Indicator 5.2.1 – Number Baseline: No Planned Target: Yes | 1 | Memorandum of understanding with the PIREDD signed with technical services in 2019. Technical agents of the land administration are involved in project monitoring. | Activities report |
| Output 5.3 Agriculture Advisory Councils Operational Indicator 5.3.1 – Number Baseline: No Planned Target: Yes | 4 | 4 Territories. | Activities report of the Comité Agricole Ruraux de Gestion (Rural Agricultural Management Committee) |
| Output 5.4 Map(s) of the various formal or informal-sector land holdings, public and private Indicator 5.4.1 – Number Baseline: No Planned Target: Yes | 404 | The process continues in the 4 Territories. | Provincial map Participation map |
| Ouput 5.5 Agriculture and Cadastre Services are functional Indicator 5.5.1 – Number Baseline: No Planned Target: Yes | 4 | Memoranda of understanding with the different technical services are signed and many of their staff participate in the project work (agriculture, land use planning). | Activities report |
| Output 5.6 - Village areas mapped in a participatory way Indicator 5.5.2– Percentage Baseline: No Planned Target: Yes | 80% | 404 out of 600 expected | Management Plans |
| Outcome 7 Human pressure on forests, linked to migratory phenomena and demographic dynamics, is reduced |  |  |  |
| Output 7.1 Contraceptive prevalence increased. Indicator 7.1.1 – Percentage Baseline: Yes Planned Target: Yes | 0 | During the period under review, the project conducted a CTMP assessment mission. A first meeting will be held in early 2021 and a work plan for outreach activities will be produced. | Activities report |
| Output 7.2 Farm households in the Mai-Ndombe District who have benefited from awareness programs regarding family planning and the prevention of Ebola and HIV / AIDS Indicator 7.2.1 – Number Baseline: No Planned Target: Yes | 0 | As above. | Activities report |
| Outcome 8 Good governance ensured through effective, cross-cutting and integrated, transparent, equitable and sustainable implementation of REDD +, based on results, and integrating information, consultation, participation and ownership of all stakeholders, equitably between women and men |  |  |  |
| Output 8.1 Number of government institutions strengthened or established and operational Indicator 8.1.1 – Number; Provincial Forest Council established; Rural Agriculture Management Committee established Baseline: No Planned Target: Yes | 130 Local Development Committees created or reestablished. The project supported the holding of the General Assembly of the Forest Advisory Council. 15 CARG and 4 CART (territory level) created or reestablished. |  | Statutes and rules of procedure |
| Output 8.1 Participants in consultation activities during the implementation phase of the project Indicator 8.1.2 – Number disaggregated by gender Baseline: No Planned Target: Yes | Since the launching of the project activities, about 109,527 people have been consulted, sensitized and/or trained, including 82,085 men (75%), 27,441 women (25%), 8,230 PA (8%) and 101,297 Bantu (92%). |  | Attendance list Activities report |

- Democratic Republic of Congo – Supporting Indigenous Peoples rights and participation in REDD+

- Narrative reporting on results

Following the approval of the proposal in October 2016, the WB started the preparation of the investment as an additional financing (US$ 1.8 million) to the on-going Forest-Dependent Community Support Project (FDCSP), which is currently supported with a US$ 6 million grant from the Forest Investment Program (Dedicated Grant Mechanism window).

The FDCSP project has been effective since June 2016 and is executed by CARITAS Congo and the National Execution Agency (NEA). Thus, the project was only in its first months of operation when the preparation of the additional financing started (additional financing can only occur after at least a year of implementation). In 2017, the FDCSP faced some challenges related to governance, procurement, and reporting, which caused delays in the preparation of the additional financing. The project safeguards expert was hired in September 2017 and initiated the update of the safeguard documents and the consultation of the stakeholders in the three new Territories covered by the expanded project. These were requirements for the additional financing. The consultations and the revision of the safeguards documents were completed during the second half of 2018. Unfortunately, at that time, CARITAS, the implementation agency, did not comply with Financial Management requirements (delays in the submission of the audit report). The additional financing had to be postponed until the audit report was submitted and satisfactory to the Bank. In 2019, several actions undertaken by the project stakeholders improved the pace of project implementation and the Financial Management was rated as Moderately Satisfactory. These improvements made it possible to continue the additional financing process. In December 2019, the project was authorized to move to appraisal, then hosted negotiation in April 2020. Unfortunately, due to COVID restrictions to travel and organize workshops for capacity building, the project was assessed as a risk project and the approval and signing was postponed until there were evidences that the project would be resilient to the COVID situation.

In August 2020, the project established clear guidelines on the modalities to execute the micro-projects and the field activities. In November 2020, the project signed its first three micro-project, and subsequently lifted the condition of disbursement that was restricting the field operation. As all operational issues have been solved by December 2020, the signing is expected in April 2021.

In terms of disbursements, the project has been operating exclusively on the FIP/DGM funds, but activities and targets have been set based on financing provied by both garnts. As soon as the additional grant is signed, its disbursement rate is expected to match that of the FIP/DGM grant with results attributable to both grants.

In terms of results, the project is showing progress towards its objectives. Greater support to the stakeholders has facilitated the participation of Indigenous Peoples (IP) in the land tenure reform, has improved the governance of IP organizations and has increased the capacities for self-representation and self-organization, especially through the project’s Grievance and Redress Mechanism. The process to secure the IP rights in five community forests has been launched. The most challenging activities are the micro-projects to test and improve the capacities for sound natural resource management at the community level. After testing three different approaches to identify and design inovative and effective micro-projects in a participative manner, the steering committee has approved a first batch of micro-projects, which were signed in October 2020. Six other microprojects have been identied and should be signed early in 2021.

Information about the project can be found on: http://peuplesautochtones.cd.

- Indicator Based Performance Assessment

|  | Achieved Indicator Targets | Reasons for Variance with Planned Target | Source of Verification |
| --- | --- | --- | --- |
| Outcome 1 Quality of the governance structure, inclusion of the Indigenous Peoples |  |  |  |
| Output 1.1 Share of territories with a score of three or more on IPLC representation in land and forest management discussions at the local level Indicator 1.1.1 – % Baseline: 0 Planned Target: 70% | Data collected from local leaders show that 63% of the project Territories were assessed as having a participation of IP in the landscape management processes | Additional training on the forest code and land tenure laws are still to be performed | Project survey of the local leaders |
| Outcome 2 Participation of the Indigenous Peoples in the governance structure for land and forest management |  |  |  |
| Output 1.2 IPLC satisfaction rate regarding IPLC representativeness in the discussions on land use held by the CN-REDD and CONAREF Indicator 1.2.1 – % Baseline: N/A Planned Target: 70% | The opinion of about 50 IP leaders is monitored. Current satisfaction rate regarding the participation of the IP in the CONAREF work is 63.3% | Additional training on the forest code and land tenure laws are still to be performed. In addition, the project will include about 50 more leaders in the pool for the survey. | Project survey of the local leaders |
| Outcome 3 community-based land and forest governance is tested to increase the capacities of the communities for landscape management |  |  |  |
| Output 3.1 Aggregate score on community-based land and forest governance in the pilot sites Indicator 3.1.1 Baseline: 0 Planned Target: 60 (if 4 sites) – 90 (if 6 sites) | The progress toward the establishment of the Community Forest concession is rated on a scale from 0 to 25 based on detailed criteria (thus a maximum of 150 for 6 sites). Current assessment shows a cumulative score of 51. | Work is now launched in 5 locations. | Assessment of the progress made based on the progress report from the firm supporting the communities in each site. |

# Closed operations - archived

- Cameroon (CLOSED)

- Narrative reporting on results

Following transfer of funds in October 2016, the team initiated the grant-financed work with the Client and partners and began preparations to sign the Grant Agreement between the World Bank (WB) and the Government of Cameroon. Outstanding legal or administrative issues were addressed at this time.

The Grant Agreement package was prepared and circulated in early 2017 and was signed on November 22, 2017. The Republic of Cameroon shared the Forest Investment Program (FIP) investment plan with the CAFI Executive Board (EB) in November and December 2017. The CAFI EB reviewed the FIP investment plan and their comments were received on March 19, 2018. A technical working session focusing on the investment plan was held during the mission the CAFI EB members organized in Cameroon and held February 26-27, 2018 to discuss expectations regarding the CAFI investment plan. In September 2018, an international consultant together with two national consultants were hired to address the CAFI EB comments and finalize the National Investment Framework (NIF).

The advanced draft NIF was submitted in March 2019 for independent evaluation, with the evaluators’ comments circulated in April 2019. These comments revealed, inter alia, the need for: i) a revised theory of change; ii) an alignment with country’s development priorities and strategies; and iii) a clear country vision. In addition to these comments, the CAFI EB Bonn expressed its willingness to initiate a policy dialogue with the Government. As a result, a new set of activities were discussed with the CAFI Secretariat during its mission in Yaoundé (June 3-14, 2019). Three national consultants and one international consultant were recruited in October 2019 to: i) support the policy dialogue process; and ii) revise the draft NIF and align it with sectoral priorities in the key land use sectors. Additional consultations were held from October to December 2019 with a high-level meeting held on December 18, 2019.

The main outcome of the grant was partially achieved because a draft NIF was produced and submitted in December 2019, but it still requires further consultations with relevant sectoral ministries and partners. It has resulted in a portfolio of potential forest-smart interventions in low-carbon impact agriculture, landscape restoration, promotion of the efficient use of wood energy, and other cross-cutting aspects, such as land-use planning and governance. Final targeted outputs were achieved. Several consultation meetings were held and benefited about 700 persons (over 30 percent of the participants were women) in the five agroecological zones of Cameroon. Relevant policy dialogue, the finalization of the NIF, and the subsequent negotiation of a letter of intent were not completed by the time the grant closed on December 31, 2019.

- Indicator Based Performance Assessment

|  | Achieved Indicator Targets | Reasons for Variance | Source of Verification |
| --- | --- | --- | --- |
| Outcome 1:Cameroon has developed a comprehensive multi-sector NIF for reducing emissions from deforestation and forest degradation and an accompanying financial mechanism that would enable channeling of funds for its implementation. Indicator: REDD+ NIF and financial mechanism. Baseline: REDD+ NIF and financial mechanism not yet prepared, consulted on or endorsed. Planned Target: REDD+ NIF and financial mechanism that has been consulted and endorsed by relevant stakeholders. | A draft NIF was presented to the CAFI EB, and an advanced draft was shared in March 2019, December 2019 and reviewed by independent evaluators in April 2019. An improved version that considers independent evaluators comments was shared on December 27, 2019. | A final version was not submitted because the draft NIF requires further consultations with relevant sectoral ministries and partners. | CAFI Board Minutes |
| Output 1.1 Consultancy firm enlisted for the drafting of the NIF document Indicator 1.1.1 – NIF document drafted Baseline: No Planned Target: Yes | A consultancy firm was contracted and a draft NIF was available in December 2017. The draft NIF presented in December 2017 required significant revisions. An international consultant and two national consultants were recruited in September 2018 to improve the document’s quality. The Government submitted the draft NIF in March 2019 and four other consultants were recruited in October 2019 to improve the draft NIF, revise the theory of change, present the vision of the land use sector. An improved version was shared on December 27, 2019. |  | Draft NIF available |
| Output 1.2: Organization of regional and national consultations/workshops on REDD+ investment priorities, involving key stakeholders (i.e. national and sub-national level, IPs, local communities) for the enrichment and validation of the NIF Indicator 1.2.1 – Consultations/workshops with relevant stakeholders held Baseline: No Planned Target: Yes | Several consultation meetings were organized: From 2017 to December 2019, the consultancy firm organized: 10 workshops at the national level and in the 5 agroecological zones of Cameroon (about 700 persons were consulted; over 30% of the participants were women). The government also capitalized on the consultations done during the elaboration of other strategic studies of the REDD+ National Strategy that consulted over 3,000 persons. From October to December 2018, the international and national consultants organized: A kick-off workshop on November 25, 2018. About 60 persons participated and they were from coming from different ministries (Forestry, Environment, Planning, Energy, Health, Social Affairs, Mining, Livestock, Gender Equality, Presidency), government agencies (National Observatory for Climate Change) and development partners (WWF, ProForest, World Bank and GIZ). A consultation and NIF enrichment workshop were held in March 2019. October-December 2019, additional meetings were held including a meeting with Secretary Generals from line ministries. Meetings were held with Cameroon’s Financial and technical Partners based in Yaoundé | Details of any investment programs/budgets to be streamlined and finalized with a high-level political engagement needed with key actors in sector and sub-sector | Project Activity Report |
| Output 1.3: Analytical work in specific sectors or on specific activities to inform the NIF on key drivers of deforestation and forest degradation and other relevant baseline studies. Indicator 1.3.1 – Sectoral analysis report produced Baseline: No Planned Target: Yes | Need for additional conversation to identify the strategic axes for government commitments (such as non-conversion of certain types of forest as in other LOIs signed by CAFI; sustainable forest exploitation, zero-deforestation commodities etc.) that could form the basis of a future letter of intent in line with present and future drivers of forest loss identified in the national investment framework | It was not done because the draft NIF is still to be endorsed by the CAFI EB. | Project Activity Report |
| Output 1.4: Design and reinforcing of institutional arrangements to support the execution, supervision, monitoring and evaluation of the NIF Indicator 1.4.1 – Institutional arrangements established Baseline: No Planned Target: Yes | This is part of the draft NIF. |  |  |
| Output 1.5: Logistical and coordination support for CN-REDD in support of elaborating a National Investment Framework Indicator 1.5.1 – NIF document drafted Baseline: No Planned Target: Yes | NIF document has been drafted (see above) |  |  |
| Output 1.6: Communication and knowledge management activities Indicator 1.6.1 – Communication and knowledge materials produced Baseline: No Planned Target: Yes | See Output 1.2 |  |  |

- Republic of Congo (CLOSED)

- Narrative reporting on results:

In the Republic of Congo (RoC), the investment planning process for CAFI and the FIP has been jointly prepared in accordance with the investment plan design. After initial delays, the CAFI Preparation Fund Grant Agreement was signed on March 23, 2017.

Since then, diagnoses of agroforestry value chains, fuel wood production, legal and political context, and co-benefits were completed in early 2017. On the basis of its national REDD+ strategy, the Government of RoC produced its investment plan with the support of an international consulting firm. The Government organized extensive consultations during the preparation period, including two sets of consultation events spanning the entire country (33 events in total), gathering approximately 1,036 stakeholders, and a national validation workshop. The Government presented a first draft to the CAFI EB on October 10, 2017, and the CAFI EB provided written comments on November 22, 2017. The FIP Sub-Committee endorsed the investment plan on December 13, 2017. The Government submitted version 7 of the Investment Plan on 28 August 2018, for a second independent review. The recommendations of the second independent review of the Investment Framework were submitted on September 4, 2018; the final version of the investment plan was conditionally adopted, subject to a final review of the Investment Plan on October 29, 2018 by the CAFI EB.

The grant executed by the Government closed on December 31, 2018, and the Bank supervision ended on March 31, 2019. As both child Trust Funds have been legally closed, the financial figures related to this operation are final. Both grants were fully disbursed.

- Indicator Based Performance Assessment

|  | Achieved Indicator Targets | Reasons for Variance | Source of Verification |
| --- | --- | --- | --- |
| Outcome 1 Republic of Congo has developed and implemented a single, comprehensive, broadly supported, multi-sector REDD+ NIF to achieve significant results at a large scale. Indicator: REDD+ NIF Baseline: REDD+ NIF not yet prepared, consulted on or endorsed. Planned Target: Single REDD+ NIF that has been consulted and endorsed by development partners, relevant government departments, CSOs and IPs. | Final version conditionally approved on October 2018. |  | The submission of version 7a of the NIF. Decision EB.2018.13. |
| Output 1.1 Consultancy to take stock of the existing REDD+ documentation, draft, consolidate and produce the NIF Indicator 1.1.1 – Final report delivered Baseline: No Planned Target: Yes | Submission of version 6.a of the NIF to the CAFI Secretariat on 7 May 2018. Two independent reviews of the NIF version 6.a sent by the CAFI Secretariat to the Government 22 May 2018. Submission of version 6B of the National Investment Plan for a second independent review. Recommendations of the second independent review of the Investment Framework transmitted on 4 September 2018 |  | NIF |
| Output 1.2 Consultancy to incorporate the final set of strategic options that address key drivers of deforestation and forest degradation in the National REDD+ Strategy, and extend the sectoral economic analyses as needed (i.e. industrial agriculture sector, mining sector, others) Indicator 1.2.1 – Final report delivered Baseline: No Planned Target: Yes | Submission of version 6.a of the NIF to the CAFI Secretariat on 7 May 2018. Two independent reviews of the NIF version 6.a sent by the CAFI Secretariat to the Government 22 May 2018. Submission of version 6B of the National Investment Plan for a second independent review. Recommendations of the second independent review of the Investment Framework transmitted on 4 September 2018 |  | NIF |
| Output 1.3 Facilitation of cross-sectoral coordination and broad multi-sectoral consensus-building workshops to support the NIF in alignment with the National REDD+ Strategy, with involvement of CONA-REDD and relevant key ministries Indicator 1.3.1 – Workshops held Baseline: No Planned Target: yes | Multiple rounds of broad-based consultations and coordination workshops were held. Creation of a Task Force under Prime minister to help facilitate cross sectoral coordination |  | Activity reports. Nomination Order |
| Output 1.4 Consultation workshops on the NIF, with involvement of private sector, CSOs, local communities and IPs, at both the national level (in Brazzaville) and at the departmental level Indicator 1.4.1 – Workshops held Baseline: No Planned Target: Yes | 33 consultation workshops held. Specific platforms have also been created: - Private Sector Platform - Government/Donors Platform |  | Workshop minutes. |
| Output 1.5 Consultancy to design the institutional arrangements in support of the execution, supervision, monitoring and evaluation of the NIF, including a manual for implementation and necessary trainings for the concerned institutions Indicator 1.5.1 – Final report delivered Baseline: No Planned Target: Yes | Creation of a Task Force so that NIF’s implementation is supervised by Prime Minister |  |  |
| Output 1.6 Communications and knowledge activities, such as consultancies, dissemination events, production of printed materials, and the production of a communications plan for the implementation phase Indicator 1.6.1 – Communications plan delivered Baseline: No Planned Target: Yes | Outreach workshops have been organized on both NIF and LOI. |  |  |

# Footnotes

PARRSA: “Programme d'appui à la réhabilitation et à la relance du secteur agricole” - Agriculture Rehabilitation and Recovery Support Program.

CAFI Joint Declaration between Donor Countries and Organizations, Central African Partner Countries and South-South Partners, September 29, 2015

LCLS stands for legally Closed, meaning that the financial figures are final.

Initially, FDCSP was covering 16 territories only. With this additional financing, the area for micro-projects has been broadened and three new territories (Bikoro, Kahele and Walikle) have been added to the initial 16 territories for the governance system.

Note: Outcomes, outputs, indicators and targets should be as outlines in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.