## joint financials
FINANCIAL REPORT 1 JANUARY 2019 - 31 MAY 2020
INTEGRATED APPROACH TO BUILDING PEACE IN THE NIGERIA FARMER-HERDSMEN CONFILCT
CUMMLATIVE REPORT
Outcome/ Output number | Outcome/ output/ activity formulation: | Budget for UNDP (not including staff, general operating costs and indirect fee) | 1st tranch of 70% | First tranch to UNDP | Actual expenditure | Difference | Percentage utilized | Budget for UN Women (not including staff, general operating costs and indirect fee) | 1st tranch of 100% | First tranch to UNWOMEN | Actual expenditure | Difference | Percentage utilized | Budget for FAO (not including staff, general operating costs and indirect fee) | 1st tranch of 70% | First tranch to FAO | Actual expenditure | Difference | Percentage utilized | Budget for OHCHR (not including staff, general operating costs and indirect fee) | 1st tranch of 100% | First tranch to OHCHR | Actual expenditure | Difference | Percentage utilized | Total fund for 18 months | Total first tranch | Total Actual expenditure | Difference | Total Percentage utilized
OUTCOME 1: Effective and gender-sensitive infrastructure for peace in place at the state level to support conflict prevention
Output 1.1: | Establishment of state-level agency/commission/structure to drive gender-sensitive peacebuilding agenda | 55000 | 70% | 38500 | 15603.69 | 22896.31 | 40.53% | 10000 | 100% | 10000 | 86.76 | 9913.24 | 0.8676% | 0 | 70% | 0 |  |  |  | 0 | 100% | 0 |  |  |  | 65000 | 48500 | 15690.45 | 32809.55 | 32.35%
Activity 1.1.1: | Mapping and review of State Agencies / Commission / structures, CSOs engaged in peace and security, and existing EWERS available in the states and make practical recommendations | 30000 | 70% | 21000 | 2311.34 | 18688.66 | 11.01% |  | 100% | 0 |  |  |  |  | 70% | 0 |  |  |  |  | 100% | 0 |  |  |  | 30000 | 21000 | 2311.34 | 18688.66 | 11.01%
Activity 1.1.2: | Advocacy and provision of technical support to establish an Agency / Commission / structure | 15000 | 70% | 10500 | 13292.35 | -2792.35 | 126.6% | 10000 | 100% | 10000 | 86.76 | 9913.24 | 0.8676% |  | 70% | 0 |  |  |  |  | 100% | 0 |  |  |  | 25000 | 20500 | 13379.11 | 7120.89 | 65.26%
Activity 1.1.3: | Inter-state exchange for learning and sharing of good practices | 10000 | 70% | 7000 | 0 | 7000 | 0% |  | 100% | 0 |  |  |  |  | 70% | 0 |  |  |  |  | 100% | 0 |  |  |  | 10000 | 7000 | 0 | 7000 | 0%
Output 1.2: | State peacebuilding Agency / Commission / structure supported to drive gender-sensitive response to farmers-herders crisis | 162960 | 70% | 114072 | 0 | 114072 | 0% | 52960 | 100% | 52960 | 47793.36 | 5166.64 | 90.24% | 0 | 70% | 0 |  |  |  | 0 | 100% | 0 |  |  |  | 215920 | 167032 | 47793.36 | 119238.64 | 28.61%
Activity 1.2.1: | Support through facilitating coordination meetings with ministries, departments, CSOs/CBOs, traditional and religious institutions, and women and youth networks to promote coordination around peace | 12960 | 70% | 9072 | 0 | 9072 | 0% | 12960 | 100% | 12960 | 45229.3 | -32269.3 | 349% |  | 70% | 0 |  |  |  |  | 100% | 0 |  |  |  | 25920 | 22032 | 45229.3 | -23197.3 | 205.3%
Activity 1.2.2: | Targeted support to peacebuilding Agency / Commission / structure in operationalizing relevant elements of UNSCR 1325 |  | 70% |  |  |  |  | 30000 | 100% | 30000 | 2564.06 | 27435.94 | 8.547% |  | 70% | 0 |  |  |  |  | 100% | 0 |  |  |  | 30000 | 30000 | 2564.06 | 27435.94 | 8.547%
Activity 1.2.3: | Support to CSOs to engage in community monitoring activities on farmers-herders crisis and reporting to peacebuilding Agency / Commission / structure | 120000 | 70% | 84000 | 0 | 84000 | 0% |  | 100% | 0 |  |  |  |  | 70% | 0 |  |  |  |  | 100% | 0 |  |  |  | 120000 | 84000 | 0 | 84000 | 0%
Activity 1.2.4 | Targeted support to enable early response from Agency / Commission / structure based on early warning signs to promote gender-sensitive dialogue and mediation as a first step to resolving a crisis | 30000 | 70% | 21000 | 0 | 21000 | 0% | 10000 | 100% | 10000 | 0 | 10000 | 0% |  | 70% | 0 |  |  |  |  | 100% | 0 |  |  |  | 40000 | 31000 | 0 | 31000 | 0%
Output 1.3: | Early warning and early response capacity developed, supported and improved | 165000 | 70% | 115500 | 16816.78 | 98683.22 | 14.56% | 27000 | 100% | 27000 | 18205.65 | 8794.35 | 67.43% | 0 | 70% | 0 |  |  |  | 0 | 100% | 0 |  |  |  | 192000 | 142500 | 35022.43 | 107477.57 | 24.58%
Activity 1.3.1: | Develop and implement ICT-based EWERS | 75000 | 70% | 52500 | 1168.17 | 51331.83 | 2.225% | 10000 | 100% | 10000 | 0 | 10000 | 0% |  | 70% | 0 |  |  |  |  | 100% | 0 |  |  |  | 85000 | 62500 | 1168.17 | 61331.83 | 1.869%
Activity 1.3.2: | Capacity building and system strengthening to the EWER institutions in target states | 75000 | 70% | 52500 | 12445.87 | 40054.13 | 23.71% | 12000 | 100% | 12000 | 18205.65 | -6205.65 | 151.7% |  | 70% | 0 |  |  |  |  | 100% | 0 |  |  |  | 87000 | 64500 | 30651.52 | 33848.48 | 47.52%
Activity 1.3.3: | Advocacy at national and state levels with top government officials and security agencies to enhance effective response to conflict early warnings | 15000 | 70% | 10500 | 3202.74 | 7297.26 | 30.5% | 5000 | 100% | 5000 | 0 | 5000 | 0% |  | 70% | 0 |  |  |  |  | 100% | 0 |  |  |  | 20000 | 15500 | 3202.74 | 12297.26 | 20.66%
Output 1.4: | Foster a constructive dialogue through promotion of inter-ethnic and inter-religious exchanges | 165000 | 70% | 115500 | 77754.69 | 37745.31 | 67.32% | 15000 | 100% | 15000 | 0 | 15000 | 0% | 0 | 70% | 0 |  |  |  | 0 | 100% | 0 |  |  |  | 180000 | 130500 | 77754.69 | 52745.31 | 59.58%
Activity 1.4.1: | Support to one CSO to build capacity and raise awareness with traditional rulers and religious leaders on peaceful coexistence, strengthening local level conflict prevention mechanisms, convening town hall meetings, and providing safe spaces for dialogue to take place. | 120000 | 70% | 84000 | 77754.69 | 6245.31 | 92.57% |  | 100% | 0 |  |  |  |  | 70% | 0 |  |  |  |  | 100% | 0 |  |  |  | 120000 | 84000 | 77754.69 | 6245.31 | 92.57%
Activity 1.4.2: | Consultative meetings with stakeholders on legislation around open grazing | 30000 | 70% | 21000 | 0 | 21000 | 0% | 10000 | 100% | 10000 | 0 | 10000 | 0% |  | 70% | 0 |  |  |  |  | 100% | 0 |  |  |  | 40000 | 31000 | 0 | 31000 | 0%
Activity 1.4.3: | Sensitization and awareness raising activities amongst pastoralists, crop farmers, and members of the public on the cost of conflict and economic benefits of peaceful coexistence | 15000 | 70% | 10500 | 0 | 10500 | 0% | 5000 | 100% | 5000 | 0 | 5000 | 0% |  | 70% | 0 |  |  |  |  | 100% | 0 |  |  |  | 20000 | 15500 | 0 | 15500 | 0%
TOTAL $ FOR OUTCOME 1: |  | 547960 | 70% | 383572 | 110175.16 | 273396.84 | 28.72% | 104960 | 100% | 104960 | 66085.77 | 38874.23 | 62.96% | 0 | 70% | 0 |  |  |  | 0 | 100% | 0 |  |  |  | 652920 | 488532 | 176260.93 | 312271.07 | 36.08%
OUTCOME 2: Strengthening Economic Interdependence between Farmers and Herders
Output 2.1: | Improved land, fodder/feedstock and water management to reduce competition over natural resources | 0 | 70% | 0 |  |  |  | 0 | 100% | 0 |  |  |  | 545355 | 70% | 381748.5 | 112695 | 269053.5 | 29.52% | 0 | 100% | 0 |  |  |  | 545355 | 381748.5 | 112695 | 269053.5 | 29.52%
Activity 2.1.1: | Surveying of 5,000 Ha for one state in support of the National Livestock Development Plan |  | 70% | 0 |  |  |  |  | 100% | 0 |  |  |  | 145000 | 70% | 101500 | 7000 | 94500 | 6.897% |  | 100% | 0 |  |  |  | 145000 | 101500 | 7000 | 94500 | 6.897%
Activity 2.1.2: | Pilot pasture development through land preparation, provision of water harvesting structures, pasture production, processing and conservation |  | 70% | 0 |  |  |  |  | 100% | 0 |  |  |  | 372355 | 70% | 260648.5 | 86195 | 174453.5 | 33.07% |  | 100% | 0 |  |  |  | 372355 | 260648.5 | 86195 | 174453.5 | 33.07%
Activity 2.1.3: | Assessment of alternative fodder/feedstock opportunities and information disseminated to both farmers and herders |  | 70% | 0 |  |  |  |  | 100% | 0 |  |  |  | 13000 | 70% | 9100 | 9000 | 100 | 98.9% |  | 100% | 0 |  |  |  | 13000 | 9100 | 9000 | 100 | 98.9%
Activity 2.1.4: | Training of 60 Agricultural extensions officers on alternative feedstocks and value chains |  | 70% | 0 |  |  |  |  | 100% | 0 |  |  |  | 15000 | 70% | 10500 | 10500 | 0 | 100% |  | 100% | 0 |  |  |  | 15000 | 10500 | 10500 | 0 | 100%
Output 2.2: | Livelihood opportunities at agricultural/pastoral interface improved | 311000 | 70% | 217700 | 4610.92 | 213089.08 | 2.118% | 0 | 100% | 0 |  |  |  | 0 | 70% | 0 |  |  |  | 0 | 100% | 0 |  |  |  | 311000 | 217700 | 4610.92 | 213089.08 | 2.118%
Activity 2.2.1: | Profile farmers, pastoralists, CBOs, vocational training centers, women and youths and conduct an assessment on livelihood opportunities | 50000 | 70% | 35000 | 4610.92 | 30389.08 | 13.17% |  | 100% | 0 |  |  |  |  | 70% | 0 |  |  |  |  | 100% | 0 |  |  |  | 50000 | 35000 | 4610.92 | 30389.08 | 13.17%
Activity 2.2.2: | Supporting vocational training for farmers, herders, women, youth and victims of conflict | 60000 | 70% | 42000 | 0 | 42000 | 0% |  | 100% | 0 |  |  |  |  | 70% | 0 |  |  |  |  | 100% | 0 |  |  |  | 60000 | 42000 | 0 | 42000 | 0%
Activity 2.2.3: | Providing startup kits for graduates of vocational training programmes | 35000 | 70% | 24500 | 0 | 24500 | 0% |  | 100% | 0 |  |  |  |  | 70% | 0 |  |  |  |  | 100% | 0 |  |  |  | 35000 | 24500 | 0 | 24500 | 0%
Activity 2.2.4: | Strengthen existing cooperative platforms & CBOs through provision of knowledge products, advisory services and sensitization | 36000 | 70% | 25200 | 0 | 25200 | 0% |  | 100% | 0 |  |  |  |  | 70% | 0 |  |  |  |  | 100% | 0 |  |  |  | 36000 | 25200 | 0 | 25200 | 0%
Activity 2.2.5: | Convene three high-level meetings between private sector and state to raise awareness of fodder and feedstocks value chain and investment opportunities | 30000 | 70% | 21000 | 0 | 21000 | 0% |  | 100% | 0 |  |  |  |  | 70% | 0 |  |  |  |  | 100% | 0 |  |  |  | 30000 | 21000 | 0 | 21000 | 0%
Activity 2.1.3: | Conduct capacity building for 300 conflict-affected people on value chain development around livestock production and markets | 40000 | 70% | 28000 | 0 | 28000 | 0% |  | 100% | 0 |  |  |  |  | 70% | 0 |  |  |  |  | 100% | 0 |  |  |  | 40000 | 28000 | 0 | 28000 | 0%
Activity 2.2.7: | Provide catalytic support to alternative fodder production | 60000 | 70% | 42000 | 0 | 42000 | 0% |  | 100% | 0 |  |  |  |  | 70% | 0 |  |  |  |  | 100% | 0 |  |  |  | 60000 | 42000 | 0 | 42000 | 0%
TOTAL $ FOR OUTCOME 2: |  | 311000 | 70% | 217700 | 4610.92 | 213089.08 | 2.118% | 0 | 100% | 0 |  |  |  | 545355 | 70% | 381748.5 | 112695 | 269053.5 | 29.52% | 0 | 100% | 0 |  |  |  | 856355 | 599448.5 | 117305.92 | 482142.58 | 19.57%
OUTCOME 3: Enhanced accountability and transparency promotes increased effectiveness of security response to the farmers-herders crisis
Output 3.1: | Capacity of monitoring, investigation and follow up on human rights offences enhanced | 0 | 70% | 0 |  |  |  | 30000 | 100% | 30000 | 7605.75 | 22394.25 | 25.35% | 0 | 70% | 0 |  |  |  | 262960 | 100% | 262960 | 63847.14 | 199112.86 | 24.28% | 292960 | 292960 | 71452.89 | 221507.11 | 24.39%
Activity 3.1.1: | Pilot human rights monitoring and reporting mechanism through National Human Rights Commission (NHRC)/NGO/CSO partnership in one state |  | 70% | 0 |  |  |  |  | 100% | 0 |  |  |  |  | 70% | 0 |  |  |  | 250000 | 100% | 250000 | 53847.14 | 196152.86 | 21.54% | 250000 | 250000 | 53847.14 | 196152.86 | 21.54%
Activity 3.1.2: | Support to NHRC in convening CSOs, CBOs involved in human rights monitoring in each state |  | 70% | 0 |  |  |  |  | 100% | 0 |  |  |  |  | 70% | 0 |  |  |  | 12960 | 100% | 12960 | 10000 | 2960 | 77.16% | 12960 | 12960 | 10000 | 2960 | 77.16%
Activity 3.1.3: | Capacity building and awareness raising on sexual exploitation and abuse (SEA) and sexual and gender-based violence (SGBV) |  | 70% | 0 |  |  |  | 30000 | 100% | 30000 | 7605.75 | 22394.25 | 25.35% |  | 70% | 0 |  |  |  |  | 100% |  |  |  |  | 30000 | 30000 | 7605.75 | 22394.25 | 25.35%
Output 3.2: | Increased civil-military/security agencies cooperation and dialogue | 14514.02 | 70% | 10159.814 | 14430.93 | -4271.116 | 142% | 0 | 100% | 0 |  |  |  | 0 | 70% | 0 |  |  |  | 20000 | 100% | 20000 | 4649.12 | 15350.88 | 23.25% | 34514.02 | 30159.814 | 19080.05 | 11079.764 | 63.26%
Activity 3.2.1: | Capacity building and sensitization of security agencies on codes of conduct and rules of engagement |  | 70% | 0 |  |  |  |  | 100% | 0 |  |  |  |  | 70% | 0 |  |  |  | 15000 | 100% | 15000 | 4649.12 | 10350.88 | 30.99% | 15000 | 15000 | 4649.12 | 10350.88 | 30.99%
Activity 3.2.2: | Advocacy to deploy human rights desk of Nigerian Army alongside any military deployment in the three states |  | 70% | 0 |  |  |  |  | 100% | 0 |  |  |  |  | 70% | 0 |  |  |  | 5000 | 100% | 5000 | 0 | 5000 | 0% | 5000 | 5000 | 0 | 5000 | 0%
Activity 3.2.3: | Support local level platforms for dialogue and exchange with security agencies and informal security actors (i.e. vigilante groups) | 14514.02 | 70% | 10159.814 | 14430.93 | -4271.116 | 142% |  | 100% | 0 |  |  |  |  | 70% | 0 |  |  |  |  | 100% |  |  |  |  | 14514.02 | 10159.814 | 14430.93 | -4271.116 | 142%
TOTAL $ FOR OUTCOME 3: |  | 14514.02 | 70% | 10159.814 | 14430.93 | -4271.116 | -337.9% | 30000 | 100% | 30000 | 7605.75 | 22394.25 | 25.35% | 0 | 70% | 0 |  |  |  | 282960 | 100% | 282960 | 68496.26 | 214463.74 | 24.21% | 327474.02 | 323119.814 | 90532.94 | 232586.874 | 28.02%
OUTCOME 4: An improved understanding of the crisis encourages evidence-based advocacy, targeted investments and innovative solutions to reduce the impact of farmer-herder conflict
Output 4.1: | Information Management and Analysis Unit provides reliable and credible information on farmers-herders crisis | 85000 | 70% | 59500 | 30828.35 | 28671.65 | 51.81% | 0 | 100% | 0 |  |  |  | 0 | 70% | 0 |  |  |  | 0 | 70% | 0 |  |  |  | 85000 | 59500 | 30828.35 | 28671.65 | 51.81%
Activity 4.1.1: | Information gathered under the project and through partners are collated and analyzed | 10000 | 70% | 7000 | 0 | 7000 | 0% |  | 100% | 0 |  |  |  |  | 70% | 0 |  |  |  |  | 100% | 0 |  |  |  | 10000 | 7000 | 0 | 7000 | 0%
Activity 4.1.2: | GIS-mapping capabilities enable spatial plotting of attacks to inform trends in the crisis | 15000 | 70% | 10500 | 15400 | -4900 | 146.7% |  | 100% | 0 |  |  |  |  | 70% | 0 |  |  |  |  | 100% | 0 |  |  |  | 15000 | 10500 | 15400 | -4900 | 146.7%
Activity 4.1.3: | Production of analytical briefs and updates on the crisis in the three states help provide partners with a nuanced and well-informed understanding of the crisis | 60000 | 70% | 42000 | 15428.35 | 26571.65 | 36.73% |  | 100% | 0 |  |  |  |  | 70% | 0 |  |  |  |  | 100% | 0 |  |  |  | 60000 | 42000 | 15428.35 | 26571.65 | 36.73%
Output 4.2: | Objective and verified information on the crisis is made publicly available | 9000 | 70% | 6300 | 0 | 6300 | 0% | 0 | 100% | 0 |  |  |  | 0 | 70% | 0 |  |  |  | 0 | 100% | 0 |  |  |  | 9000 | 6300 | 0 | 6300 | 0%
Activity 4.2.1: | Publishing outputs on online repositories and websites for wide distribution and sharing with the public | 5000 | 70% | 3500 | 0 | 3500 | 0% |  | 100% | 0 |  |  |  |  | 70% | 0 |  |  |  |  | 100% | 0 |  |  |  | 5000 | 3500 | 0 | 3500 | 0%
Activity 4.2.2: | Engagement with State Ministries of Information help ensure that state-level media houses are made aware of the information and analysis generated | 3000 | 70% | 2100 | 0 | 2100 | 0% |  | 100% | 0 |  |  |  |  | 70% | 0 |  |  |  |  | 100% | 0 |  |  |  | 3000 | 2100 | 0 | 2100 | 0%
Activity 4.2.3: | Social media platforms disseminate reports, briefs and infographics widely | 1000 | 70% | 700 | 0 | 700 | 0% |  | 100% | 0 |  |  |  |  | 70% | 0 |  |  |  |  | 100% | 0 |  |  |  | 1000 | 700 | 0 | 700 | 0%
TOTAL $ FOR OUTCOME 4: |  | 94000 | 70% | 65800 | 30828.35 | 34971.65 | 46.85% | 0 | 100% | 0 |  |  |  | 0 | 70% | 0 |  |  |  | 0 | 100% | 0 |  |  |  | 94000 | 65800 | 30828.35 | 34971.65 | 46.85%
Project personnel: |  | 426388.05 | 70% | 298471.635 | 285862.16 | -5852.675 | 95.78% | 160395 | 100% | 160395 | 119205.14 | 41189.86 | 74.32% | 96506.25 | 70% | 67554.375 | 0 | 67554.375 | 0% | 0 | 100% | 0 |  |  |  | 683289.3 | 526421.01 | 405067.3 | 121353.71 | 76.95%
Project Manager (P-3) |  | 203362 | 70% | 142353.4 | 220041.57 | -77688.17 | 154.6% |  | 100% | 0 |  |  |  |  | 70% | 0 |  |  |  |  | 100% | 0 |  |  |  | 203362 | 142353.4 | 220041.57 | -77688.17 | 154.6%
Project Officer Benue/Nasarawa |  |  | 70% | 0 |  |  |  |  | 100% | 0 |  |  |  |  | 70% | 0 |  |  |  |  | 100% | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
Driver Benue/Nasarawa |  |  | 70% | 0 |  |  |  |  | 100% | 0 |  |  |  |  | 70% | 0 |  |  |  |  | 100% | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
Project Officer Taraba (NO-B) |  | 115807.5 | 70% | 81065.25 | 27227.88 | 53837.37 | 33.59% |  | 100% | 0 |  |  |  |  | 70% | 0 |  |  |  |  | 100% | 0 |  |  |  | 115807.5 | 81065.25 | 27227.88 | 53837.37 | 33.59%
Driver Taraba (G2) |  | 26374.5 | 70% | 18462.15 |  |  |  |  | 100% | 0 |  |  |  |  | 70% | 0 |  |  |  |  | 100% | 0 |  |  |  | 26374.5 | 18462.15 | 0 | 18462.15 | 0%
Monitoring and Evaluation Analyst (40%) |  | 46323 | 70% | 32426.1 | 27227.88 | 5198.22 | 83.97% |  | 100% | 0 |  |  |  |  | 70% | 0 |  |  |  |  | 100% | 0 |  |  |  | 46323 | 32426.1 | 27227.88 | 5198.22 | 83.97%
Programme Finance/Admin (33%) (G3) |  | 11521.05 | 70% | 8064.735 | 9980.67 | -1915.935 | 123.8% |  | 100% | 0 |  |  |  |  | 70% | 0 |  |  |  |  | 100% | 0 |  |  |  | 11521.05 | 8064.735 | 9980.67 | -1915.935 | 123.8%
Procurement & Logistics Assistant (50%)(G6) |  | 23000 | 70% | 16100 | 1384.16 | 14715.84 | 8.597% |  | 100% | 0 |  |  |  |  | 70% | 0 |  |  |  |  | 100% | 0 |  |  |  | 23000 | 16100 | 1384.16 | 14715.84 | 8.597%
Communications Officer (NO-A) |  |  | 70% | 0 |  |  |  | 44587.5 | 100% | 44587.5 | 45820.97 | -1233.47 | 102.8% |  | 70% | 0 |  |  |  |  | 100% | 0 |  |  |  | 44587.5 | 44587.5 | 45820.97 | -1233.47 | 102.8%
Pasture Development Expert (NO-B) |  |  | 70% | 0 |  |  |  |  | 100% | 0 |  |  |  | 57903.75 | 70% | 40532.625 | 0 | 40532.625 | 0% |  | 100% | 0 |  |  |  | 57903.75 | 40532.625 | 0 | 40532.625 | 0%
Animal Husbandry Expert (NO-B) |  |  | 70% | 0 |  |  |  |  | 100% | 0 |  |  |  | 19301.25 | 70% | 13510.875 | 0 | 13510.875 | 0% |  | 100% | 0 |  |  |  | 19301.25 | 13510.875 | 0 | 13510.875 | 0%
Irrigation Engineer (NO-B) |  |  | 70% | 0 |  |  |  |  | 100% | 0 |  |  |  | 19301.25 | 70% | 13510.875 | 0 | 13510.875 | 0% |  | 100% | 0 |  |  |  | 19301.25 | 13510.875 | 0 | 13510.875 | 0%
Women's Protection and Empowerment Officer (NO-B) |  |  | 70% | 0 |  |  |  | 115807.5 | 100% | 115807.5 | 73384.17 | 42423.33 | 63.37% |  | 70% | 0 |  |  |  |  | 100% | 0 |  |  |  | 115807.5 | 115807.5 | 73384.17 | 42423.33 | 63.37%
Project general operating costs: |  | 129300 | 70% | 90510 | 21042.48 | 69467.52 | 23.25% | 4700 | 100% | 4700 | 19719.69 | -15019.69 | 419.6% | 5700 | 70% | 3990 | 0 | 3990 | 0% |  | 100% | 0 |  |  |  | 139700 | 99200 | 40762.17 | 58437.83 | 41.09%
Vehicle |  | 80000 | 70% | 56000 | 20365.4 | 35634.6 | 36.37% |  | 100% | 0 |  |  |  |  | 70% | 0 |  |  |  |  | 100% | 0 |  |  |  | 80000 | 56000 | 20365.4 | 35634.6 | 36.37%
Project equipment - Computers |  | 8000 | 70% | 5600 | 0 | 5600 | 0% | 2000 | 100% | 2000 | 111.12 | 1888.88 | 5.556% | 3000 | 70% | 2100 | 0 | 2100 | 0% |  | 100% | 0 |  |  |  | 13000 | 9700 | 111.12 | 9588.88 | 1.146%
Project equipment - Projector |  | 600 | 70% | 420 | 0 | 420 | 0% |  | 100% | 0 |  |  |  |  | 70% | 0 |  |  |  |  | 100% | 0 |  |  |  | 600 | 420 | 0 | 420 | 0%
Project equipment - Photocopier/Printer |  | 1000 | 70% | 700 | 0 | 700 | 0% |  | 100% | 0 |  |  |  |  | 70% | 0 |  |  |  |  | 100% | 0 |  |  |  | 1000 | 700 | 0 | 700 | 0%
Furniture (desks, chairs, conference table, UPS) Taraba office |  | 4500 | 70% | 3150 | 469 | 2681 | 14.89% |  | 100% | 0 |  |  |  |  | 70% | 0 |  |  |  |  | 100% | 0 |  |  |  | 4500 | 3150 | 469 | 2681 | 14.89%
Generator Taraba office |  | 10000 | 70% | 7000 | 0 | 7000 | 0% |  | 100% | 0 |  |  |  |  | 70% | 0 |  |  |  |  | 100% | 0 |  |  |  | 10000 | 7000 | 0 | 7000 | 0%
Internet for Taraba office |  | 7200 | 70% | 5040 | 208.08 | 4831.92 | 4.129% |  | 100% | 0 |  |  |  |  | 70% | 0 |  |  |  |  | 100% | 0 |  |  |  | 7200 | 5040 | 208.08 | 4831.92 | 4.129%
Electricity (including diesel costs for generator) Taraba office |  | 9000 | 70% | 6300 | 0 | 6300 | 0% |  | 100% | 0 |  |  |  |  | 70% | 0 |  |  |  |  | 100% | 0 |  |  |  | 9000 | 6300 | 0 | 6300 | 0%
Office Consumables |  | 9000 | 70% | 6300 | 0 | 6300 | 0% | 2700 | 100% | 2700 | 19608.57 | -16908.57 | 726.2% | 2700 | 70% | 1890 | 0 | 1890 | 0% |  | 100% | 0 |  |  |  | 14400 | 10890 | 19608.57 | -8718.57 | 180.1%
Project Evaluation/Audit |  | 50000 | 70% | 35000 | 0 | 35000 | 0% |  | 100% | 0 |  |  |  |  | 70% | 0 |  |  |  |  | 100% | 0 |  |  |  | 50000 | 35000 | 0 | 35000 | 0%
SUB-TOTAL PROJECT BUDGET: |  | 1573162.07 | 70% | 1101213.449 | 466950 | 615801.299 | 42.4% | 300055 | 100% | 300055 | 212616.35 | 87438.65 | 70.86% | 647561.25 | 70% | 453292.875 | 112695 | 340597.875 | 24.86% | 282960 | 100% | 282960 | 68496.26 | 214463.74 | 24.21% | 2803738.32 | 2137521.324 | 860757.61 | 1276763.714 | 40.27%
Indirect support costs (7%): |  | 110121.3449 | 70% | 77084.9414 | 29302.69 | 47782.2514 | 38.01% | 21003.85 | 100% | 21003.85 | 14752.87 | 6250.98 | 70.24% | 45329.2875 | 70% | 31730.5013 | 0 | 31730.5013 | 0% | 19807.2 | 100% | 19807.2 | 4794.74 | 15012.46 | 24.21% | 196261.6824 | 149626.4927 | 48850.3 | 100776.1927 | 32.65%
TOTAL PROJECT BUDGET: |  | 1683283.4149 | 70% | 1178298.3904 | 496252.69 | 682045.7004 | 42.12% | 321058.85 | 100% | 321058.85 | 227369.22 | 93689.63 | 70.82% | 692890.5375 | 70% | 485023.3762 | 112695 | 372328.3762 | 23.23% | 302767.2 | 100% | 302767.2 | 73291 | 229476.2 | 24.21% | 3000000.0024 | 2287147.8167 | 909607.91 | 1377539.9067 | 39.77%

## Lifecycle budget
Annex D - PBF project budget
Note: If this is a budget revision, insert extra columns to show budget changes.
Table 1 - Project budget by Outcome, output and activity
Outcome/ Output number | Outcome/ output/ activity formulation: | Budget for UNDP (not including staff, general operating costs and indirect fee) | Budget for UN Women (not including staff, general operating costs and indirect fee) | Budget for FAO (not including staff, general operating costs and indirect fee) | Budget for OHCHR (not including staff, general operating costs and indirect fee) | Total | Allocation of budget reserved for direct action on gender equality | Percent of budget for each output reserved for direct action on gender eqaulity (if any): | Any remarks (e.g. on types of inputs provided or budget justification, for example if high TA or travel costs)
OUTCOME 1: Effective and gender-sensitive infrastructure for peace in place at the state level to support conflict prevention
Output 1.1: | Establishment of state-level agency/commission/structure to drive gender-sensitive peacebuilding agenda | 55000 | 10000 | 0 | 0 | 65000 | 37500 | 57.69%
Activity 1.1.1: | Mapping and review of State Agencies / Commission / structures, CSOs engaged in peace and security, and existing EWERS available in the states and make practical recommendations | 30000 |  |  |  | 30000 | 15000 | 50% | Mapping review gender analysis, reccommendations for gender sensitive structures and EWERS
Activity 1.1.2: | Advocacy and provision of technical support to establish an Agency / Commission / structure | 15000 | 10000 |  |  | 25000 | 17500 | 70% | Gender balanced structures, EWERS target woemn and youth, gender considereations inlucive in PB approach employed
Activity 1.1.3: | Inter-state exchange for learning and sharing of good practices | 10000 |  |  |  | 10000 | 5000 | 50% | Gender equality ensured on exchanges, UNW promotes gender issues through targeted briefings
Output 1.2: | State peacebuilding Agency / Commission / structure supported to drive gender-sensitive response to farmers-herders crisis | 162960 | 52960 | 0 | 0 | 215920 | 122848 | 56.9%
Activity 1.2.1: | Support through facilitating coordination meetings with ministries, departments, CSOs/CBOs, traditional and religious institutions, and women and youth networks to promote coordination around peace | 12960 | 12960 |  |  | 25920 | 16848 | 65% | UN Women's contribution requested to specifically support state-level women's networks on peacebuilding, linking up to state peace architecture; mainstreamed through UNDPs approaches
Activity 1.2.2: | Targeted support to peacebuilding Agency / Commission / structure in operationalizing relevant elements of UNSCR 1325 |  | 30000 |  |  | 30000 | 30000 | 100% | Implementation on gender
Activity 1.2.3: | Support to CSOs to engage in community monitoring activities on farmers-herders crisis and reporting to peacebuilding Agency / Commission / structure | 120000 |  |  |  | 120000 | 36000 | 30% | Contracting of impartial CSO to undertake community monitoring; disaggregated monitoring of gender and youth
Activity 1.2.4 | Targeted support to enable early response from Agency / Commission / structure based on early warning signs to promote gender-sensitive dialogue and mediation as a first step to resolving a crisis | 30000 | 10000 |  |  | 40000 | 40000 | 100% | UN Women to provide targeted support towards ensuring inclusion of women and girls in dialogue and mediation efforts
Output 1.3: | Early warning and early response capacity developed, supported and improved | 165000 | 27000 | 0 | 0 | 192000 | 106500 | 55.47%
Activity 1.3.1: | Develop and implement ICT-based EWERS | 75000 | 10000 |  |  | 85000 | 47500 | 55.88% | UNDP to lead on the development and implementation of an ICT-based EWERS. UN Women to support through ensuring system is gender sensitive, leveraging gender sensitive indicators and supporting a gender-sensitive response.
Activity 1.3.2: | Capacity building and system strengthening to the EWER institutions in target states | 75000 | 12000 |  |  | 87000 | 49500 | 56.9% | Approaches target men, women and youth equitably and fairly
Activity 1.3.3: | Advocacy at national and state levels with top government officials and security agencies to enhance effective response to conflict early warnings | 15000 | 5000 |  |  | 20000 | 9500 | 47.5% | Travel expenses for senior officials to States, production of advocacy briefs and materials
Output 1.4: | Foster a constructive dialogue through promotion of inter-ethnic and inter-religious exchanges | 165000 | 15000 | 0 | 0 | 180000 | 91500 | 50.83%
Activity 1.4.1: | Support to one CSO to build capacity and raise awareness with traditional rulers and religious leaders on peaceful coexistence, strengthening local level conflict prevention mechanisms, convening town hall meetings, and providing safe spaces for dialogue to take place. | 120000 |  |  |  | 120000 | 60000 | 50% | UNDP will put out call for proposals to CSOs to support on this activity in the states. Ouputs gender and youth apporpriate.
Activity 1.4.2: | Consultative meetings with stakeholders on legislation around open grazing | 30000 | 10000 |  |  | 40000 | 19000 | 47.5% | UNDP and UN Women to hold consultative stakeholder meetings in the states on legislation around open grazing. Consultations will ensure that the impact of legislation on women's political, economic and social spheres is brought to the fore.
Activity 1.4.3: | Sensitization and awareness raising activities amongst pastoralists, crop farmers, and members of the public on the cost of conflict and economic benefits of peaceful coexistence | 15000 | 5000 |  |  | 20000 | 12500 | 62.5% | Targeted sensitization of women and girls, as well as sensitization of men to women's concerns/needs highlight economic benefits and opportunities for both men and women.
TOTAL $ FOR OUTCOME 1: |  | 547960 | 104960 | 0 | 0 | 652920 | 358348 | 54.88%
OUTCOME 2: Strengthening Economic Interdependence between Farmers and Herders
Output 2.1: | Improved land, fodder/feedstock and water management to reduce competition over natural resources | 0 | 0 | 545355 | 0 | 545355 | 330735.5 | 60.65%
Activity 2.1.1: | Surveying of 5,000 Ha for one state in support of the National Livestock Development Plan |  |  | 145000 |  | 145000 | 14500 | 10% | Surveying will include consultations with women and youth groups to ensure input is received from these stakeholders in the surveying process.
Activity 2.1.2: | Pilot pasture development through land preparation, provision of water harvesting structures, pasture production, processing and conservation |  |  | 372355 |  | 372355 | 37235.5 | 10% | One 150 Ha pilot in one of the affected states that includes the preparation of pasture as well as water harvesting structure and irrigation system. UN Women technical support will oversee the pasture pilot to monitor its gender sensitivity, ensuring that both men and women benefit from the pilot.
Activity 2.1.3: | Assessment of alternative fodder/feedstock opportunities and information disseminated to both farmers and herders |  |  | 13000 |  | 13000 | 6500 | 50% | Gender disaggregated assessment makes specific recommendations to the impacts of alternative fodder and feedstocks on women and youth.
Activity 2.1.4: | Training of 60 Agricultural extensions officers on alternative feedstocks and value chains |  |  | 15000 |  | 15000 | 15000 | 100% | 60 Agric officers trained across 3 states, 2 days per state. Training will strive to include an equal gender balance, and extension packages targeting female farmers will be actively promoted
Output 2.2: | Livelihood opportunities at agricultural/pastoral interface improved | 311000 | 0 | 0 | 0 | 311000 | 114250 | 36.74%
Activity 2.2.1: | Profile farmers, pastoralists, CBOs, vocational training centers, women and youths and conduct an assessment on livelihood opportunities | 50000 |  |  |  | 50000 | 25000 | 50% | Data disaggregated with specific recommendations for women and youth on livelihood opportunities.
Activity 2.2.2: | Supporting vocational training for farmers, herders, women, youth and victims of conflict | 60000 |  |  |  | 60000 | 45000 | 75% | The project will strive for targeting 75% women and young girls to promote their access to sustainable livelihoods and employment.
Activity 2.2.3: | Providing startup kits for graduates of vocational training programmes | 35000 |  |  |  | 35000 | 26250 | 75% | The project will strive for targeting 75% women and young girls to promote their access to sustainable livelihoods and employment.
Activity 2.2.4: | Strengthen existing cooperative platforms & CBOs through provision of knowledge products, advisory services and sensitization | 36000 |  |  |  | 36000 | 18000 | 50% | Knowledge products, sensitization and advisory services will have a focus on gender sensitivity and empowerment of women and girls.
Activity 2.2.5: | Convene three high-level meetings between private sector and state to raise awareness of fodder and feedstocks value chain and investment opportunities | 30000 |  |  |  | 30000 | 9000 | 30% | Meetings facilitated with Governors' of affected states and the private sector to support awareness raising around investment opportunities for alternative fodder and feedstock production. Private sector partners with a track record of supporting women and youth will be especially targeted.
Activity 2.1.3: | Conduct capacity building for 300 conflict-affected people on value chain development around livestock production and markets | 40000 |  |  |  | 40000 | 20000 | 50% | Awareness raising and sensitization around transitioning the livestock industry and leveraging the economic benefits of strengthened value chain development. Targeted engagement of women and youth to ensure their inclusion in value chain development.
Activity 2.2.7: | Provide catalytic support to alternative fodder production | 60000 |  |  |  | 60000 | 18000 | 30% | 30% will be dedicated specifically to female farmers to promote inclusion in the alternative feedstock/fodder production value chain.
TOTAL $ FOR OUTCOME 2: |  | 311000 | 0 | 545355 | 0 | 856355 | 444985.5 | 51.96%
OUTCOME 3: Enhanced accountability and transparency promotes increased effectiveness of security response to the farmers-herders crisis
Output 3.1: | Capacity of monitoring, investigation and follow up on human rights offences enhanced | 0 | 30000 | 0 | 262960 | 292960 | 111480 | 38.05%
Activity 3.1.1: | Pilot human rights monitoring and reporting mechanism through National Human Rights Commission (NHRC)/NGO/CSO partnership in one state |  |  |  | 250000 | 250000 | 75000 | 30% | Pilot includes gender disaggregated information and focused on abuses particularly affecting women and youth, with recommendations on enhanced reporting / monitoring / responses.
Activity 3.1.2: | Support to NHRC in convening CSOs, CBOs involved in human rights monitoring in each state |  |  |  | 12960 | 12960 | 6480 | 50% | Support to convening 20 members (gender balanced) per state per month for coordination on human rights
Activity 3.1.3: | Capacity building and awareness raising on sexual exploitation and abuse (SEA) and sexual and gender-based violence (SGBV) |  | 30000 |  |  | 30000 | 30000 | 100% | 6 workshops specifically targeted to address major challenges faced by women and girls.
Output 3.2: | Increased civil-military/security agencies cooperation and dialogue | 14514.02 | 0 | 0 | 20000 | 34514.02 | 8854.206 | 25.65%
Activity 3.2.1: | Capacity building and sensitization of security agencies on codes of conduct and rules of engagement |  |  |  | 15000 | 15000 | 4500 | 30% | 3 workshops conducted with strategic-level officers, which incorporates elements of preventing violence against women and protection of women and girls.
Activity 3.2.2: | Advocacy to deploy human rights desk of Nigerian Army alongside any military deployment in the three states |  |  |  | 5000 | 5000 |  | 0% | Publishing reports, updates on human rights, advocacy missions to military operations commands
Activity 3.2.3: | Support local level platforms for dialogue and exchange with security agencies and informal security actors (i.e. vigilante groups) | 14514.02 |  |  |  | 14514.02 | 4354.206 | 30% | Targeted focus on ensuring women and youth are able to engage in platforms promoted
TOTAL $ FOR OUTCOME 3: |  | 14514.02 | 30000 | 0 | 282960 | 327474.02 | 120334.206 | 36.75%
OUTCOME 4: An improved understanding of the crisis encourages evidence-based advocacy, targeted investments and innovative solutions to reduce the impact of farmer-herder conflict
Output 4.1: | Information Management and Analysis Unit provides reliable and credible information on farmers-herders crisis | 85000 | 0 | 0 | 0 | 85000 | 43000 | 50.59%
Activity 4.1.1: | Information gathered under the project and through partners are collated and analyzed | 10000 |  |  |  | 10000 | 10000 | 100% | Gender disaggregated analysis is produced.
Activity 4.1.2: | GIS-mapping capabilities enable spatial plotting of attacks to inform trends in the crisis | 15000 |  |  |  | 15000 | 15000 | 100% | Purchase of 2 licenses for GIS mapping alongside subscriptions for data presentation ensures gender disaggregated breakdown, analysis and presentation of findings.
Activity 4.1.3: | Production of analytical briefs and updates on the crisis in the three states help provide partners with a nuanced and well-informed understanding of the crisis | 60000 |  |  |  | 60000 | 18000 | 30% | GIS Assistant Salary cost. Special preference will be given to female candidates who meet the qualifications.
Output 4.2: | Objective and verified information on the crisis is made publicly available | 9000 | 0 | 0 | 0 | 9000 | 1500 | 16.67%
Activity 4.2.1: | Publishing outputs on online repositories and websites for wide distribution and sharing with the public | 5000 |  |  |  | 5000 | 1500 | 30% | Subscription costs, printing costs. UN Women Communications Officer will ensure that informational outputs are disseminated in a way that enables women and youth to easily access information and analysis.
Activity 4.2.2: | Engagement with State Ministries of Information help ensure that state-level media houses are made aware of the information and analysis generated | 3000 |  |  |  | 3000 |  | 0%
Activity 4.2.3: | Social media platforms disseminate reports, briefs and infographics widely | 1000 |  |  |  | 1000 |  | 0% | Subscription costs
TOTAL $ FOR OUTCOME 4: |  | 94000 | 0 | 0 | 0 | 94000 | 44500 | 47.34%
Project personnel: |  | 426388.05 | 160395 | 96506.25 | 0 | 683289.3 | 160395
Project Manager (P-3) |  | 203362 |  |  |  | 203362
Project Officer Benue/Nasarawa | [5 empty] | 0 |  |  | In-kind contribution to this project
Driver Benue/Nasarawa | [5 empty] | 0 |  |  | In-kind contribution to this project
Project Officer Taraba (NO-B) |  | 115807.5 |  |  |  | 115807.5
Driver Taraba (G2) |  | 26374.5 |  |  |  | 26374.5
Monitoring and Evaluation Analyst (40%) |  | 46323 |  |  |  | 46323 |  |  | 40% in-kind contribution to this project
Programme Finance/Admin (33%) (G3) |  | 11521.05 |  |  |  | 11521.05 |  |  | 67% in-kind contribution to this project
Procurement & Logistics Assistant (50%)(G6) |  | 23000 |  |  |  | 23000
Communications Officer (NO-A) |  |  | 44587.5 |  |  | 44587.5 | 44587.5 |  | Part time position (50%)
Pasture Development Expert (NO-B) |  |  |  | 57903.75 |  | 57903.75 |  |  | Covered for 9 months
Animal Husbandry Expert (NO-B) |  |  |  | 19301.25 |  | 19301.25 |  |  | Covered for 3 months
Irrigation Engineer (NO-B) |  |  |  | 19301.25 |  | 19301.25 |  |  | Covered for 3 months
Women's Protection and Empowerment Officer (NO-B) |  |  | 115807.5 |  |  | 115807.5 | 115807.5
Project general operating costs: |  | 129300 | 4700 | 5700 |  | 139700
Vehicle |  | 80000 |  |  |  | 80000
Project equipment - Computers |  | 8000 | 2000 | 3000 |  | 13000
Project equipment - Projector |  | 600 |  |  |  | 600
Project equipment - Photocopier/Printer |  | 1000 |  |  |  | 1000
Furniture (desks, chairs, conference table, UPS) Taraba office |  | 4500 |  |  |  | 4500
Generator Taraba office |  | 10000 |  |  |  | 10000
Internet for Taraba office |  | 7200 |  |  |  | 7200
Electricity (including diesel costs for generator) Taraba office |  | 9000 |  |  |  | 9000
Office Consumables |  | 9000 | 2700 | 2700 |  | 14400
Project Evaluation/Audit |  | 50000
SUB-TOTAL PROJECT BUDGET: |  | 1573162.07 | 300055 | 647561.25 | 282960 | 2803738.32 | 1128562.706 | 40.25% | Percentage of gender equality is based on the total programmed costs under this budget.
Indirect support costs (7%): |  | 110121.3449 | 21003.85 | 45329.2875 | 19807.2 | 196261.6824
TOTAL PROJECT BUDGET: |  | 1683283.4149 | 321058.85 | 692890.5375 | 302767.2 | 3000000.0024

## FAO budget review
Table 2 - Project budget by UN cost category
Note: If this is a budget revision, insert extra columns to show budget changes.
CATEGORIES | Amount UNDP |  | Amount UN Women |  | Amount FAO |  | FAO Revised Budget | Amount OHCHR |  | Total tranche 1 | Total tranche 2 | PROJECT TOTAL
| Tranche 1 (70%) | Tranche 2 (30%) | Tranche 1 (100%) | Tranche 2 (0%) | Tranche 1 (70%) | Tranche 2 (30%) |  | Tranche 1 (100%) | Tranche 2 (0%)
1. Staff and other personnel | 340471.635 | 145916.415 | 160395 | 0 | 67554.375 | 28951.875 | 52905 | 0 | 0 | 568421.01 | 174868.29 | 743289.3
2. Supplies, Commodities, Materials | 177072 | 75888 | 62960 | 0 | 265898.5 | 113956.5 | 379855 | 20460 | 0 | 526390.5 | 189844.5 | 716235
3. Equipment, Vehicles, and Furniture (including Depreciation) | 72870 | 31230 | 2000 | 0 | 2100 | 900 | 3000 | 0 | 0 | 76970 | 32130 | 109100
4. Contractual services | 232400 | 99600 | 22000 | 0 | 110600 | 47400 | 59948 |  |  | 365000 | 147000 | 512000
5.Travel | 65100 | 27900 | 50000 | 0 | 5250 | 2250 | 38100 | 12500 | 0 | 132850 | 30150 | 163000
6. Transfers and Grants to Counterparts | 195659.814 | 83854.206 |  |  |  |  | 55100 | 250000 | 0 | 445659.814 | 83854.206 | 529514.02
7. General Operating and other Direct Costs | 17640 | 7560 | 2700 | 0 | 1890 | 810 | 58653 | 0 | 0 | 22230 | 8370 | 30600
Sub-Total Project Costs | 1101213.449 | 471948.621 | 300055 | 0 | 453292.875 | 194268.375 | 647561 | 282960 | 0 | 2137521.324 | 666216.996 | 2803738.32
8. Indirect Support Costs (must be 7%) | 77084.9414 | 33036.4035 | 21003.85 | 0 | 31730.5013 | 13598.7863 | 45329.27 | 19807.2 |  | 137383.1654 | 58878.4995 | 196261.6649
TOTAL | 1178298.3904 | 504985.0245 | 321058.85 | 0 | 485023.3763 | 207867.1613 | 692890.27 | 302767.2 | 0 | 2274904.4894 | 725095.4955 | 2999999.9849