## OVERALL REPORTING INSTRUCTIONS
OVERALL INSTRUCTIONS
1 | All questions/sections must be responded to before submitting to secretariat. Once the document is uploaded in the relevant folder (as per instruction below) please email the secretariat.
2 | To ensure high quality narrative and results reports please pay attention to the following details: a) A well written, succinct summary that is very clear about what was done during the reporting period and results achieved, with a priority on concrete activities, beneficiaries reached and achievements beyond processes b) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document; c) In case certain indicators are not longer relevant, an explanation for why they are not. d) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document and how they align with the overall SERP joint workplan, and connection to reporting on global-level SERP indicators e) Indicate the relevant SERP monitoring framework global indicators that were contributed to as part of this project. f) An honest analysis of challenges faced, the responses to these challenges and the extent to which these responses were successful or not g) Go beyond generic, standard and well documented features of successful project implementation when reflecting on innovation and focus on what is truly new for you and which could enable replication efforts
3 | You must submit this completed workbook by uploading it in the relevant Project Folder here (https://undp.sharepoint.com/:f:/r/sites/covid19mptfcall1/Shared%20Documents/2020-REPORT?csf=1&web=1&e=j3cc3J). Please note if you are unsure of your project number please refer to http://mptf.undp.org/factsheet/fund/COV00
A | ANNUAL REPORT
DEADLINE: 31 January 2021
4 | ALL projects that received funds in 2020 must complete annual report, HOWEVER if you have your project ending on 31st December 2020 - your FINAL report is your annual report.
5 | If you received a no-cost extension on your project please do the annual report and in a few months time you can update the annual report to include activities to complete your end of project report.
6 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.
B | END OF PROJECT - FINAL REPORT
DEADLINE: 31 January 2021
7 | ALL projects that received funds in 2020 must complete annual report, HOWEVER if you have your project ending on 31st December 2020 - your FINAL report is your annual report.
8 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.

## General Information-Annual
Programme Title & Project Number |  | Programme Duration
Programme Title: | Supporting essential sexual, reproductive, maternal, newborn, child and adolescent health services during COVID-19 in Lao PDR | Overall Duration (months) | Six months
Programme Number (if applicable) |  | Start Date (dd.mm.yyyy) | June 2 2020
MPTF Office Project Reference Number: | 121675 | Original End Date (dd.mm.yyyy) | December 31 2020
Country | Lao PDR | Current End date(dd.mm.yyyy)
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | UNFPA, UNAIDS, UNICEF | National counterparts (government, private, NGOs & others) and other International Organizations | MoH, namely Department of Hygiene and Health Promotion with Mother and Child Health Centre, Centre for Communication and Education, Department of Health Care and Rehabilitation, and Department of Health Professional Education with the Lao Association of Midwives (LAM) at central level. Luangprabang province through the provincial and district health offices
Report Cleared By
o Name: | Sara Sekkenes
o Title: | Resident Coordinator
o Email address: | sara.tollefsen@un.org
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the Secretary-General's Designate
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Annual
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum) | A programme to mitigate the potential disruption to the essential RMNCAH services was initially proposed following the evidence in the first quarter of 2020. The original assumption was that COVID-19 infection would spread widely, even in Lao PDR. However, to the present day, the country maintains one of the lowest rates of COVID-19 infection in the world. With this, the programme was able to fully redesign preparedness and mode of service delivery and to test it. Using a guideline developed by collaborative efforts of the three agencies (UNFPA, UNICEF and WHO) at regional level, three options were proposed as possible solutions to maintain the essential RMNCAH services in Lao PDR. Achievements in these areas are: 1. Strengthening safety of existing health facilities, task shifting and alternate service delivery modalities: Health providers in the three selected districts of Luang Prabang were provided technical support to ensure that their health facilities implement essential infection prevention and control, triage and risk screening. A guidance on supporting risk assessment for changing delivery modality of selected scheduled antenatal care and postnatal care (ANC/PNC) to home visit/ remote communication such as tele-counselling/consultation was developed, including tools to support health information (Patient record) and psycho-social support for providers themselves. This also included establishing the number of pregnant women in a specific area. Provision of psychosocial support to women through national hotline (work with Lao Women’s Union (LWU), Lao Youth Union (LYU) and, Vientiane Youth Centre) continued effectively. 2. Mobile services: support health care providers (maternal child health (MCH) staff, midwives) to carry out home visits for high risk mothers and newborns in ANC/PNC care during COVID-19 crisis. Results showed increased access to these essential services. Communities were provided with loudspeakers and amplifiers to disseminate key messages regarding COVID-19 to reduce fears as well as providing information on how best to access care when required. For People Living with HIV, access to care improved through the support of two CSOs. 3. Tele-health mechanism: since the lockdown was lifted earlier than other countries, there was not a need to develop on-line training module, however, as part of the care delivery modality the telehealth component was tested. The use of tele-consultation for health promotion, prevention and counselling helped to reduce exposure at facilities. This became a preferred model by both clients and providers. This has the potential to be expanded across the country and used in areas that are difficult to access, including during the seasonal flooding where women are often cut off from accessing routine care. Despite the relative short implementation time, it is evident that the programme achieved the targets set, with various components ready for roll out and expansion across the country.
2 | Purpose (and Beneficiaries) | Please include the number of direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups | The aim of the intervention is to support the MoH to develop clear mechanisms to address barriers for the clients to access services including the physical (due to lockdown, etc.), financial (due to unemployment, stressed financial services) and social (fear of getting infected when seeking services) barriers. Beneficiaries include the MoH who have been able to test a simplified SRMNCAH service delivery system that will allow health workers to operate safely during the pandemic. Direct beneficiaries from Luang Prabang, Phoukhoun and Phonthong districts are: 38 healthcare workers, 7 core trainers from Luang Prabang College of Health Sciences, Provincial Hospital and Health Department, 35,988 women of reproductive age, 1,502 pregnant women, and 963 newborns. Indirect beneficiaries: Nine (9) staff from Lao Women’s Union, nine (9) staff from Lao Youth Union and 19 volunteers from Vientiane Youth Centre.
3.1 | Results: Outcome Level | Please include outcome level results achieved | Under the MPTF, aside from the national and provincial level, further work with the district and community level are being done — district hospitals, health centres and rural communities (zone 2 – 3 villages are targeted because they are difficult to access). Details of these were provided in the interim report, as well as the process of developing the essential RMNCAH Services during COVID-19 package. https://drive.google.com/file/d/12iwHnkGsrsYixWXmGiAXfZGAm3ARLJzy/view?usp=sharing https://drive.google.com/file/d/17TG8kQ-UdcR_jIRXDzUyrh5Pz3ve6BrA/view?usp=sharing All 38 participants/health service providers were also trained in Psychosocial Support with an aim to provide them with some tools to maintain their psychosocial well-being in the COVID-19 situation. Through the training they have learned, such as stress relief techniques, peer support for stress management (including active listening skill development and awareness of inner voice) and support mechanism at the organisational level. Following the training, providers immediately put in place the different measures required to protect themselves and their clients, based on what they learned. They reorganized health facilities with sinks installed outside of their facilities for handwashing, hand sanitizer prepared, screening and triaging prepared in all the health facilities within conditions that they have available. In-coming patients are advised to wash their hands properly, wear facemasks, have their temperature checked before entering health facilities. Access to services clearly increased following implementation. Based on the data in DHIS2, both proportion of women receiving Antenatal Care the first time (ANC 1) increased more than 40% and ANC 4, the increase was more than 10%. This included the access during the mobile outreach which showed that 211 mothers have received ANC1 and 127 mothers have received ANC 4 (within 2 days and up to 42 days) and 346 mothers have received PNC provided through mobile outreach. As a result of the programme, the contraceptive use—pill, injectable, implant and IUD use— has significantly increased (from October – December, 2020). Women were more confident to access care, and staff did not fear their clients.
3.2 | Results: Output Level | Please include output level results achieved | Pls see the link below to an updated workplan https://drive.google.com/file/d/1VD0WW3WN8rZqosw4TvNLaSX3oQhmcvsy/view?usp=sharing The trainings provided through this programme have enabled the health service providers to adapt to new ways of working and technologies to ensure that the provision of essential RMNCAH services during COVID-19 or similar situations in the future. Trained health service providers expressed their confidence in the delivering essential health services to mothers, children and patients in general in a safe as they were aware of the proper procedures, including the Infection Prevention and Control (IPC) measures that they had to follow. Following the training, providers immediately put in place the different measures required to protect themselves and their clients, based on what they learned. They reorganized health facilities with sinks installed outside of their facilities for handwashing, hand sanitizer prepared, screening and triaging prepared in all the health facilities within conditions that they have available. The telehealth is an innovative approach introduced as part of the programme to maintain essential RMNCAH services. It is considered effective and an efficient way to provide care, especially in Phonthong district where access is often difficult, with or without COVID-19. 138 women have already benefited from the telehealth service as part of the antenatal and postnatal care. This innovation for Lao PDR is very useful for patients to get immediate assistance or referral as needed and for health care providers to develop knowledge and skills with regard to early detection of at risk pregnant women and children with danger signs. This approach has already been integrated into the RMNCAH Plan of Action 2021 for other provincial areas to commence implementation, including Savannakhet, Bolikhamxai, Bokeo, Champasack and Oudomxai provinces. The tele-health function has been recommended to continue as part of the routine health services beyond the COVID-19 pandemic, especially during seasonal flooding and where women might become isolated. UNAIDS completed the development of a community guideline to provide tele-health services for People Living With HIV in 11 ART sites. Approximately 50 (31 females) participants consisting of People Living With HIV peers, nurses and doctors working in the treatment sites received training on use of the guideline to provide remote support on ARV uptake and adherence, care and psychosocial support during the COVID-19 pandemic. The participants were trained on the techniques for the provision of tele-health services including core messages for target groups. UNAIDS advocated with government partners to continue using the guideline, not only during the COVID-19 pandemic, but also post COVID-19 as tele-health services can reduce the cost of travel of People Living With HIV. Central Training of Trainers for the online IMNCI was facilitated remotely by the University of Melbourne with participants from the Lao Paediatric Association, University Health Sciences and MOH and with local partners. UNICEF supported the development and introduction of guidelines on oxygen therapy for paediatrics along with job aids for health workers. Health workers from 4 provinces were trained on oxygen therapy and the use of oxygen therapy equipment. UNICEF supported Training of Trainers and training of health workers using innovative technology, including video-based training and simulation. The University of Melbourne conducted a remote training for 12 master trainers from the University of Health Sciences, teaching hospital and Children’s Hospital, to roll out oxygen therapy for paediatrics. 27 Paediatricians and nurses and 59 health workers in Bokeo, Luang Prabang, and Attapeu provinces were trained on the provision of oxygen therapy based on the new guidelines. MoH supported by UNICEF, UNFPA, INGOs (WVI) and partners convened the consultation workshop for strengthening village health volunteers for Community based Primary Health Care from 23-25 November 2020, with. representatives from the line departments working in RMNCAH and WASH, the Department of Health Professional Education, development partners and NGOs. The main outcome of the workshop was the revision/development of draft guidance on VHV-related tasks, selection and incentives protocols, training materials and plans, and supervision and evaluation formats under the different programs for RMNCAH. This VHV messages, including newborn timely referral in detection of dangers signs and the Communtiy IMNCI, have been modeled in Pha Oudoum in Bokeo. Materials on danger signs in newborns and children and use of ORS plus zinc for diarrhea management has been disseminated to selected health centres in BK, LPB, SVK, ATP, BLK.
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words) | The key challenge is the fact that the implementation timeframe is very short. The programme has only been in operation 6 months and ongoing support and advocacy will be needed to integrate the adapted RMNCAH services , especially the tele-health modality, into the routine health services. The technical competancy of the health centre staff and volunteers in RMNCAH service provision remains low and further training is required for the remote services approach to be user friendly and effective long term. The project determined that there are 79 health service providers from 3 district hospitals and 16 health centers undertaking routine work on essential RMNCAH services, 46% of whom are trained in Family Planning (FP), only 16% trained in Basic Emergency Obstetric and Neonatal Care (BEmONC), 23% trained in Antenatal Care & Postnatal Care (ANC&PNC), 20% trained in Early Essential Newborn Care (EENC), 51% trained in Integrated Management of Newborn and Childhood Illness (IMNCI), and 27% trained in Nutrition. Key challenges in project implementation include some heads of the ART sites in the Vientiane capital contemplates the new SOP for Community ARV Drug Dispensing require a lot of preparatory work and staff time, the tele-health service concept is new to Laos so capacity of service providers are still limited, some People Living With HIVs live in remote areas where the telephone and internet usage is limited and some health service providers do not see the importance of the new innovative approaches and do not have a sense of urgency to roll out the new approach due to the fact that the COVID-19 report cases in the country is not yet high.
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words) | Telehealth: Given that this modality of reaching clients in the communities commenced in October 2020, it has already shown some positive results. The modality was found useful for patients in terms of early problem detection and responsive solutions and for health care providers in terms of relevant knowledge and skill development to deliver quality services in order to reduce maternal and child mortality and morbidity as an ultimate end. In Lao PDR, access for mothers and children to essential health services at health facilities remains problematic due to scattered and remote geographical conditions. The telehealth approach is, therefore, considered relevant and should be promoted as part of the routine health services. The telehealth should be promoted and supported to continue beyond the COVID-19 situation. Consultation through WhatsApp group for health providers is an effective way to provide instant support to health providers at the health center and district levels. Staff at health centre level, who are often isolated and far from the District Health office, can received immediate technical support required to deal with difficult cases. The platform helps to bring the practicing community close together and foster good collaboration and discussion on specific issues. It is recommended that this platform continues to function, but may need to be formalized to have more experienced staff taking turns to monitor questions and provide support. Sustainability: The development process was very participative. All 5 strategic objective sub-committees were brought together to provide technical inputs to the development of these materials. Five formal sessions, several informal sessions and validation meeting were held prior to the first training for health service providers to take place in Luang Prabang. Following the feedback from the first training, the job aid and training guidelines were revised as a result. In order to ensure sustainability of the programme, five core trainers at provincial level (from College of Health Sciences, Provincial Hospital and Health Department in Luang Prabang Province) were also trained through mentoring and co-facilitation of the trainings using the guideline on essential RMNCAH services during COVID-19 and Psychosocial Support. These core trainers conducted the second batch held in November 2020. The Luang Prabang Provincial Health Department and College of Health Sciences are now in a position to expand to other districts that have not received training.
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words)
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken. | Research on remote ANC/PNC will be conducted in February 2021 as part of the regional work
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place | Next steps in the process to implement the programme (no cost extension up to March 31st 2021): Activity Jan Feb Mar 1. Printing the essential RMNCAH Services during COVID-19 Training Guide and Job Aid 2. Constructive supervision and monitoring 3. Conduct ANC/PNC remote contact research and Lessons learned documentation 4. Dissemination meeting 5. Final report There were adjustments made to the Outcome/outputs from the original proposal, as outlined in the midterm progress report, that reduced the scope of implementation for the entire province of Luang Prabang to focus on three strategic districts based on the discussion/agreement with the provincial health team.
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners. | There is no budget revision based on the original proposal. However, UNFPA has made additional core budget of 17,000 $ available to support the programme since the psychosocial component required specific technical support which was not originally planned, as well as further 15,000 $ for a staff to cover the extension period of three months. MPTF budget received is fully utilised

## RBM-Annual
| Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 1[1] | • Phoukhoun District: The actual baseline is 59.5% up to June. This indicator is fully achieved as targeted (100%): 100% of 505 pregnant women have received ANC1 by the end of December 2020 • Phonthong District: The actual baseline is 49.1% up to June.This indicator is fully achieved as targeted (100%): 734 of pregnant women have received ANC1 by the end of December 2020 | • Luang Prabang District: It is noted that Luang Prabang District is close to the provincial hospital. It is obvious that most pregnant women visit the provincial hospital instead of the district hospital because of better health facilities. But, there is no effective system in place to track how many pregnant women from the Luang Prabang district hospital catchment area having received ANC from the provincial hospital. At the same time, the provincial hospital does not have its data available in the DHIS2. As a result, it shows the low percentage (9.1%) of ANC1 for Luang Prabang District, but does not reflect reality. Therefore, setting a target to achieve is not applicable (NA). | DHIS2
Indicator: 2.1a1 – proportion of pregnant women receiving at least 1 ANC check
Baseline: 91 %
Planned Target: 100%
2.1a2 – proportion of pregnant women receiving at least 4 ANC checks Baseline: 59% Planned Target: 80% | • Phoukhoun District: The actual baseline is 36.1% up to June.This indicator is almost achieved as targeted (80%): 78.4% of 505 pregnant women have received ANC4. • Phonthong District: The actual baseline is 23.5% up to June.This indicator is not achieved as targeted at (80%): 56% of 734 pregnant women have received ANC4. | • Luang Prabang District: (the same explanation as above) • Phonthong District: This indicator is not achieved as targeted at (80%): 56% of 734 pregnant women having received ANC4 is quite significant, given the fact that actual baselinewas as low as 23.5%. | DHIS2
2.1b1 - # of people living with HIV receiving support from home delivery of life saving drugs and telehealth services Baseline: 0 Planned Target: 5200 | The SOP for Community ARV Drug Dispensing was developed and introduced to 80 service providers (doctors, nurse, pharmacist, and People Living With HIV) working in 10 ART sites in seven provinces, including providing support for coaching and monitoring at the sites. Furthermore, a community guideline was also developed to provide tele-health services for People Living With HIV in 11 ART sites. 50 participants consisting of People Living With HIV peers, nurses and doctors working in the treatment sites received training on use of the guideline to provide remote support on ARV uptake and adherence, care and psychosocial support during the COVID-19 pandemic.
2.1b2 - # of people receiving support from home visits for SRMNCAH care Baseline: 1425 received ANC1 home visits 890 received ANC4 home visits 222 received PNC within 2 days Planned Target: 1567 received ANC1 home visits 979 received ANC4 home visits 244 received PNC within 2 days | Targets related to ANC1 & ANC4 are not achieved. However, the target related to PNC within 2 days is fully achieved: • Luang Prabang District: PNC within 2 days is fully achieved: All 22 women after deliveries have received PNC.within 2 days. • Phoukhoun District:PNC within 2 days is fully achieved: all 138 women after deliveries have received PNC within 2 days • Phonthong District: PNC within 2 days is fully achieved: all 71 women after deliveries have received PNC within 2 days. | There are a very few staff at health facilities, and thus mobile outreach is not conducted regularly. Accordingly, the intervention has not achieved the target. There are some pregnant women receiving ANC1 & ANC4 through home visit since October - December 2020: • Luang Prabang District: The actual baseline of ANC1 through home visit is only 12: the actual achievement is 56 pregnant women provided with ANC1 through home visit. The actual baseline of ANC4 is only 9: that is, 37 pregnant women have actually received ANC4 through hom visit. • Phoukhoun District: The actual baseline of ANC1 through home is 23: The actual achievement is 81 pregnant women. The actual baseline of ANC4 through home visit is 23: the actual achievement is, 72 pregnant women have received ANC4 through home visit. • Phonthong District: The actual baseline of ANC1 throug home visit is 36: the actual achievement is 74 pregnant women. The actual baseline of ANC4 through home visit is is 10: there are 18 pregnant women having received ANC4. | Monthly reported by 3 district hospitals and 16 health centers
2.1b3 - # of people receiving support by telehealth services for SRMNCAH care Baseline: 0 Planned Target: 14270 | New target is 150: the actual is 148 almost achieved: • Luang Prabang District: This indicator is almost achieved as targeted (50): that is, 46 women have received ANC and PNC through the telehealth. • Phoukhoun District: This indicator exceeds the targeted (50): 52 women have received ANC and PNC through the telehealth. • Phonthong District: This indicator is not reached (50): the actual is, 40 women have received ANC and PNC through the telehealth. | Since October 2020, the telehealth has rolled out. The trained health service providers still need more support to be confident in providing the telehealth. Yet, support is provided through WhatsApp by the advisory team (Provincial team and UNFPA). Despite, the new method and limited time, the telehealth is more and more recognized as an effective and efficient approach to detecting at right pregnant women for referral and care in a timely manner. The Ministry of Health high officials are supportive of the telehealth approach recommending to integrated into the plan of action 2021 in Luang Prabang, Savannakhet, Bokeo, Boulikhamxay povinces. | Monthly reported by 3 district hospitals and 16 health centers Annual Review and Planning Meeting on 24 December 2020, Ministry of Health
2.1c1 - # of CSOs and NGOs engaged in community health awareness activities Baseline: 0 Planned Target: 2 CSOs | Yes. It is fully achieved. 2 INGOs were involved in the planning process to scale up. That is, Luang Prabang Provincial Health Department highly considered this is the good approah to maintaining RMNCAH services during COVID-19. On 25 December 2020, it hosted an Introductory Meeting with all heads of 12 district health offices and district hospitals and INGOs (Swiss Red Cross and Save the Children) working in the field of RMNCAH. There were 82 participants joining the meeting. Luang Prabang Health Department is planning to coordinate with all INGOs to expand this modality to other districts throughout the province. The capacity of two CSOs - Association for People Living with HIV/AIDS and the Community Health Inclusion Association were strengthened to respond to the COVID-19 pandemic. 99 PLWHIV peers, 21 MSM, 50 FSW received training on COVID-19 prevention measures for delivery of COVID-19 information in the context of HIV response. The training participants have promoted key protection messages among their peers namely wearing mask, washing hands and practicing social distancing.
Ouput 1.1.1 Health system strengthened, and resilience built on SRMNCAH service provision | Yes. It is fully achieved: Essential RMNCAH Services during COVID-19 Training Guide and Job Aid are developed and Finalized. The Ministry of Health high officials are supportive of the adapted RMNCAH service modality, for example the telehealth approach. The Annual Review and Planning of the Ministry of Health recommended to integrated the telehealth into the plan of action 2021 in Luang Prabang, Savannakhet, Bokeo, Bolikhamxay provinces.
Indicator 2.2.1a – reorganized plan of SRMNCAH service for crisis developed service provision
Baseline: No
Planned Target: Yes
Indicator 1.2.1a – essential medicine for home delivery mechanisms for people living with HIV/AIDS developed incl. telehealth opportunities for patients | UNAIDS completed the development of community guideline to provide tele-health services for PLWHIV in 11 ART sites.
Baseline: No
Planned Target: Yes
Indicator 2.2.1.c – partnership with CSO/INGOs established to ensure continuity of SRMNCAH services | Yes. It is fully achieved. In the process of developing and adopting the Essential RMNCAH Services during COVID-19 Training Guide and Job Aid, INGOs like Save the Children, Swiss Red Cross were invited to participate. They were also invited by Luang Prabang Provincial Health Department to the Introductory Meeting coordination and scaling up this modality through Luang Prabang.
Baseline: No
Planned Target: Yes
Please inlcude all three: Baseline, Planned Target and Achieved Targets
[1] Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.

## Communication-Annual
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
https://drive.google.com/file/d/1VUeuoiRbwRU8mxIjJytww7xfp386Kv-I/view?usp=sharing
https://drive.google.com/file/d/1c9db1y3-NQok5mGIqS5R394ktuZgNtDY/view?usp=sharing
https://drive.google.com/file/d/1PCEMe7b9T1ZT725x7PjrXxDNdzYTo3_p/view?usp=sharing
https://drive.google.com/file/d/1YcXoSP73yVB5BofJOUwCArnYQOHSJBf7/view?usp=sharing
https://drive.google.com/file/d/1gR1Q0NXXPlBPP4usy0pDwQ0hWNjheu4u/view?usp=sharing
https://drive.google.com/file/d/1JtAw34wbBNd0GA57-CBAidteMCdEj0RI/view?usp=sharing
https://drive.google.com/file/d/1T9YRWTJc7C-A9r7kJc7_0crGmxan45g9/view?usp=sharing
https://drive.google.com/file/d/1CgCyjXBXpP83UGbI3bLN0efJDIcH8OMJ/view?usp=sharing
2. Upload here: Communications and Visibility (OPTIONAL)
Fund's Communication Guidelines is posted here: http://mptf.undp.org/document/download/25941
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well picture material please make sure you include all credits and upload them in high resolution Call1 countries.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board
https://lao.unfpa.org/en/news/lao-women-econsult-their-reproductive-health-needs
https://drive.google.com/file/d/1PniV25ECmoLglQcnOp6FySPQeIxwhapU/view?usp=sharing
https://www.laophattananews.com/archives/98836
http://kpl.gov.la/En/Detail.aspx?id=57395
https://drive.google.com/file/d/1MQahO2-2qtl5QwFmXh1O7eCBBWwcjtRb/view
https://drive.google.com/file/d/1lbCcUChnN3fS0gr3aaNGTuXAQzoiNanu/view?usp=sharing

## General Information-Final
Programme Title & Project Number | Programme Duration
Programme Title: | Overall Duration (months)
Programme Number (if applicable) | Start Date (dd.mm.yyyy)
MPTF Office Project Reference Number: | Original End Date (dd.mm.yyyy)
Country | Current End date(dd.mm.yyyy)
Recepient UN Organizations | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | National counterparts (government, private, NGOs & others) and other International Organizations
Report Cleared By
o Name:
o Title:
o Email address:
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the relevant decision-making body/Steering Committee.
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Final
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum)
2 | Purpose (and Beneficiaries) | Please include the number of both direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups
3.1 | Results: Outcome Level | Please include outcome level results achieved
3.2 | Results: Output Level | Please include output level results achieved
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words)
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words)
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words)
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken.
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners.

## RBM-Final
| Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 1[1]
Indicator:
Baseline:
Planned Target:
Output 1.1
Indicator 1.1.1:
Baseline:
Planned Target:
Indicator 1.1.2:
Baseline:
Planned Target:
Output 1.2
Indicator 1.2.1:
Baseline:
Planned Target:
Indicator 1.2.2:
Baseline:
Planned Target:
Please inlcude all three: Baseline, Planned Target and Achieved Targets
[1] Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.

## Communication-Final
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
2. Upload here: Communications and Visibility (OPTIONAL)
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well picture material please make sure you include all credits and upload them in high resolution Call1 countries.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board