## OVERALL REPORTING INSTRUCTIONS
OVERALL INSTRUCTIONS
1 | All questions/sections must be responded to before submitting to secretariat. Once the document is uploaded in the relevant folder (as per instruction below) please email the secretariat.
2 | To ensure high quality narrative and results reports please pay attention to the following details: a) A well written, succinct summary that is very clear about what was done during the reporting period and results achieved, with a priority on concrete activities, beneficiaries reached and achievements beyond processes b) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document; c) In case certain indicators are not longer relevant, an explanation for why they are not. d) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document and how they align with the overall SERP joint workplan, and connection to reporting on global-level SERP indicators e) Indicate the relevant SERP monitoring framework global indicators that were contributed to as part of this project. f) An honest analysis of challenges faced, the responses to these challenges and the extent to which these responses were successful or not g) Go beyond generic, standard and well documented features of successful project implementation when reflecting on innovation and focus on what is truly new for you and which could enable replication efforts
3 | You must submit this completed workbook by uploading it in the relevant Project Folder here (https://undp.sharepoint.com/:f:/r/sites/covid19mptfcall1/Shared%20Documents/2020-REPORT?csf=1&web=1&e=j3cc3J). Please note if you are unsure of your project number please refer to http://mptf.undp.org/factsheet/fund/COV00
A | ANNUAL REPORT
DEADLINE: 31 January 2021
4 | ALL projects that received funds in 2020 must complete annual report, HOWEVER if you have your project ending on 31st December 2020 - your FINAL report is your annual report.
5 | If you received a no-cost extension on your project please do the annual report and in a few months time you can update the annual report to include activities to complete your end of project report.
6 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.
B | END OF PROJECT - FINAL REPORT
DEADLINE: 31 January 2021
7 | ALL projects that received funds in 2020 must complete annual report, HOWEVER if you have your project ending on 31st December 2020 - your FINAL report is your annual report.
8 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.

## General Information-Annual
Programme Title & Project Number |  | Programme Duration
Programme Title: | COVID-19 EMERGENCY RESPONSE FOR CONTINUITY OF MATERNAL AND NEW-BORN HEALTH SERVICES | Overall Duration (months) | 11
Programme Number (if applicable) |  | Start Date (dd.mm.yyyy) | 2020-12-05
MPTF Office Project Reference Number:[2] |  | Original End Date (dd.mm.yyyy) | 31/12/2021
Country | MALAWI | Current End date(dd.mm.yyyy) | 31/03/2021
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | UNFPA, UNWomen, WHO | National counterparts (government, private, NGOs & others) and other International Organizations | Ministry of Health-Reproductive Heath Unit; Family Planning association of Malawi (FPAM), National Health Helpline “Chipatala cha pa foni and CCJP (Catholic Commission for Justice and Peace).
Report Cleared By
o Name: | Juliana Lunguzi
o Title: | SRHR Coorinator
o Email address: | jlunguzi@unfpa.org
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the Secretary-General's Designate
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Annual
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum) | Covid-19 specific maternal neonatal health service guidelines were developed together with UNFPA, World Health Organization and the Ministry of Health for medical professionals to follow in the healthcare of pregnant women. 1,500 copies of these guidelines were distributed to healthcare facilities across Malawi. A further 50,000 copies of guidelines for the treatment of pregnant women during Covid-19 were distributed. These allowed consistent implementation of procedures to reduce exposure and risk for pregnant women across Malawi. A total of 33 out of a target of 46 health centres supported have fully functional mechanisms in place for both the treatment of pregnant women and safe antenatal and birth facilities. These were supported by 151 specialized birth attendants to bolster their capacity. Virtual training in partnership with the Association of Malawian Midwives, the Association of Obstetrics and Gynaecologists and the Nurses Council of Malawi was also supported to ensure consistent implementation of the guidance across health institutions. To provide safe and comprehensive Emergency Obstetric and Newborn Care-EmONC services hospital equipment including 3 ventilators,10 anaesthesia machines, 20 patient monitors, 10 ultra sound machines, 56 doppler foetal heart machines, 10 vacuum extraction machines, 20 infant scales, 30 suction machines and 100 hand operated resuscitators for infants were provided to treatment centres. Equipment was also provided to focal personnel at four central hospitals , five zonal offices and six districts across Malawi- Mzimba, Karonga, Mulanje, Zomba, Mangochi and Thyolo- to enable continuity of services monitoring by providers and to access information on care during the Covid-19 pandemic. Almost 60,000 pieces of personal protective equipment were procured for healthcare professionals in the Covid-19 treatment Comprehensive Emergency Obstetric and Newborn Care-CEmONC and Basic Emergency Obstetric and Newborn Care- BEmONC service centres including makeshift taps and sinks to promote handwashing practices. To strengthen continuity of maternal and newborn care services including comprehensive obstetric emergency services refurbishment of 4 safe delivery areas were completed. The radio campaign supported has included promoting referrals and 114,917 men and boys were involved in referral and information sharing on Covid-19. A specialized hotline received calls from 182,727 women and adolescents sharing vital information and providing counselling with experienced operators providing expert advice. The Ministry of Health in coordination with UNFPA has also established a reporting mechanism of Covid-19 pregnant women in the national situation report for more accurate information dissemination, follow up, visibility and response. This was under a concerted effort with the Public Health Institute of Malawi surveillance unit capturing data from all 45 testing sites. A series of 16 programmes were aired on 14 different radio and television stations throughout the Covid-19 pandemic highlighting referral pathways and information on sexual and reproductive health and rights. To increase community reach 50 male champions were selected to promote women and adolescent girls and their access to health services as part of the action plans from the HeForShe Barbershop toolbox.
2 | Purpose (and Beneficiaries) | Please include the number of direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups | 75,600 safe births were attended by skilled health personnel during Covid-19. 256,282 women utilized maternal and newborn services during Covid-19 (ages 15-44) 182,727 women of childbearing age including pregnant women and adolescents accessed advice and counselling from a hotline service. 114,917 men and boys involved in referral and information sharing on Covid-19. Estimated reach of community radio 2,000,000; bulk SMS 549,689, direct engagement 14,248, 182,727 accessed hotline.
3.1 | Results: Outcome Level | Please include outcome level results achieved | 268,168 pregnant women have continuity in utilization of Maternal and Newborn health services throughout the Covid-19 pandemic. 75,600 safe births were attended by skilled health personnel during Covid-19. 90 percent of pregnant women including adolescents attending ANC in the target facilities attend all their scheduled ANC visits during the COVID-19 period. 80 percent of all designated BEmONc facilities that performed all 7 signal functions during the COVID-19 period.
3.2 | Results: Output Level | Please include output level results achieved | 51,500 copies of guidelines and protocols distributed to health centres nationwide. 33 health facilities that have mechanisms in place for treatment of pregnant women during covid-19 in line with protocols and guidelines that are aligned to WHO standards. 33 Covid-19 treatment centres, hospitals and health centres that have Covid-19 safe antenatal and birth facilities. 151 of safe birth attendants attended by UNFPA supported personnel during Covid-19. An estimated 2,563, 937 accessed information, advice and counselling from a hotline service or public outreach campaign on community radio. 884 women accessing referrals to COVID-19 treatment centres. 114,917 men and boys involved in referral and information sharing on covid-19.
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words) | The fiduciary risk level remains low and the UNFPA managed HACT framework has ensured transparency in procurement and value for money. The most significant challenge was related to the delays in procurement and delivery due to pressures of Covid-19 on the already fragile health sector. A further challenge in this response was the speed at which decision making and procurement processes could be accelerated during the start of the pandemic. Virtual consultations over key intervention sites with government departments were crucial to the delivery of the emergency response. At the same time, however, it also required considerable time and planning in the face of a growing crisis. Because of competing priorities coupled with bureaucratic red tape various activities including refurbishments of theatres were delayed. Covid-19 proof working methods also raised challenges in site meetings and liaising with key departments in government. This led to delays in disbursement of funds. In order to expedite processes UNFPA assigned operational priorities to procurement and key milestones have since been achieved. Covid-19-specific commodities were also in very low supply including personal protective equipment but also regular supply chains and transport infrastructure were affected as global and local supply chains and the transport of commodities slowed down mirroring economic shutdowns.
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words) | The pandemic has also created increased demand for data and data driven solutions. Rapidly evolving patterns in the spread, testing, deaths and recoveries of Covid-19 cases requires “fast” data to remain relevant. The National Statistical Office and UNFPA primarily utilize “slow” data for example censuses, surveys, annual population estimates, which can be too static to inform decision-making in rapidly changing environments such as pandemics but can also be employed to inform response strategies, priorities and plans. In this respect, we have learnt how important it is to have access to joined up data systems that can utilize a range of presently disparate data platforms able to respond to real time emergencies where time and information can be the critical differences between life and death. Technology is a complementary tool rather than a replacement for our working environment is one of the key lessons learnt in 2020. Technological solutions and flexible models for engaging with communities are extremely promising but will require investment and a period of time to be fully adopted. New more flexible and remote services using digital technologies can play a crucial role in taking pressure off the healthcare system and empowering communities with the promotion of advice and self-care services. This can improve services, and although it cannot replace physical interactions with and within communities, there is a crucial place for innovative technical solutions. Engaging with communities at all levels remains crucial and this requires a strong physical presence and engagement in the field. Communities engaging their local leaders face-to-face to hold them accountable and resolve issues have assisted in accelerating implementation and coordination of activities. Empowering communities with skills and knowledge to do things for themselves gives them a sense of control of their lives from physical learning.
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words) | The 3 UN agencies have demonstrated the importance of working together to achieve synergies and leverage on resources. Other partners that have been involved include College of Medicine and Kamuzu College of nursing to adapt and disseminate the FFP/MNH guidelines to health workers. They have also been involved in orienting the health workers on the guidelines thorugh virtual platforms. CCJP through its three dioceses has leveraged on existing partnerships with state and non-state actors at district and community levels to facilitate the buy-in of the interventions. District Councils in all the five districts (Blantyre, Mulanje, Mwanza, Lilongwe and Mzimba) have been very supportive in providing information and personnel to help mobilize community structures. The councils have also ensured that the implementing dioceses are part of the respective district COVID-19 Task Force teams. This has ensured that interventions are complementary and not in isolation and duplicated. In one example, CCJP Lilongwe has been linked to Concern Universal (CU) a local NGO who have interventions on COVID-19 response in the same TA as the MPTF project (TA Tsabango). Similarly, in Mzuzu CCJP has been linked to COIDA a local NGO which implements a similar project in Traditional Authority Chindi. Project specific partners such as Chipatala cha pa foni have also been instrumental in the design and dissemination of information through community radios. Additionally, messages developed have been recorded into jingles translated into 3 local languages and posters that will be disseminated in health centers during the final quarter of implementation. With support from MPTF through UN Women Malawi, Chipatala cha pa foni (CCPF) the national health helpline, worked with CCJP to orient CCPF workers to GBV concepts, identification, referral and reporting. CCPF has received additional equipment and temporary staff with support from MPTF which has led to more people accessing CCPF services. A total of 6919 clients were reached with health information of which 3827 were interested in Covid-19 information. Maternal health information was provided to a total of 363 pregnant women while 1050 adolescents were among the beneficiary of quality health information. The COVID19 response did not isolate pregnant women and those women of childbearing age as special target group. The project highlighted the need of not leaving anyone behind and making sure that special groups like pregnant women need special targeting and the data reporting also needs a special highlight of pregnant women who needed special follow-up and care.
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken. | EmONC assessment completed A rapid assessment of effects of Covid 19 on pregnant women and the youth in 3 districts completed
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place | While there was initial plans to refurbsh theatres in a minimum of 6-districts the estimations from MoH required large financial inputs-hence the plan was revisited to focus on EmONC equipment procurement and refurbish a theatre in 2 identified district. The Ministry undertook an EmONC assessment to understand the effects of Covid 19 on FP/MNH services in the country. Some of the work was supported with financial support form the project. i.e. data analysis and generation of tables in readiness for the report writing. the draft report is now out.
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners. | Human resources was recruited to support programme implementation. Equipment and supplies were procured as per project plans as part of protective wear for project implementation, support to virtual communication and equipment and supplies for the provision of MNH care services. Available agency resources were leveraged to ensure maximum output of the project. The project was not implemented in isolation. Other resources were mobilized both locally and regionally to support MNH service provision. For example through 2gether 4SRHR project, WHO procured Covid 19 testkits and printed registers wheich were handed over to the Ministry of Health. UNW: Support provided for 6 CCPF support staff; 10 Desktops, 2 Laptops, 10 GSM Handsets and 3 Mobile Phones; 1000 masks, 1000 hand santinizers, 1000 buckets, 1000 bars of soap

## RBM-Annual
| Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
| 268168 |  | MOH/UNFPA
Indicator: Outcome: Pregnant women have continuity in utilization of Maternal and Newborn health services throughout the Covid-19 pandemic.
Baseline:0
Planned Target: 300,000
Outcome indicators | 268168 |  | MOH/UNFPA
1 Pregnant women have continuity in utilization of Maternal and Newborn health services throughout the Covid-19 pandemic.
Target: 300,000
2 Number of safe births attended by skilled health personnel during Covid-19.
Target: 140,000 | 75600 |  | MOH/UNFPA
3 Percentage of pregnant women including adolescents attending ANC in the target facilities that attend all their scheduled ANC visits during the COVID-19 period.
Target: 100 | 90 |  | MOH/UNFPA
4 Percentage of all designated BEmONc facilities that performed all 7 signal functions during the COVID-19 period
Target: 100 | 80 |  | MOH/UNFPA
Output 1.1.1: Protocols and guidelines established to review guidelines and ensure compliance of facilities for the treatment of pregnant women during Covid-19
Number of copies of guidelines and protocols distributed to health centers nationwide. | 51500 |  | MOH/UNFPA
Target: 20,000
Number of health facilities that have mechanisms in place for treatment of pregnant women during covid-19 in line with protocols and guidelines that are aligned to WHO standards.
Target 46 | 33 |  | MOH/UNFPA
Output 1.2.1 Strengthened continuity of maternal and new-born health services including provision of comprehensive obstetric care services operations during covid-19
Number of Covid-19 treatment centers, hospitals and health centers that have Covid-19 safe antenatal and birth facilities.
Target 46 | 33 | Rehabilitation of operating thares completed | MOH/UNFPA
Number of safe births attended by UNFPA supported personnel during Covid-19.
Target 290 attendants | 151 |  | MOH/UNFPA
Output 1. 3.1 Increased access to information, support and referral systems
Number of women of childbearing age including pregnant women and adolescents accessing advice and counselling from a hotline service.
Target 4,000,000 | #REF! | Estimated reach of community radio 2,000,000; bulk SMS 549,689, direct engagement 14,248, 182,727 accessed hotline
Number of women accessing referrals to COVID-19 treatment centers. | 182,727 accessed hotline
Target 1000 (revised to correct mistake in project document) | 884
Number of men and boys involved in referral and information sharing on covid-19.
Target 350,000 | 114917

## Communication-Annual
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
‘Discrimination nearly drove me to the edge’ Grace, not real name, woke up feeling exhausted. She had an appointment with her doctor for the monthly antenatal session. She pulled herself out of bed and readied for her journey to the hospital. When she reached the hospital, the COVID-19 screening team discovered that her temperature was abnormally high. She was referred for further testing as they suspected that she may be infected by COVID-19. The results came out positive. “I couldn’t believe it at first when they told me of the results,” says Grace who was eight months pregnant, “I had thought the symptoms I was having were the result of my pregnancy.” Pain and more pain Health staff advised her to go home and self-isolate as the symptoms weren’t that severe. She was to come back after 14 days for another test. However, after a few days, Grace had difficulties in breathing. She went back to the hospital and was given some antibiotics. “I was treated as an out-patient,” explains Grace. “However, I felt that I needed to stay a bit in the hospital as I wasn’t feeling well. I took heart in the fact that I was to come back to the hospital in a few days for may antenatal session.” Grace went back to hospital as advised by the health staff. When it was her turn to see the nurse, she handed over her health passport. The nurse panicked when she realized that Grace was COVID-19 positive. She dropped the health passport on the table and rushed out of the room. Feeling discriminated because of COVID-19 The reaction of the nurse almost caused a commotion in the antenatal room. The health staff convened a quick meeting and ushered Grace into a separate room. “They didn’t use the regular door for patients to get me out of the room,” she recollects with a voice ridden with emotions. “They used the back door. I feared for the worst since even the health staff were afraid to be close to me.” Alone in the isolation room, Grace waited for medical help that never came. Around 4.pm, a clinician came only to tell her to go home. “I was devastated as I was in the room since eight in the morning,” she says. “My head was throbbing and couldn’t think straight. I felt like I was already dead.” Back home, Grace narrated her ordeal to her husband. The pair then sought advice from a friend in Lilongwe, working in the medical sector. He told them about success stories of pregnant women with COVID-19 getting treated at Kamuzu Central ‘s (KCN) Ethel Mutharika maternity ward in Lilongwe. They immediately sought for a transfer to Lilongwe. The couple’s decision would prove to be wise. Grace’s pregnancy was the fourth. But she lost all the three children. Renewed hope at Kamuzu Central Hospital “I feared for the worst as I had been going through difficult pregnancies and now this discrimination,” recalls Grace, “However, I was relieved when we arrived at Ethel Mutharika ward. We met a doctor who was so helpful and treated us like any other patient.” Doctor Priscilla Mwanza, who attended to Grace says, after having heard of her previous pregnancy history, she immediately knew that she required more than special care. “Most patients in her situation become very anxious, and can develop mental problems if they don’t receive immediate medical support,” she says. “When she arrived, I made sure that we take her through all the routine procedures such as testing for other diseases like diabetes and also ultrasound’ “In her case, she also needed counselling. We did that and also assured her that, as an institution, will do our best to have her treated and so that she delivers her child in good health.” After treatment at KCN, Grace finally tested negative, and by then, she was due to give birth. And she delivered a bouncing boy. “We named him Jefter, which means ‘mighty man’,” she says. “For me his birth is more than a miracle as I went through a lot and came out alive. I am very much grateful to the health staff at KCN, especially Dr. Mwanza, who was there for me all the time.” The Joint Program, through the United Nations Multi Partner Trust Fund (MPTF), has been supporting KCN maternity wing with variety of supplies to enable health workers to offer pregnant women suffering from COVID-19 specialised treatment. Some of the equipment includes 20 litre water buckets, medical masks for health staff, gowns, scrub suits, head and shoe covers. Across the country, UNFPA is also supporting the refurbishment of maternity facilities to provide specialised care to pregnant women suffering from coronavirus.

## Communication-Final
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
In the words of Alepher Matemba Banda: “She can take charge of her body, monitor her health status and be safe, all because of a phone call”
Thirty- one-year old Alepher Matemba Banda is a Hotline nurse at Chipatala cha pa foni, a national health Helpline in Malawi. Alepher was a participant of a gender-based violence and health, supported by UN Women with funding from UN Multi-Partner Trust Fund Office (MPTF). Forty hotline nurses and technicians were taught how to provide pregnant women and adolescent girls with information, support and referral systems on gender-based violence and Maternal, Neonatal and Sexual Reproductive Health in light of COVID-19.
Recently, the majority of calls I receive on the hotline concern challenges that clients are facing with the outbreak of COVID-19. Many pregnant women are worried because they do not have resources to prevent getting COVID-19, while girls are concerned about unplanned pregnancies due to scarcity of family planning methods in health facilities. I provide information on COVID-19 signs and symptoms, locations of test centres and preventative measures using a computerized system. Our clients, who are mostly pregnant women and adolescent girls call through a toll-free line 54747.
Lately, there has been an increased number of callers seeking information on COVID-19, but we also receive calls from clients on incidents of gender-based violence. Before I was trained on gender-based violence and health, I didn’t have a clear understanding of what gender-based violence is, so I couldn’t adequately identify forms of gender-based violence and handle clients facing violence. If I suspected cases of violence, I would just report the case to my supervisor without providing any temporary assistance to the client. The training was an eye opener for me. When listening to a client, I am now able to identify survivors of gender-based violence, what type of violence they are experiencing and help them without re-victimising them. The best thing is that I now know about the police victim support unit and other organisations that I refer clients to.
I have been working at Chipata cha pa foni for 3 years, in that time my focus was on health information, now, when I’m working, I can recognize underlying issues like gender-based violence that clients are struggling with. I am so proud to have the knowledge and skills to help scared pregnant women or adolescent girl facing difficult situations. She can take charge of her body, monitor her health status and be safe, all because of a phone call.
Picture credit of UNW- The National Health helpline (chipatala Cha pa foni) - August 2020
See - Fund's Trello Board
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well picture material please make sure you include all credits and upload them in high resolution Call1 countries.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.

## Images
Bwaila hospital refurbishments
Multiparameter equipment for monitoring.