## OVERALL REPORTING INSTRUCTIONS
OVERALL INSTRUCTIONS
1 | All questions/sections must be responded to before submitting to secretariat. Once the document is uploaded in the relevant folder (as per instruction below) please email the secretariat.
2 | To ensure high quality narrative and results reports please pay attention to the following details: a) A well written, succinct summary that is very clear about what was done during the reporting period and results achieved, with a priority on concrete activities, beneficiaries reached and achievements beyond processes b) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document; c) In case certain indicators are not longer relevant, an explanation for why they are not. d) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document and how they align with the overall SERP joint workplan, and connection to reporting on global-level SERP indicators e) Indicate the relevant SERP monitoring framework global indicators that were contributed to as part of this project. f) An honest analysis of challenges faced, the responses to these challenges and the extent to which these responses were successful or not g) Go beyond generic, standard and well documented features of successful project implementation when reflecting on innovation and focus on what is truly new for you and which could enable replication efforts
3 | You must submit this completed workbook by uploading it in the relevant Project Folder here (https://undp.sharepoint.com/:f:/r/sites/covid19mptfcall1/Shared%20Documents/2020-REPORT?csf=1&web=1&e=j3cc3J). Please note if you are unsure of your project number please refer to http://mptf.undp.org/factsheet/fund/COV00
A | ANNUAL REPORT
DEADLINE: 31 January 2021
4 | ALL projects that received funds in 2020 must complete annual report, HOWEVER if you have your project ending on 31st December 2020 - your FINAL report is your annual report.
5 | If you received a no-cost extension on your project please do the annual report and in a few months time you can update the annual report to include activities to complete your end of project report.
6 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.
B | END OF PROJECT - FINAL REPORT
DEADLINE: 31 January 2021
7 | ALL projects that received funds in 2020 must complete annual report, HOWEVER if you have your project ending on 31st December 2020 - your FINAL report is your annual report.
8 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.

## General Information-Annual
Programme Title & Project Number |  | Programme Duration
Programme Title: | COVID-19 EMERGENCY RESPONSE FOR CONTINUITY OF MATERNAL AND NEW-BORN HEALTH SERVICES | Overall Duration (months) | 11
Programme Number (if applicable) |  | Start Date (dd.mm.yyyy) | 2020-12-05
MPTF Office Project Reference Number:[2] |  | Original End Date (dd.mm.yyyy) | 31/12/2021
Country | MALAWI | Current End date(dd.mm.yyyy) | 31/03/2021
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | UNFPA, UNWomen, WHO | National counterparts (government, private, NGOs & others) and other International Organizations | Ministry of Health-Reproductive Heath Unit; Family Planning association of Malawi (FPAM), National Health Helpline “Chipatala cha pa foni and CCJP (Catholic Commission for Justice and Peace).
Report Cleared By
o Name: | Juliana Lunguzi
o Title: | SRHR Coorinator
o Email address: | jlunguzi@unfpa.org
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the Secretary-General's Designate
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Annual
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum) | This report responds to the progress made so far in enabling pregnant women to access basic maternal and new-born health services during the COVID-19 pandemic by delivering three outputs: 1) Protocols and guidelines established to ensure compliance of facilities for the treatment of pregnant women amidst COVID-19; 2) Strengthened continuity of maternal and new-born care services including comprehensive obstetric emergency services during COVID-19; and 3) increased access to information, support and referral systems for pregnant women and new-borns. MNH (Maternal Neonatal Health) services guidelines were developed by the Ministry of health with technical and financial support from the UNFPA, WHO. A total of 1500 MNH guidelines were printed and handed over to the Ministry of Health, Reproductive Health Department and distributed to all facilities in August through the zonal offices for all 5 zones, Northen, Central East, Central West, South East and South West zones. Support with internet connectivity was provided through the RHD, the association of Midwives and Obstetrics and gynaecology to ensure virtual participation on updates on MHH protocols and share on-going lessons on the management of positive covid-19 clients. WHO procured 15 Laptops which were provided to focal personnel at central hospitals 4, zonal offices 5 and 6 districts across Malawi (Mzimba, Karonga, Mulanje, Zomba, Mangochi and Thyolo) to enable continuity of services monitoring by providers in selected districts to access information on MNH care during the COVID Pandemic. UNFPA has also procured additional laptops for RHD,MoH central and other Zone managers that will enable them to access virtual information on MNH. UNFPA through Ministry of Health supported a dedicated person to follow up COVID-19 response plans thereby ensuring on-going surveillance of the situation of covid19 pregnant women in the national situation report for more accurate information dissemination, follow up, visibility and response. This was under a concerted effort with the Public health institute of Malawi surveillance unit capturing data from all 45 testing sites. Currently Malawi has 55 pregnant women (data capture ongoing) who tested positive for COVID. In supporting the continuity of health services UNFPA procured various PPEs (Personal Protective Equipment) delivered through Ministry of Health to health facilities providing CEmONC (Comprehensive Emergency Obstetric and Newborn services) and BEmONC (Basic Emergency Obstetric and Newborn Care services. A total 2,400 pieces of buckets with taps to promote handwashing practices as preventive measures against the pandemic were procured and distributed in various service delivery points with a priority given to the 11COVID-19 treatment centres. A total of 960 theatre tunics and 250 reusable cloth aprons for our frontline health workers, 3500 boxes of a 100 pairs per box of disposable gloves and 50,000 N95 Masks for Personal Protection of the Hospital staff were procured locally and globally and they were distributed in service delivery points. In collaboration with WFP, selected districts were supported with temporary tents for the provision of MNH sevices. One district Dedza is being supported with the refurbishment of 2-operating theatres to ensure continuity of EmONC services. UNFPA procured hospital equipment which will benefit the facilities in providing better care in terms of MNH services. Equipment included 3 ventilators,10 Anaesthesia Machines, 20 Patient Monitors,10 Ultra sound Machines, 56 Doppler foetal heart machines, 10 Vacuum Extraction Machines, 20 Infant scales, 30 Suction machines and 100 Hand operated resuscitators for infants. The procurement through these activities will reach out to women, allowing them improved access to care in 10 districts countrywide and create more spaces for women to access CEmONC services. The lesson learnt was that with COVID-19 being an infectious disease, having one operating theatre per district hospital posed a lot of challenges for pregnant women who required caesarean section. Additionally,under this output, in collaboration with Family Planning association of Malawi (FPAM). Community Based distribution agents were trained in 15 communities to ensure provision of family planning services at the doorstep. This was done in view of the limited mobility that came with COVID-19 and the stigma that was associated with visiting health facilities. CBDAs therefore ensured continuity of care through access to family planning service right at the doorstep.under the reporting period, Under the reporting period, UN Women established partnerships with, the National Health Helpline “Chipatala cha pa foni and CCJP (Catholic Commission for Justice and Peace). The project aims to showcase two result areas i.e. (i) Increase access to SRHR-Material and New-born information and services including Gender Based Violence to women and girls including the survivors; and (ii) mobilise men and boys towards addressing gender norms and barriers to ensure support for women so that they effectively seek out services and reach clinics. Amongst the activities CCJP has conducted so far include the following: Startup activities which included a planning meeting with the UN Women and all implementing partners and others; development of a Monitoring and Evaluation (M &E) framework; and project concept orientation with district structures thus District Executive Committee (DEC) and District Health Management Committees (DHMC).Introductory meetings at community level thus with Area Development Committees (ADC), Health Advisory Committees (HAC), Village Health Committee (VHC), Police VSU and Health Surveillance Assistants have been done. A total of 16 radio programmes have been supported during the period under review (6 for Mzuzu diocese, 3 Lilongwe and 5 for Blantyre). The programs have contributed to the awareness on access to SRHR and the popularization of the project interventions. The community radio stations engagedwere; , Tigabane and Mzimba community radio stations; Maziko and Lutha radio and TV stations; Mnzati and Radio Maria respectively. The programs have since facilitated the and promoted access to SRHR information and referrals Identification of 50 (10 each per district) male champions including the clergy. The Champions are expected to support women and the adolescents to access health services as part of the action plans from the HeForShe Barbershop toolbox orientation and capacity building sessions conducted in all target districts. They will also engage in referrals and information sharing on Covid-19 which for the latter have started and the project is yet to get data on the referrals conducted so far. Engagement meetings with gate keepers to discuss the gender norms and barriers to women health seeking Behaviours. A total of 39 gate keepers have been reached so far. Provide on-going psychosocial counseling and for the reporting period a total of 1,443 women (158 previously reported and 1,285 recently reported in Mzuzu) have been reached with the services. The emphasis here was on referrals and information sharing for the pregnant women and the adolescent to access health services at the health facilities in the respective target areas Engaged 67 (30F,37M). health workers and other GBV district stakeholders in the target health centres on referral pathways and the linkages between GBV, Covid-19 and SRHR During the period under review, CCJP in all its target districts also engaged the DHOs through the DHMCs to lobby for the provision of transport to pregnant women. The meetings also aimed to identify the target areas/health facilities for the project. The areas/health facilities were chosen based on the intensity of the problems the project aims to address which includes Covid-19 prevalence and current challenges regarding access to maternal and new born health services being experienced in the areas. The project was hence thought to complement the sectors limited support in these resource constrained health centers.
2 | Purpose (and Beneficiaries) | Please include the number of direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups | 300,000 Pregnant women directly benefit by improved access to antenatal, labour and deliveries (including caesarean section to those in need) and post-natal care during the critical period of Covid-19. 800 women of childbearing age (ages 15 - 44) including adolescent girls (ages 10 - 19) were targeted to access advice and counselling from a hotline service directly. 500 Men and young boys in all communities were targeted to be involved in referral and information sharing on covid-19.
3.1 | Results: Outcome Level | Please include outcome level results achieved | Number of women who have utilized MNH services during Covid-19. # 256,282. Percentage of pregnant women including adolescents attending ANC in the target facilities that attend all their scheduled ANC visits during the COVID-19 period # 88.9%. Number of copies of guidelines and protocols distributed to health centers nationwide #1500. Data Analysis for establishment of generation tables for EmONC assessment done. A total of 50-males champions; 30-gate keepers discussion gender norms; 1443 women reached with referrals for SRHR services; 67 health workers engaged to provide referral pathways.
3.2 | Results: Output Level | Please include output level results achieved | Number of women of childbearing age including pregnant women and adolescents accessing advice and counselling from a hotline service # 6919. Number of women accessing referrals to COVID-19 treatment centers #198. Number of men and boys involved in referral and information sharing on covid-19 #476
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words) | Delay in implementation of the program as the whole health sector was overwhelmed with the response. Due to the global procurement pressure with COVID-19, delays with procurement of EmONC equipment was experiened; however progress was made albeit slow. Bureaucratic red tape in implementation of various activities-like refurbishments of theatres, government did not act with urgency on choice of areas to be supported. .Organising district level meeting with DEC and DHO in some cases as formal processes including Covid 19 restrictions had to be followed before meetings could be approved; hence took longer than expected and thus delayed project implementation. Where possible, after the consultations some few additional activities have been carried out to ensure that some outputs are delivered on time.Project period too short The project has been implemented for 6 months. While the project aimed to provide immediate response following challenges posed by covid 19, there were some behavioral aspects that the project aimed to address and these needed more time. Again, COVID 19 secondary impacts have continued to rise following the second wave. It is therefore a challenge to register project impact at this stage.
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words) | a) Involvement of health personnel in psychosocial counseling: CCJP planned to use its network of social workers which included the male championed identified under the project to help provide psychosocial counseling to survivors of GBV and those directly affected or infected with COVID-19. Engagements with the District Health Management Committees revealed that it would not be prudent to engage CCJP social workers in COVID-19 affected families as it would be putting them at high risk. Instead, it was recommended that such counseling be carried out by health personnel with proper Personal Protective Equipment (PPE). CCJP social workers will provide psychosocial support for GBV victims in collaboration with Victim Support Unit (VSU) personnel and as whistle blowers for suspected COVIDi-19 patients. The revelations have been echoed in Blantyre and Lilongwe. b) Contextual considerations in provision of transport to pregnant women and/or victims of GBV: The project planned to provide transport to pregnant women in critical conditions where vulnerable women, girls or survivors of violence cannot make it to health facilities. While it may not be as practical to use bicycle ambulances in urban settings, the approach was highly recommended in Mulanje and Blantyre rural. It is recommended that UN women be engaged on a possible re-profiling of the budget to accommodate such an initiative. c) Promotion of a one-stop-center model: Noting that the project involves multiple partners where coordination and data sharing is paramount, the inception stage has revealed that adopting a one-stop-center model would be more applicable and cost effective. In this model, the project would facilitate outreach programmes where health personnel could provide SRHR services, VSU provide a platform for reporting cases and disseminate information on GBV and COVID at one spot. It is envisaged that such an approach would help spread the messages faster while at the same time enhancing access to SRHR and GBV services and referrals. Engagements with the DHOs in Blantyre and Lilongwe have made some pointers towards this approach. d) Capacity building on GBV and Referral pathway for GBV: The training of health professional in particular those working in the National Health helpline, on GBV and referral pathway has proved to essential for the workers in responding to the callers particularly those faced and experiencing GBV issues. As a matter of fact, there has been an increase in the number of callers seeking information and guidance on this. See below on point 8, a story by one of the helpline workers giving her testimony on this. e) Virtual trainings: While service providers have special preference for training in person, the project has highlighted that virtual training is key and reduces time spent for service providers to go for trainings in person. This further allows to reach out to more service providers with information. f) Mobile health services: It is possible to decongest health facilities by ensuring that services like family planning are provided at the door step. This also allows for provision of other health services beyond family planning. g) CEmONC components: Having theatres that are readily available for pregnant women further reduces complications that arise due to delays in accessing obstetric care. 6. Budget Revisions (only if applicable) There was a plan to recruit health service providers but this plan did not go further since government already recruited additional staff and sustainability was questioned should additional staff be recruited. There was also a pan to conduct baseline assessment but the process was discouraged due to the short period of implementation.
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words) | CCJP through its three dioceses has leveraged on existing partnerships with state and non-state actors at district and community levels to facilitate the buy-in of the interventions. District Councils in all the five districts (Blantyre, Mulanje, Mwanza, Lilongwe and Mzimba) have been very supportive in providing information and personnel to help mobilize community structures. The councils have also ensured that the implementing dioceses are part of the respective district COVID-19 Task Force teams. This has ensured that interventions are complementary and not in isolation and duplicated. In one example, CCJP Lilongwe has been linked to Concern Universal (CU) a local NGO who have interventions on COVID-19 response in the same TA as the MPTF project (TA Tsabango). Similarly, in Mzuzu CCJP has been linked to COIDA a local NGO which implements a similar project in Traditional Authority Chindi. Project specific partners such as Chipatala cha pa foni have also been instrumental in the design and dissemination of information through community radios. Additionally, messages developed have been recorded into jingles translated into 3 local languages and posters that will be disseminated in health centers during the final quarter of implementation. With support from MPTF through UN Women Malawi, Chipatala cha pa foni (CCPF) the national health helpline, worked with CCJP to orient CCPF workers to GBV concepts, identification, referral and reporting. CCPF has received additional equipment and temporary staff with support from MPTF which has led to more people accessing CCPF services. A total of 6919 clients were reached with health information of which 3827 were interested in Covid-19 information. Maternal health information was provided to a total of 363 pregnant women while 1050 adolescents were among the beneficiary of quality health information. The COVID19 response did not isolate pregnant women and those women of childbearing age as special target group. The project highlighted the need of not leaving anyone behind and making sure that special groups like pregnant women need special targeting and the data reporting also needs a special highlight of pregnant women who needed special follow-up and care.
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken. | During the implementation phase, there was an on-going asessment of the status of Emergency Obstetric care services in the country, of which preliminary results will be out in due course. WHO and UNFPA supported the process which will also share some level of disruption that was encounetred with provision of MNH services.
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place | Initially the project planned to recruit human resources but this was changed after MoH indicated minimal need in the area. While there was initial plans to refurbsh theatres in a minimum of 6-districts the estimations from MoH required large financial inputs-hence the plan was revisited to focus on EmONC equipment procurement and refurbish a theatre in 1 identified district.
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners. | Human resources was recruited to suppotr programme implementation. Equipment and supplies were procured as per project plans as part of protective wear for project implementation, support to virtual communication and equipment and supplies for the provision of MNH care services. Available agency resources were leveraged to ensure maximum output of the project. The project was not implemented in isolation.

## RBM-Annual
| Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
_ftn1
Indicator: Outcome: Pregnant women have continuity in utilization of Maternal and Newborn health services throughout the Covid-19 pandemic.
Baseline:
Planned Target:
Output 1.1 | 90 | Data capture on-going | MOH/UNFPA
Indicator 1.1.1:
Percentage of pregnant women including adolescents attending ANC in the target facilities that attend all their scheduled ANC visits during the COVID-19 period.
Target: 100
Number of women who have utilized MNH services during Covid-19.
Target: 300,000 | 256282 | Data capture still on-going, other facilities yet to report | MOH/UNFPA
Number of safe births attended by skilled health personnel during Covid-19.
Target: 140,000 | 75600 | Data capture still on-going, other facilities yet to report. Covid resulted in low turn out of pregnant mothers from fear. | MOH/UNFPA
Percentage of all designated BEmONc facilities that performed all 7 signal functions during the COVID-19 period
Target: 100 | 80 | Data capture ongoing. Other Facilites yet to report. | MOH/UNFPA
| 1500 |  | MOH/WHO/UNFPA
Outcome 2: Protocols and guidelines established to review guidelines and ensure compliance of facilities for the treatment of pregnant women during Covid-19
Protocols and guidelines established to review guidelines and ensure compliance of facilities for the treatment of pregnant women during Covid-19
Target: 1500
Number of health facilities that have mechanisms in place for treatment of pregnant women during covid-19 in line with protocols and guidelines that are aligned to WHO standards.
Target: 11 | 4 | Assessment of Facilities for approval as covid sites yet to be undertaken. | MOH/UNFPA
Outcome 3: Strengthened continuity of maternal and new-born health services including provision of comprehensive obstetric care services operations during covid-19.
Number of Covid-19 treatment centers, hospitals and health centers that have Covid-19 safe antenatal and birth facilities. | 1 | BOQs were higher than planned and MoH provided just 1 great need that was responded to.
Target: 11 | 4 | Equipment has arrived. To be installed | MOH/UNFPA
Number of safe births attended by UNFPA supported personnel during Covid-19. |  | Data compilation on-going
Target: 290 | 151 | Not all facilities have compiled and reported their data | MOH/UNFPA
Increased access to information, support and referral systems (UNW)
Number of women of childbearing age including pregnant women and adolescents accessing advice and counselling from a hotline service.
Target: 800 | 6919 | The hotline service has only been fully active as of September. The response is favourable. | MOH/UNW/NGO
Number of women accessing referrals to COVID-19 treatment centers.
Target: 100 | 198 | There have been no cases that have required referrals in the reporting period which has coincided with a national drop on new cases of COVID-19 | MOH/UNW/NGO
Number of men and boys involved in referral and information sharing on covid-19
Target: 500 | 476 | As anticipated, after the training of the male champions and other engagements with men and boys, they are now being involved in facilitating referrals, psychosocial support to pregnant women and awareness raising on Covid-19 in the target areas. A total of 92 men and boys have so far been reached and are now involved in provision of such services. This includes the Health Personnel, Police Victim Support officers and the gate keepers who have continued to provide the necessary support in terms of information sharing on COVID 19 in all the five targeted districts. The health workers are the one directly involved in psychosocial support to those infected or affected with Covid-19 for safety reasons. Others is mainly to do with information sharing and referrals | MOH/UNW/NGO

## Communication-Annual
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
‘Discrimination nearly drove me to the edge’ Grace, not real name, woke up feeling exhausted. She had an appointment with her doctor for the monthly antenatal session. She pulled herself out of bed and readied for her journey to the hospital. When she reached the hospital, the COVID-19 screening team discovered that her temperature was abnormally high. She was referred for further testing as they suspected that she may be infected by COVID-19. The results came out positive. “I couldn’t believe it at first when they told me of the results,” says Grace who was eight months pregnant, “I had thought the symptoms I was having were the result of my pregnancy.” Pain and more pain Health staff advised her to go home and self-isolate as the symptoms weren’t that severe. She was to come back after 14 days for another test. However, after a few days, Grace had difficulties in breathing. She went back to the hospital and was given some antibiotics. “I was treated as an out-patient,” explains Grace. “However, I felt that I needed to stay a bit in the hospital as I wasn’t feeling well. I took heart in the fact that I was to come back to the hospital in a few days for may antenatal session.” Grace went back to hospital as advised by the health staff. When it was her turn to see the nurse, she handed over her health passport. The nurse panicked when she realized that Grace was COVID-19 positive. She dropped the health passport on the table and rushed out of the room. Feeling discriminated because of COVID-19 The reaction of the nurse almost caused a commotion in the antenatal room. The health staff convened a quick meeting and ushered Grace into a separate room. “They didn’t use the regular door for patients to get me out of the room,” she recollects with a voice ridden with emotions. “They used the back door. I feared for the worst since even the health staff were afraid to be close to me.” Alone in the isolation room, Grace waited for medical help that never came. Around 4.pm, a clinician came only to tell her to go home. “I was devastated as I was in the room since eight in the morning,” she says. “My head was throbbing and couldn’t think straight. I felt like I was already dead.” Back home, Grace narrated her ordeal to her husband. The pair then sought advice from a friend in Lilongwe, working in the medical sector. He told them about success stories of pregnant women with COVID-19 getting treated at Kamuzu Central ‘s (KCN) Ethel Mutharika maternity ward in Lilongwe. They immediately sought for a transfer to Lilongwe. The couple’s decision would prove to be wise. Grace’s pregnancy was the fourth. But she lost all the three children. Renewed hope at Kamuzu Central Hospital “I feared for the worst as I had been going through difficult pregnancies and now this discrimination,” recalls Grace, “However, I was relieved when we arrived at Ethel Mutharika ward. We met a doctor who was so helpful and treated us like any other patient.” Doctor Priscilla Mwanza, who attended to Grace says, after having heard of her previous pregnancy history, she immediately knew that she required more than special care. “Most patients in her situation become very anxious, and can develop mental problems if they don’t receive immediate medical support,” she says. “When she arrived, I made sure that we take her through all the routine procedures such as testing for other diseases like diabetes and also ultrasound’ “In her case, she also needed counselling. We did that and also assured her that, as an institution, will do our best to have her treated and so that she delivers her child in good health.” After treatment at KCN, Grace finally tested negative, and by then, she was due to give birth. And she delivered a bouncing boy. “We named him Jefter, which means ‘mighty man’,” she says. “For me his birth is more than a miracle as I went through a lot and came out alive. I am very much grateful to the health staff at KCN, especially Dr. Mwanza, who was there for me all the time.” The Joint Program, through the United Nations Multi Partner Trust Fund (MPTF), has been supporting KCN maternity wing with variety of supplies to enable health workers to offer pregnant women suffering from COVID-19 specialised treatment. Some of the equipment includes 20 litre water buckets, medical masks for health staff, gowns, scrub suits, head and shoe covers. Across the country, UNFPA is also supporting the refurbishment of maternity facilities to provide specialised care to pregnant women suffering from coronavirus.

## General Information-Final
Programme Title & Project Number | Programme Duration
Programme Title: | Overall Duration (months)
Programme Number (if applicable) | Start Date (dd.mm.yyyy)
MPTF Office Project Reference Number: | Original End Date (dd.mm.yyyy)
Country | Current End date(dd.mm.yyyy)
Recepient UN Organizations | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | National counterparts (government, private, NGOs & others) and other International Organizations
Report Cleared By
o Name:
o Title:
o Email address:
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the relevant decision-making body/Steering Committee.
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Final
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum)
2 | Purpose (and Beneficiaries) | Please include the number of both direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups
3.1 | Results: Outcome Level | Please include outcome level results achieved
3.2 | Results: Output Level | Please include output level results achieved
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words)
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words)
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words)
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken.
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners.

## RBM-Final
| Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
_ftn1
Indicator:
Baseline:
Planned Target:
Output 1.1
Indicator 1.1.1:
Baseline:
Planned Target:
Indicator 1.1.2:
Baseline:
Planned Target:
Output 1.2
Indicator 1.2.1:
Baseline:
Planned Target:
Indicator 1.2.2:
Baseline:
Planned Target:
Please inlcude all three: Baseline, Planned Target and Achieved Targets
_ftnref1

## Communication-Final
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
2. Upload here: Communications and Visibility (OPTIONAL)
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well picture material please make sure you include all credits and upload them in high resolution Call1 countries.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board