## OVERALL REPORTING INSTRUCTIONS
OVERALL INSTRUCTIONS
1 | All questions/sections must be responded to before submitting to secretariat. Once the document is uploaded in the relevant folder (as per instruction below) please email the secretariat.
2 | To ensure high quality narrative and results reports please pay attention to the following details: a) A well written, succinct summary that is very clear about what was done during the reporting period and results achieved, with a priority on concrete activities, beneficiaries reached and achievements beyond processes b) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document; c) In case certain indicators are not longer relevant, an explanation for why they are not. d) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document and how they align with the overall SERP joint workplan, and connection to reporting on global-level SERP indicators e) Indicate the relevant SERP monitoring framework global indicators that were contributed to as part of this project. f) An honest analysis of challenges faced, the responses to these challenges and the extent to which these responses were successful or not g) Go beyond generic, standard and well documented features of successful project implementation when reflecting on innovation and focus on what is truly new for you and which could enable replication efforts
3 | You must submit this completed workbook by uploading it in the relevant Project Folder here (https://undp.sharepoint.com/:f:/r/sites/covid19mptfcall1/Shared%20Documents/2020-REPORT?csf=1&web=1&e=j3cc3J). Please note if you are unsure of your project number please refer to http://mptf.undp.org/factsheet/fund/COV00
A | ANNUAL REPORT
DEADLINE: 31 January 2021
4 | ALL projects that received funds in 2020 must complete annual report, HOWEVER if you have your project ending on 31st December 2020 - your FINAL report is your annual report.
5 | If you received a no-cost extension on your project please do the annual report and in a few months time you can update the annual report to include activities to complete your end of project report.
6 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.
B | END OF PROJECT - FINAL REPORT
DEADLINE: 31 January 2021
7 | ALL projects that received funds in 2020 must complete annual report, HOWEVER if you have your project ending on 31st December 2020 - your FINAL report is your annual report.
8 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.

## General Information-Annual
Programme Title & Project Number |  | Programme Duration
Programme Title: | Safeguarding and Protecting the Most Vulnerable: Enhancing Jamaica’s Shock Responsive Social Protection Mechanisms in support of vulnerable Groups including children. | Overall Duration (months) | 5 MONTHS
Programme Number (if applicable) |  | Start Date (dd.mm.yyyy) | 2020-05-19
MPTF Office Project Reference Number: | 121616 | Original End Date (dd.mm.yyyy) | 2021-03-31
Country | JAMAICA | Current End date(dd.mm.yyyy) | 31/1/2021
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | UNICEF, JAMAICA; FAO JAMAICA | National counterparts (government, private, NGOs & others) and other International Organizations | MINISTRY OF LABOUR AND SOCIAL SECURITY & MINISTRY OF FINANCE AN THE PUBLIC SERVICE; MINISTRY OF AGRICULTURE AND FISHERIES [MOAF]; THE RURAL AGRICULTURAL DEVELOPMENT AUTHORITY [RADA]
Report Cleared By
o Name: | Shelly Trim
o Title: | Data and Results and Reporting Officer
o Email address: | shelly.trim@un.org
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the Secretary-General's Designate
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Annual
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum) | The project supported the safeguarding and protection of vulnerable farmers and poor Jamaicans registered with the Ministry of Labour and Social Security [MLSS]. It formed part of a decisive response to socioeconomic needs within the context of a diminishing fiscal space and limited human capital, against the backdrop of a global pandemic. The effects of the pandemic have been particularly detrimental to the poorest and most vulnerable social groups with incalculable negative impacts on rural farm families, children, and those with a disability. Through routine cash transfers to poor vulnerable families and the marketing of agricultural farm produce of poor rural farmers the resilience of approximately 4,100 beneficiaries were buttressed as part of the broader social protection system in Jamaica. Consistent with the resources provided through the Multi-Partner Trust Fund, the activities bolstered the capacity and responsiveness of the Government of Jamaica lead Agencies – Ministry of Agriculture and Fisheries [MOAF] and the MLSS - Protection System commencing between August 2020 by supporting local food produce consumption, and the protection and promotion of human capital accumulation. In particular, the Social Protection floor was strengthened through horizontal and vertical expansions, considering that approximately 25% of Jamaica’s children are living in poverty with those with disabilities and living in rural and peri-urban areas disproportionately affected. Parallel cash and in-kind support were provided against the backdrop of Jamaica having recorded over 5,500 positive COVID-19 cases, with over 600 being children and youth ages 0-19 years. Beneficiaries were identified through the MLSS Management Information System administered by the Programme of Advancement Through Health and Education (PATH) as well as through the Rural Agricultural Development Authority [RADA]. Recipients included: pregnant mothers; women who were lactating; families who have children with disabilities; and female farmers. Through the collaborative efforts of UNICEF and FAO care packages were also provided to children and their families registered with the Jamaica Council for Persons with Disabilities and the Early Stimulation Programme (ESP). Noteworthy is that the ESP is an early intervention programme for children (0-6 years) with various types of developmental disabilities for which the cost of services become exponentially chronic. With over 135,000 jobs being lost within the 2nd and 3rd quarters and the Planning Institute of Jamaica’s projection that the economy would have recorded declines in output ranging from 8-10 per cent, as a result of the coronavirus , strategically, the project has contributed to providing a cushion for the poorest and most vulnerable, and advanced efforts to expand social protection programmes, especially for PwD’s. The MPTF resources has contributed to softening the economic shock providing a 40% increase in the value of goods programmed by the Government, as well as providing an additional benefit beyond what was allocated. Altogether, 5,535 cash transfers were disbursed over the period and 1,000 care packages, providing a well-needed financial boost to targeted households facilitating a cushion to alleviate the harsh economic conditions; bolster the livelihoods of female farmers; and furthering a pathway that will augment social protection mechanisms and advanced efforts to expand social protection programmes, especially for PwD’s. The MPTF resources has contributed to softening the economic shock providing a 40% increase in the value of goods programmed by the Government, as well as providing an additional benefit beyond what was allocated
2 | Purpose (and Beneficiaries) | Please include the number of direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups | 757 Households with Pregnant and Lactating women. 2,180 Households (1,340 boys & 840 girls) with children with disabilities. 1,000 Households targeted through ESP, JCPD & PATH with girls and boys ages 3-5 years experiencing food insecurity because of the effects of Covid-19. 200 farmers have participated in the agriculture produce support programme.
3.1 | Results: Outcome Level | Please include outcome level results achieved | Result 1: 2,937 children with disabilities and pregnant/lactating women on PATH received approximately US$30 increase in PATH benefits for three (3) payments between August to December 2020. Result 2: Develped Memorandum of Undetstanding between UNICEF and MLSS that includes Pathways/protocol to trigger shock responsive cash interventions in the case of emergencies. Result 3: 200 Farm families have access to economic protection
3.2 | Results: Output Level | Please include output level results achieved | Output 1.1 Financial boost for 3 months provided to the most poor and vulnerable households headed by women and men to mitigate social and economic risks of COVID-19. (families with girls and boys with disabilities, pregnant and lactating women and girls and female-headed farm households in rural areas Output 1.2 Distribution of food care packages for approximately 1,000 families at risk with girls and boys Output 1.3 Established pathways/protocol to trigger immediate humanitarian support and cash transfers in future emergencies Output 3. An upgraded programme to facilitate the Ministry of Agriculture and Fisheries to implement buy-back programmes Output 4. Established pathway/protocol for buy-back programme linked to social protection mechanism to support the female headed farmers and others who are in extremely vulnerable conditions during the COVID-19 recovery phase. Output 5. 200 farmers have participated in buyback programme
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words) | The project with the MLSS established a rigorous monitoring schedule which facilitated continuous feedback and opportunity to mitigate potential risks. In collaboration with the Government partners the project managed its processes with a view toward ensuring physical and psychological safety of beneficiaries through the transfer of resources via electronic means, limiting their exposure to Covid-19; as well as, helping to reduce the emotional strain from loss of income by supporting their food security efforts. The application of the relevant FAO’s policies and those of the Ministry of Agriculture and Fisheries [MOAF] delayed project implementation. While both organizations have created a fast track process to approve and implement emergency projects there are still process gaps that has affected the timely execution of projects in the context of disasters. There was limited capacity of the staff within the local FAO representation office to finalize all necessary documents and clearance took longer than anticipated; this was further complicated by the fact that The LOA to finalise the agreement between FAO and the MOAF was a novel mechanism to the technical personnel both at FAO JAM and MOAF. Data and clearances which were required from the Ministry of Agriculture and Fisheries to assist in the finalization of the documents was slow as was the spending down on the funds under the programme. The FAO Jamaica team has documented the lessons learnt in particular the LOA mechanism for future reference when this mechanism is utilized. The team also recommends that: • The FAO and MOAF review its fast track mechanism. • For emergency projects which are by nature very time sensitive, the FAO should in a timely manner, engage the UN with a view to harmonize the systems and procedures used in the UN and its Specialized Agencies to reduce process friction relative to approvals of documents and funds transfers. • The MOAF need to better define what trigger mechanisms that will lead to programmes more readily designated an emergencies and therefore get fast tracked through its emergency procedures. Covid-19 restricted movement and health concerns of FAO, partner personnel and beneficiaries. The FAO team implemented remote meetings using ICT video conferencing – Zoom, Microsoft Teams, Google Meet to protect staff, partner, and beneficiaries During the period of highest mobilization and execution owing to heavy and extended rainfall produce availability first choice agricultural produce was reduced significantly and their cost increased by multiples. The FAO had to adjust to produce that were able to withstand the then weather conditions and remain wholesome. Funds were delayed reaching the Ministry of Agriculture Fisheries [MOAF] from the FAO was not direct because of the GOJ procedures. The funds first have to be sent to a consolidated fund and then transferred from that Fund to the MOAF. The MOAF identified funds earmarked for upcoming activities not yet started and mobilized these funds to execute the project until the FAO allocated funds became available to MOAF from the consolidated fund.
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words) | For the first time, the resources have opened the door to continue this fruitful collaboration. Opportunities exist: • To work with the MLSS and advocate for modifications in the value of the cash transfers provided to households with children with disabilities in consideration of routine academic and medical services, which are likely to erode the residual value of the cash benefit. • With over twenty (20) years of implementation experience, PATH has proven to have a robust system to identify disadvantaged families through its Beneficiary Management Information System and the public assistance systems, especially in the event of an emergency. • In relation to its payment mechanism the MLSS has built out a consistent modality to effect payments to beneficiaries on a bi-monthly basis. Notwithstanding, these modalities are often administratively onerous, and require considerable public investments. • Given the existing strictures there is a level of inflexibility which does not easily accommodate humanitarian features in emergencies. Some of the costs incurred could be transferred toward enhancing the value of the benefit. • To advocate for an expansion of the digitization of payments, as well as consideration for features that facilitate easier access in emergencies. • With additional resources UNICEF would be able to assist the Government to enhance future policies on digital payments • To configure arrangements to focus on produce naturally in season as they tend to be able to thrive better under the expected weather conditions • Many female farmers are involved more in livestock than with crop production. Current intervention has a bias towards crops. Future interventions need to take this into account to enhance even greater female participation. • Many females farmers who have participated in the programme are less visible compared to their male counterparts because of the roles that they often play in the farm family. They tend to be the ones that keep the records and making added value products for example. These roles played are quite often overlooked and not captured in reports on programmes. • The absence of an embedded national ADRM strategy for the agriculture industry reduces its resilience to natural and economic shocks and the speed of at which the industry is able to begin recovery actions to return normal livelihood pursuits. • Working with cooperatives and organized community-based farmers groups improves community level response through more efficient coordination, mobilization, and production of food resources. • There are significant untapped opportunities within GOJ Ministries and Agencies for the substitution of imported food staples more local produce that will support the GOJ’s policy on food security and food import reduction. • We now have the MOAF with designated locations where farmers and buyers meet to transact business and farmers are paid immediately with cash and cheques or by electronic funds transfer the next day. This is a significant change from what used to obtain before where the norm was farmers were paid weeks after rather than the now one to two days to receive payment.
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words) | UNICEF partnered with the MLSS and the Ministry of Finance and the Public Service (MOFP) to support horizontal and vertical expansions of Jamaica’s flagship social protection programme- PATH. The MOFP provided fiscal supervision of the project while the MLSS coordinated the delivery and reconciliation of benefits to the recipients. Consistent with the Global Humanitarian Response Plan the project complimented the coordinated appeal, in its inclusion of specific metrics to ensure that key vulnerabilities were highlighted, adding another layer of support toward Jamaica’s incremental achievement of key targets under the Sustainable Development Goals (SDGs) and Jamaica’s Vision 2030- SDG’s 1, 2 and 10, no poverty, zero hunger and reducing inequalities- through timely injection of resources and sustainable development initiatives, such as child sensitive shock responsive social protection. These partnerships have provided opportunity for more robust discussions geared toward the development of parallel measure tailored to multiple deprivations and complement routine transfers at or above the existing value. [catalytic programmatic outcome] • The FAO in pursuing the implementation of the Programme has influenced collaborations between key partners working to provide support to affected beneficiaries. This has led to the MOAF improving coordination and by extension efficiency within participating value chains. The relationship forged between MOAF and MLSS was critical in getting farmers produce into market spaces that it wasn’t. • FAO supported the MOAF as they moved to identify select companies as purveyors and forged agreements with the purveyors to provide market outlet support to farmers under the MOAF market support purchase programme. The Purveyors were facilitated to forge new business arrangements with affected farmers through MOAF. [new partnership; programmatic outcome] • Working with the MOAF on this programme has allowed the FAO technical team to glean a more in depth understanding of MOAF/RADA capacity in value chain development and agriculture marketing. This will allow FAO to better develop programmes to address gaps observed. • The FAO and its sister agency UNICEF have shown that material synergies can be realised while collaborating in support of the Host Country. A more detailed cooperation framework could be embedded in the project development process. [synergistic programmatic outcome] • The activities of the project complemented Jamaica’s Medium-Term Socio-Economic Policy Framework [2018 – 2021]; National Outcomes 3 and 14. [catalytic programmatic outcome] • Farmers are paid sooner – at the point of sale with cheques or electronic transfer of funds to their bank accounts within two for the produce that they sell through the programme. [catalytic financial and programmatic outcome] • Ministry of Labour and Social Security [MLSS] has developed linkages with agriculture produce suppliers as part of its social safety net support to vulnerable members of the population – women, persons with disabilities, students on the PATH Programme. This is an additional market outlet for farmers affected by the COVID-19 and also a nutrition boost for vulnerable populations. This will lead to greater consumption of local produce, improving food security and substituting local foods for food imports. [new partnerships, catalytic programmatic outcome]
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken. | Field work for MPTF Grant survey currently being administered to approximatley 250 recipieints. Findings are expected to be presented early February 2021
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place | FAO received an extension owing to weather related delays.
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners. | UNICEF Jamaica partnered with the Ministry of Finance and the Public Service and Ministry of Labour and Social Security to support its Programme of Advancement Through Health and Education. The MOFP provided fiscal supervision of the project resources while the MLSS coordinated the targetting, delivery and reconciliation of benefits to the recipients. Procurement of goods, such as care packages and the service of an administrative focal point was executed through direct collaboration between the MLSS and UNICEF FAO received Romanian Government financial support that allowed for greater impact of the intervention. MOAF existing partner personnel operating an agricultural marketing programme were assigned to the MPTF programme where their experience played a critical role in the programme’s execution.

## RBM-Annual
| Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 1 Existing social protection programmes extended vertically and horizontally targeting most vulnerable households (families (headed by females and males) with girls and/or boys with disability, pregnant and lactating women ) | 3,808 (aprox13,000 people)- Average household size 3.5 members | The Programme of Advancement through Health and Education, PATH administered by the Ministry of Labour and Social Security is a dynamic programme and there is daily movement within the beneficiary population | PATH by Benefit Category Report MLSS Annual Review Report Data
Indicator:
Baseline: 0
Planned Target: 3,750 (11,000 people)
Output 1.1 Financial boost for 3 months provided to the most poor and vulnerable households headed by women and men to mitigate social and economic risks of COVID-19. (families with girls and boys with disabilities, pregnant and lactating women and girls and female-headed farm households in rural areas | 2,808* Boys-1,340 Girls- 840 Women- 628 | Daily movement within the beneficiary population | Ministry of Labour and Social Security Progress Update August-November 2020
Indicator 1.1.1: Number of households headed by women and men receiving cash transfers
Baseline: 0
Planned Target: 2760
Output 1.2 Distribution of food care packages for approximately 1,000 families at risk with girls and boys
Indicator 1.2.1: Number of families headed by women and men receiving support/food packages | 1000* *MPTF |  | MLSS Annual Review Report Data
Baseline: 0
Planned Target: 1,000
Output 1.3 Established pathways/protocol to trigger immediate humanitarian support and cash transfers in future emergencies | Developed a Memorandum of Understanding for the provision of humanitarian assistance in emergencies and the technical support toward the development of shock responsive social protection measures. | Document awaiting signature | MOU Document
Indicator 1.3.1 Establishment of pathways/ protocols for emergency preparedness and response
Baseline: 0
Planned Target: Memorandum of Understanding
Outcome 2: Most vulnerable people have access to social and economic protection mechanisms | 200 | The project has received an extension owing to weather related delays | Ministry of Agriculture and Fisheries Progress Update
Indicator:
Baseline: 0
Planned Target: 1000
Output 2.1 Livelihoods of female farmers in the parishes of St Mary, Portland and St Thomas stabilized as a result of the MICAF produce buy-back programme | 200 | The project has received an extension owing to weather related delays | Ministry of Agriculture and Fisheries Progress Update
Indicator 2.1.1 Number of female farmers participating in buy-back programme | 200 | The project has received an extension owing to weather related delays | Ministry of Agriculture and Fisheries Progress Update
Baseline: 0
Planned Target:1000
Output 2.2 Upgraded programme to facilitate the ministry of agriculture to implement buy-back programmes | 1 | Not Applicable | Ministry of Agriculture and Fisheries Progress Update
Indicator 2.2.1 Adequate storage for agriculture products purchased under buy-back programme
Baseline: 0
Planned Target:1
Output 2.3.Established pathways/protocol for buy-back programme linked to social protection mechanism to support the female headed farmers and others who are in extremely vulnerable conditions during the COVID-19 recovery phase | 1 | Not Applicable | Ministry of Agriculture and Fisheries Progress Update
Indicator 2.2
Baseline: 0
Planned Target:1
Please include all three: Baseline, Planned Target and Achieved Targets
[1] Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.
The Socio-Economic Programmatic Framework
Pillar 2 - PROTECTING PEOPLE: Social protection and basis services
Indicator 2.1- Number of people reached with critical WASH supplies (including hygiene items) and services, disaggregated by sex, age group and at-risk population | 2125 Including sanitation material provided for children in state care estimated @ 1500 children |  | https://www.unicef.org/jamaica/press-releases/dcs-receives-1-million-unicef-jamaica-covid-19-response https://www.unicef.org/jamaica/press-releases/unicef-donates-supplies-childrens-homes-covid-19
Indicator 2.2- Number of children supported with distance/home-based learning, disaggregated by sex | 302232 Methodology for estimates revised to ensure removal of double counting. Disaggregation not available from all sources - Estimated 300,000 children impacted by teacher training in Virtual learning. 1708 play & learn kits (849 boys,859 girls) 524 tablets for children with special needs (318 boys, 206 girls) |  | https://jis.gov.jm/unicef-donates-tablets-to-assist-students-with-special-needs/ https://www.unicef.org/jamaica/press-releases/ffp-partners-unicef-donate-1100-educational-kits-children
a. Meals: Hot meal and/or snack provided regularly in targeted schools to primary schoolchildren
i. Girls in primary school)
i. Boys in primary school
iii. Children in primary school (gender data unavailable)
b. Take-home ration as alternative to meals: Food provided as an alternative to the meal during school closure/interruption
i. Girls in primary school)
i. Boys in primary school
ii. Children in primary school (gender data unavailable)
c. Cash based transfer as alternative to meals: Cash provided as an alternative to the meal during school closure/interruption
i. Girls in primary school)
ii. Boys in primary school
ii. Children in primary school (gender data unavailable)
d. Voucher as an alternative to meals: Voucher provided as an alternative to the meal during school closure/interruption
i. Girls in primary school)
ii. Boys in primary school
iii. Children in primary school (gender data unavailable)
Indicator 2.4- Whether the country has measures in place to address gender-based violence (GBV) during the COVID-19 pandemic |  | Achieved through Spotlight Initiative | https://www.youtube.com/watch?v=aoV4c4QUUoU https://www.youtube.com/watch?v=rLdbNfCsp_o
i. integrate violence prevention and response into COVID-19 response plans
ii. raise awareness through advocacy and campaigns, with targeted messages to both women and men
iii. provide options for women to report abuse and seek help without alerting perpetrators | 100 women (92 young women , 8 girls )
iv. ensure continued functioning of shelters for victims of violence and expand their capacity
v. ensure women’s access to justice through police and justice responses to address impunity of perpetrators and protect women and their children
Indicator 2.5- Number of beneficiaries of social protection schemes and services related to the COVID-19 pandemic, disaggregated by type of programme, territory (rural/urban), sex, age group and at risk population
a) Cash transfer programmes | 13000 beneficiaries in 3808 households provided with supplementary cas an in kind support. Includes: 2180 (1340 Boys , 840 girls) children with disabilities – 555 Pregnant and lactating Mothers (MPTF) |  | https://www.unicef.org/jamaica/press-releases/path-gets-big-boost-unicef
b) Cash for work (productivity)
c) Water and sanitation services |  | Discussions underway to support sanitation in schools
d) Food and nutrition schemes
e) Legal aid services
f) Human right protection services
g) Psychosocial support services | 1321 Includes 400 teenage mothers at the Womens Centre and 872 mothers and 49 fathers parents and caregivers accesssin UNICEF supported helplines |  | https://www.unicef.org/jamaica/parents-call-these-numbers-get-help-during-covid-19

## Communication-Annual
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
A blog post: https://blogs.unicef.org/jamaica/sometimes-even-heroes-need-a-helping-hand/
Press release: https://www.unicef.org/jamaica/press-releases/path-gets-big-boost-unicef
2. Upload here: Communications and Visibility (OPTIONAL)
Fund's Communication Guidelines is posted here: http://mptf.undp.org/document/download/25941
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well picture material please make sure you include all credits and upload them in high resolution Call1 countries.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board

## General Information-Final
Programme Title & Project Number | Programme Duration
Programme Title: | Overall Duration (months)
Programme Number (if applicable) | Start Date (dd.mm.yyyy)
MPTF Office Project Reference Number: | Original End Date (dd.mm.yyyy)
Country | Current End date(dd.mm.yyyy)
Recepient UN Organizations | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | National counterparts (government, private, NGOs & others) and other International Organizations
Report Cleared By
o Name:
o Title:
o Email address:
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the relevant decision-making body/Steering Committee.
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Final
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum)
2 | Purpose (and Beneficiaries) | Please include the number of both direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups
3.1 | Results: Outcome Level | Please include outcome level results achieved
3.2 | Results: Output Level | Please include output level results achieved
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words)
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words)
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words)
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken.
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners.

## RBM-Final
| Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 1[1]
Indicator:
Baseline:
Planned Target:
Output 1.1
Indicator 1.1.1:
Baseline:
Planned Target:
Indicator 1.1.2:
Baseline:
Planned Target:
Output 1.2
Indicator 1.2.1:
Baseline:
Planned Target:
Indicator 1.2.2:
Baseline:
Planned Target:
Please inlcude all three: Baseline, Planned Target and Achieved Targets
[1] Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.

## Communication-Final
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
2. Upload here: Communications and Visibility (OPTIONAL)
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well picture material please make sure you include all credits and upload them in high resolution Call1 countries.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board