## OVERALL REPORTING INSTRUCTIONS
OVERALL INSTRUCTIONS
1 | All questions/sections must be responded to before submitting to secretariat. Once the document is uploaded in the relevant folder (as per instruction below) please email the secretariat.
2 | To ensure high quality narrative and results reports please pay attention to the following details: a) A well written, succinct summary that is very clear about what was done during the reporting period and results achieved, with a priority on concrete activities, beneficiaries reached and achievements beyond processes b) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document; c) In case certain indicators are not longer relevant, an explanation for why they are not. d) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document and how they align with the overall SERP joint workplan, and connection to reporting on global-level SERP indicators e) Indicate the relevant SERP monitoring framework global indicators that were contributed to as part of this project. f) An honest analysis of challenges faced, the responses to these challenges and the extent to which these responses were successful or not g) Go beyond generic, standard and well documented features of successful project implementation when reflecting on innovation and focus on what is truly new for you and which could enable replication efforts
3 | You must submit this completed workbook by uploading it in the relevant Project Folder here (https://undp.sharepoint.com/:f:/r/sites/covid19mptfcall1/Shared%20Documents/2020-REPORT?csf=1&web=1&e=j3cc3J). Please note if you are unsure of your project number please refer to http://mptf.undp.org/factsheet/fund/COV00
A | ANNUAL REPORT
DEADLINE: 31 January 2021
4 | ALL projects that received funds in 2020 must complete annual report, HOWEVER if you have your project ending on 31st December 2020 - your FINAL report is your annual report.
5 | If you received a no-cost extension on your project please do the annual report and in a few months time you can update the annual report to include activities to complete your end of project report.
6 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.
B | END OF PROJECT - FINAL REPORT
DEADLINE: 31 January 2021
7 | ALL projects that received funds in 2020 must complete annual report, HOWEVER if you have your project ending on 31st December 2020 - your FINAL report is your annual report.
8 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.

## General Information-Annual
Programme Title & Project Number |  | Programme Duration
Programme Title: | UN support to control spread and minimize the social-economic impact of COVID-19 in Lesotho | Overall Duration (months) | 6 months
Programme Number (if applicable) |  | Start Date (dd.mm.yyyy) | 28.05.2020
MPTF Office Project Reference Number: | 121732 | Original End Date (dd.mm.yyyy) | 31.12.2020
Country | Lesotho | Current End date(dd.mm.yyyy) | 31.12.2020
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | UNICEF, UNDP,UNFPA, WHO | National counterparts (government, private, NGOs & others) and other International Organizations | Lesotho Red Cross Society, Econet Telecom Lesotho, NUL, RISE International, Ministry of Health, Ministry of Local Government (District Administrator's Office), Ministry of Social Development, Lesotho Network of People Living with HIV/AIDS, Gender Link, Christian Health Association of Lesotho (CHAL)
Report Cleared By
o Name: | Anurita Bains
o Title: | Resident Coordinator a.i
o Email address: | abains@unicef.org
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the Secretary-General's Designate
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Annual
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum) | The project has successfully supported COVID-19 coordination at the national, district and community level, enhanced disease surveillance, strengthened infection prevention and protected other essential health services.The deployment of District Coordination Assistants engaged through the Project enhanced reporting and implementation of a decentralized response in the districts. With the support of the project, the Kingdom of Lesotho has successfully reported COVID-19 cases to WHO within 24 hours, and a referral system has been established for COVID-19 patients, to minimise the spread of COVID-19 in health facilities. Disease surveillance was strengthened through the creation of a new digital application, Bophelo-ka-Mosebeletsi, which enabled village health workers (VHW) to undertake community surveillance, monitoring and quarantining suspected COVID-19 cases. The project provided VHWs in Quthing and Mokhotlong with 1,081 mobile gadgets and partnered with Econet Telecom Lesotho to enable free internet access whilst using the app. The app significantly increased the number of suspected patients that VHW could observe and reduced their travel costs by preventing the need to regularly provide paper-based reports to local health facilities. Infection prevention and control was strengthened through undertaking healthcare assessments to gauge the situation across the country, training of healthcare workers, community health agents and community leaders, and through mass community sensitisation regarding COVID-19. Capacity was also strengthened at border points to screen returning migrants. Regular epidemiological reports addressing key variables such as person, place and time were produced and shared during weekly Partners Meetings. The reports produced during the period show COVID-19 case fatality rate of 2.6% which is within the set target of less than 10%. Essential health services were maintained at all 193 health facilities in the Kingdom of Lesotho. Vaccinations, family planning services, TB and HIV services were amongst those that continued despite COVID-19. 138,618 of the targeted 150,000 people were reached with COVID-19 related messages in six districts. The messages were delivered through health facilities and in different communities. 113,590 people were reached with WASH services at health facilities, isolation/quarantine centres, high-risk communities and open spaces). In terms of partnership the project developed partnerships with : Government, Christian Health Association of Lesotho, Lesotho Red Cross Society and the business community (Econet). In the area of surveillance, the project has partnered with one of the two telecommunication service providers in the country for hosting of the mobile application for use at community level (Econet). UN collaborated with the Maseru City Council to install 48 water stations in all key areas around the Maseru bus-stop areas and market centres. UN also engaged RISE International, a social enterprise for youth entrepreneurship development, for construction and installation of the water stations. UN also partnered with Econet Telecom Lesotho – a mobile network operator to provide free access to internet services for the village health workers for use of the Bophelo App. Nonetheless, the project was not without its challenges. The delays in COVID-19 patients seeking medical attention, industrial strikes by health workers, healthcare staff shortages and high turnover rates all complicated the COVID-19 response.
2 | Purpose (and Beneficiaries) | Please include the number of direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups | The establishment of the Bophelo-ka-Mosebeletsi digital app directly benefitted 147,030 suspected COVID-19 patients within communities and 708 healthcare workers that were trained to use the app. The app further benefitted the wider public through freeing healthcare facilities from being overwhelmed by COVID-19 patients and from slowing community transmission. Of the 147,030 suspected COVID-19 cases that benefitted from the app, 83,807 were female, 63,223 were male, 7,352 were below 5 years old, 22,055 were aged 5-11, 102,920 were ages 11-59 and 14,703 were aged 60 or above. Of the 708 healthcare workers, 682 were village health workers (21 male and 661 female), 18 were nurses and 8 were data clerks. The continuation off essential health services directly benefitted 446,823 people who were reached with family planning and HIV and/or TB Screening. A further 500,000 people were reached with COVID-19 information through Radio, TV and posters. 138,618 (M:45,744; F:48,516; C:44,348) of the targeted 150,000 people were reached with COVID-19 related messages in six districts. The messages were delivered through health facilities and in different communities. 113,590 people ( (M:34,047; F:40,892 C:38,621) were reached with WASH services at health facilities, isolation/quarantine centres, high-risk communities and open spaces). 509 health workers trained on IPC (345 females and 164 males) and 2510 community health agents and leaders.
3.1 | Results: Outcome Level | Please include outcome level results achieved | Project outcome: COVID-19 transmission and mortality reduced and/or prevented in Lesotho As at the end of December 2020, the mortality rate stood at 1.7%: there were 55 deaths out of 3,005 confirmed cases. The project contributed in the reduction of COVID-19 transmission and mortality at all levels. At the national level, the project supported weekly data collection that was shared during weekly health partners meetings, co-chaired by the WHO and Ministry of Health. The data presented informed debate and policy decisions (such as the COVID-19 tier restrictions levels), which contributed towards reducing national COVID-19 transmission. At the district level, the deployment of District Coordination Assistants has supported a decentralised COVID-19 response and enabled greater communication between the situation on the ground and policymakers. At the community level, the training of healthcare workers to respond to COVID-19 and the establishment of the Bophelo-ka-Mosebeletsi app slowed COVID-19 transmission and therefore reduced the mortality rate.
3.2 | Results: Output Level | Please include output level results achieved | Output 1: Strengthened coordination, planning and monitoring at national, district and community level Coordination structures are in place at national and district level. District Coordination Assistants have been deployed to the ten districts to strengthen coordination at this level. Regular support was provided to the National COVID-19 Secretariat (NACOSEC) in developing policy and strategic guidance in the national response.136 community structures strengthened on COVID-19 preparedness, response and recovery.The IHR core capacity and health emergency preparedness has increased by three percentage points in coordination, laboratory and food safety – from 12% to 15%. Referral system from health facility to hospital and facilities ear-marked for isolating and managing severe and critical COVID-19 cases is in place and rapid response teams trained on the referral pathway. The implementation of the system is outlined in the national guidelines. Disease surveillance was strengthened through the creation of a new digital application, Bophelo-ka-Mosebeletsi, which enabled village health workers (VHW) to undertake community surveillance, monitoring and quarantining suspected COVID-19 cases. The project provided VHWs in Quthing and Mokhotlong with 1,081 mobile gadgets and partnered with Econet Telecom Lesotho to enable free internet access whilst using the app. The app significantly increased the number of suspected patients that VHW could observe and reduced their travel costs by preventing the need to regularly provide paper-based reports to local health facilities. Output 2 Enhanced disease surveillance for rapid case detection and management, investigation, tracing and monitoring of contacts Established Bophelo-ka-Mosebeletsi app to enhance community surveillance, which also reduced VHWs weekly travel costs. A minimum of M256.00 ($17.00) has been saved for VHWs residing close to the healthcare facilities, or M1,024.00 ($69) for VHWs residing further afield. Capacity was strengthened at border points to screen returning migrants. Regular epidemiological reports addressing key variables such as person, place and time were produced and shared during weekly Partners Meetings. The reports produced during the period show COVID-19 case fatality rate of 2.6% which is within the set target of less than. With the support of the project, the Kingdom of Lesotho has successfully reported COVID-19 cases to WHO within 24 hours, and a referral system has been established for COVID-19 patients, to minimise the spread of COVID-19 in health facilities. Output 3: Strengthened mechanisms and measures for infection prevention and control at health facility and in community settings 138,618 people reached with critical information to prevent and control COVID-19 at community level and 70 ground handwashing stations installed in health care facilities and in communities and 6,000 households supported to install household tippy taps for handwashing. Hygiene and environmental cleaning supplies was procured and given to the 2 major isolation centres in Mafeteng and Berea with beneficiaries reaching over 5000. With support of the project, 95% of public health facilities are implementing screening and triaging based on the national guidelines At community level,UN partnered with Lesotho Red Cross Society to conduct awareness campaigns. Based on a knowledge needs assessment conducted in the communities, messaging was developed and tailored to the community needs.In addition, infection prevention and control guidelines were developed and distributed to the communities in the districts; 158 community structures in all the 6 districts have been capacitated on response and coping to COVID-19. With the establishment of IPC committees in the districts and training of Community Health Workers(CHW) and Community Leaders the awareness raising on COVID-19 prevention and managemenent was further strengthened. Based on a WASH needs assessment done in 50 communities in the 6 districts, UN provided handwashing stations for health facilities, border entry points and other high-risk areas like the Maseru market centres. . Output 4: Continuity of other essential health services maintained Essential health services were maintained at all 193 health facilities in the Kingdom of Lesotho, through implementing WHO’s Pillar 9: the continuation of essential health services. Vaccinations, family planning, TB and HIV services were amongst those that continued despite COVID-19, directly benefitting over 446,283 people that received essential health services during the pandemic.
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words) | i. Quality of care in treatment or isolation facilities caused reluctance of suspect cases and some of the confirmed cases to be managed in these facilities. There was shortage of required equipment; personal protective equipment and heating facilities. Equipment and PPE were procured and distributed through government and support from partners. ii. Communities delay seeking medical attention when they have flu-like signs illnesses due to fear of quarantine and isolation. Despite on-going risk communication and community engagement, visits to health facilities due to flu-like illnesses continued to be lower than before COVID-19 period. Risk communication and community engagement will be intensified to change people’s perception and uptake of the established interventions. iii. Access to health services got paralysed for a week during the industrial action lead by Coalition of Health Professionals Association in early July 2020. Government engaged with the Coalition representatives and agreement reached for ending the strike.Further, government-imposed COVID-19 movement restrictions affected access to healthcare facilities and community settings, reducing the ability to conduct field missions and monitoring. In order to overcome the movement restrictions, district-based staff were better utilised and remote monitoring was embraced iv. Shortage of equipment and supplies for the management of cases and for maintaining appropriate infection prevention and control measures. Government was supported to procure required supplies through the COVID-19 Partners Platform – Supply Chain Portal coordinated through the UN System. v. Change of government in early June 2020 was followed by the establishment of a new coordination structure NACOSEC which replaced the National Emergency Command Centre. The change resulted in some implementation issues between Ministry of Health and NACOSEC. The UN played advocacy and brokering functions that lead to some improvement in the working relationships between the two. The intervention of the UN including the regular weekly Partners’ meeting will be continued to address the situation. vi. The newness of COVID-19 and the lack of information surrounding the disease also posed a challenge globally. In response, the project had to adopt a flexible approach to respond to new information as it emerged. For example, COVID-19 communications documents took advantage of existing hygiene communication strategies, but had to be ready to change with new information.
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words) | The project recruited 10 District Coordination Assistants resulting in improved health sector coordination of the response and this translated the implementation of the nine pillars of COVID-19 response into concrete action at district and community levels. This measure improved data management and compilation of district reports that were shared with stakeholders in the districts and the national level. Maseru district established a Partners working forum that convened every month to plan key actions for the next month while also providing updates on achievements of the previous month. Each of the partners presented resources they had to support the district response. Based on priorities, needs and challenges noted during the deployment of the coordinators, the ten districts submitted mini-proposals to strengthen the response which resulted in WHO allocating an average of US$25,000 to each district. This support strengthened the roles of different structures in the districts (traditional leaders like chiefs and community councils) to play an active role in the response. In terms of gender marker, the project aimed to "make a significant contribution to gender equality and/or the empowerment of women and girls" - while the project did not discriminate beneficiaries’ in terms of their gender during the delivery of planned interventions, it is worth noting that among the district coordination assistants 70% were women. More than 90% of the village health workers trained were women. The experience and lessons learnt from this project (implementation of gender markers) has been very useful in the medium-term review of WHO work in the country which has GER as one of the six dimensions that are assessed. In addition, Learning from communities on their own infection, prevention and control measures and strategies for responding to health emergencies. Communities need to be given a platform to share their coping strategies that can be incorporated to training curriculum. The importance of strengthening community structures enhances reach and also sustains sound health practices. Involvement of local entreprenuers to develop solutions - in this project, local enterprises were heavily involved in developing and adapting group handwashing stations that were installed in health care facilities and communities.
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words) | Weekly health partners meetings Weekly health partners meetings were held every Tuesday, co-chaired by the WHO and Ministry of Health. The meetings discussed the national COVID-19 response, identified challenges and priorities, sought partners support for the national COVID-19 response and enhanced coordination between partners. The national COVID-19 response is aligned to the WHO SPRP and thus the COVID-19 MPTF. The MPTF provided 19% of the total financing provided for the national response from 11 donors and enhanced delivery under five pillars: leadership; surveillance and rapid response; infection prevention and control; points of entry; and continuity of essential health services. Multiple UN agencies also supported the national COVID-19 response and so the project enhanced inter-agency partnerships, beyond the agencies involved in the MPTF. Bophelo-ka-Mosebeletsi The creation and roll-out of the Bophelo-ka-Mosebeletsi digital app involved numerous partnerships. The mobile application was developed through the UNDP Lesotho Accelerator Lab in partnership with the National University of Lesotho. Whilst the roll-out of the app partnered with Econet Telecom Lesotho (ETL) through enabling free internet access for users of the app. ETL also provided a 20% discount for procuring mobile gadgets for the village health workers. Implementing partners A number of partners worked with the project to implement project activities. Rise built handwashing stations in health facilities and Lesotho Red Cross Society built handwashing stations in communities.
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken. | During the implementation of the project, an assessment on the effects of COVID-19 on access to health services was conducted and the results were incorporated in the development of operational plans to improve access to services and to develop plans to enhance child immunisation services.
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners.

## RBM-Annual
| Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 1[1] |  | Some attributes to the score for core capacities were outside the scope of the project to influence | IHR (2005) Statte Party Annual Report of 2020
Indicator: 1.1. International Health Regulations (IHR) capacity and health emergency preparedness increased to 20% | 15%
Baseline: 12%
Planned Target: 20%
Indicator: 1.2. COVID-19 associated mortality maintained below 10% | 1.7%
Baseline 0
Planned Target: <10%
Output I: Strengthened Coordination, planning and monitoring of COVID-19 National Response at national and community level | 1 national and 10 district coordination centres in place | Not applicable | Situational reports and monthly reports from DCAs
Indicator 1.1.1: Availability of a functional National and district Coordination Structures
Baseline: 0
Planned Target: 1 national and 10 district coordination centres
Indicator 1.1.2: Referral system for care of COVID-19 in place and functional | Yes - system in place | Not applicable | Situationa reports and Case Management Guidelines
Baseline: No
Planned Target: Yes
Indicator 1.1.3: Extent to which data is used to inform policy decision dissaggregated by source: (a) traditional health register (b) Digital technologies (big data and artificial intelligence) | 3 | Not applicable | Situational reports and monthly reports from DCAs
Baseline: (a) 1 (b) 0
Planned Target: (a) 3 - Fully (b) 2 - Minimal
Output II: Enhanced disease surveillance for rapid case detection and management, tracing and monitoring | 98% | The first two notifications delayed due to clearance issues in the government system | Actual notification and results published
Indicator 1.2.1: Proportion of confirmed COVID-19 cases reported to WHO within 24 hours disaggregated by district, community, gender and age
Baseline: 0
Planned Target: 100
Indicator 1.2.2: Proportion of self-quarantined travellers monitored disaggregated by district, community, gender and age | 50.6% | Available staff could not cope with the workload. Most of those monitored were covered while in government facilities | Situational reports and points of entry reports
Baseline: TBD
Planned Target: 80%
Indicator 1.2.3: Number of epidemiological and situational reports produced and shared | 25 epidemiological reports | Data flow from districts was poor before deployment of coordination assistants | Weekly presentations to partners and NACOSEC
Baseline:0
Planned Target: 30
Output II: Strengthened measures and mechanisms for infection prevention and control at health facility and in community settings | 500,0000 people reached ( TV and radio) were used to reach people with COVID and SRHR messages, pamphlets and brochures were also placed in public spaces. 138,618 people in communities (M:45,744; F:48,516; C:44,348) |  | Red Cross and LENEPHWA project reports
Indicator 1.3.1: Number of people reached with quality COVID-19 messaging and information at health facility and community levels (disaggregated by gender and age)
Baseline: 0
Planned Target: Total 150,000 (M: 50,200, F: 52,300, C: 47,500)
Indicator 1.3.2: Number of operational IPC committees at (a) hospital, (b) health facility and (c) community levels | 13 hospitals & Communities: 430 structures | Remaining 5 hospitals and health centres could not be reached due to limited funding. 430 community structures. Number not reached on time due to COVID-19 restrictions for movements and gatherings | Situational reports and monthly reports from DCAs
Baseline: 0
Planned Target: Total 100 (a. 50; b. 50 c. 500)
Indicator 1.3.3: Number of people (disaggregated by gender) trained on IPC (a) health care workers and (b) community health agents and (c ) leaders) | 509 health workers trained (345 females and 164 males) - 2510 community health agents and leaders. | Not applicable | Situational reports and monthly reports from DCAs
Baseline: a. - 0; b. - 0; c. - 0
Planned Target: a. 200 health workers ; b. 200 community health agents ; c. 100 leaders
Indicator 1.3.4: Number of people accessing WASH services at (health facilities, isolation/quarantine centres, high-risk communities and open spaces (disaggregated by gender and age) | 113,590 people (M:34,047; F:40,892 C:38,621) |  | Reports from MoH for supplies; Rise for handwashing stations in health care facilities; LRCS for wash services in communities
Baseline:
Planned Target: 50,000 (Males: 16700; Females: 17500; Children: 15800)
Indicator 1.3.5: Proportion of hospitals with functional triaging at OPD | 95% | Intervention had not been rolled out and monitored in private hospitals | Situational reports and monthly reports from DCAs
Baseline: 4.5%
Planned Target: 100%
Output IV: Continuity of essential health services maintained | 446 823 people (FP, HTS,COVID-Screening, TB screening, Education) Condoms distributed= 456 345 85% (3,016,725 OPD visits) | Not applicable | DHIS2 and Red Cross and Ministry of Health project Reports
Indicator 1.4.1: Proportion of people (disaggregated by type of services, gender and age) continuing to receive essential health services and key messaging
Baseline: 0
Planned Target: 70%
Indicator 1.4.2: Proportion of public health facilities supported to continue to provide essential health services | 100% | All health facilities provided essential health services except during health workers strikes in July and October | Situational reports and monthly reports from DCAs
Baseline: 0
Planned Target: 90%
Indicator 1.4.3: Proportion of public health facilities delivering integrated outreach services as part of essential health services | 47% UNFPA supported facilities plus baseline | Lockdown instituted by the country limited travel to the community level | Situational reports and monthly reports from DCAs and Red Cross, LENEPHWA and MOH Project Reports
Baseline: 25%
Planned Target: 50%
[1] Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.

## Communication-Annual
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
Impact story has been submitted on Sharepoint
2. Upload here: Communications and Visibility (OPTIONAL)
Visibility links https://web.facebook.com/watch/live/?v=1309000855936875&ref=watch_permalink https://web.facebook.com/watch/live/?v=345188926549448&ref=watch_permalink https://web.facebook.com/watch/live/?v=339790223765055&ref=watch_permalink https://web.facebook.com/UNDPLesotho/posts/from-manual-to-digital-undp-through-lesotho-accelerator-lab-in-partnership-with-/2713717015568288/?_rdc=1&_rdr
Fund's Communication Guidelines is posted here: http://mptf.undp.org/document/download/25941
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well picture material please make sure you include all credits and upload them in high resolution Call1 countries.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board

## General Information-Final
Programme Title & Project Number | Programme Duration
Programme Title: | Overall Duration (months)
Programme Number (if applicable) | Start Date (dd.mm.yyyy)
MPTF Office Project Reference Number: | Original End Date (dd.mm.yyyy)
Country | Current End date(dd.mm.yyyy)
Recepient UN Organizations | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | National counterparts (government, private, NGOs & others) and other International Organizations
Report Cleared By
o Name:
o Title:
o Email address:
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the relevant decision-making body/Steering Committee.
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Final
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum)
2 | Purpose (and Beneficiaries) | Please include the number of both direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups
3.1 | Results: Outcome Level | Please include outcome level results achieved
3.2 | Results: Output Level | Please include output level results achieved
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words)
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words)
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words)
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken.
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners.

## RBM-Final
| Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 1[1]
Indicator:
Baseline:
Planned Target:
Output 1.1
Indicator 1.1.1:
Baseline:
Planned Target:
Indicator 1.1.2:
Baseline:
Planned Target:
Output 1.2
Indicator 1.2.1:
Baseline:
Planned Target:
Indicator 1.2.2:
Baseline:
Planned Target:
Please inlcude all three: Baseline, Planned Target and Achieved Targets
[1] Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.

## Communication-Final
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
2. Upload here: Communications and Visibility (OPTIONAL)
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well picture material please make sure you include all credits and upload them in high resolution Call1 countries.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board