## OVERALL REPORTING INSTRUCTIONS
OVERALL INSTRUCTIONS
1 | All questions/sections must be responded to before submitting to secretariat. Once the document is uploaded in the relevant folder (as per instruction below) please email the secretariat.
2 | To ensure high quality narrative and results reports please pay attention to the following details: a) A well written, succinct summary that is very clear about what was done during the reporting period and results achieved, with a priority on concrete activities, beneficiaries reached and achievements beyond processes b) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document; c) In case certain indicators are not longer relevant, an explanation for why they are not. d) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document and how they align with the overall SERP joint workplan, and connection to reporting on global-level SERP indicators e) Indicate the relevant SERP monitoring framework global indicators that were contributed to as part of this project. f) An honest analysis of challenges faced, the responses to these challenges and the extent to which these responses were successful or not g) Go beyond generic, standard and well documented features of successful project implementation when reflecting on innovation and focus on what is truly new for you and which could enable replication efforts
3 | You must submit this completed workbook by uploading it in the relevant Project Folder here (https://undp.sharepoint.com/:f:/r/sites/covid19mptfcall1/Shared%20Documents/2020-REPORT?csf=1&web=1&e=j3cc3J). Please note if you are unsure of your project number please refer to http://mptf.undp.org/factsheet/fund/COV00
A | ANNUAL REPORT
DEADLINE: 31 January 2021
4 | ALL projects that received funds in 2020 must complete annual report, HOWEVER if you have your project ending on 31st December 2020 - your FINAL report is your annual report.
5 | If you received a no-cost extension on your project please do the annual report and in a few months time you can update the annual report to include activities to complete your end of project report.
6 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.
B | END OF PROJECT - FINAL REPORT
DEADLINE: 31 January 2021
7 | ALL projects that received funds in 2020 must complete annual report, HOWEVER if you have your project ending on 31st December 2020 - your FINAL report is your annual report.
8 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.

## General Information-Annual
Programme Title & Project Number |  | Programme Duration
Programme Title: | Supporting provincial health preparedness and surge capacities, including at points of entry in Lao PDR | Overall Duration (months) | 10
Programme Number (if applicable) |  | Start Date (dd.mm.yyyy) | 20.05.2020
MPTF Office Project Reference Number: | 121676 | Original End Date (dd.mm.yyyy) | 31.12.2020
Country | Lao PDR | Current End date(dd.mm.yyyy) | 30.03.2021
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | UN HABITAT, IOM, UNODC | National counterparts (government, private, NGOs & others) and other International Organizations | WHO, Ministry of Health, Ministry of Home Affairs, and Ministry of Public Security.
Report Cleared By
o Name: | Sara Sekkenes
o Title: | Resident Coordinator
o Email address: | sara.tollefsen@un.org
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the Secretary-General's Designate
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Annual
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum) | The project supported the Government of Lao PDR though relevant ministries, to implement effective preparedness activities to prevent potential widespread of COVID-19 transmission across Lao PDR. There is no community transmission to date and all COVID-19 positive cases were detected among travelers. A project kickoff meeting in June 2020 with WHO, UNODC, HABITAT, UNCDF, IOM, and UNDP was held. Counterparts from Ministry of Health, Ministry of Public Security, Ministry of Public Works, and Ministry of Home Affairs participated. Agencies immediately appointed project focal points and drafted work plans. UNDP facilitated and bound the agencies together to synchronize activities, share information, support with reporting, and liaise with RCO. The project contributed to the establishment of a working mechanism for the improved capacity in screening and surveillance at POEs. IOM selected 7 points of entry (POE) to support along with the Department of Immigration (DOI), General Department of Public Security, MoPS. (2) international airport, (5) International Land Borders were selected as there are high flow of migration, trucks, and challenges for trafficking in persons. Standard Operating Procedures (SOPs) on Immigration and SOP on Transportation, POE Checklist Assessment and other related documents have been translated into Lao language and are ready for adaption into jointly developed SOPs with DOI to align with the PM Decree 558, PM Decree 06 on COVID-19 Response, Ministry of Public Security (MoPS’s) Decree 112, WHO standard, and other related ASEAN Standard. These were used at training sessions at 7 POEs where frontline officials received PPE. IOM, DOI, DOIR, and provincial taskforce and provincial police head quarter have jointly assessed and provided training at the POE in the Northern, Central, and Southern province as: Lao PDR-China POE (Boten), Lao PDR – Thailand (Friendship Bridge 04 (Bokeo), and Luangprabang International Airport, Lao PDR - Thailand (Friendship Bridge 03 (Khammoune), Lao PDR - Thailand (Friendship Bridge 02 (Savannakhet), Savannakhet International Airport, Pakse International Airport, and Lao PDR - Thailand (Vangtao International Land Border -Champasak). These POEs are main doors to overseas and neighboring countries where there is very high risk on COVID-19 and Trafficking in Person. For example: Boten in Luang Namtha has very high flow of trucks for goods, trucks for railway construction, and railway workers. UNODC has coordinated with IOM and WHO to have a cohesive approach in developing and delivering training to POE. UNODC training material, agenda, pre and post evaluation tests and survey for the UNODC-lead trainings targeting Border Liaison officers developed, designed, and translated. Meanwhile, UN-Habitat provided Water, Sanitation and Hygiene (WASH) support to six quarantine centres in four provinces by i) conducting rapid assessment to identiy needs gap; ii) providing WASH services and infrastructure such as new toilets, hand-washing stations, shower facilities, water pipes, taps, hygiene suppies; and iii) developing and distributing Information, Education and Communication (IEC) materials on good WASH practice. Info guides and pocket guides on COVID-19 precautions for frontline officers were finalized, printed and delivered to officers during training sessions at POEs (3000 copies of back pocket guides and 500 copies of info guides, in addition to the pro bono copies already distributed). UNODC held four training sessions for Lao officials and a training-of-trainers at UNODC in Vientiane on 17 September 2020 for representatives from the Ministry of Public Security in preparation of training sessions which were held as follows : Workshops on 6-7 October, 20-21 October, and 3-4 November for officers stationed at BLOs in Southern, Central, and Northern Lao PDR, respectively. In total 81 (79M/2F) officers representing 20 BLOs were trained. UNDP collaboratated with the Ministry of Home Affairs (MoHA), Ministry of Health (MoH) and WHO to support local government officials in 4 provinces witth their preparations to prevent, contain and treat Covid-19 through enhanced public services and community engagement. About 200 local level government officials participated in four Provincial Workshops (Champasak, Bokeo, LuangNamtha, and Sayaboury). Facilitators from MoH, MoHA, UNDP, and WHO engaged with authorities to identify existing practices, available resources, and needs to respond to COVID-19. A joint inspection of seven Provincial Quarantine Centers with MoH, MoHA, UNDP and local government officials has been completed. The inspections utilized a checklist produced by MoH and WHO with MPTF partner feedback. UNDP along with MoHA and local authorities provided the assessed quarantine centers with light renovations, PPE, bedding, kitchen supplies, sanitation equipment, and computers. A Quarantine Center Profile and Occupant Registry was developed and is being piloted by the MoH.
2 | Purpose (and Beneficiaries) | Please include the number of direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups | IOM - The key purpose of the project is for "To support the government of Lao People's Democratic Republic to responde to COVID-19 particularly the Department of Immigration, General Department of Public Security, Ministry of Public Security in their immediate management of Points of Entry (PoEs), providing them with the necessary Personal Protective Equipment (PPE) to safely manage border operations and assist with effective first response where specialized health workers are not present". The total beneficiaries reached at the PoEs is 508 frontline officials, (375M/133F). UNODC - 81 (79M/2F) officers trained at workshops for representatives from 20 BLOs across Lao PDR, 83 (66M, 17F) district and village level authorities attended debriefing sessions hosted by their colleagues who attended UNODC training sessions. UN-HABITAT - Six (6) quarantine centres across four provinces were supported with improved WASH services and infrastructure. Direct beneficiaries are those who stayed at these quarantine centres during this reporting period, which include a total of at least 8343 people (4136 women and 4207 men). UNDP - Provincial level strengthening workshop participants from the Government in 4 provinces. Sept 7-8 Bokeo Province= 71 participants / 23 female. LuangNamtha Province Sept 10-11 = 73 participants / 18 female. Champasak Province Sept 30 to Oct 1 = 93 participants / 32 female. Sayaboury Province Oct 8 -9 = 84 participants / 23 female. UNDP - Quarantine Center Database - Beneficiaries of the dashboard are the MoH and relevant government officials required to register and possibly trace occupants at each center. UNDP - Quarantine Center renovations and supplies. Beneficiary Data to be based on the number of occupants in the quarantine centers supported over a 6 month period. from December 2020. Data from Ministry of Health shows approximate quaratine Center occupancy from April 2020 to Jan 10 2021 - Champasak centers = 13,352 persons. Bokeo center is. 783. Luangnamtha.1,338 and Sayaboury 4,257.
3.1 | Results: Outcome Level | Please include outcome level results achieved | The Government of Lao PDR, through the Ministry of Health and other relevant ministries and institutions effectively prepared and responded to potential widespread of COVID-19 transmission across Lao PDR. IOM - There are three key outcomes set and have been achieved by IOM and its implementating partners at the 7 PoEs as: 1) Procurement and distribution of appropriate Personal Protective Equipment (PPE) for relevant frontline officials at the PoEs, according to the World Health Organization (WHO) Standards and national guideline. There are Personal Protective Coat (14 pics), Gloves (43,700 pics), N95 masks (1700 pics), Goggles (1090 pics), Hand Sanitizer (3773 pics), Plastic face shield (924 pics), Handheld thermometer scan (204 pics), Disinfectant Sprayer (275 pics), Floor Cleaning Detergent ( 30 bottles), and Toilet Cleaning Detergent (30 bottles). 2) Capacity development for immigration authorities to implement health-complient border procedures. At the PoEs, IOM has provided two days training to the frontline officials which consists of Immigration, Customs, Animal and Plants quarantine, Health official, Visa on arrival, Transportation companies, Lao Airline, Skyway Airline, Provincial Quarantine Center Official, Provincial Taskforce, and PoE Management Board Office in which in which there are 508 frontline officials, 375 males and 133 females. These officials benefitted from the mapping assessment consultations and trainings at the PoEs. 3) Information, Education, and Communication (IEC) material for migrants crossing at PoEs: By cooperating with DOI, DOIR, and related sectors at the field, IOM has developed the information sheet for Inbound and Outbound migrants (21,500 copies), Inbound and Outbound Diagram to show the flow of the migrants at each PoEs and the analysis of the PoE mapping report. Out of these, IOM also innovates and develop the QR Code for sharing the information and training materials from central to frontline officials and the migrants crossing the PoEs as: One QR Code for frontline officials and one QR code for crossing migrants to facilitating the easiness to access timely information on COVID-19 to ensure that they know how to protect themselve through their mobile phone. SOP Development for both immigration and transportation the migrants from POE to quarantine center or hotels are one of the key documents that IOM will work with MoSP on the next step. 4) IOM has also worked with WHO, UNODC, DOI, DOIR, and DCDC to develop the SOP on immigration and transportation at each PoE that align the Prime Minister Decree 558 on PoE Management, PM Order 06, ASEAN Standard, and other COVID-19 Response Order accordingly. A total of 500 copies, both Lao and English versions of the SOPs were provided in Lao language to frontline officials. UNODC - UNODC sucessfully trained 2 national law enforcement trainers and 81 (79M/2F) frontline officers from 20 BLO locations across Lao PDR on key measures to prevent the spread of COVID-19 at and accross land borders, delivered training material, info guides, and pocket guides to BLOs, and equipped officers at 20 BLOs with personal protective equipment. Together, these intiatives have better prepared law enforcement to prevent the spread of disease at and across land borders in the case of a future outbreak of COVID-19. An additional 83 (66M/17F) district and village level authorities were subsequently trained by participants in UNODC trainings. UN-HABITAT - i) Rapid assessment conducted at six quarantine centres in four provinces (Savannakhet, Luanprapang, Xayaboury and Champassak) and one registration point; ii) WASH infrastructures and goods provided at six quarantine centres such as gender-separated bathrooms, shower facilities, hand-washing stations, water piles, taps, hygiene supplies; and iii) IEC materials developed and distributed at six quarantine centres on good WASH practice. UNDP and the Ministry of Health provided Provincial Governors in 4 provinces with a report defining lessons learned and resources needed to in order to respond to Covid-19.
3.2 | Results: Output Level | Please include output level results achieved | IOM-The project was able to achieve the following outputs from Sept-Dec 2020. 1) IOM undertook 7 PoE mapping assessments to understand challenges in existing capacities of infrastructure, processes and personnel to respond to a virus outbreak, to which IOM tailored its trainings and simulations, as well as procured PPE to ensure safe and effective border management during the pandemic. A total of 199 (147M/52F) frontline officials attended these PoE mapping assessments and consultations. 2) Procure and distribute the PPE to the frontline officials, crossing migrants, and participants to the training for 7 Points of Entry for 172,455 PPE items, this included: 1) Medical Gown (14), Gloves (41700), Surgical Mask (124300), N95 (1500), Goggle (890), Hand Sanitizer (2773), Plastic Face Mask (764), Handheld thermometer scan (194), Disinfection sprayer (260), Floor cleaning detergent (30), and Toilet cleaning detergent (30). 3) 508 (375M/133F) frontline officials were equipped with necessary knowledge and experience needed to effectively manage suspected and/or probable COVID-19 cases at border crossing points across 7 PoEs. Frontline officials were trained on the SOP for Frontline Border Officials at the Point of Entry in Response to the COVID-19 Outbreak, including on PPE. A total of 500 copies, both Lao and English versions of the SOPs were provided in Lao language to frontline officials. To ensure a multi-sectoral and multi-agency approach, IOM invited representatives from WHO, the Ministry of Health and UNODC to be trainers at these two-day trainings. At each PoE, the training has been run over two full days in which the day one focussing on the background knowledge of COVID-19 and personal prevention and the day two, all participants visit the PoE, both inbound and outbound, to observe the flow of the migrants and figure out where they need to improve. This silulation practice has include the discussion on the referral of migrants to the qurantine center and the documents approval also. IOM has also worked with WHO, UNODC, DOI, DOIR, and DCDC to develop the SOP on immigration and transportation at each PoE that align the Prime Minister Decree 558 on PoE Management, PM Order 06, ASEAN Standard, and other COVID-19 Response Order accordingly. Noted that there are three pending activities to get done before the end of 31st March 2021 as: 1) SOP development and printing. 2) Monitoring. 3) Learning workshop and final report. 4) In total, 28,000 IEC materials were developed, printed and distributed to 7 PoEs on COVID-19 symptoms and precautions; safe return to Lao People’s Democratic Republic from Thailand and necessary quarantine measures and safe migration and accessing jobs during COVID-19. Also, QR codes were developed to share latest COVID-19 information with frontline officials and migrants. Visual diagrams demonstrating in and outbound passenger and vehicle flows at the 7 PoEs were developed to enhance understandings among frontline officials. UN-HABITAT - i) WASH assessment report prepared and gaps identified at six quarantine centres; ii) WASH services and infrastructure provided, including 37 gender-sensitive WASH facilities; iii) IEC materials developed and distributed at six quarantine centres. UNODC successfully trained 2 national level trainers to deliver training on preventing the spread of COVID-19, and trained directly 81 (79M/2F) officers from 20 BLO locations in Lao PDR. An additional 83 (66M/17F) district and village level authorities were subsequently trained by participants in UNODC trainings. Combined with the successful implementation of IOM's training sessions for PoE officers, this meets/exceeds the objective of representatives from 17 BLOs and 200 officers trained. In addition to the training, UNODC provided officers with 3000 copies of a pocket guide on preventing the spread of COVID-19, 500 COVID-19 info guides, and PPE for officers at 20 BLO locations. UNDP developed a national quarantine center profile and occupant registry dashboard for Ministry of Health to pilot and manage. 4 Provincial workshops were held to strategize with local authorties on needs, roles and responsobilties to respond to Covid-19. About 200 local officials participated and results from each workshop passed to the provincial governors. 7 quarantine centers recevied detailed inspections from WHO and Ministry of Health which resulted in supplying PPE, kitchen supplies, bedding, IT equipment, and renovations.
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words) | The time to develop the proposal was very short but the UN agencies ambitiously did their best to unite and develop a project concept and activities. Appointing a lead agency, UNDP, and project facilitator did assist in gluing agencies together and synchronizing activities. The biggest challenge was the delay in approving projects with implementing government partners. The Ministry of Public Security (MoPS) requested separate project agreements with UNODC and IOM. This was a time consuming process in which MoPS was not able to officially implement any activity or identify government focal points until September when a project was approved. As activity/ project approvals took time, delivery schedules are delayed and a project extension for some activities was needed. The synchronizing of activities with other partners proved difficult as well. For example the UNDP Provincial level workshops commenced in September with MoH, MoHA, and WHO while UNODC and IOM were getting project approvals from Ministry of Public Security. However, once agreements were established, the rollout of the training activites and material went smoothly and as planned. Forging relations with all UN and Government entities in a harmonious manner took some energy and time to get the momentum going. Coordination and timely identification of needs posed some challenges as each agency has a different working relationship and technical focus with Government counterparts as well as schedules of availability. This made coordinating inter-agency missions to jointly assess cross-sectoral needs in mutually agreed locations difficult and resulted in delays in conducting initial assessments and other activities. To conduct joint training among different agencies and line-ministries need better coordination and time for preparation. At the same time, the lesson and the methodology to provide in the training need to be prepared beforehand in the team as trainers. The simulation of the real situation at the POE is very important and needed for all frontline officials. so it need more time to coordinate and prepare well from all sectors. The COVID-19 response should be done as quick as possible as it is disease disaster outbreak.
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words) | IOM - As COVID-19 Pendemic Outbreak is the first experience for the government of Lao PDR, there is no Standard Operating Procedure (SOP). As many sectors, both UN, government, general public, and INGOs responding to the situation actively and responsively, the lesson learnt from mapping assessment, training, related governmental document on PoE management and COVID-19 response. IOM will develop the SOP on immigration and transportation at each POEs for the readiness and proper future responding that align the PM decree 558, PM order 06, ASEAN Standard, and other key legal documents respectively. This will be one jigsaw puzzle to feeding the MOSP strategy on POE and COVID-19 responding. UNODC successfully trained 2 national level trainers to deliver training on preventing the spread of COVID-19, and trained directly 81 (79M/2F) officers from 20 BLO locations in Lao PDR. An additional 83 (66M/17F) district and village level authorities were subsequently trained by participants in UNODC trainings. Combined with the successful implementation of IOM's training sessions for PoE officers, this meets/exceeds the objective of representatives from 17 BLOs and 200 officers trained. In addition to the training, UNODC provided officers with 3000 copies of a pocket guide on preventing the spread of COVID-19, 500 COVID-19 info guides, and PPE for officers at 20 BLO locations. UN-HABITAT - IEC materials could have been distributed at a very beginning stage of the project in more coordinated manner across all agencies involved since basic messages to prevent Covid-19 are the same irrespective of each agency's mandate UNDP participated in the development of 7 Quarantine Center assessments in 4 provinces.WHO led the development of a quarnatine assessment guideline to facilitate inspectors to rectify issues at a center. The UNDP also developed with feedback from the Ministry of Health, a national quarantine center profile and occupant registry dashboard. The dashboard is owned by the Ministry of Health Department of Communicable Disease. The Dashboard will facilitate the capturing, logging and analysis of data related to conditions of quarantine centers and potential needs. Also information about occupants at the center may facilitate tracing situations if need be.
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words) | The positive attitude and good will from all partners generated new relations that could be capitalized on for future projects and activities. The professional bonds took time to forge but during activity development, the combined efforts of all experts involved resulted in effective planning and activity implementation. The UN Agencies, with additional funding, could expand on various components of this project with their government counterparts. The largest hurdles experienced to date were initiating partnerships with the Government. The persistence has paid off with cooperative realtionships between the Department of Immigration, Ministry of Health, Ministry of Public Security, IOM, WHO and UNODC. This project also united MoH, MoHA, WHO, UNDP and HABITAT as well. Provincial level authorities engaged with the project included the Governor's office, District Governors, village chiefs, members of the COVID- 19 Taskforce, officials from provincial departments representing line ministries including police, military and immigration. At the beginning of the project, funds and activities were managed by the UN Agencies until UNDP entered into a Letter of Agreement with their Government partner, Ministry of Home Affairs (MoHA). MoHA’s contribution to the project and performance was recognized from the onset and played a much larger operational role that encompassed relationship building with MoH and WHO, workshop set up in the provinces, and logistics for quarantine center assessments. Hiring a project facilitator to navigate relations with partners and become a stable focal person to support partners with administration of the project proved essential. In addition, good existing partnership with local authorties, including thier in-kind contributions, was critical in conducting rapid assessment, coordinating monitoring missions, and facilitating inception workshops in a timely manner. The project has been approved by Ministry of Foreign Affairs (MoFA). However HABITAT, UNODC and IOM were instructed by their Government Counterparts to obtain separate alternative project/works agreementswhich took a few months to produce. Perhaps we could have called upon MoFA to expedite or waive the need for separate agreements and or allow line ministries to proceed with working on the project.
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken. | UNDP- MoH, MoHA, WHO, UNDP assessment of 7 quarantine centers in 4 provinces has shown the government and developing partners the huge needs to enhance, maintain, and manage public quarantine centers. IOM- POE mapping at 7 POEs shows that there are many gaps and challenges. More support above and beyond this project is needed such as: Physical distancing protocols at borders, knowledge on how to prevent, protect, and detect COVID-19 for frontline officials, foreign truck driver protocols, foreign worker processing, returning migrant responsibilities, lack of PPE, disposal of PPE, lack of IEC, enhance POE official training. UN-HABITAT- Rapid WASH asessment of six quarantine centres in four provinces has illustrated various needs beyond WASH (e.g. food, health professionals, management/governance, etc) to a varying degree and that continued support is needed beyond completion of the project.
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place | The development of a Ministry of Health managed Dashboard to profile each quarantine center and collect and analyze data on those quarantined nationwide was originally planned to be a simple database for the selected managers of assessed provincial quarantine centers. Funds originally planned to pass through UNCDF to Districts to renovate or procure supplies for quarantine centers was revised. Instead, funds were transferred locally in Lao through Ministry of Home Affairs (MoHA) using existing transfer systems. This was done to avoid losing funds through transfer and exchange fees to UNCDF in New York and back to Lao again. Also MoHA was a key partner assessing quarantine centers and ensuring provisions and works were complete.
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners. | The participation from the Government counterparts was extremely engaging and supportive. In relationship to Provincial Government Strengthening workshops, the MoH and MoHA led much of the planning and organization with UNDP and WHO support. The in-kind contribution from WHO must also be acknowledged. Their technical inputs, facilitation, and collaboration with MoH was critical to UNODC and IOM trainings as well as UNDP workshops and quarantine center assessments. WHO is funding a workshop in February of 2021 to unite key officials from the Provincial Government strengthening workshops to brief each other on Covid-19 response achievements and challenges in the presence of MoH, MoHA, WHO, UNDP and US CDC. The WHO aims to stregthen public health through enhanced local government capacities. UNODC -UNODC in-kind contributions - Delivery of the first batch PPE (masks, gloves protective suits, hand sanitizer, thermometers), Staff time (Project Coordinator P4 based in Bangkok, Thailand, and national staff based in Lao PDR who supported the delivery of the training sessions) UN-HABITAT- Good partnership with provincial authorities, Covid-19 Committee, and Nam Papa State-owned Enterpise (NPSE), responsible for provision and management of water supply in each province, including in-kind contributions, was crucial in conducting the rapid assessment, coordinating visits and procuring and installing WASH infrastructure. UN-Habitat also recieved additional US $314,280 from the Swiss Development Cooperation Agency to complement the project.

## Communication-Annual
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
https://drive.google.com/drive/folders/1NLSxcUdFPmRGRI-9KVke441pyMLPzrJe?usp=sharing
2. Upload here: Communications and Visibility (OPTIONAL)
Fund's Communication Guidelines is posted here: http://mptf.undp.org/document/download/25941
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well picture material please make sure you include all credits and upload them in high resolution Call1 countries.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board

## RBM-Annual
| Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 1[1] | 1) Procurement and distribution of appropriate Personal Protective Equipment (PPE) for relevant frontline officials at the PoEs and quarantine centers completed. 2) Quarantine centers enhanced with renovations, IEC material, bedding, and kitchen material. WASH infrastructure enhanced with gender-separated bathrooms, shower facilities, hand-washing stations, water pipes, taps, hygiene supplies. 3) White papers produced based on Provincial Health Governance workshops led by the Ministry of Home Affairs (MoHA) and Ministry of Health (MoH) whom facilitated over 300 local government officials in 4 provincial workshops to share provincial level protocols to prevent, contain and treat Covid-19 through enhanced public services and community engagement. 4) A Quarantine Center Profile and Occupant Registry was developed and is being piloted by the Ministry of Health. 5) Screening and surveillance capacity building ongoing at 27 Points of Entry (7 border points and 20 border liaison offices). Standard Operating Procedures (SOPs) on Immigration and SOPs on Transportation, POE Checklist Assessment and other related documents have been translated into Lao language and are ready for adaption into jointly developed SOPs with Department of Immigration to align with the PM Decree 558, PM Decree 06 on COVID-19 Response, Ministry of Public Security (MoPS’s) Decree 112, WHO standard, and other related ASEAN Standard. 6) Migrant inclusive messaging developed and disseminated to inbound and outbound migrants to counter misinformation and prevent against COVID-19 |  | Monitoring visit by UN staff and progress report with photos from the partners
Indicator:The Government of Lao PDR, through the Ministry of Health and other relevant ministries and institutions effectively prepared and responded to potential widespread of COVID-19 transmission across Lao PDR.
Baseline:
Planned Target:
Output 1.1: Lao PDR has improved its capacity in screening and surveillance at POEs | UNODC: 1. Back pocket guides and info guides have been developed, designed translated and are in the process of being printed (3000 copies) 2.Training agenda set and agreed upon with IOM and WHO 3.Training material, pre-post evaluation test and survey developed and shared with IOM and WHO 4. 6-7 October: Training for 28 (27M, 1F) officers from 6 BLO locations in Southern Lao PDR, Pakse, Champasak Province 5. 20-21 October: Training for 28 officers (27M, 1F) from 7 BLO locations in Central Lao PDR, Paksan, Bolikhamsi Province 6. 3-4 November: Training for 25 (25M) officers from 7 BLO locations in Northern Lao PDR, Luang Namtha, Luang Namtha ProvinceProvince 7. 26 October: Participant-led training for 40 (29M/11F) district and village-level authorities in Champasak Province, Lao PDR, hosted by representatives from BLO Vang Tao. 8. 1 December: Participant-led training for 21 (20M/1F) district and village-level authorities in Champasak Province, Lao PDR, hosted by representatives from BLO Nongnokkien and BLO Meuang Sen. 9. 28 December: Training for 22 (17M/5F) district and village-level authorities in Champasak Province, Lao PDR, hosted by representatives from BLO Singsamphan. IOM: exceeded over the target and trained the frontline officials for 508 (375 M/ 133 F) |  | Project Records, Training Records, Attendance Records, Pre/Post Test Results
Indicator 1.1.1:# of border office staff trained in infection, prevention and control operations, improving physical distancing and people movements at PoEs Data to be disaggregated by sex, age, position and PoE
Baseline: 0
Planned Target: UNODC: 200 frontline border officials trained Officials at 17 PoEs part of the BLO network are provided with training material (back pocket guides and posters) tailored at strengthening the response of border officials to COVID-19 in border areas in respect of human rights
Indicator 1.1.2a: # of border office staff trained in basic health surveillance, health clearance formalities and forms, law enforcement and human rights dimension during COVID-19at PoEs Data to be disaggregated by sex, age, position and PoE | UNODC: Two (2) national level trainers (1M/1F) received Taining of Trainers and supported the roll-out of three (3) training workshops to 81 Border Liaison Officers (79M/2F) from 20 BLOs across Lao PDR. (see Indicator 1.1.1) An additional 83 (66M/17F) district and village level authorities were subsequently trained through a peer-to peer modality following UNODC trainings. IOM: exceeded over the target and trained the frontline officials for 508 (375 M/ 133 F) |  | Project Records, Training Records, Attendance Records, Pre/Post Test Results
Baseline: 0
Planned Target: 200 frontline border officials trained
Indicator 1.1.2b: % of border guards equipped with PPE (UNODC in kind contribution) | UNODC: procured equipment to support 200 officers at 20 BLOs, including: -24800 surgical masks -440 eye goggles -9800 gloves -272 protective suits -94 temperature scanners -400 bottles of hand sanitizer (500mL ea.) IOM: procured the following equipment following its POE assessment: Personal Protective Coat (14 pieces) Gloves (43,700 pieces) N95 masks (1700 pieces) Goggles (1090 pieces) Hand Sanitizer (3773 pieces) Plastic face shield (924 pieces) Handheld thermometer scan (204 pieces) Disinfectant Sprayer (275 pieces) Floor Cleaning Detergent (30 bottles) Toilet Cleaning Detergent (30 bottles) |  | Project Records, Training Records, Attendance Records, Pre/Post Test Results
Baseline: -
Planned Target: 200 frontline border officials equipped
Indicator 1.1.3: Health service case identification and triage at PoEs enhanced | IOM conducted assessments and SOP trainings at 7 international PoEs (Land Border and Airports) to the frontline officials. Standard Operating Procedures were developed on immigration and transportation at each PoE, a total of 500 copies, were provided in Lao language to frontline officials. IOM developed IEC material on COVID-19 symptoms and precautions; safe return to Lao People’s Democratic Republic from Thailand and necessary quarantine measures and safe migration and accessing jobs during COVID-19 – 21,500 copies were disseminated to inbound and outbound migrants |  | 1) Master plan on border health. 2) Action plan. 3) Data collection forms from returned migrants and travelers.
Baseline:0
Planned Target: 20 POEs
Output 1.2: District governments enabled to prepare for and manage quarantine and isolation centres
Indicator 1.2.1: Rapid disbursement of funds to provincial and district level administrations for facility preparedness and management assisted based on rapid assessment needs. | 6 Quarantine centers and 1 isolation center in 7 Districts (4 Provinces) received funding to repair and procure materials. Funds were transferred through Ministry of Home Affairs through existing fund transfer channels to districts. Joint WHO, Ministry of Health, UNDP and MoHA inspections were completed in 7 quarantine centers based on an MPTF developed quarantine center checklist led by WHO. | Additional isolation center at a hospital in Sayaboury was assessed in addition to the other quarantine centers. | UNDP participation in assessments documented in trip reports and photos. Also quarantine center improvement monitoring visits and material delivery and handovers completed by Ministry of Home Affairs officials.
Baseline: 0
Planned Target: 6 Districts
Indicator 1.2.4: Number of meetings of Online and virtual multi-stakeholder coordination platforms | Indicator not relevant after project workplan developed with specific partners, outputs, and activities.
Baseline:
Planned Target:
Indicator 1.2.5: Provincial level preparedness plans for # of provinces | 4 white paper like reports were generated by the Ministy of Home Affairs based on the feedback from local officials participating in the 4 Provincial workshops facilitated by Ministry of Health, Ministry of Home Affairs, WHO, and UNDP. |  | Ministry of Home Affairs developed documents with UNDP review.
Baseline: 0
Planned Target: 4
Output 1.3:Effective management of quarantine and isolation centres in selected districts
Indicator 1.3.1: MoHA and provincial and district administrations are assisted in the implementation of the MoH guidelines on IPC quarantine/isolation facilities | Joint quarantine center inspections with WHO, Ministry of Health, UNDP and Ministry of Home Affairs were completed in 6 Quarantine centers and 1 isolation center in 7 Districts (4 Provinces) | Additional isolation center at a hospital in Sayaboury was assessed in addition to the other quarantine centers. | UNDP participation in assessments documented in trip reports and photos.
Baseline: 0
Planned Target: 6 Districts
Indicator 1.3.2: Number of locations identified for a. Quarantine; and b. isolation centres with links with health checks and referrals | The government had already appointed, closed, or opened facilities.
Baseline: 0
Planned Target:0
Indicator 1.3.3: Number of temporary gender-sensitive WASH facilities built with hygiene consumables; number of gender-sensitive Information, Education and Communication (IEC) materials distributed | 37 gender-sensitive WASH facilities were built, including bathrooms and shower facilities across six quarantine centres. |  | Monitoring missions by UN-Habitat staff, progress report and update from the partner
Baseline: 0
Planned Target: 37
Indicator 1.3.4: # of cases provided with psychosocial support such as information in migrants’ language to reduce stress; interpretation services during testing, Data to be disaggregated by sex, age and migrant language | Achieved Indicator Targets: 28000 IEC was developed, printed and distributed in Lao language to 7 PoEs on COVID-19 symptoms and precautions. IEC topic "safe return to Lao People’s Democratic Republic from Thailand and necessary quarantine measures and safe migration." |  | 1) Data collection. 2) Final result report.
Baseline: 0
Planned Target: 3000 migrants
Indicator 1.3.5:% of quarantine and isolation centres adequately disinfected and returned to their original purpose | Indicator not relevant after project workplan developed with specific partners, outputs, and activities. Also the government had already returned or was in process of returning public buildings such as schools back to their original purpose.
Baseline:
Planned Target:

## General Information-Final
Programme Title & Project Number | Programme Duration
Programme Title: | Overall Duration (months)
Programme Number (if applicable) | Start Date (dd.mm.yyyy)
MPTF Office Project Reference Number: | Original End Date (dd.mm.yyyy)
Country | Current End date(dd.mm.yyyy)
Recepient UN Organizations | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | National counterparts (government, private, NGOs & others) and other International Organizations
Report Cleared By
o Name:
o Title:
o Email address:
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the relevant decision-making body/Steering Committee.
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Final
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum)
2 | Purpose (and Beneficiaries) | Please include the number of both direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups
3.1 | Results: Outcome Level | Please include outcome level results achieved
3.2 | Results: Output Level | Please include output level results achieved
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words)
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words)
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words)
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken.
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners.

## RBM-Final
| Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 1[1]
Indicator:
Baseline:
Planned Target:
Output 1.1
Indicator 1.1.1:
Baseline:
Planned Target:
Indicator 1.1.2:
Baseline:
Planned Target:
Output 1.2
Indicator 1.2.1:
Baseline:
Planned Target:
Indicator 1.2.2:
Baseline:
Planned Target:
Please inlcude all three: Baseline, Planned Target and Achieved Targets
[1] Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.

## Communication-Final
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
2. Upload here: Communications and Visibility (OPTIONAL)
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well picture material please make sure you include all credits and upload them in high resolution Call1 countries.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board