## OVERALL REPORTING INSTRUCTIONS
OVERALL INSTRUCTIONS
1 | All questions/sections must be responded to before submitting to secretariat. Once the document is uploaded in the relevant folder (as per instruction below) please email the secretariat.
2 | To ensure high quality narrative and results reports please pay attention to the following details: a) A well written, succinct summary that is very clear about what was done during the reporting period and results achieved, with a priority on concrete activities, beneficiaries reached and achievements beyond processes b) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document; c) In case certain indicators are not longer relevant, an explanation for why they are not. d) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document and how they align with the overall SERP joint workplan, and connection to reporting on global-level SERP indicators e) Indicate the relevant SERP monitoring framework global indicators that were contributed to as part of this project. f) An honest analysis of challenges faced, the responses to these challenges and the extent to which these responses were successful or not g) Go beyond generic, standard and well documented features of successful project implementation when reflecting on innovation and focus on what is truly new for you and which could enable replication efforts
3 | You must submit this completed workbook by uploading it in the relevant Project Folder here (https://undp.sharepoint.com/:f:/r/sites/covid19mptfcall1/Shared%20Documents/2020-REPORT?csf=1&web=1&e=j3cc3J). Please note if you are unsure of your project number please refer to http://mptf.undp.org/factsheet/fund/COV00
A | ANNUAL REPORT
DEADLINE: 31 January 2021
4 | ALL projects that received funds in 2020 must complete annual report, HOWEVER if you have your project ending on 31st December 2020 - your FINAL report is your annual report.
5 | If you received a no-cost extension on your project please do the annual report and in a few months time you can update the annual report to include activities to complete your end of project report.
6 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.
B | END OF PROJECT - FINAL REPORT
DEADLINE: 31 January 2021
7 | ALL projects that received funds in 2020 must complete annual report, HOWEVER if you have your project ending on 31st December 2020 - your FINAL report is your annual report.
8 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.

## General Information-Annual
Programme Title & Project Number | Programme Duration
Programme Title: | Overall Duration (months)
Programme Number (if applicable) | Start Date (dd.mm.yyyy)
MPTF Office Project Reference Number: | Original End Date (dd.mm.yyyy)
Country | Current End date(dd.mm.yyyy)
Recepient UN Organizations | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | National counterparts (government, private, NGOs & others) and other International Organizations
Report Cleared By
o Name:
o Title:
o Email address:
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the Secretary-General's Designate
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Annual
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum)
2 | Purpose (and Beneficiaries) | Please include the number of direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups
3.1 | Results: Outcome Level | Please include outcome level results achieved
3.2 | Results: Output Level | Please include output level results achieved
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words)
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words)
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words)
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken.
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners.

## RBM-Annual
| Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 1[1]
Indicator:
Baseline:
Planned Target:
Output 1.1
Indicator 1.1.1:
Baseline:
Planned Target:
Indicator 1.1.2:
Baseline:
Planned Target:
Output 1.2
Indicator 1.2.1:
Baseline:
Planned Target:
Indicator 1.2.2:
Baseline:
Planned Target:
Please inlcude all three: Baseline, Planned Target and Achieved Targets
[1] Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.

## Communication-Annual
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
2. Upload here: Communications and Visibility (OPTIONAL)
Fund's Communication Guidelines is posted here: http://mptf.undp.org/document/download/25941
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well picture material please make sure you include all credits and upload them in high resolution Call1 countries.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board

## General Information-Final
Programme Title & Project Number |  | Programme Duration
Programme Title: | Shock responsive social protection to reduce the socioeconomic impact of the COVID-19 pandemic on poor households, while ensuring support for an early and sustainable recovery | Overall Duration (months) | 6 months
Programme Number (if applicable) |  | Start Date (dd.mm.yyyy) | 2021-05-20
MPTF Office Project Reference Number: | 121711 | Original End Date (dd.mm.yyyy) | 2021-11-20
Country | El Salvador | Current End date(dd.mm.yyyy)
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | WFP FAO | National counterparts (government, private, NGOs & others) and other International Organizations | CENTA, Municipality of Tacuba, UNWomen, UNICEF
Report Cleared By
o Name: | Silvia Vides
o Title: | Partnership Officer in RCO
o Email address: | silvia.vides@un.org
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the relevant decision-making body/Steering Committee.
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Final
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum) | The project designed and tested in the municipality of Tacuba a model of Shock Responsive Social Protection applicable and scalable using the national social protection Programmes. WFP, FAO, UNWomen, UNICEF and UNHCR designed and implemented an integrated response through Multipurpose Cash Based Transfer; agriculture inputs and technical assistance; and support to prevent violence against women, girls, boys and adolescents. The main activities included: 1. Coordination with all the institutions involved in the project for the mechanism of delivery of the project deliverables. 2. Approval of criteria for the selection of participants: to be a producer of basic grains, not to receive other support for production by the government, mother heads of households, households with children under 9 years of age, households with older adults or with disabilities. 3. Identification of 2,190 families and 1,000 smallholders in the municipality to be included in the Single Register of Participants (RUP) and to receive unconditional multipurpose cash and/or the provision of inputs. 4. In close colaboration with the National Centre for Agricultural and Forestry Technology (CENTA), provision virtual training and technical assistance on bean production in the form of video tutorials and one-off visits to plots. The implementation was affected by the COVID-19-related mobility restrictions, so the following adjustments were needed: 1. The functions of the staff to be contracted with the MPTF were assumed by CENTA and the local government. 2. Farmer field schools was substitued by virtual trainings. 3. The delivery of the inputs a daily schedule was made to avoid agglomerations and a biosecurity plan was designed with those for the time of for the days of delivery of the inputs. This Project allowed to reduce the impact of COVID-19 on households and other local stakeholders by providing support in the form of inputs and cash transfers in Tacuba, especially to the most vulnerable groups. 2,190 vulnerable families were assisted by means of vertical and horizontal expansion of the SRSP model; 1,000 smallholder farmers houselds received agricultural incentives and training as a mitigation measure to the crisis; and in total 2,190 vulnerable families strengthened in the prevention of gender violence. At a institutional level, the project showed how the model can be used in El Salvador for crisis response in municipalities, and allowed to include the Ministry of Agriculture in crisis response using the social protection system.
2 | Purpose (and Beneficiaries) | Please include the number of both direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups | 2,190 (1135 women and 1055 men) families were assisted through the Shock Responsive Social Protection model, jointly with the Central Government and the Municipalities. Among them, 1,000 families received agricultural incentives.Which included 497 women and 503 men, and 4,000 indirect beneficiaries.
3.1 | Results: Outcome Level | Please include outcome level results achieved | The Shock Responsive Social Protection (SRSP) scalable model was created and tested. The Standard Operation Procedures (SOPs) was designed and finished. For the model and SOP's elaboration, an interinstitutional work team was formed with the House of the President's team in charge of the social protection programs. Developing the model and SOPs required identifying and distributing resposibilities within the different institutions. | Outcome 1. Shock Responsive Social Protection applicable and scalable model created and tested using the national social protection programs.
3.2 | Results: Output Level | Please include output level results achieved | Output 1.1.1: 2,190 vulnerable families were assisted by means of vertical and horizontal expansion of the Shock Responsive Social Protection model. To ensure the future scalability of the designed model, WFP tested it by leveraging funding and assisting the identified families for 3 months under the Cash Based Transfer (CBT) modality. The resources allowed to incorporate into the social protection system, vulnerable families whom had not previously participated in social programs, with special emphasis on women heads of families, families with children under 7 years of age, people with disabilities and indigenous families. Output 1.1.2: 1,000 smallholder farmers houselds (with 49.7% of female-headed households) received agricultural incentives and training on alternative livelihood as a mitigation measure to the crisis. The Municipal Government requested the incorporation of a group of families in vulnerable conditions. The request implied the need to update the RUP file in order to verify and standardize the targeting of the families to attend. Output 1.1.3: 2,190 vulnerable families strengthened in the prevention of gender violence. With the technical assistance of UNWOMEN and UNICEF as partner agencies, it was possible to incorporate information, education and communication material on the prevention of gender-based violence against girls and women. | Output 1.1.1: 2,500 vulnerable families due to food insecurity, poverty and the effects of COVID19 in the department of Ahuachapan, are assisted by means of vertical and horizontal expansion of the Shock Responsive Social Protection model Output 1.1.2: 1,000 vulnerable rural household’s food security and resilience affected by COVID-19 improved through the improvement of their livelihoods Output 1.1.3: 2,500 vulnerable families due to food insecurity, poverty and the effects of COVID19 strengthened in the prevention of gender violence
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words) | The main challenge was identifying the families using the Government's RUP tool. It was outdated, so WFP had to carry out a survey in the field that delayed the first transfer. Also, the new identified families did not have the documentation required to register in the RUP. WFP and the local government staff supported families in updating their documents for the registration. The COVID-19 protocols established by financial providers caused some delay as more dates for the transfers were necessary in order to maintain social distancing. Due to the short time for the implementation and the COVID-19 restrictions, the project provided organic agricultural inputs instead of producing them with the beneficiaries, not generating long term capacity in the families, and face-to-face trainings were replaced by informational and educational videos. To overcome the restricted access to communities due to COVID-19 mobility restrictions and due to high rates of violence WFP and FAO were accompanied by local government staff. Moreover, the functions of the staff to be contracted with the MPTF were assumed by CENTA and the local government. The closeness with an election event required constant monitoring by WFP and FAO to avoid the risk of the support getting politicized. All participating families had access to a feedback platform. Complaints about the use of the transfers, harassment, abuse and sexual exploitation were received and all cases were resolved.
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words) | The Social Protection System in El Salvador can be used for crisis response in the municipalities where the RUP is updated and there is work team in the field. The understanding of the social protection system by the institutions involved is a priority. The information available in the system makes the identification by gender and age possible, which facilitates an approach to address the gender gaps in the targeting process under gender analysis.
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words) | The MPTF financing allowed to include CENTA as part of the Ministry of Agriculture in crisis response using the social protection system. This alliance allowed the following effects: 1) Inclusion of agriculture programs into the functioning of the social protection system. 2) Follow up on investments in agriculture promoted by FAO and WFP. 3) Inter-institutional alliances for future interventions using this model will be strenghtened.
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken. | The baseline was undetaken at the beginning of the project implementation. The final evaluation is being finalized.
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place | Due to field mobility restrictions for UN officials, the strategy to accompany the project was designed with and through local actors. The functions of the staff to be contracted with the MPTF have been assumed by CENTA and the local government.
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners. | As part of the COVID 19 response, WFP, in coordination with FAO, UNICEF and UNWOMEN, developed an intervention to complement the actions under the MPTF. WFP provided assistance to the 1,000 smallholder farmers families in Tacuba (50.3% men and 49.7% women) to improve their basic grains harvestpost-management capacities. WFP delivered 1,000 postharvest kits for a total value of $ 119,250.00, (consisting of 1 metal postharvest silo with a grain storage capacity of 0.8 MT, a wooden pallet and an information on its use) to expand the storage capacity of the area by 800 MT. WFP also prepared 4 audiovisual materials to be disseminated through cell phones memory cards (for a total value of $ 6,000.00), to strengthen their capacities in good practices of postharvest and commercialization. This effort allowed families to reduce post-harvest losses and store their products while waiting for better sales prices.

## RBM-Final
| Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 1[1] | The SOP and a reactive social protection model for emergencies have been completed. It was prepared with the participation of institutions in the implementation of the project. | N/A | Finished document.
Indicator 1.1: The national Social Protection programs expanded to assist the families vulnerable due to the effects of COVID19
Baseline: 0
Planned Target: 1
Indicator 1.2: Vulnerable food insecure families due to poverty and the effects of COVID19 assisted in the framework of national Social Protection programs | 2,190 families were assisted using the RUP of the social protection system as a targeting instrument. | In certain cases the targeting tool used by RUP social programs did not have the complete information to locate or to identify the family's number to be able to contact them remotely. | Transfer verification list from the financial providers.
Baseline: 0
Planned Target: 2,500 Households
Output 1.1.1: 2,500 vulnerable families due to food insecurity, poverty and the effects of COVID19 in the department of Ahuachapan, are assisted by means of vertical and horizontal expansion of the Shock Responsive Social Protection model | 2,190 families were assisted. In 40 percent of the families there was a vertical expansion, in which the families that were already part of one of the government's social programs and this project were assisted with an additional bonus for their living conditions. And 60 percent of the identified families received a horizontal expansion of the social protection system, because they had not previously participated in social programs and they joined temporarily through this intervention. | Although it was possible to identify the 2,500 families that met the criteria to be assisted, due to mobility restrictions it wasn't possible to let the families know about the benefits of the project because in their RUP file there wasn't a contact number. This was one of the opportunities identified to update the RUP files. | Databases of the delivery records of the financial providers.
Indicator 1.1.1: Shock Responsive Social Protection-assisted vulnerable families receive unconditional multipurpose cash transfers
Baseline: 0
Planned Target: 2,500 Households
| 1,000 families were assisted through agricultural incentives and training as an alternative livelihood as a mitigation measure to the crisis. | N/A | List of beneficiaries with details of agricultural incentives received
Output 1.1.2: 1,000 vulnerable rural household’s food security and resilience affected by COVID-19 improved through the improvement of their livelihoods
Indicator 1.1.2: Shock Responsive Social Protection-assisted vulnerable families receive unconditional multipurpose cash transfers
Baseline: 0
Planned Target: 1,000
Output 1.1.3: 2,500 vulnerable families due to food insecurity, poverty and the effects of COVID19 strengthened in the prevention of gender violence | Families received educational material prepared by UNWOMEN and UNICEF on gender-based violence prevention for women and girls. | The educational material was delivered to all the families identified and notified. The reason for not delivering all the planned material was due the lack of information on the RUP file. | Lists of families and delivered educational materials.
Indicator 1.1.3: Shock Responsive Social Protection-assisted families receive informative materials and telephone cards for violence prevention and care consultations
Baseline: 0
Planned Target: 2,500 Households
[1] Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.

## Communication-Final
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
2. Upload here: Communications and Visibility (OPTIONAL)
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well picture material please make sure you include all credits and upload them in high resolution Call1 countries.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board