## OVERALL REPORTING INSTRUCTIONS
OVERALL INSTRUCTIONS
1 | All questions/sections must be responded to before submitting to secretariat. Once the document is uploaded in the relevant folder (as per instruction below) please email the secretariat.
2 | To ensure high quality narrative and results reports please pay attention to the following details: a) A well written, succinct summary that is very clear about what was done during the reporting period and results achieved, with a priority on concrete activities, beneficiaries reached and achievements beyond processes b) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document; c) In case certain indicators are not longer relevant, an explanation for why they are not. d) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document and how they align with the overall SERP joint workplan, and connection to reporting on global-level SERP indicators e) Indicate the relevant SERP monitoring framework global indicators that were contributed to as part of this project. f) An honest analysis of challenges faced, the responses to these challenges and the extent to which these responses were successful or not g) Go beyond generic, standard and well documented features of successful project implementation when reflecting on innovation and focus on what is truly new for you and which could enable replication efforts
3 | You must submit this completed workbook by uploading it in the relevant Project Folder here (https://undp.sharepoint.com/:f:/r/sites/covid19mptfcall1/Shared%20Documents/2020-REPORT?csf=1&web=1&e=j3cc3J). Please note if you are unsure of your project number please refer to http://mptf.undp.org/factsheet/fund/COV00
A | ANNUAL REPORT
DEADLINE: 31 January 2021
4 | ALL projects that received funds in 2020 must complete annual report, HOWEVER if you have your project ending on 31st December 2020 - your FINAL report is your annual report.
5 | If you received a no-cost extension on your project please do the annual report and in a few months time you can update the annual report to include activities to complete your end of project report.
6 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.
B | END OF PROJECT - FINAL REPORT
DEADLINE: 31 January 2021
7 | ALL projects that received funds in 2020 must complete annual report, HOWEVER if you have your project ending on 31st December 2020 - your FINAL report is your annual report.
8 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.

## General Information-Annual (hidden)
Programme Title & Project Number |  | Programme Duration
Programme Title: | Addressing gaps in Ghana’s Pandemic Response for the most vulnerable populations | Overall Duration (months) | 7 months
Programme Number (if applicable) | 121705 | Start Date (dd.mm.yyyy) | 20th May, 2020
MPTF Office Project Reference Number: | 121705 | Original End Date (dd.mm.yyyy) | 31st Dec, 2020
Country | Ghana | Current End date(dd.mm.yyyy) | 31st Dec, 2020
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | WHO, UNFPA, UNDP, UNICEF | National counterparts (government, private, NGOs & others) and other International Organizations | Ministry of Health, Ministry of Gender, Children and Social Protection, Ghana Health Service, Domestic Violence and Victim Support Unit (DOVVSU), Police, Dept. of Social welfare, Judicial Service, Commission on Human Rights and Administrative Justice, Media, Traditional and Religious Authorities, relevant MMDAs, Development Partners and CSOs
Report Cleared By
o Name: | Charles Abani
o Title: | Reesident Coordinator, Ghana
o Email address: | Charles.Abani@un.org
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the Secretary-General's Designate
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Annual (hidden)
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (AGENCY WORD LIMIT UP TO 120 WORDS MAXIMUM IN OTHER TO ACHIEVE THE 500 WORD LIMIT)
2 | Purpose (and Beneficiaries) | Please include the number of direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups
3.1 | Results: Outcome Level | Please include outcome level results achieved
3.2 | Results: Output Level | Please include output level results achieved
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words) (AGENCY SHOULD PROVIDE UP TO 120 WORDS MAXIMUM IN OTHER TO ACHIEVE THE 500 WORD LIMIT)
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words) (AGENCY SHOULD PROVIDE UP TO 120 WORDS MAXIMUM IN OTHER TO ACHIEVE THE 500 WORD LIMIT)
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words) (AGENCY SHOULD PROVIDE UP TO 120 WORDS MAXIMUM IN OTHER TO ACHIEVE THE 500 WORD LIMIT)
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken.
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners.

## RBM-Annual (hidden)
| Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 1[1]
Indicator:
Baseline:
Planned Target:
Output 1.1
Indicator 1.1.1:
Baseline:
Planned Target:
Indicator 1.1.2:
Baseline:
Planned Target:
Output 1.2
Indicator 1.2.1:
Baseline:
Planned Target:
Indicator 1.2.2:
Baseline:
Planned Target:
Please inlcude all three: Baseline, Planned Target and Achieved Targets
[1] Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.

## Communication-Annual (hidden)
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
2. Upload here: Communications and Visibility (OPTIONAL)
Fund's Communication Guidelines is posted here: http://mptf.undp.org/document/download/25941
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well picture material please make sure you include all credits and upload them in high resolution Call1 countries.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board

## General Information-Final
Programme Title & Project Number |  | Programme Duration
Programme Title: | Addressing gaps in Ghana’s Pandemic Response for the most vulnerable populations | Overall Duration (months) | 7 months
Programme Number (if applicable) | 121705 | Start Date (dd.mm.yyyy) | 20th May, 2020
MPTF Office Project Reference Number: | 121705 | Original End Date (dd.mm.yyyy) | 31st Dec, 2020
Country | Ghana | Current End date(dd.mm.yyyy) | 31st Dec, 2020
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | WHO, UNFPA, UNDP, UNICEF | National counterparts (government, private, NGOs & others) and other International Organizations | Ministry of Health, Ministry of Gender, Children and Social Protection, Ghana Health Service, Domestic Violence and Victim Support Unit (DOVVSU), Police, Dept. of Social welfare, Judicial Service, Commission on Human Rights and Administrative Justice, Media, Traditional and Religious Authorities, relevant MMDAs, Development Partners and CSOs
Report Cleared By
o Name: | Charles Abani
o Title: | Resident Coordinator, Ghana
o Email address: | Charles.Abani@un.org
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the relevant decision-making body/Steering Committee.
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Final
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum) | Under pillar 1, the joint programme • supported the finalization and dissemination of a guidance document to ensure continuity of service delivery during disease outbreaks in general and during COVID-19 in particular. • facilitated supportive supervisory visits to health facilities using standard checklists by the regional and district teams to identify service delivery gaps and provide appropriate support. • provided a dedicated training to health staff on continuity of essential health and nutrition (H&N) services including Infant and Young Child Feeding (IYCF) and immunization in the context of COVID • ensured the identification and treatment of children with Severe Acute Malnutrition (SAM) through the provision of essential nutrition supplies for early detection and management of (SAM) and active case search. • Supported the dissemination of key messages on service continuity through multiple communication channels. • led orientation and training on enhanced inspection, COVID-19 communication and sanitary burials within key 2020 pandemic epicenters in Accra, Kumasi and Obuasi. • rehabilitated WASH infrastructures and provided handwashing facilities in 6 health facilities at outpatient areas • provided hand washing devices in 6 schools in the Accra Metropolitan Area in preparation for the reopening of schools. Under pillar 2, the joint programme • strengthened the setting up, implementation and monitoring of an emergency cash transfer including its communications, monitoring and evaluation; • enhanced CSOs social accountability capacity. Under Pillar 3, the Joint programme • Enhanced knowledge and capacity of representatives from 67 religious organizations (Moslem and Christian); 5 women’s groups from identified Covid-19 hotspots in Accra (Nima, Mamobi, Agbogloshie/ Old Fadama and Madina). These were engaged as change agents. • Established a COVID-19 hotline at the Commission for Human Rights and Administrative Justice (CHRAJ) and created 10 safe spaces across the five target communities. Presently, 526 SGBV cases have been linked to services. • Enhanced awareness and knowledge to prevent, mitigate and respond to COVID-19 related stigma and discriminations and SGBV issues through intense public education and sensitization. • Procured and distributed over 2500 dignity kits and essential items. These were used as entry points for the provision of SGBV and SRHR information and services including Family Planning. • Joint programme partnered with state institutions, CSOs to build the resilience of the vulnerable women and girls in COVID-19 hotspots communities. With complementary funding, the JP supported the completion of a CSO SGBV shelter and furnished the same.
2 | Purpose (and Beneficiaries) | Please include the number of direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups | Pillar 1: Targeted beneficiaries include health workers, frontline WASH staff, communities, caregivers, children and adolescents. ● 2185 health workers (321 males; 1864 females) benefitted from capacity building on continuity of essential health services. In detail, the following training have been provided: - capacity building on guidelines developed during the outbreak (including Maternal and Neonatal Health Care), Infection Prevention and Control (IPC), appropriate use of Personal Protective Equipments (PPEs) and promotion of service utilization in the context of COVID-19; - capacity building on reproductive, maternal, newborn, child and adolescent health and nutrition (RMNCAHN); - training on accurate documentation reporting into the Maternal and Child Health Record Book (MCHRB). ● 252 people (106 males and 146 females) including community, traditional and religious leaders, NGOs, the media, teachers, transport unions officers, and caregivers took part in advocacy/stakeholder meetings to empower them and gain their support in the service demand drive. This led to an increase in OPD attendance in 4 of the 5 implementing districts during the project implementation period. ● 346,931 people comprising men, women and adolescents were reached with key health and nutrition messages with a consequent CWC increased attendance from 4619 boys and 4591 girls in April 2020 to 31,034 girls and 32,086 girls. ● 1261 caregivers received IYCF counselling while 873 children 6-59 months with SAM were identified and currently receiving treatment. These were due to timely procurement and delivery of supplies for early detection and treatment of Severe Acute Malnutrition (SAM) and the support in conducting active SAM case search in all related communities ● 14,156 people (2,338 men, 6,388 women; 5430 girls and boys) were reached through enhanced hygiene promotion focusing on handwashing in 10 communities. The initiative included risk communication in 101 public spaces (public toilets and markets) and the provision of PPE for about 150 frontline WASH staff in key MMDAs in the Greater Accra Region. ● An estimated 1,046 patients (1,006 females and 140 male) and 502 health workers (72 male and 430 female) were reached with the provision of improved WASH facilities in 6 health centres in the Ashiedu -Keteke, La-Nkwantanang and Ashaiman Municipalities/Sub-Metropolitan areas. ● 8,037 children (4,005 girls and 4,032 girls) have been reached with the provision of handwashing in 16 schools in the Accra Metropolitan area. Pillar 2. Targeted beneficiaries included extremely poor family and vulnerable people. ● 1,451,604 extremely poor families (796,517 female; 655,087 male out of which 131,915 persons living with disability) benefited from an emergency double payment with a top-up to support social distancing ● 150,000 additional vulnerable people (orphans, people on the street, people with disability, kayayei, alleged witches) benefited from a temporary horizontal cash transfer scale-up provided by a new mobile money payment modality Pillar 3: Targeted beneficiaries were women and girls, market queens and kings, traditional leaders, Paralegals, Health workers, Psychologists, and Men between the ages of 12 and 60. These include: ● Direct beneficiaries were 2636 (1,428 Females and 1208 males; Indirect beneficiaries were 424,155 (204,250 Males and 219,905 Females). ● 20 female Health workers have increased knowledge on SGBV to enable them conduct routine screening of SGBV in health facilities. ● 21 females and 4 men engaged as managers of SGBV hotline and 16 males and 9 females had increased capacity to manage, respond and refer SGBV and stigma cases effectively. ● 2500 vulnerable women and Girls received dignity kits ● 60 males were engaged as COVID-19 SGBV ambassadors to facilitate community awareness ● 16 females and 58 males from 37 religious institutions and five women groups had their capacity built to support the anti-stigma campaign in their various communities ● 3000 critical social welfare, criminal justice system and civil registration staff provided with gloves, hand sanitizers, masks.
3.1 | Results: Outcome Level | Please include outcome level results achieved | Pillar 1: Reduction in maternal deaths from 142 per 1,000 institutional live births in 2019 to 128 in 2020. Pillar 2: At national level, 53% out of the most vulnerable people (45% men; 55% women; 46% adults; 54% children) covered by social protection programmes (around 1.5 million person) Pillar 3: There were varying levels of increased knowledge among the genders in all five target communities. less than 10% of the population before the project had any knowledge on the negative effects of stigma on individuals and how they can help prevent and respond to it. 51.2% of males and 48.8% of females in Momobi; 36% of males and 64% of females in Nima; 48% of males and 52% of females in Agbogbloshie as well as 54.8% males and 45.2% females in Madina have demonstrated increased knowledge on stigma and discrimination. However only 1.47 females in Mamobi, 1.2% males and 1.2% females in Agbogbloshie utilised available hotline and psycho-social support services. The low level of utilisation of anti-stigma services was due to the late set up of hotlines and community spaces due to some implementation challenges. The services are now available, and the communities have been made aware of them, thus we are likely to see increased utilisation in the coming months.
3.2 | Results: Output Level | Please include output level results achieved | Under Pillar one: 1. 346,931 vulnerable groups have improved access to improved health facilities through the dissemination of key messages and demand creation activities on the need for service continuity. 2. 30 health facilities oriented on and supported to implement the guidelines and protocols to deliver essential health services in the context of COVID-19 2. 6 supportive supervisory visits carried out and health institutions have improved capacity to provide essential health services 3. 1537 Health workers have improved capacity to offer RMNCHN services including immunization. 4. 1261 Mothers/ caregivers have increased knowledge on optimal IYCF practices through quality IYCF counseling and access to immunization services. 5. 873 malnourished children have access to appropriate nutritional care. 6. 14,156 people ( 2,338 men, 6,388 women and 5,480 children) were reached through enhanced hygiene promotion focusing on handwashing in 10 communities. The initiative included risk communication in 101 public spaces 8. 150 frontline WASH staff received Personal Protective Equipment (PPE). 9. 1,845 patients and 860 staff were reached with the provision of improved WASH facilities (including handwashing) in 10 health centres 10. About 8,037 children reached with the provision of handwashing in 16 schools Under Pillar two 1. Technical options for targeting and reaching recipients were provided and partially adopted by the Government of Ghana and its Development Partners. 2. Communication strategy for social protection COVID response to reach cash transfer recipients was designed and rolled out during emergency payment with specific focus on gender dimensions 3. 3-layered M&E strategies implemented including LEAP monitoring, RapidPro SMS survey, and CSOs monitoring Under Pillar Three: Communities members and relevant institutions in target communities have enhanced knowledge and capacity to prevent, mitigate and respond to COVID-19 related stigma and discrimination through intense public education and targeted training. Specifically, outputs were: ● 1,338 women, girls and boys reached with essential services including SGBV and SRHR. ● 18 community initiatives implemented on COVID 19, SGBV and SRHR including FP ● 2,500 women and girls provided with dignity kits. ● 67 traditional and religious organizations and leaders engaged as change agents on COVID-19 and SGBV prevention and reporting. ● 5 women’s groups from identified Covid-19 hotspots (Nima, Mamobi, Agbogloshie/ Old Fadama and Madina) in the Greater Accra Region, have enhanced knowledge and capacity through training and have contributed towards advocacy efforts in their communities on the ill-effect of stigma and discrimination on victims and the COVID response. ● A total of 2,230 calls were received through the SGBV helpline out of the said number, 526 were SGBV related cases that were referred to DOVVSU for support. ● 3000 critical social welfare, criminal justice system and civil registration staff provided with gloves, hand sanitizers, masks. ● Established a hotline at the Commission for Human Rights and Administrative Justice as well as created 10 safe spaces across the five target communities. ● Victims of COVID-19 Stigma have access to support services with the Community members have increased knowledge on COVID-19 related stigma and discriminations through intense public education and sensitization and are now able to prevent, mitigate and access support services if they become victims. ● 200,000 people were reached with anti-stigma messages via Twitter and Facebook. 25,830 messages were received and shared as a result of the challenge “Letyourvoicecount” launched on social media.
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words) | ● A key challenge for the joint programme was that a significant amount of time was spent at the planning phase which caused some delays in implementation. The team reviewed the workplan to fast-track activities to ensure all outputs and outcome targets are met. ● Consultation with implementing partners took more time than expected and delayed the implementation of some of the activities. However, through constant engagement with the leadership at the regional level implementation was fast tracked. ● Also the bureaucracy of Implementing Partners (IPs) contributed to a late start of the project and in keeping to implementation and reporting timelines. Other competing national assignments of IPs including mass Yellow Fever and Polio immunization campaigns created further challenges. Continuous dialogue with senior IP managers and sustained advocacy on prioritization of the MPTF project helped immensely in dealing with these challenges. ● Engaging Government and development partners to convey a common strategy on emergency cash transfer was a quite long and complex process. Additionally, the usage of the new payment modality is still proving challenging with a lot of initial learning lessons on which to build on to provide an improved shock responsiveness of Ghana's Social Protection system in the long term. ● Changes to work schedules and environment due to COVID-19 impacted on delivery of services ● Delays on the establishment/refurbishment of hotlines and safe spaces respectively affecting the timely access to support services for victims of stigma. Previous partnerships with service providers was leverage to get results, though delayed ● Observing the COVID-19 protocol and mobilizing the vulnerable people including Kayayei for activities was a bit challenging because of the uniqueness of the target population. Some of the activities had to be done in the evenings and on Sundays to ensure adequate participation and prevent loss of daily wages. ● The floating nature of the Kayayei. This was addressed by putting in place group leaders who acted as a liaison between the Kayayei and the project team. The leader shared information with group members upon their return to Accra. Existing paralegal associations and partners (FIDA and PAYDP) were used to reach them. ● Language barrier as a high number of the Kayayei spoke little or no English. Interpreters were utilized.
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words) | 1. Engaging community leaders and local organizations in the essential service delivery implementation promotes strong local ownership and community support. 2. Capacity building and continued supportive supervision is required by health service providers at all levels of service delivery to ensure consistency and quality health care/interventions. 3. Data on public engagement disaggregated by gender suggests that in key public places - mainly markets, stores and lorry stations - more women were reached than men. This could be a useful entry point into households and communication could be tailored to leverage women's position and roles in households. 4. Protocols and procedures between the Ministry of Gender, Disaster Management Authority, Ministry of Finance and telecom/payment providers need to be put in place for rapid identification and enrolment of beneficiaries for future crises, and payment modalities tested for faster and more secure deployment. 5. The use of audiovisuals such as videos and pictures, storytelling, peer to peer and group sharing also enable quality engagement with the Head porters (Kayayei).
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words) | ● Strengthened partnership with Ghana Health Service ensured an uptake of the health services at facility level. ● Engagement and involvement of volunteers and opinion leaders at community level helped to boost the confidence of the community beneficiaries in the health system and maintain good health seeking behaviors. ● The WASH component was implemented in partnership with Environmental Health Officers (EHOs) and district focal points School hygiene Education Programme (SHEP) Ghana Health Services focal person in targeted Municipal Assembly areas. The WASH infrastructure support in health facilities were provided by CSO (Rural Water Development Programme). The EHOS in particular were able to use their existing relationships in their own working areas (wards) to disseminate critical IPC messages (e.g., frequent handwashing with soap) with groups such as market women (street vendors) and lorry drivers in local markets and lorry parks, means bigger number of people might have had indirect access to risk communication to move beyond direct participants. . ● the active collaboration with the Ministry of Gender and other development partner allow to fill critical technical gaps related to cash transfer system such as on design and on beneficiary communications and particularly on Monitoring and Evaluation (including the use of mass SMS-survey tools) It also allowed to support a dialogue around more sustainable financing of shock responsive social protection and strengthen information management systems for cash transfer delivery in emergencies. The partnerships with multiple CSOs allowed the JP to strengthen their social accountability. Private sector: • Leveraged additional resources from Prudential Life Insurance Ghana. These contributed to the provision of dignity kits, SRHR information, registering of over 500 kayayei under the National Health Insurance and the provision of food to vulnerable women and girls over a period of 6 months. ● State: For the effective coordination and response to SGBV, we partnered and supported DOVVSU and MOGCSP for coordinated response and provision of essential services for vulnerable women and girls. ● Civil Society engagement: Purim African Youth Development Platform and International Federation of Women Lawyers Ghana were engaged for SGBV information, service provision and advocacy. ● Partnered with community and informal structures: paralegals, Kayayei association, Market queens and Kings for community entry and mobilization and awareness creation. ● Partnership with the National Health Insurance Authority to register about 500 vulnerable women and girls (Kayayei) under the scheme. ● In partnership with the National Entrepreneurship and Innovation Programme, (Government initiative) led to 500 female Kayayei benefiting from vocational training. Partnership brokered with the Ghana Psychological Association, ensured that victims of COVID-19 related stigma had access to quality services and operators of community safe spaces have enhanced capacity to offer basic psychosocial services as a first line of support.
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken. | The JP conducted the following assessments: ● A pre and post implementation assessment. The pre-assessment focused on documenting the nature and incidence of stigma as well as the preferred mediums of communication for the community. This made the mediums used for public education more targeted for the achievement of the results. ● The post assessment focused on identifying the immediate impact of the project, especially the public sensitization. Results indicate enhanced knowledge of the public on how to prevent, mitigate and access support services. ● Assessment on Gender-Based Violence in the Context of Covid-19 in Ghana and Its Implications for Policy and Programming ● Domestic Violence and Victim Support Unit Covid-19 Impact Assessment. ● A study was conducted by the Joint progrmme on the Muti-Sectoral Strategy and Operational Guidance for Development and Implementation of the Ghana Sex Offender Registry.
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place | ● To ensure vulnerable groups have access to improved health facilities and optimal knowledge on IYCF practices, one of the planned activities was printing of IE&C materials including counseling cards to equip health staff to provide quality IYCF counseling. This activity could not be fully implemented due to the limited timeframe to update and print the IE&C materials. The materials have been updated and are ready for printing in Q 1 of 2021. ● The funding that was allocated to this activity was therefore used to procure anthropometric equipment to be used for detecting malnutrition – this will address one of the key challenges identified by GHS, Greater Accra team. The anthropometric equipment is required to enable the health staff to adequately monitor the nutritional status of children 0-59 months and be able to provide appropriate support to the caregiver timely especially in the context of COVID-19. Additional resources have been mobilized to print the IE&C materials.
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners. | • UNFPA recruited a consultant to coordinate the implementation of the MPTF Funds. Additional resources were mobilized by the programme; these included: Prudential Life Insurance Ghana, Joint UNFPA UNICEF Adolescent Girls Programme, UNFPA Country office and Headquarters also supported with the refurbishment of the National SGBV shelter and a National call centre for the provision of services for survivors of SGBV and those at risk. • The programme additionally mobilized resources from the World Bank Pandemic Emergency Fund which supported the development of Standard Operating Procedures and management structure for two shelters: the National SGBV Shelter of the Domestic Violence Secretariat of the Ministry of Gender, Children and Social Protection and Pearl Safe Haven Shelter.

## RBM-Final
| Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 1[1] : Continuity of essential health (including TB and HIV treatment) and nutrition services, access to safe water and hygiene infrastructure (such as provision of running water and handwashing facilities) for at-risk populations are ensured.
Indicator 1.2.: Percentage of household in target area with Handwashing facilities where water and soap are present | N/A | Because of continued risk of COVID-19 pandemic, no survey at households level was not possible.The 2020 Census was rescheduled to April 2021. Hence it was not possible to measure this indicator | Census/MICS /Sample Survey
Baseline: 49.7
Target: 52
Output Indicator 1.1.1a No communities reached with enhanced HWWS promotion for COVID-19 prevention | 10 communities (About 14,156 people: 2,338 men, 6,388 women and 5,480 children) reached in 2 MMDAs (Klottey Korle Municipal and Accra Metropolitan Areas) with enhanced hygiene messages, focussed on handwashing. 101 locations, including public toilets, markets and public areas were reached with COVID-19 communication. | Based on the risk identified, 10 poor-urban communities were targeted for risk communication including 20 public toilets in those communities. In addition, the Environmental Health Officers (EHOs) also disseminated IPC messages in 81 public places and premises based on identified needs. The public premises also included shops, abattoirs and other classes of premises that were not planned for. | Partners and UNICEF staff field monitoring reports, UNICEF Project report
Baseline: 0
Target: 30 public spaces and 10 public toilets in 2 MMAA
Indicator 1.1.2: Number of unserved public places in high risk areas with functional handwashing available | 10 health facilities reached with WASH support (rehabilitations water supply and handwashing facilities completed. 16 schools in Accra Metropolitan Area provided with handwashing facilities. These are estimated to reach at least 4,032 boys and 4,005 girls when schools are fully reopened | Initially constrained, however, the target has been reached as at 18 January 2020. In addition, hand washing facilities were provided in 16 schools identified as needing urgent support by the School Health Education Programme (SHEP) Accra. | Partners and UNICEF staff field monitoring reports, UNICEF Project report
Baseline: 0
Planned Target: 10 heatlh facilties
Output Indicator 1.1.3 No of institutions/ facilities provided with protective equipment for front-line staff to support WASH activities | 150 critical frontline WASH staff in 2 MMDAs were provided with PPE (300 hand sanitizers, 150 sets of light PPEs and 50 sets of re-usable heavy PPEs).. | PPEs were provided, as needed, to other MMDAs within the Greater Accra Metropolitan Area, who were similarly also experiencing cases and therefore needed to carry out sanitary burials and community engagements with the support of PPEs | Partners and UNICEF staff field monitoring reports, UNICEF Project report
Baseline:0
Target: 20 EOHS in 2 MMAA
Indicator 1.2.: Maternal deaths per 1,000 institutional live births | 128 | N/A | GHS/DHIMS ( 2020
Baseline: 142
Planned Target: 140
Output Indicator 1.2.1 ANC coverage (pregnant women making four ANC visits during the period of pregnancy) disaggregated by age | 83.5% | Key messages on the need for continuity of essential services were developed and dessiminated through multiple channels of communication including durbars, Television, Community Information Centres and radios. This gave reassurance to the general public especially mothers and caregivers that it is safe to continue to access and demand for quality health care services like ANC for pregnant women and Growth Monitoring and Promotion services for children under 5 even in the context of Covid-19. This explains the high ANC coverage. | GHS/DHIMS ( Dec.2020)
Baseline: 54.3%
Target: 60.0%
Output Indicator 1.2.2: Number of health facilities oriented on and supported to implement the guidelines and protocols to guide delivery of essential health services in the context of COVID-19 | 140 |  | GHS/DHIMS ( Dec.2020)
Baseline: 0
Target: 30
Output indicator 1.2.3: Penta3 coverage under 1 (Proportion of children fully immunized (using Penta3 as proxy) | 78.5% | under reporting due to system (DHIMS 2) breakdown. Most facilities could not make the entries | GHS/DHIMS ( Dec.2020)
Baseline: 56.7%
Planned Target: 80%
Output Indicator 1.2.4a: CWC attendance - Number of CWC female attendance (0-59 months ) | 32086 | Key messages on the need for continuity of essential services were developed and dessiminated through multiple channels of communication including durbars, Television, Community Information Centres and radios. This gave reassurance to the general public especially mothers and caregivers that it is safe to continue to access and demand for quality health care services like Growth Monitoring and Promotion services for children under 5 even in the context of Covid-19. This explains the high CWC attendance. | GHS/DHIMS ( Dec.2020)
Baseline: 4591
Planned Target: 12,000
Output Indicator 1.2.4b: CWC attendance - Number of CWC male attendance (0-59 months ) | 31034 | Key messages on the need for continuity of essential services were developed and dessiminated through multiple channels of communication including durbars, Television, Community Information Centres and radios. This gave reassurance to the general public especially mothers and caregivers that it is safe to continue to access and demand for quality health care services like Growth Monitoring and Promotion services for children under 5 even in the context of Covid-19. This explains the high CWC attendance. | GHS/DHIMS ( Dec. 2020)
Baseline: 4619
Planned Target: 10,000
Indicator 1.3.1a: Early initiation of breastfeeding rate | 82.4% | target achieved | GHS/DHIMS ( 2020)
Baseline: 75.4 %
Planned Target: 80.0%
Indicator : 1.3.1.b Number of children aged 6-59 months with SAM who are admitted for treatment | 873 | target achieved | GHS/DHIMS (2020) & GHS activity report
Baseline: 666
Planned Target: 800
Indicator 1.4: Number of supportive supervisory visits conducted | 6 | With the funds allocated for supportive supervision, thanks to the partershp with GHS-GAR it was possible to provide additional capacity building to health facilities not in target and therefore contributing to enhance the continuity of essential health services at subdistrict level | GHS-Activity report (Dec.2020)
Baseline: 0
Planned Target: 4
Outcome 2.Government has increased capacity in designing and implementing COVID related Social Protection measures including basic services, mainstreaming the needs of specific vulnerable groups, including girls and women. | 53% | target achieved | Report from the Ministry of Gender, Children and Social Protection
Outcome Indicator 2.1: Percentage of most vulnerable people disaggregated by sex, age and locality covered by social protection programmes
Baseline: 0%
Target: 50%
Output Indicator 2.1.1: Government has a range of gender-sensitive options for scaling up cash transfers using existing SP systems and programmes in Ghana to most vulnerable persons | Options for SP response provided and adopted by GoG and DPs. | Government and partners adopted priority categories for horizontal expansion of cash transfers including (a) homeless persons (b) persons with disabilities, (c) women peddling goods on the street (kayayei) (d) orphans and vulnerable children (e) victims of the floods in the north | Final report and annexes
Baseline: No technical options for targeting and reaching recipients provided
Target: Technical options for targeting and reaching recipients provided
Output Indicator 2.1.2: Communications campaign is set up to accompany emergency Social Protection interventions for the most vulnerable, emphasising the needs of girls and women | Communications strategy was defined and rolled out during emergency payment | Communications strategy included innovative sms-based push messaging as well as CSO enagement | Final report and annexes
Baseline: No current pandemic-response social protection communication strategy
Target: Communication strategy designed and developed for SP COVID response to reach recipients of grants done with specific focus on gender dimensions
Output Indicator 2.1.3: 2.1.3 Implementation of SP interventions are monitored and fed into sector coordination throughout intervention to check whether they address needs of the most vulnerable | 3-layered M&E strategy implemented including LEAP monitoring, RapidPro SMS survey and CSO monitoring | Carried out for ad hoc vertical and horizontal cash transfers, and moreover being incorporated into general social protection toolkit used by government | Final report and annexes
Baseline: M&E strategy for double LEAP payments currently in progress
Target: M&E strategy for double LEAP payments finalized and implemented to face COVID-responsive SP. Disaggregation of data by gender.
Outcome 3[1] | Increased anti-stigma knowledge Mamobi (51.2% males; 48.8% females) Nima (36% males; 64% of females) Agbogbloshie (48% males; 52% females) Madina (54.8% males; 45.2% females Utilisation of anti-stigma services 1.47 females in Mamobi, 1.2% males and 1.2% females in Agbogbloshie | The low level of utilisation of anti-stigma services was due to the late set up of hotlines and community spaces due to some implementation challenges. The services are now available, and the communities have been made aware of them, thus we are likely to see increased utilisation in the coming months. | Post Implementation Assessment Report by CHRAJ
Indicator: Enhanced access to SGBV and anti-stigma information and essential services for vulnerable groups for effective prevention, mitigation, and response to COVID-19 impacts.
Baseline:0
Planned Target: 50%
Output 3.1a Vulnerable women and girls have improved access to SGBV information, essential services and crisis support
Indicator 3.1.1 a&b. Percentage of affected population with increased knowledge and utilization of SGBV and anti-stigma services disaggregated by sex, age and locality | 1338 | N/A | Statistics from service providers
Baseline: 250
Planned Target: 750
Indicator 3.1.2:Number of community initiatives implemented on COVID 19, SGBV and SRHR including FP | 18 | The project duration was inadequate to meet the planned target. | Partner reports
Baseline: 0
Planned Target: 20
Indicator 3.1.3:Number of women and adolescent girls provided with dignity kits | 2500 | N/A | Reports and Distribution lists
Baseline: 1000
Planned Target:2000
Indicator 3.1.4:Number of traditional and religious leaders engaged as change agents on SGBV prevention and reporting | 30 | N/A | Implementation Reports
Baseline:0
planned Target:30
Output 3.2 Communities and relevant institutions have enhanced awareness and capacity to prevent, mitigate and respond to COVID-19 related stigma and discrimination
Indicator 3.2.1 Number of community engagements to reduce stigma and discrimination implemented in each of the 5 COVID hotspots targeted | 15 | Each of the five communities benefitted from three different community engagement activity | Anti-Stigma public Education Report by CHRAJ
Baseline: 0
Planned Target: 10
Indicator 3.2.2 Number of rapid assessments on stigma and discrimination conducted | 2 | N/A | Pre and Post Implementation Assessment Reports by CHRAJ
Baseline: 0
Planned Target: 2
Indicator 3.2.3. Functional mechanism to receive and address COVID-19 related stigma and discrimination in place | One hotline mechanism in place too receive and address in place PlaceCOVID-19 related stigma and discrimination in place | N/A | Project Progress Report from CHRAJ
Baseline: None in Place
Planned Target: At Least one in place
Indicator 3.2.4, At least 3 of the 5 COVID hotspots targeted has a safe space for victims of stigma and discrimination | 5 | All 5 targeted COVID hotspots have safe spaces | Project Progress Report from CHRAJ
Baseline: 0 Community safe spaces
Planned Target: 3 Community safe spaces
Please inlcude all three: Baseline, Planned Target and Achieved Targets
Note on D21: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This indicator is for WHO

## Communication-Final
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
Safeguarding the health of children through good nutrition
Five-year-old Georgina Osei with her mother, following adequate treatment of malnutrition. January 2021 (c) UNICEF/Adatsi/2021
Children who suffer malnutrition need a range of nutrients from a variety of foods and, in its worst form, will require therapeutic foods and milks in order to recover. Unfortunately, many health facilities across Ghana are not well-resourced to meet the needs of these children. This absence of the correct nutrients foods and milk can sometimes lead to a tragic preventable death of a little child. In Ghana, malnutrition accounts for approximately 24 percent of deaths of children under the age of five.
Such may have been the case for five -year old, Georgina Osei from Nungua in the Greater Accra region who suffered from severe acute malnutrition (otherwise known as wasting) in September 2020. Georgina was admitted in Princess Marie Louise children’s hospital in Accra Central with a weight of 7.3 kg.
However, Georgina was not recovering as fast as expected. After almost seven weeks of receiving treatment, she had gained just 1.3 kg.
The hospital, at the time of Georgina’s admission, had a few cartons of the therapeutic foods for the management of severe acute malnutrition, which was received through donations, barely enough to meet the needs of the many children in the hospital for treatment and care. Princess Marie Louise Hospital therefore resorted to rationing the few cartons of these foods, so that all eligible children could benefit. This impeded recovery since the patients were not getting the right rations to meet their needs.
To support the hospital to continue to provide essential health and nutrition services in the wake of COVID-19 pandemic, the United Nations Multi-Partner Trust Fund (MPTF), through UNICEF donated 35 cartons of therapeutic food and milk to the facility in November 2020.
In addition to the essential nutrition supplies, the staff at the facility were given training on continuity of essential health and nutrition services including infant and young child feeding, management of Severe Acute Malnutrition and immunization in the context of COVID-19. This brought the staff so much joy since they wanted to see the SAM cases in their facility recover faster.
Anna Ofori, a Nutrition Officer with Princess Marie Louise Children’s Hospital, is one of the beneficiaries of the training.
Anna Ofori, Nutrition officer at Princess Marie Louise Children’s Hospital offering IYCF counseling. January 2021 (c) UNICEF/Adatsi/2021
She said, “This is one of the best trainings ever. I can now adequately support caregivers to optimally feed their infants and young children and adequately manage severe acute malnutrition in the context of COVID-19. I know the right messages to give and how to attend to my clients and offer services amidst COVID-19. I learnt about COVID-19 protocols and adhere to them while at work and outside work. I’m more confident now and not scared of contracting COVID-19 because I now know what to do. I also encourage caregivers who visit the facility to comply with the COVID-19 safety protocols so that they do not contract the virus.’’
Following the donation to the hospital, Georgina was given the adequate ration per her weight. She received 21 sachets of RUTF every week until she was discharged on 4th December 2020 with a weight of 10.0 Kg.
Georgina’s mother who is a trader was very happy that her daughter was restored to good health.
She said “I thought my daughter was going to be in the hospital forever. Before, my child was not gaining weight as required and my business was also going down. I can now smile again. My daughter is well again. I can now concentrate on my business to grow. Thank you to those who supported the hospital with this magic food. God bless you.’’
2. Upload here: Communications and Visibility (OPTIONAL)
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well picture material please make sure you include all credits and upload them in high resolution Call1 countries.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board
\
VIDEOS DEVELOPED
1. The joint programme undertook a COVID-19 antistigma social media campaign in the month of June, July and August. The anti – stigma post and messages had the top reach and impact amongst other posts on the UNDP social media platform. A presentation on the social media analysis is saved here: https://docs.google.com/presentation/d/1_Ydz367v6eXIVoZuq_C6osMlvoP78dhN22kkzsBNgaQ/edit?usp=sharing
2. Additionally, an Anti-stigma Video was developed in various Ghanaian languages - https://twitter.com/UNDPGhana/status/1309103909999456258?s=20
UNICEF Ghana Country Representative, Anne -Claire Dufay and Nutrition Specialist, Ruth Situma handed over nutrition supplies including RUTF, F-75, F-100 & MUAC tapes to Greater Accra Team for early detection and management of severe acute malnutrition ©UNICEF/2020