## Activity budget Jan-sept, 2020
Annex D - PBF project expenditures (Indicative)
Project: Sierra Leone ( PBF/IRF – 339- 00119354)-Promoting Women’s Safety and Security for Sustainable Peace in Southern Sierra Leone economic empowerment in Sierra Leone
Note: If this is a budget revision, insert extra columns to show budget changes.
Table 1 - PBF project budget by Outcome, output and activity
Outcome/ Output number | Outcome/ output/ activity formulation: | Budget by recipient organization (CARITAS BO) in USD | Expenditure/ Committed to date (CARITAS BO) | Percent of budget for each output reserved for direct action on gender eqaulity (if any): 67% GEWE | Level of expenditure/ commitments in USD (to provide at time of project progress reporting): | Any remarks (e.g. on types of inputs provided or budget justification, for example if high TA or travel costs)
OUTCOME 1: Women CBOs have enhanced capacities for advocacy to reduce SGBV in communities.
Output 1.1 | Three women’s groups have capacities for identifying strategies to prevent and reduce SGBV and conflict Management. | 65000 | 33000 | 100 | 22921
Activity 1.1.1: | Training of 3 women CBOs in SGBV prevention and reduction strategies, conflict prevention and conflict management. | 5000 | 5000 | 100 | 5000 | This activity was done through a consultancy
Activity 1.1.2: | Grants to 3 CBOs for capacity building for project implementation | 60000 | 28000 | 46.6667 | 17921
Output 1.2 | Women CBOs are trained in participatory advocacy approaches for conflict prevention | 6000 | 5500 | 91.6667 | 5500
Activity 1.2.1: | Training of women’s groups in participatory advocacy | 6000 | 5500 | 91.6667 | 5500 | This activity was done through a consultancy
Output 1.3 | Women CBOs are supported for court monitoring, reporting and providing psychosocial support to SGBV survivors | 9000 | 4300 | 96.6667 | 4300
Activity 1.3.1: | Weekly monitoring of the courts to support SGBV survivors with social-legal counseling and data collection of cases reported. | 6000 | 2800 | 46.6667 | 2800
Activity 1.3.2: | Women CBOs set up E-Alerts to report conflict incidence and SGBV in communities | 3000 | 1500 | 50 | 1500
TOTAL $ FOR OUTCOME 1: |  | 80000
OUTCOME 2: Women and girls in communities with High SGBV rates are able to access basic services and empowered to make decisions that are taken into account by the public.
Output 2.1 | Basic health and legal services are available for SGBV survivors . | 24000 | 8950 | 100 | 8950
Activity 2.1.1: | Provision of medical treatment for SGBV survivors and medical report for use in court | 10000 | 3000 | 30 | 3000
Activity 2.1.2: | Provision of paralegal Services for SGBV survivors | 10000 | 3950 | 39.5 | 3950
Activity 2.1.3: | Provision of Psychosocial support to SGBV survivors | 4000 | 2000 | 50 | 2000
Output 2.2 | Women are organized into Women Action Groups at Chiefdom levels to advocate for the elimination of Violence against women and girls . | 12000 | 6012 | 100 | 6012
Activity 2.2.1: | 20 women Action Group established | 1000 | 1000 | 100 | 1000
Activity 2.2.2: | Monthly meetings with existing women’s village associations to sensitize on GEWE and SGBV. | 1000 | 650 | 65 | 650
Activity 2.2.3: | Provision of materials to WAGs for safe spaces for SGBV survivors | 10000 | 4362 | 43.62 | 4362
Output 2.3 | Women farmers have strengthened their financial capabilities and have access to gender sensitive financial products. | 34000 | 18100 | 100 | 18100
Activity 2.3.1: | Assertiveness and leadership Training for women and girls who are members of community decision making structures. | 10000 | 8000 | 80 | 8000
Activity 2.3.2: | Development of 20 Community plans for conflict and SGBV prevention | 4000 | 2100 | 52.5 | 2100
Activity 2.3.3: | Support for priority policy actions in community plan | 20000 | 8000 | 40 | 8000
Output 3.1 | Men and boys in target communities can show evidence of behavior change in the families and communities | 17000 | 2000 | 0 | 2000
Activity 3.1.1: | Establishment of 20 male support groups for violence prevention and SGBV. | 2000 | 2000 | 0 | 2000
Activity 3.1.2: | Training of men and boys in male support groups on GEWE, SGBV and conflict prevention. | 15000 |  | 0 | 0
Output 3.2 | Men and boys are engaged as GEWE and conflict prevention advocates. | 32000 | 10000 | 26.6667 | 10000
Activity 3.2.1: | Development of 20 advocacy plans for male engagement in conflict prevention, SGBV prevention and promoting GEWE. | 2000 | 2000 | 0 | 2000
Activity 3.2.2: | Support campaigns by men and boys on GEWE on special international and national days. | 30000 | 8000 | 26.6667 | 8000
Output 3.3 | Men and boys are engaged as GEWE and conflict prevention advocates. | 31000 | 5200 | 96.7857 | 4300
Activity 3.3.1: | Hold community meetings to set criteria with communities for male champions for GEWE | 4000 | 2100 | 52.5 | 1200
Activity 3.3.2: | Award 20 outstanding male Gender Champions with livelihood support projects (micro grants) | 20000 |  | 0
Activity 3.3.3: | Household monitoring of male champions and production of case studies on male engagemetn on GEWE | 7000 | 3100 | 44.2857 | 3100
TOTAL $ FOR OUTCOME 3: |  | 150000 |  |  | 19411
Project personnel costs if not included in activities above |  | 13140 | 6570 | 50 | 3250
Project operational costs if not included in activities above |  | 9234 | 4617 | 50 | 4723
End of Project evaluation |  | 10000 | 0 | 0 | 0
Project M&E budget (5-7%) |  | 18000 | 9000 | 50 | 5778
SUB-TOTAL PROJECT BUDGET: |  | 280374
Indirect support costs (7%): |  | 19626.18 | 9813.09 | 50 | 5660 | 33.8313
TOTAL PROJECT BUDGET: |  | 300000.18 | 123062.09 |  | 101494 | 82.4738