SECRETARY-GENERAL’S PEACEBUILDING FUND

PBF PROJECT PROGRESS REPORT TEMPLATE

PBF PROJECT progress report

COUNTRY: Guinea-Bissau

TYPE OF REPORT: semi-annual, annual OR FINAL Final

date of report: 14 June 2020

| Project Title: Support, Coordination and Monitoring in Guinea-Bissau 2018 - 2019 Project Number from MPTF-O Gateway: 00108262 |
| --- |
| PBF project modality: IRF PRF | If funding is disbursed into a national or regional trust fund: Country Trust Fund Regional Trust Fund Name of Recipient Fund: |
| List all direct project recipient organizations (starting with Convening Agency), followed type of organization (UN, CSO etc): UNDP List additional implementing partners, Governmental and non-Governmental: |
| Project commencement date: 19/12/2017 Project duration in months: 6 month No-Cost Extension until 30 December 2019 |
| Does the project fall under one of the specific PBF priority windows below: Gender promotion initiative Youth promotion initiative Transition from UN or regional peacekeeping or special political missions Cross-border or regional project |
| Total PBF approved project budget* (by recipient organization): : $ 944,356 : $ : $ : $ Total: $ 944,356. *The overall approved budget and the release of the second and any subsequent tranche are conditional and subject to PBSO’s approval and subject to availability of funds in the PBF account How many tranches have been received so far: 01 |
| Report preparation: Project report prepared by: Janet L. Murdock Project report approved by: Dr. Mamadou Diallo, DSRSG/RC Did PBF Secretariat clear the report: N/A Any comments from PBF Secretariat on the report: N/A Has the project undertaken any evaluation exercises? Please specify and attach: No |

NOTES FOR COMPLETING THE REPORT:

- Avoid acronyms and UN jargon, use general / common language.

- Be as concrete as possible. Avoid theoretical, vague or conceptual discourse.

- Ensure the analysis and project progress assessment is gender and age sensitive.

PART 1: RESULTS PROGRESS

  - Overall project progress to date

Briefly explain the status of the project in terms of its implementation cycle, including whether all preliminary/preparatory activities have been completed (1500 character limit):

The PBF Secretariat project was slated to end in June. It receive a No-Cost-Extension to 30 December 2019 to enable the preparation of a new project document.  The project is, thus, finished. Surveys conducted with project managers and implementors consistently rated the technical support and capacity building efforts of the PBF Secretariat as Excellent or Very Good with an ocasional Good or Fair rating. No one ever rated any PBF services as poor.

Considering the project’s implementation cycle, please rate this project’s overall progress towards results to date:

In a few sentences, summarize what is unique/ innovative/ interesting about what this project is trying/ has tried to achieve or its approach (rather than listing activity progress) (1500 character limit).

The Secretariat has worked hard to build name recognition for the PBF in GB. When the coordinator arrived in August 2016, very few people knew about the PBF or that GB is a PBC country. The Secretariat has greatly enhanced the visibility of the PBF in GB by speaking a project events, enahancing communication effort of the project and by procuring a unique song and a video of the song by a famous GB singer/songwriter. The song has become a national peace anthem and plays continuously on the radio an on TV. Through stricter enforcement of rules regarding visibility of PBF funded events, the PBF is  becoming more widely recognized in Bissau and the regions. The 27 small grants also enhanced the visibility of the PBF throughout the country and especially in the most heavily targeted regions of Gabu and Cacheu. The PBF Secretariat also sponsored numerous initiatives for International Peace Day that strengthened name recognition of the PBF. The only reason that the PBF doesn’t have greater visibility is because the political mission is also called a peacebuilding mission and thus many civil society actors confuse the PBF with the mission not recognizing that the PBF is funding many projects that the mission is responsible for implementation. The PBF now has a solid reputation of supporting the people of GB in their peace efforts.

In a few sentences summarize major project peacebuilding progress/results (with evidence), which PBSO can use in public communications to highlight the project (1500 character limit):

As discussed above better name recognition and improved reputation of the PBF is one of the main acheivements of this project. Collectively, the projects in the PBF portfolio enabling very concrete and recognizable actions in favor of peace that have contributed to the PBF having a solid positive image in the country. That reputation helped peacebuilders we supported leverage a healthy relationship with national authorities which has enable greater national appropriation of the PBF project by national authorities. Another major accomplishement of this project was that it was able to ensure the closure of 15 old projects, some that dated back to 2008. As this writing all old projects are closed.

In a few sentences, explain how the project has made real human impact, that is, how did it affect the lives of any people in the country – where possible, use direct quotes that PBSO can use in public communications to highlight the project (1500 character limit):

Five projects that the PBF Secretariat oversaw in the period of the project fit the category of bottom-up projects that in one way or another allowed common people  - youth ande womens groups - to get engaged in peacebuilding issues of concern to them and that affect their lives.  The PBF processes reprioritized youth, in particular, as change agents, a sector that had been neglected by UN and other donor programming.  The 2 initiatives of small grants projects with a collective 27 projects are the kind of projects that enable real human impact especially for the most vulnerable groups in society like the disabled and albino communities. Misconceptions about albinism has diminished due to public sensitization with scientific information. The organization of Albinos gained recognition by the Community of Portuguese Lanaguage countries and us such will have access to an international advocacy platform. The PBF Secretariat contributed to the Booklet on Small Grants that shows the human impacts of the 27 small grants projects.

If the project progress assessment is on-track, please explain what the key challenges (if any) have been and which measures were taken to address them (1500 character limit).

If the assessment is off-track, please list main reasons/ challenges and explain what impact this has had/will have on project duration or strategy and what measures have been taken/ will be taken to address the challenges/ rectify project progress (1500 character limit):

The project has caught up with essencial task since April with the return of the Coordinator who was absent for health reasons for 6 months in 2018 and 2019. However, with the departure of M&E Officer in March 2019, the Coordinator has not been able to monitor implememntation of project in a systematic manner, nor did the Secretariat organize the envisioned capacity-building events due to the lack of programmatic support as the project lost it NOB in June 2018 and slot was not filled until May 2020, after the end of the project.

Please attach as a separate document(s) any materials highlighting or providing more evidence for project progress (for example: publications, photos, videos, monitoring reports, evaluation reports etc.). List below what has been attached to the report, including purpose and audience.

The Patche de Rima song and video are available on iTunes,Youtube and other music platforms.

  - Result progress by project outcome

The space in the template allows for up to four project outcomes. If your project has more approved outcomes, contact PBSO for template modification.

Outcome 1:   The effective development, implementation, monitoring, oversight of peacebuilding projects and the overall strategic direction of the PBF portfolio in Guinea-Bissau is ensured.

Rate the current status of the outcome progress:

Progress summary: Describe main progress under this Outcome made during the reporting period (for June reports: January-June; for November reports: January-November; for final reports: full project duration), including major output progress (not all individual activities). If the project is starting to make/ has made a difference at the outcome level, provide specific evidence for the progress (quantitative and qualitative) and explain how it impacts the broader political and peacebuilding context. Where possible, provide specific examples of change the project has supported/ contributed to as well as, where available and relevant, quotes from partners or beneficiaries about the project and their experience. (3000 character limit)?

PBF Secretariat operations ran with reduced staff with the departure of the National Officer in June 2018 and the M&E Officer in March 2019. The 1st hiring processes did not yield any viable candidates and we had to conduct a second hiring process that lasted until May 2020. The lack of an M&E is prejudicial to the full performance of  M&E responsibilities, nevertheless agencies did updtate their M&E Plan upon request. The lack of a NOB overloaded the Coordinator with administrative task which detracts from her capacity to provide consistent technical support.

The equipment of this office dated to the establishment of the office in 2009. The computers beyond warrently are being replaced. The 12 year old PBF vehicle was also replaced. Nevertheless, the Secretariat is providing effective oversight, communication and coordination of Projects. Given the level of project activity, partners did not have time for monthly meetings in the last year of implementation but this was compensated  with more frequent one on one meetings with project Coordinators, visit to project sites and participation in project activities. The two projects with small grants initiatives worked well together to call, select and announce the winners of a competitive process. The PBF Secretariate played a critical role in supporting these projects with that process and accompanying the implementation of the 27 projects. The PBF secretariat attends all UNCT meetings and keeps Senior Management briefed on PBF/PBC matters. In this period the Secretariate has been very active in enabling the development of 2 new substantive projects in addition to the Secretariat project document.  The secretariate contributed to briefing of the new senior managers and to two Security Council reports and enabled the initial preparation of 3 yearly visits of the PBC chair. The Secretariat reviewed all drafts of half-year, Annual and Final Reports by agencies and provides constructive feedback. The office reviewed 7 Final Project Reports and 3 Evaluations and provided constructive feedback and provided political analysis as well as talking points and speecheis for PBF financed events. We held at least monthly phone meetings with PBSO to provide updates on Project Implementation ans we kept national focal points updated and abreast of PBF Business. The Secretariat provided a comprehensive mid year report in Portuguese to national focal points to ensure greater national appropriation of the project portfolio. We inssure that project teams invite national focal points on monitoring visits and key project event.

Outcome 2:  The agencies implementing PBF funded projects are in a position to deliver on the implementation, monitoring and evaluation of effectively designed peacebuilding projects, while communicating effectively the results of their interventions.

Rate the current status of the outcome progress:

Progress summary: (see guiding questions under Outcome 1)

The PBF Secretariat provide project teams with hands-on technical support on a daily basis. The Secretariat provided over 10 trainings to projects beneficiaries, including mediaton/dialogue training, Conflict Resolution training, Conflic Analysis training, restorative justice, conflict sensitive reporting, induction training and participatory evaluation.  We supported the small grants initiative with advice and tools for managing the selection process and reviewed each of the 13 UNDP grant proposals. With regard to Output 2.2: Strengthen social communication and peacebuilding advocacy, the PBF Secretariat was very creative and proactive in ensuring that PBF was recognized at events, on publications, etc.  In addition to the original song by a famous guinean artist that immediately boosted the PBFs recognition, the team worked to ensure International Peace Day celebrations the last three years. While hampered by not being included on the Transition Working Group, the coordinator  managed to help identify the topics of two new projects, shepparded one through the approval process and penning on of the prodocs.

Outcome 3:

Rate the current status of the outcome progress:

Progress summary: (see guiding questions under Outcome 1)

Outcome 4:

Rate the current status of the outcome progress:

Progress summary: (see guiding questions under Outcome 1)

  - Cross-cutting issues

| National ownership: How has the national government demonstrated ownership/ commitment to the project results and activities? Give specific examples. (1500 character limit) | The national appropriation grow significantly during the duration of the project. After submitting a comprehensive report in June, National Focal Points showed increased interest and promised to organize a meeting with the Council of Ministers but it did not happen because of COVID-19. The Coordinator ensured project invited the PBF Focal Points to key events of the Small Grants as well as representatives of relevant ministries which help increase support for project activities. The Head of the National Forest showed particular interest in one small grant in the Boe forest and traveled 3 hours at night on a motorcycle to be at the tree planting the next day, quite a commitment from a 78 year old man. The top traditional leaders of both Gabu and Cacheu accompanied the small grants underway the in those regions with great enthusiasm |
| --- | --- |
| Monitoring: Is the project M&E plan on track? What monitoring methods and sources of evidence are being/ have been used? Please attach any monitoring-related reports for the reporting period. (1500 character limit)? | The monitoring of this project was weakended by the resignation of the M&E Officer. Usually we do a survey of project managers for the semi-annual and year end evalutions to capture satisfaction levels with the services of the PBF Secretariat but without the M&E Officer to conduct the survey and tabulate results. We missed conducting the surved for only one evaluation period. |
| Evaluation: Provide an update on the preparations for the external evaluation for the project, especially if within last 6 months of implementation or final report. Confirm available budget for evaluation. (1500 character limit) | No project evaluation is expected on the Secretariat project because it isnt a substantive project |
| Catalytic effects (financial): Did the project lead to any specific non-PBF funding commitments? If yes, from whom and how much? If not, have any specific attempts been made to attract additional financial contributions to the project and beyond? (1500 character limit) | The PBF Secretariat was active in donor configuration to ensure that other donors understand PBF projects. It was these connections that enable UNWomen to link to the EU election monitoring projects and combinte efforts after the pull out of the Gore Institute. This led the the very successful womens situation room. |
| Catalytic effects (non-financial): Did the project create favourable conditions for additional peacebuilding activities by Government/ other donors? If yes, please specify. (1500 character limit) | The donors configuration also helped identify common interests an explore catalytic effects of the projects. For example many of the CSOs that . |
| Exit strategy/ sustainability: What steps have been taken to prepare for end of project and help ensure sustainability of the project results beyond PBF support for this project? (1500 character limit) | As long as the PBF remains in GB, there will always be the need for an independent oversight structure and given the lack of technical capacity in peacebuilding methodologies and theoretical frameworks, there will always be a need for technical support. |
| Risk taking: Describe how the project has responded to risks that threatened the achievement of results. Identify any new risks that have emerged since the last report. (1500 character limit) | The PBF helped the projects address the bottlenecks and threats to implementation and strategies creative ways to accelerate delivery. The PBF helped the project reprogram left over funds of 2 projects for COVID-19 responses. The high staff turn around of international staff supporting the project is a big risk. Three IUNV left in the middle of project implementation for various reasons. There premature departure jeopardized project delivery because the Agencies do not have adequate staff. |
| Gender equality: In the reporting period, which activities have taken place with a specific focus on addressing issues of gender equality or women’s empowerment? (1500 character limit) | The PBF Secretariat regularly supports project development with a gender lense to insure PBF expectations for gender prioritization is adressed. 2 substantive projects under development in 2019 have Gender ratios of 29% and 15% respectfully, |
| Other: Are there any other issues concerning project implementation that you want to share, including any capacity needs of the recipient organizations? (1500 character limit) |  |

1.3 INDICATOR BASED PERFORMANCE ASSESSMENT: Using the Project Results Framework as per the approved project document or any amendments- provide an update on the achievement of key indicators at both the outcome and output level in the table below (if your project has more indicators than provided in the table, select the most relevant ones with most relevant progress to highlight). Where it has not been possible to collect data on indicators, state this and provide any explanation. Provide gender and age disaggregated data. (300 characters max per entry)

|  | Performance Indicators | Indicator Baseline | End of project Indicator Target | Current indicator progress | Reasons for Variance/ Delay (if any) | Adjustment of target (if any) |
| --- | --- | --- | --- | --- | --- | --- |
| Outcome 1 The effective development, implementation, monitoring, oversight of peacebuilding projects and the overall strategic direction of the PBF portfolio in Guinea-Bissau is ensured | Indicator 1.1 Evaluation of PBF Secretariat through UN leadership, AFPs (and potentially national stakeholders | TBD |  |  | Semester surveys conducted generally except december gave PBF Secretaria above average ratings |  |
|  | Indicator 1.2 |  |  |  |  |  |
|  | Indicator 1.3 |  |  |  |  |  |
| Output 1.1 Output 1.1 PBF Secretariat operations are running | Indicator 1.1.1 PBF Secretariat staff attend approved trainings Baseline: 0 Target: ? | 0 | TBD | 01 | M&E Speciaist participated in an on-line training of evaluation of peacebuilding proejcts. Unfortunately she left soon after |  |
|  | Indicator 1.1.2 Offices and equipment are continued available and operational Baseline: NA Target: NA |  |  |  | 4 computers and vehicle were purchased to replace outdated equipment |  |
| Output 1.2 Effective oversight, communication and coordination enabled to ensure Oversight, Coherence and Complementarity between Projects | Indicator 1.2.1 Quality report submitted by the deadline Baseline: 0 Target: 3 | 0 | 03 | 04 | We have never met the deadline for submission of all project reports due to late submissions by project teams and in December 2029, Coordinator was busy preparing 3 prodocs and had not NOB or M&E to support the work of the Secretariat. |  |
|  | Indicator 1.2.2 Leadership provided quality support and documentation to make decisions Baseline: NA Target: 1 update per semester | 1 per semester |  | 03 | PBF contributed to 3 induction briefings of 2 SRSGs and one DSRSG, 2 Security Council Reports and 3 PBC meetings |  |
| Output 1.3 | Indicator 1.3.1 |  |  |  |  |  |
|  | Indicator 1.3.2 |  |  |  |  |  |
| Output 1.4 | Indicator 1.4.1 |  |  |  |  |  |
|  | Indicator 1.4.2 |  |  |  |  |  |
| Outcome 2 The agencies implementing PBF funded projects are in a position to deliver on the implementation, monitoring and evaluation of effectively designed peacebuilding projects, while communicating effectively the results of their interventions. | Indicator 2.1 PB programs progress toward implemented by RUNOs is on track - % of projects implemented | 4% | 70% | 0 | 6 projects received NCE to early 2020. Two projects were completed in late 2018/2019. The delays were due primarily by the lack of people to implment activities and procurement delays - in some case 13 months to hire a consultant |  |
|  | Indicator 2.2 |  |  |  |  |  |
|  | Indicator 2.3 |  |  |  |  |  |
| Output 2.1 Output 2.1 Capacity-building of RUNOs and implementing partners enabled through tailored technical support and training | Indicator 2.1.1 Output Indicator 2.1.1 % of project proposals that are reviewed for inclusion of gender and youth aspects in peacebuilding and that include disaggregated data by sex and age in their results framework | 0 | 75 | 100 | 2 substantive projects reviewed this semester with 29 and 15% gender ratios, plus secretariate project. All GYPI 2018, 2019, 2020 were reviewed and given feedback on peacebuilding strategies and gender. 2 project for GB were successful. |  |
|  | Indicator 2.1.2 Number and type of training events convened, and number of participants | 4 | 6 | 10 | We didn’t provide training as planned with international consultants but I did provide 10 workshops in 2019 for beneficiaries of specific projects. |  |
| Output 2.2 Output 2.2 Strengthen social communication and peacebuilding advocacy: Increase awareness by national authorities, civil society and wider public of Peacebuilding Priorities and results | Indicator 2.2.1 Communication Strategy developed | 0 | 1 | 1 | Done |  |
|  | Indicator 2.2.2 Number of discussion series held | 1 | 4 |  | This is not doable as planned as it would conflict with work of the mission. Strategy changed to procure peace song and video |  |
| Output 2.3 | Indicator 2.3.1 |  |  |  |  |  |
|  | Indicator 2.3.2 |  |  |  |  |  |
| Output 2.4 | Indicator 2.4.1 |  |  |  |  |  |
|  | Indicator 2.4.2 |  |  |  |  |  |
| Outcome 3 | Indicator 3.1 |  |  |  |  |  |
|  | Indicator 3.2 |  |  |  |  |  |
|  | Indicator 3.3 |  |  |  |  |  |
| Output 3.1 | Indicator 3.1.1 |  |  |  |  |  |
|  | Indicator 3.1.2 |  |  |  |  |  |
| Output 3.2 | Indicator 3.2.1 |  |  |  |  |  |
|  | Indicator 3.2.2 |  |  |  |  |  |
| Output 3.3 | Indicator 3.3.1 |  |  |  |  |  |
|  | Indicator 3.3.2 |  |  |  |  |  |
| Output 3.4 | Indicator 3.4.1 |  |  |  |  |  |
|  | Indicator 3.4.2 |  |  |  |  |  |
| Outcome 4 | Indicator 4.1 |  |  |  |  |  |
|  | Indicator 4.2 |  |  |  |  |  |
|  | Indicator 4.3 |  |  |  |  |  |
| Output 4.1 | Indicator 4.1.1 |  |  |  |  |  |
|  | Indicator 4.1.2 |  |  |  |  |  |
| Output 4.2 | Indicator 4.2.1 |  |  |  |  |  |
|  | Indicator 4.2.2 |  |  |  |  |  |
| Output 4.3 | Indicator 4.3.1 |  |  |  |  |  |
|  | Indicator 4.3.2 |  |  |  |  |  |
| Output 4.4 | Indicator 4.4.1 |  |  |  |  |  |
|  | Indicator 4.4.2 |  |  |  |  |  |

PART 2: INDICATIVE PROJECT FINANCIAL PROGRESS

  - Comments on the overall state of financial expenditures

Please rate whether project financial expenditures are on track, delayed, or off track, vis-à-vis project plans and by recipient organization:

How many project budget tranches have been received to date and when do you expect to request the next tranche if applicable: There is only one tranche on this project

What is the overall level of expenditure/ commitment against the total budget and against the tranche(s) received so far: The total budget for this project = 944,356.32. Total Expenses through December 2019 (the end of the project)  = 881,550.02. The balance returned to be 58,222.28 .

If expenditure is delayed or off track, please provide a brief explanation (500 characters limit): We were not able to convene the trainings programs envisioned. We used left over funds to purchase computers and a new vehicle as the PBF Secretariat vehicle was over 10 years old and causing substantial funds to maintain.

Please state what $ amount was planned (in the project document) to be allocated to activities focussed on gender equality or women’s empowerment and how much has been actually allocated to date: N/A

Please fill out and attach the project document Excel budget Annex showing current project financial progress (expenditures/ commitments to date), using the original project budget table in Excel, even though the $ amounts are indicative only.

# Footnotes

Note: commencement date will be the date of first funds transfer.

Maximum project duration for IRF projects is 18 months, for PRF projects – 36 months.