## PBF
Harnessing Youth’s potential for peace in Uganda Workplan 2020-2021 ( UNDP, UNFPA, OHCHR)
Joint OUTCOME 1: State and civil society actor decision-making processes are more inclusive and enable proactive participation of youth
Joint Output 1.1: |  | Capacity of selected government ministries and departments is enhanced to effectively mainstream youth issues in decision-making mechanisms
Activities |  |  | UN Agency | Implementation timeline | [5 empty] | Implementing Partner | 1st Tranche | 2st Tranche | Total | Utilised | Balance | Percent of Utilised budget for each output reserved for direct action on gender eqaulity (if any):
|  |  |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | [6 empty] | Percent of budget for each output reserved for direct action on gender eqaulity (if any):
1.1.1.1 Support intergeneration (generation for generation) dialogues between youth and local government on peace building and social issues in the regions, including their gendered dimension. |  |  | UNDP | [6 empty] | IRCU,IPOD, NCF,TEFU | 20000 | 15000 | 35000 | 30000 | 5000 | 50% | bar: Q1 to Q2
|  |  | UNFPA | [6 empty] | ACORD | 30000 | 22500 | 52500 | 52500 | 0 | 50% | bar: Q1 to Q2
|  |  | OHCHR | [7 empty] | 0 | 0 | 0 |  | 0 | 50%
1.1.1.2 Support policy advocacy to incorporate youth issues, including gendered dimension, in district development plans |  |  | UNDP | [6 empty] | IPOD,NCF | 12000 | 9000 | 21000 | 17000 | 4000 | 50% | bar: Q1 to Q2
|  |  | UNFPA | [8 empty] | 0 | 0 |  | 0 | 50%
|  |  | OHCHR | [7 empty] | 0 | 0 | 0 |  | 0 | 50%
1.1.1.3 Support the revitalization of local and district peace committees in Buganda and Rwenzori with youth representation |  |  | UNDP | [6 empty] | OPM/DLG,IRCU | 20000 | 15000 | 35000 | 30000 | 5000 | 50% | bar: Q2 to Q2
|  |  | UNFPA | [7 empty] | 0 | 0 | 0 |  | 0 | 50%
|  |  | OHCHR | [7 empty] | 0 | 0 | 0 |  | 0 | 50%
1.1.1.4 Facilitate a rapid assessment to generate evidence on improving the inclusion of young men and women in peacebuilding to support interventions |  |  | UNDP | [6 empty] | UNDP/IRCU | 10000 | 7500 | 17500 | 10000 | 7500 | 50% | bar: Q1 to Q2
|  |  | UNFPA | [6 empty] | UNFPA | 20000 | 15000 | 35000 | 35000 | 0 | 50% | bar: Q1 to Q2
|  |  | OHCHR | [7 empty] | 0 | 0 | 0 |  | 0 | 50%
1.1.1.5 Support consultations of the national peacebuilding forums platforms with various youth platforms |  |  | UNDP | [6 empty] | OPM/IRCU | 14000 | 10500 | 24500 | 21000 | 3500 | 40% | bar: Q1 to Q3
|  |  | UNFPA | [6 empty] | ACORD | 10000 | 7500 | 17500 | 17500 | 0 | 40% | bar: Q1 to Q3
|  |  | OHCHR | [7 empty] | 0 | 0 | 0 |  | 0 | 40%
1.1.1.6 Support policy dialogues with lawmakers to advocate for youth inclusion in political and PB processes |  |  | UNDP | [6 empty] | IPOD,NCF, IRCU | 20000 | 15000 | 35000 | 20000 | 15000 | 50% | bar: Q2 to Q2
|  |  | UNFPA | [6 empty] | ACORD | 10000 | 7500 | 17500 | 17500 | 0 | 50% | bar: Q1 to Q2
|  |  | OHCHR | [7 empty] | 0 | 0 | 0 |  | 0 | 50%
Joint Output 1.2: |  | Youth pro-actively engage with leaders and elders and advocate for their own inclusion in peacebuilding processes and new peacebuilding initiatives
1.2.1.1 Support innovative communication through social media and radio for mobilization of young women and men for peacebuilding and civic awareness |  |  | UNDP | [6 empty] | CCEDU/IRCU | 16000 | 12000 | 28000 | 16000 | 12000 | 60% | bar: Q1 to Q2
|  |  | UNFPA | [6 empty] | ACORD | 14566 | 10924.5 | 25490.5 | 25490.5 | 0 | 60% | bar: Q1 to Q2
|  |  | OHCHR | [8 empty] | 0 | 0 |  | 0 | 60%
1.2.1.2 Facilitate age-graduated Ekisakaate kya Nabbagereka to inculcate positive cultural values of cohesion in Central/Buganda and Rwenzori regions facilitated |  |  | UNDP | [6 empty] | NDF | 20000 | 15000 | 35000 | 20000 | 15000 | 50% | bar: Q2 to Q2
|  |  | UNFPA | [8 empty] | 0 | 0 |  | 0 | 50%
|  |  | OHCHR | [7 empty] | 0 | 0 | 0 |  | 0 | 50%
1.2.1.3 Support Youth Chapters, Democracy Clubs, Youth-Connekt Uganda Chapter and model youth parliaments to participate at political and peacebuilding foras |  |  | UNDP | [6 empty] | RFJP/ Uganda Youth network | 28000 | 21000 | 49000 | 38000 | 11000 | 50% | bar: Q2 to Q2
|  |  | UNFPA | [8 empty] | 0 | 0 |  | 0 | 50%
|  |  | OHCHR | [7 empty] | 0 | 0 | 0 |  | 0 | 50%
1.2.1.4 Facilitate peer-peer mentorship and shadowing programmes for young women and men with experienced leaders and peacebuilders |  |  | UNDP | [6 empty] | NDF/WSR, IRCU | 16000 | 12000 | 28000 | 16000 | 12000 | 50% | bar: Q2 to Q2
|  |  | UNFPA | [8 empty] | 0 | 0 |  | 0 | 50%
|  |  | OHCHR | [7 empty] | 0 | 0 | 0 |  | 0 | 50%
1.2.1.5 Support youth gender-sensitive trainings on community level mediation, early warning and conflict prevention and policy advocacy |  |  | UNDP | [6 empty] | NECOC/ NDF | 16000 | 12000 | 28000 | 16000 | 12000 | 50% | bar: Q1 to Q2
|  |  | UNFPA | [8 empty] | 0 | 0 |  | 0 | 50%
|  |  | OHCHR | [7 empty] | 0 | 0 | 0 |  | 0 | 50%
1.2.1.6 Support Social change entrepreneur programmes and initiatives focused on peace-building for the different target communities |  |  | UNDP | [6 empty] | UNDP | 16000 | 12000 | 28000 | 16000 | 12000 | 50% | bar: Q1 to Q2
|  |  | UNFPA | [6 empty] | ACORD | 20000 | 15000 | 35000 | 33506.3 | 1493.7 | 50% | bar: Q1 to Q2
|  |  | OHCHR | [7 empty] | 0 | 0 | 0 |  | 0 | 50%
1.2.1.7 Build capacity of Non-traditional actors & institutions including performing arts, music, cultural and religious institutions supported in social mobilization of youth on peacebuilding |  |  | UNDP | [6 empty] | NDF/IRCU | 12000 | 9000 | 21000 | 12000 | 9000 | 50% | bar: Q3 to Q2
|  |  | UNFPA | [6 empty] | ACORD | 12000 | 9000 | 21000 | 21000 | 0 | 50% | bar: Q3 to Q2
|  |  | OHCHR | [7 empty] | 0 | 0 | 0 |  | 0 | 50%
1.2.1.8 Facilitate South to South learning and exchanges with experienced youth platforms/peacebuilders |  |  | UNDP | [6 empty] | UNDP | 12000 | 9000 | 21000 | 12000 | 9000 | 50%
|  |  | UNFPA | [8 empty] | 0 | 0 |  | 0 | 50%
|  |  | OHCHR | [8 empty] | 0 | 0 |  | 0 | 50%
1.2.1.9 Facilitate prominent regional sports activities such as Bika bya Buganda, FUFA DRUM and Netball to inculcate peacebuilding values for unity in Central/Buganda and Rwenzori regions |  |  | UNDP | [6 empty] | NDF/RFJP | 12000 | 9000 | 21000 | 12000 | 9000 | 50% | bar: Q3 to Q2
|  |  | UNFPA | [6 empty] | ACORD |  | 0 | 0 |  | 0 | 50% | bar: Q3 to Q2
|  |  | OHCHR | [8 empty] | 0 | 0 |  | 0 | 50%
1.2.1.10 Facilitate Integrated Leadership and Peacebuilding training for young leaders in the Buganda and Rwenzori Regions |  |  | UNDP | [6 empty] | NDF | 20000 | 15000 | 35000 | 20000 | 15000 | 50% | bar: Q1 to Q2
|  |  | UNFPA | [6 empty] | ACORD | 10000 | 7500 | 17500 | 7500 | 10000 | 50% | bar: Q1 to Q2
|  |  | OHCHR | [7 empty] | 0 | 0 | 0 |  | 0 | 50%
Joint Output 1.3: |  | Selected government and civil society actors promote youth participation in political and peacebuilding processes
1.3.1.1 Support the establishment of a mentorship platform for youth |  |  | UNDP | [6 empty] | UNDP | 10000 | 7500 | 17500 | 10000 | 7500 | 70% | bar: Q2 to Q2
|  |  | UNFPA | [7 empty] | 0 | 0 | 0 |  | 0 | 70%
|  |  | OHCHR | [7 empty] | 0 | 0 | 0 |  | 0 | 70%
1.3.1.2 Tailored gender-sensitive trainings for insider mediators to mentor youth |  |  | UNDP | [6 empty] | UNDP | 10000 | 7500 | 17500 | 10000 | 7500 | 100% | bar: Q2 to Q2
|  |  | UNFPA | [8 empty] | 0 | 0 |  | 0 | 100%
|  |  | OHCHR | [7 empty] | 0 | 0 | 0 |  | 0 | 100%
1.3.1.3 Support local governments in Rwenzori and Buganda to integrate youth issues, including their gendered dimension, in the district development plans |  |  | UNDP | [6 empty] | UNDP | 14000 | 10500 | 24500 | 14000 | 10500 | 70% | bar: Q1 to Q2
|  |  | UNFPA | [7 empty] | 0 | 0 | 0 |  | 0 | 70%
|  |  | OHCHR | [7 empty] | 0 | 0 | 0 |  | 0 | 70%
1.3.1.4 Support cultural institutions to champion youth’s social, political and economic rights |  |  | UNDP | [6 empty] | NDF | 16000 | 12000 | 28000 | 16000 | 12000 | 70% | bar: Q1 to Q2
|  |  | UNFPA | [8 empty] | 0 | 0 |  | 0 | 70%
|  |  | OHCHR | [7 empty] | 0 | 0 | 0 |  | 0 | 70%
1.3.1.5 Support the inclusion of youth issues in the draft National Peace Policy |  |  | UNDP | [6 empty] | OPM | 12000 | 9000 | 21000 | 15501.87 | 5498.13 | 70% | bar: Q2 to Q2
|  |  | UNFPA | [7 empty] | 0 | 0 | 0 |  | 0 | 70%
|  |  | OHCHR | [7 empty] | 0 | 0 | 0 |  | 0 | 70%
1.3.1.6 Capacity building to the Uganda Bureau of Statistics (UBOS) on the elaboration of statistics with disaggregated data about the youth, with a Human Rights Based Approach (HRBA) |  |  | UNDP | [6 empty] | UNDP | 0 | 0 | 0 |  | 0 | 50%
|  |  | UNFPA | [8 empty] | 0 | 0 |  | 0 | 50%
|  |  | OHCHR | [6 empty] | UHRC | 22000 | 16500 | 38500 |  | 38500 | 50% | bar: Q2 to Q3
1.3.1.7 Build capacity of youth led Organisations and networks to be stronger actors in peacebuilding processes |  |  | UNDP | [6 empty] | UNDP | 20000 | 15000 | 35000 | 25000 | 10000 | 70% | bar: Q1 to Q2
|  |  | UNFPA | [6 empty] | ACORD | 51434 | 38575.5 | 90009.5 | 90009.5 | 0 | 70% | bar: Q1 to Q2
|  |  | OHCHR | [6 empty] | UHRC |  | 0 | 0 |  | 0 | 70%
OUTCOME 2: Mistrust between law enforcement and security agencies and communities is reduced by enhancing the strict application of human rights standards
Joint Output 2.1: |  | Capacity building is provided for law enforcement and security agencies on human rights standards in their operations engaging the youth
2.1.1.1 Support UHRC in capacity building of Law enforcement agencies on Human Rights, especially in selected areas: (Kampala, Wakiso, Kasese, Bundibugyo) |  |  | UNDP | [6 empty] | UNDP | 8000 | 6000 | 14000 | 7500 | 6500 | 50% | bar: Q1; Q3 to Q4
|  |  | UNFPA | [7 empty] | 0 | 0 | 0 |  | 0 | 50%
|  |  | OHCHR | [6 empty] | UHRC | 50000 | 37500 | 87500 | 39500 | 48000 | 50% | bar: Q1; Q3 to Q4
2.1.1.2 Dialogue processes between police and youth representatives/communities in Kampala Metropolitan Area including Katwe, Kisenyi, Bwaise, Kabalagala, Kamwokya and Nansana and Kasese/Bundibugyo established |  |  | UNDP | [6 empty] | UNDP | 12000 | 9000 | 21000 | 12000 | 9000 | 50% | bar: Q2; Q4 to Q1
|  |  | UNFPA | [7 empty] | 0 | 0 | 0 |  | 0 | 50%
|  |  | OHCHR | [6 empty] | UHRC | 10000 | 7500 | 17500 | 5000 | 12500 | 50% | bar: Q2; Q4 to Q1
Joint Output 2.2: |  | The effectiveness of a monitoring, reporting and advocacy framework for human rights violations in law enforcement operations aimed at engaging the youth is strengthened
2.2.1.1 High level diplomacy meetings for UHRC and the UN to address human rights situation of young women and men with high level government and law enforcement officials |  |  | UNDP | [6 empty] | UNDP | 16000 | 12000 | 28000 | 16000 | 12000 | 50% | bar: Q1 to Q2
|  |  | UNFPA | [7 empty] | 0 | 0 | 0 |  | 0 | 50%
|  |  | OHCHR | [6 empty] | UHRC | 12000 | 9000 | 21000 | 5000 | 16000 | 50% | bar: Q1 to Q2
2.1.1.2 Strengthening the capacity of CSOs and youth organisations to monitor, report, raise and advocate on human rights concerns related to youth issues |  |  | UNDP | [6 empty] | UNDP | 8000 | 6000 | 14000 | 8000 | 6000 | 70% | bar: Q2 to Q3; Q1
|  |  | UNFPA | [7 empty] | 0 | 0 | 0 |  | 0 | 70%
|  |  | OHCHR | [6 empty] | UHRC | 20000 | 15000 | 35000 | 10000 | 25000 | 70% | bar: Q2 to Q3; Q1
Joint Output 2.3: |  | The youth capacity on human rights issues has been strengthened
2.3.1.1 Support UHRC community barazas in selected areas (Kampala, Wakiso, Kasese, Bundibugyo) to train youth on human rights and duties |  |  | UNDP | [6 empty] | UNDP | 12000 | 9000 | 21000 | 12000 | 9000 | 50% | bar: Q1 to Q3
|  |  | UNFPA | [7 empty] | 0 | 0 | 0 |  | 0 | 50%
|  |  | OHCHR | [6 empty] | UHRC | 16000 | 12000 | 28000 | 16000 | 12000 | 50% | bar: Q1 to Q3
2.3.1.2 Support CSOs to conduct human rights capacity building for youth in four (04) selected areas |  |  | UNDP | [6 empty] | UNDP | 12000 | 9000 | 21000 | 12000 | 9000 | 50% | bar: Q2 to Q3; Q1
|  |  | UNFPA | [7 empty] | 0 | 0 | 0 |  | 0 | 50%
|  |  | OHCHR | [6 empty] | UHRC | 8000 | 6000 | 14000 | 8000 | 6000 | 50% | bar: Q2 to Q3; Q1
Sub -Total: | [10 empty] | 730000 | 547500 | 1277500 | 847508.17 | 429991.83
Project personnel costs if not included in activities above PA,PC,Driver,UNV's |  |  | UNDP | [6 empty] | UNDP | 72000 | 54000 | 126000 | 37173.8048 | 88826.1952
Project operational costs if not included in activities above |  |  | UNDP | [6 empty] | UNDP | 48000 | 36000 | 84000 | 58000 | 26000 | bar: Q1 to Q2
|  |  | UNFPA | [6 empty] | UNFPA | 11077.2 | 8307.9 | 19385.1 | 18385.29 | 999.81 | bar: Q1 to Q2
|  |  | OHCHR | [6 empty] | OHCHR | 22922.8 | 17192.1 | 40114.9 | 21089.32 | 19025.58
Project M&E budget |  |  | UNDP | [6 empty] | UNDP | 46000 | 34500 | 80500 | 68037.6849 | 12462.3151
SUB-TOTAL PROJECT BUDGET: | [10 empty] | 200000 | 150000 | 350000 | 202686.0998 | 147313.9002
Indirect support costs (7%): |  |  | UNDP | [6 empty] | UNDP | 40600 | 30450 | 71050 | 43904.9352 | 27145.0648 | bar: Q1 to Q2
|  |  | UNFPA | [6 empty] | UNFPA | 13235.404 | 9926.553 | 23161.957 | 22287.4113 | 874.5457 | bar: Q1 to Q2
|  |  | OHCHR | [6 empty] | OHCHR | 11264.596 | 8448.447 | 19713.043 | 7321.2524 | 12391.7906 | bar: Q2 to Q2
TOTAL PROJECT BUDGET: | [10 empty] | 995100 | 746325 | 1741425 | 1123707.8687 | 617717.1313 | 40.23%
UNDP NEX Advance
1 | RFPJ | 231093.3858
2 | IRCU | 134905.89
3 | NDF | 0 | [7 empty] | Exp plus NEX |  |  |  | 1489707.1445 | 85.55%
4 | CCEDU | 0
Total |  | 365999.2758
UNFPA NEX Advance
1
2
3
Total |  | 0
UNFPA NEX Advance
1
2
3
Total |  | 0

## Summary
UNDP PBF Uganda - Harnessing the youth's potential
As at 15th Jan 2021
|  |  | A | B | C = B+C | D | E | F = C-D | G = (D+E)/C | H = C-D-E
No. | Agency | Project Amount | Tranche 1 | Tranche 2 | Total resources availed | Expenditure and commitments | NEX Advance | Balance | Delivery with NEX | Resource Fund Balance
1 | UNDP | 1551500 | 620600 | 465450 | 1086050 | 671118.295 | 365999.2758 | 414931.705 | 95.49% | 48932.4292
2 | UNFPA | 505782 | 202312.8 | 151734.453 | 354047.253 | 340679.0013 | 0 | 13368.2517 | 96.22% | 13368.2517
3 | OHCHR | 430468 | 172187.2 | 129140.547 | 301327.747 | 111910.5724 | 0 | 189417.1746 | 37.14% | 189417.1746
| Total | 2487750 | 995100 | 746325 | 1741425 | 1123707.8687 | 365999.2758 | 617717.1313 | 85.55% | 251717.8555