## Sheet1
Annex D - PBF project budget
Note: If this is a budget revision, insert extra columns to show budget changes.
Table 1 - PBF project budget by Outcome, output and activity
Outcome/ Output number | Outcome/ output/ activity formulation: | Budget by recipient organization in USD - Please add a new column for each recipient organization | Percent of budget for each output reserved for direct action on gender eqaulity (if any): | Level of expenditure/ commitments in USD (to provide at time of project progress reporting): JAN _NOV 2019 | Any remarks (e.g. on types of inputs provided or budget justification, for example if high TA or travel costs) | Budget Balance _2018-2019
OUTCOME 1: The effective development, implementations, monitoring, oversight of peacebuilding projects and the overall strategic direction of the PBF portfolio in Guinea-Bissau is ensured
Output 1.1: | PBF Secretariat operations are running | 747576 |  | 761734.37
Activity 1.1.1: | Prepare and approve new Prodoc for PBF Secretariat 2018-2019
Activity 1.1.2: | Evaluate and renew staff contracts | 643386 |  | 653685.83 | Salary and pos adjoint: PBF Coordinator, UNV (M&E), Natinal staff and local consultant
Activity 1.1.3: | Staff Attend Approved Trainings | 20000 |  | 5748.94 | Training
Activity 1.1.4: | Purchase of equipment (camera, photocopier, office furniture etc.) and supplies + fuel | 18100 |  | 24545.77 | Purchase of equipment, materials, fuel., Vehicle maintenance, etc
Activity 1.1.5: | Offices equipped/ operational | 66090 |  | 77753.83 | Purchase of vehicule, Rent, Communication, etc
Total expenditure - output 1.2 |  |  |  | 761734.37
Activity 1.1.6:
Activity 1.1.7:
Activity 1.1.8:
Output 1.2: | Effective oversight, communication and coordination enabled to ensure Oversight, Coherence and Complementarity between Projects | 50000
Activity 1.2.1: | Convene and facilitate TT meetings as needed to conduct PBF Business | 20000 |  | 81.97
Activity 1.2.2: | M&E Visits | 20000 |  | 471.22
Activity 1.2.3: | Meet with national counterparts as needed to inform on PBF Business | 10000
Total expenditure - output 1.2 |  |  |  | 553.19
Activity 1.2.4:
Activity 1.2.5:
Activity 1.2.6:
Activity 1.2.7:
Activity 1.2.8:
Activity 1.2.9:
Activity 1.2.10:
Activity 1.2.11:
Output 1.3:
Activity 1.3.1:
Activity 1.3.2:
Activity 1.3.3:
Activity 1.3.4:
Activity 1.3.5:
Activity 1.3.6:
Activity 1.3.7:
Activity 1.3.8:
TOTAL $ FOR OUTCOME 1: |  | 797576 |  | 762287.56 |  | 35288.44
OUTCOME 2: The agencies implementing IRF funded projects are in a position to provide effective leadership and substantive guidance to enable effective design, implementation, monitoring and evaluation of projects and with communicating the results of their implementation efforts
Output 2.1: | Capacity-building of RUNOs enabled through tailored thecnical support training | 55000
Activity 2.1.1: | Provide on-going tailored technical support in peacebuilding to RUNOs for project design and implementation | 10000
Activity 2.1.2: | Convene Training eventes in peacebuilding projects Design and Monitoring Workshop (PB Mainstreaming); Dialogue Design and methodologies; National Reconciliation Models; Innovations and cutting adge approaches to peacebuilding; nexus between gender, human rights based approaches and peacebuilding | 45000 |  | 53601.15 | International Consultant fee, dsa internt, air ticket, visa
Total expenditure output 2.1 |  |  |  | 53601.15
Output 2.2: | Strengthen social communication and peacebuilding advocacy: Increase awareness by national authorities, civil society and wider public of peacebuilding Priorities and results | 30000
Activity 2.2.1: | Develop a communication plan in conjunction with UN communication Group to ensure PBF visibility | 5000 |  | 1275.23
Activity 2.2.2: | Organize discussion series on Peacebuilding related topics with national peacebuilders (Civil siciety) | 10000 |  | 7214.7 | OCS
Activity 2.2.3: | Develop 3 Emblematic Stories in videos that feature compeling stories that arise in implementation of projects | 15000 |  | 3869.51 | Stories identification and video production
Total Expenditure output 2.2 |  |  |  | 12359.44
TOTAL $ FOR OUTCOME 2: |  | 85000 |  | 65960.59 |  | 19039.41
Project personnel costs if not included in activities above
Project operational costs if not included in activities above
Project M&E budget
Totals.
Commitment |  |  |  | 6000
SUB-TOTAL PROJECT BUDGET: 882,576 |  | 882576 |  | 834248.15 |  | 54327.85
Indirect support costs (7%): |  | 61780.32 |  | 47301.8701 |  | 3802.9495
TOTAL PROJECT BUDGET: |  | 944356.32 |  | 881550.0201 |  | 58130.7995

## Sheet2
Table 2 - PBF project budget by UN cost category
Note: If this is a budget revision, insert extra columns to show budget changes.
CATEGORIES | Amount Recipient Agency XX |  | Amount Recipient Agency XX |  | Amount Recipient Agency XX |  | Total tranche 1 | Total tranche 2 | PROJECT TOTAL
| Tranche 1 (70%) | Tranche 2 (30%) | Tranche 1 (70%) | Tranche 2 (30%) | Tranche 1 (70%) | Tranche 2 (30%)
1. Staff and other personnel | [8 empty] | 643386
2. Supplies, Commodities, Materials | [8 empty] | 20000
3. Equipment, Vehicles, and Furniture (including Depreciation) | [8 empty] | 13100
4. Contractual services | [8 empty] | 100000
5.Travel | [8 empty] | 40000
6. Transfers and Grants to Counterparts | [8 empty] | 0
7. General Operating and other Direct Costs | [8 empty] | 66090
Sub-Total Project Costs | [8 empty] | 882576
8. Indirect Support Costs (must be 7%) | [8 empty] | 61780.32
TOTAL | [8 empty] | 944356.32