## Sheet1
Annex D - PBF project budget
Note: If this is a budget revision, insert extra columns to show budget changes.
Table 1 - PBF project budget by Outcome, output and activity
Outcome/ Output number | Outcome/ output/ activity formulation: | Budget by recipient organization in USD - UNDP | Budget by recipient organization in USD - UNICEF | Percent of budget for each output reserved for direct action on gender eqaulity (if any): | Level of expenditure/ commitments in USD (to provide at time of project progress reporting): UNDP | Level of expenditure/ commitments in USD (to provide at time of project progress reporting): UNICEF | Any remarks (e.g. on types of inputs provided or budget justification, for example if high TA or travel costs) | Total budget approved by recipient organization in USD - UNICEF | Total budget reviewd for changes approval, by recipient organization in USD - UNICEF
OUTCOME 1: The population benefits from enhanced access to justice through strengthened alternative dispute resolution systems within informal and formal justice systems, and a strengthened interface between both systems, in line with international standards of administration of justice and human rights.
Output 1.1: | ADR and Restorative Justice Practices in the Formal Justice system legitimized with the particular attention to Women and Child Rights | 237500 | 115000 | 32.63% | 167447.76 | 100477 |  | 155500 | 155500
Activity 1.1.1: | Build Awareness/Advocacy of Key Stakeholders of RJ, ADR and Women’s/ Children’s Rights | 49000 | 15000 |  | 16820.8 |  |  | 15000 | 10000
Activity 1.1.1.2: | International Workshop to provide input to ADR/RJ law | 130000 | 20000 |  | 19931.76 | 9620 |  | 20000 | 15000
Activity 1.1.2: | Develop ADR/RJ draft Law for the Formal Justice Sector with TA | 25000 | 0 |  | 32000 | 0 |  | 0 | 0
Activity 1.1.3: | Develop Child Protection Law with RJ lens with Technical Assistance and Collaborative Process | 0 | 42000 |  | 0 | 54663 |  | 62000 | 72000
Activity 1.1.4: | Enhance public awareness through development of media products and coverage of project events | 5000 | 20000 |  | 15578.4 | 20618 |  | 28100 | 28100
Activity 1.1.5: | Strengthen the capacity of key actors in the formal justice sector in the implementation ADR mechanisms for conflict resolution and restorative justice, including child and women protection. | 28500 | 18000 |  | 83116.8 | 15576 |  | 30400 | 30400
Output 1.2: | Key Stakeholders in traditional justice sector have increased capacity to engage in ADR and restorative justice in compliance with Women and Children’s Rights | 84400 | 142600 | 65.17% | 94155 | 76765 |  | 205600 | 205600
Activity 1.2.1: | Map of Dispute Resolution decisions around child issues | 29400 | 25600 |  | 11856 | 20368 |  | 40600 | 40600
Activity 1.2.2: | Awareness / advocacy of key stakeholders in traditional justice in RJ, ADR and women's and children's rights. | 30000 | 30000 |  | 32528 | 17878 |  | 40000 | 40000
Activity 1.2.3: | Strengthen awarness and engagement of traditional structures, NGOs and CBOs on ADR and RJ mechanisms, including on the rights of women and children. | 10000 | 40200 |  | 37915 | 7759 |  | 52000 | 52000
Activity 1.2.4: | Monitoring of access and quality of traditional justice through CSOs and CBOs that implement programs that promote community dialogue to change behavior against social practices and norms detrimental to the health and well-being of children and women (60 communities of 5 regions) | 15000 | 45000 |  | 11856 | 30760 |  | 73000 | 73000
Output 1.3: | The collaboration/ complementarity between formal and traditional justice system is effective | 68000 | 12000 | 0% | 0 | 0 |  | 18900 | 18900
Activity 1.3.1: | Creation of functional mechanism of cooperation between formal and informal justice actors | 38000 | 12000 |  |  | 0 | 3 ToRs launched (1 international and 2 national experts) and application deadlines closed, now pending procurement long-listing of experts. | 18900 | 18900
Activity 1.3.2: | Develop legal framework on traditional justice boundaries | 30000 | 0 |  |  | 0 | 2 ToRs launched (1 international and 1 national expert) and application deadlines closed, now pending procurement long-listing of experts. |  | 0
TOTAL $ FOR OUTCOME 1:
Project personnel costs if not included in activities above |  | 84000 | 70000 | n/a | 47917.6 | 56254.17 |  | 100000 | 100000
Project operational costs if not included in activities above |  | 52500 | 24402 | n/a | 25824.27 | 4848 |  | 34860 | 34860
Project M&E budget |  | 21000 | 9000 | n/a | 137.5 | 0 |  | 18000 | 18000
SUB-TOTAL PROJECT BUDGET: |  | 547400 | 373002 | n/a | 335482.13 | 238344.17 |  | 532860 | 532860
Indirect support costs (7%): |  | 38318 | 26110 | n/a | 10740.26 | 13152.47 |  | 37300 | 37300
TOTAL PROJECT BUDGET: |  | 585718 | 399112 | n/a | 346222.39 | 251496.64 |  | 570160 | 570160

## Sheet2
Table 2 - PBF project budget by UN cost category
Note: If this is a budget revision, insert extra columns to show budget changes.
CATEGORIES | Amount Recipient Agency XX |  | Amount Recipient Agency XX |  | Amount Recipient Agency XX |  | Total tranche 1 | Total tranche 2 | PROJECT TOTAL
| Tranche 1 (70%) | Tranche 2 (30%) | Tranche 1 (70%) | Tranche 2 (30%) | Tranche 1 (70%) | Tranche 2 (30%)
1. Staff and other personnel
2. Supplies, Commodities, Materials
3. Equipment, Vehicles, and Furniture (including Depreciation)
4. Contractual services
5.Travel
6. Transfers and Grants to Counterparts
7. General Operating and other Direct Costs
Sub-Total Project Costs
8. Indirect Support Costs (must be 7%)
TOTAL