## Consolidated
GPI : Promoting Women's Engagement in Waste Management to Prevent Conflict in Sri Lanka
Joint Project Workplan : UN Women - UNOPS - Chrysalis
Output | Activity | 2020 | [10 empty] | 2021 |  |  |  |  | Payment Schedule
|  | Q1 |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  | 2020 |  |  |  | 2021
|  | Feb | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | Q1 | Q2 | Q3 | Q4 | Q1 | Q2
Output 1.1: Increased knowledge and capacities among women to identify and respond to emerging conflicts within/among communities. | Activity 1.1.1: Baseline and perception surveys, conflict and gender analyses, stakeholder mapping, value chain analysis on SWM (how gender dimensions work in the value chain, how masculinity is interlinked, and how economic benefits can be extracted out of this value chain).
1.1.1.1: Baseline & perception Survey and stakeholder mapping exercise
1.1.1.2: Conflict and Political Analysis
1.1.1.3: Gender Analysis
1.1.1.4: Value chain analysis on SWM
Activity 1.1.2: Series of local-level, multi-stakeholder dialogues convening cross-party elected officials, public officials, CSOs, religious and media representatives to identify common issues (including SWM) and solutions. Includes support for implementation of identified solutions.
1.1.2.1: 03-day mutli stakeholder dialogues (in Puttalam and Mannar) convening cross-party elected officials, public officials, CSOs, religious and media representatives to identify common issues (emphasis on solid-waste managment) and solutions. Day 01 - elected officials and public officials; Day 02 - CSOs and media representatives; Day 03 - religious leaders.
1.1.2.2: 03-day follow sessions, bringing together all stakeholders (in Puttalama and Mannar) to consolidate identified solutions and provide support for the implementation of the identified solutions, particularly targeting SWM.
Activity 1.1.3: Quick-win community mobilisation activities in both districts by Praja Mandala including 'Diversity Kitchen' programmes
1.1.3.1: Discussion with village level government officials, CBO members and Community Consultations
1.1.3.2: Planning of Mobilisation activities with government officials, CBO members and Community leaders
1.1.3.3: Conduct Quick-win mobilization activities + Diversity Kitchen programs
Activity 1.1.4: Capacity building for women community leaders on conflict analysis, conflict management and conflict resolution to act as intermediaries among communities.
1.1.4.1 Conduct a rapid need assessment to identify capacity/skill gaps
1.1.4.2 Based on need assessment findings hire consultant(s) or consultancy firm
1.1.4.3. Conduct capacity building trainings for women and men community leaders
Activity 1.1.5: Capacity building for women community leaders on developing alternative narratives to ethno-religious intolerance and other potential drivers of emerging conflicts, and dissemination of these community-developed narratives/messaging.
1.1.5.1: 03-day dialogues (In Puttalam and Mannar) with women community leaders, (who have attended Chrysalis trainings on conflict analysis and possibly also attended UN Women's multi-party dialogues). The dialogues should build on the conflict analysis/managment sessions conducted by Chrysalis.
1.1.5.2: 03-day sessions (In Puttalam and Mannar) on ethno-religious intolerance and drivers of emerging conflicts, with an emphasis on SWM. Creation of online/offline platform for women to develop messaging on religious tolerence and social cohesion if communities mobilise to address common issues, partcularly solid-waste management within a post Covid-19 climate.
1.1.5.3: Creation of online/offline platform to disseminate social change-driven messaging.
1.1.5.4: Dissemination of online (social media posts) and offline (leaflets, newspaper articles) messages promoting community coehsion and ethnic harmony.
Activity 1.1.6: Engaging men and women to address issues of SWM and peacebuilding and identify champions to lead the relational changes at the community/local level.
1.1.6.1: Conduct a mapping exercise to identify women and men champions
1.1.6.2: Conduct a capacity needs assessment to identify knowledge/skills gaps
1.1.6.3 Capacity building programs on identified training needs
1.1.6.4: Coaching and mentoring women and men leaders
1.1.6.5: Recognising and rewarding women and men leaders for their contribution
Activity 1.1.7: Formation of Youth Task Force and building young people's capacity to address community level issues (linked to PM).
1.1.7.1 Competitive recruitment process to join young girls and boys to youth task force
1.1.7.2 Involve youth task force members with planned training programs
1.1.7.3 Provide soft skills and specialized training programs (social media, story telling, community video)
1.1.7.4 Involve youth task force members with project activities
1.1.7.5 Regular experience sharing and review discussions
[18 empty] | 0 | 0 | 0 | 0 | 0 | 0
Output 1.2: Increased women’s engagement with local municipalities related to policy and decision-making on critical issues including SWM. | Activity 1.2.1: Establish or strengthen existing Praja Mandala to collectively identify and address community issues through Participatory Rural Appraisals (PRAs) supported by Village Development Plans (VDPs); build their capacity for effective implementation of VDPs; and supporting Praja Mandala to implement community level initiatives with the leadership of women and youth. Includes Community Action Grants to tackle waste related issues.
1.2.1.1: Discussions with Provincial CouncilàLocal Government DepartmentàLocal Government AuthoritiesàDistrict and Divisional Secretariats
1.2.1.2: Identify suitable GN divisions (40) for the project in consultation with key government officials
1.2.1.3: Formation / reformation of Praja Mandalas
1.2.1.4: Registration of Praja Mandalas with Local Authorities
1.2.1.5: Conduct needs assessment of Praja Mandalas selected for the project
1.2.1.6: Capacity building programs for key Praja Mandala members
1.2.1.7: Conduct PRA and develop VDP (Peacebuilding and SWM will be integral parts of the VDP)
1.2.1.8: Facilitate proposal development by Praja Mandalas to structure community initiatives based on VDP priorities
1.2.1.9: Provide action grants for Praja Mandalas to implement community initiatives
1.2.1.10: Debriefing sessions with Praja Mandala to assess outcomes, lessons and challenges in implementing community initiatives
Activity 1.2.2: Capacity building of Local Government officials to effectively adopt measures to mitigate existing conflict and future conflicts (community development & PRA, soft skill development, conflict analysis, gender, peacebuilding and problem solving, negotiations) - including on SWM with UNOPS.
1.2.2.1: Conduct a capacity needs assessment to identify knowledge/skills gaps
1.2.2.2: Capacity building programs on identified training needs
Activity 1.2.3: Capacity building and engagement with local councillors (both male and female) on gender-responsiveness and collective leadership for peacebuilding, community development and economic growth - including exchange programme in the Northern Province on adopting gender-responsive approaches within LAs.
1.2.3.1: Exchange programme with Northern province for both women and men councilors to adopt Gender responsive approaches within local authorities
Activity 1.2.4: Capacity building for women community leaders on collective leadership and decision-making at community/municipality levels, including awareness on access to local authorities.
1.2.4.1: 02-day dialogues (In Puttalam and Mannar) with women community leaders to identify common sentiments on collective leadership and decisionmaking, while building a network of committed women. (The group should include women from Praja Mandalas, as well as women that have undergone sessions on conflict analysis/management with Chrysalis, and the workshops on developing alternate narratives with UN Women).
1.2.4.2: 02-day training workshops (In Puttalam and Mannar) on collective leadership and decisionmaking for community leaders that participated in the dialogues. The group of women should be provided with opportunities to discuss solutions to tackle preveleant issues on SWM facing their communities within a post-Covid 19 climate.
1.2.4.3: Mentorship programmes, connecting women community leaders with role models at local government authorities.
Activity 1.2.5: Establishment of district level Women Councillors' Caucuses and support its operationalization at Local Authority levels - with a focus on peacebuilding and community development.
1.2.5.1: Establishment of district level women caucuses to address women and youth issues effectively in the Local authority levels
1.2.5.2: Supporting the operationalization (quarterly meetings) of women caucuses in the district to tackle waste and peace building issues in the community level effectively via Praja mandala
1.2.5.3: Facilitate Shared Platform discussions among key project actors
Activity 1.2.6: Supporting/engaging with Inter-Religious District and Divisional Committees to promote tolerance/respect within and amongst communities – linking with Praja Mandala and the trained women community leaders.
1.2.6.1: Formation or Reformation of Inter-religious groups (linking Praja Mandala and women leaders) at district and divisional levels
1.2.6.2: Facilitate regular sessions and meetings among inter-religious groups/committees to discuss about SWM and Peacebuilding approaches
Activity 1.2.7: Cross-regional exchanges among trained women across divisions within each district and amongst the two districts.
1.2.7.1 Facilitate a cross-regional exchange programs
1.2.7.2 Facilitate 3 cross-divisional exchange programs
Activity 1.2.8: Series of village “townhalls” for citizens to directly interact with respective elected and public officials (good practice from Kurunegala Multi-Party Dialogue).
1.2.8.1: Trained women community leaders to connect with elected public officials (in Puttalam and Mannar), to convene townhall meetings discussing common issues faced in the community.
1.2.8.2: Trained women community leaders and elected officials to conduct townhall meetings in Puttalam and Mannar to assess community support for SWM initiatives.
[18 empty] | 0 | 0 | 0 | 0 | 0 | 0
Output 1.3: Economically and socially empowered women, changed gender relations, and improved practices of environmental remediation amongst all communities in Puttalam and Mannar. | Activity 1.3.1: Supporting women led-initiatives at the local authority level to implement participatory solutions on waste collection (led by women councillors and PM).
1.3.1.1: Develop women-led initiatives through design thinking process (Involving UNOPS)
1.3.1.2: Support the implementation women-led initiatives on waste collection.
Activity 1.3.2: Engage with local authorities (and potentially private sector partners) on creating income-generating opportunities for women and youth through the monetizing of waste collection.
1.3.2.1: Mapping of private sector entities working on SWM
1.3.2.2: Conduct consultative meetings with local authorities and identified private sector actors
1.3.2.3: Facilitate session with the Private sector partners and Local authorities to revise the SWM plans (Technical Supports from UNOPS)
Activity 1.3.3: Collective designing of SWM initiatives (women / youth led) at the Local authority level to mitigate conflict related to SWM and Pollution - Partly supporting 4 LAs.
1.3.3.1: Designing of SWM initiatives at local authority levels with the participation of women and youth leaders, private sector entities and environmental authorities
1.3.3.2: Conduct community consultative to validate the developed solutions (Conflict and Gender Sensitivity)
1.3.3.3 Finalize the solutions based on community consultative findings.
1.3.3.4: Support the implementation of SWM solutions
1.3.3.5: Documenting the process of introducing and implementing a new SWM initiative
Activity 1.3.4: Supporting household level greening initiatives and home gardening (Training and material support for selected household level - representing all the classes of community).
1.3.4.1: Develop a selection criterion to select households in the targeted Local Authority areas
1.3.4.2: Form an independent selection committee to identify 250 households each from a local authority areas
1.3.4.3: Providing training on household SWM techniques and home gardening
1.3.4.4: Support households to initiative SWM and home gardening
[18 empty] | 0 | 0 | 0 | 0 | 0 | 0
Output 2.1 Technical advisory services on SWM to Puttalam district local authorities | Activity 2.1.1: Capacity building and technical advisory of local authorities to deliver and manage SWM services in Puttalam and Kalpitiya.
Activity 2.1.2: Capacity building and technical advisory of local authorities to deliver and manage SWM services in Chilaw.
Activity 2.1.3: Capacity building and technical advisory of local authorities to deliver and manage SWM services in Arachchikattu.
Activity 2.1.4: Introduction and training on M-track mobile application.
Activity 2.1.5: Assist local authorities to establish revenue generation system to support SWM
[18 empty] | 0 | 0 | 0 | 0 | 0 | 0
Output 2.2: Public education and increased community awareness and knowledge on SWM | Activity 2.2.1: Education and Awareness sessions on SWM to Praja Mandalas and local authorities.
2.2.1.1: Developing behavioural change communication tools (Forum Theatre, Puppet Shows, Street Dramas, Flash Mobs) with the identified groups/teams
2.2.1.2: Conduct awareness campaigns/sessions using the above tools
2.2.1.3: Develop, print and distribute awareness creation materials during campaigns and sessions
Activity 2.2.2: Training of Trainers and cascade trainings of Women Team Leaders/Champions on SWM.
Activity 2.2.3: Public campaign and awareness activities on waste segragation and management at household level - 3Rs and composting.
Activity 2.2.4: Public campaign and awareness activities on waste segregation and management at neighborhood level.
Activity 2.2.5: Public education and training in schools on SWM through theatre, competition and celebration of international days.
Activity 2.2.6: Youth engagement on integrated SWM practices through Youth Leadership programme.
Activity 2.2.7: Dialogue and awareness sessions with private sector on SWM practices.
Activity 2.2.8: Public campaign and awareness activities during religious festivals.
[18 empty] | 0 | 0 | 0 | 0 | 0 | 0
Output 2.3: Closure of illegal dumping sites | Activity 2.3.1: Clean up of illegal dumping sites in Puttalam
Activity 2.3.2: Clean up of illegal dumping, beach and shores sites in Chilaw
Activity 2.3.3: Clean up of illegal dumping sites in Arachchikattu
Activity 2.3.4: Clean up of illegal dumping sites in Kalpitiya
[18 empty] | 0 | 0 | 0 | 0 | 0 | 0
Output 2.4: Improved Waste Management Capacity | Activity 2.4.1: Improvement of existing composting facility in Puttalam.
Activity 2.4.2: Establishment of composting capacity in Arachchikattu and Chilaw.
Activity 2.4.3: Procurement, installation and training on the use of shredder, strainer and bale machines in Arachchikattu and Chilaw.
[18 empty] | 0 | 0 | 0 | 0 | 0 | 0
Direct Programme Management Cost | HR Cost
Administrative Cost
Monitoring & Evaluation
| GRAND TOTAL | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0
UN Women
Chrysalis
UNOPS
Note on C99: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: UNOPS and Chrysalis Joint Activity

## Draft-based on Feb workshop
Organization | 2020 | [9 empty] | 2021
| M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J
UNOPS |  |  |  | 2.1.1 | 2.1.1 | 2.1.1 | 2.1.1 | 2.1.1 | 2.1.1 | 2.1.1 | 2.1.1 | 2.1.1 | 2.1.1 | 2.1.1 | 2.1.1 | 2.1.1
|  |  |  | 2.1.2 | 2.1.2 | 2.1.2 | 2.1.2 | 2.1.2 | 2.1.2 | 2.1.2 | 2.1.2 | 2.1.2 | 2.1.2 | 2.1.2 | 2.1.2 | 2.1.2
|  |  |  | 2.1.3 | 2.1.3 | 2.1.3 | 2.1.3 | 2.1.3 | 2.1.3 | 2.1.3 | 2.1.3 | 2.1.3 | 2.1.3 | 2.1.3 | 2.1.3 | 2.1.3
UNW | 2020 M: Send out the letter and orientation to stakeholders; 2020 A: 1.1.2; 2020 M: 1.1.2; 2020 J: 1.1.2; 2020 O: 1.1.5; 2020 N: 1.1.5
Orientation
Chrysalis | 2020 M: 1.1.1; 2020 A: 1.1.1; 2020 M: 1.1.1; 2020 J: 1.1.1; 2020 J: 1.1.1
| 1.2.1 | 1.2.1 | 1.2.1 | 1.2.1 | 1.2.1 | 1.2.1 | 1.2.1 | 1.2.1 | 1.2.1 | 1.2.1 | 1.2.1 | 1.2.1 | 1.2.1 | 1.2.1 | 1.2.1 | 1.2.1
|  |  | 1.1.3 | 1.1.3 | 1.1.3
|  |  | 1.1.7 | 1.1.7 | 1.1.7 | 1.1.7 | 1.1.7 | 1.1.7 | 1.1.7 | 1.1.7 | 1.1.7 | 1.1.7 | 1.1.7 | 1.1.7 | 1.1.7
[6 empty] | 1.1.4 | 1.1.4 | 1.1.6 | 1.1.6
|  |  | 1.2.2 | 1.2.2
|  |  | 1.2.3 | 1.2.3 | [5 empty] | 1.2.5
|  | 1.2.6 | 1.2.6 | 1.2.6 | 1.2.6 | 1.2.6 | 1.2.6 | 1.2.6 | 1.2.6 | 1.2.6 | 1.2.6 | 1.2.6 | 1.2.6 | 1.2.6 | 1.2.6 | 1.2.6
[11 empty] | 1.2.7 | 1.2.7
1.3.1
1.3.2
1.3.3
1.3.4
[10 empty] | 2.2.1 | 2.2.1 | 2.2.1 | 2.2.1 | 2.2.1 | 2.2.1 | 2.2.1
Note on I13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Select both the counilors and PM Leader
Note on J13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Select both the counilors and PM Leader
Note on B19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Coupling with UNOPS Assesment within the scope
Note on C19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Coupling with UNOPS Assesment within the scope
Note on D19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Coupling with UNOPS Assesment within the scope
Note on E19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Coupling with UNOPS Assesment within the scope
Note on F19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Coupling with UNOPS Assesment within the scope
Note on D21: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Two approaches for PMs exists and Non-exists Reply: Scoping will feed to this activity
Note on E21: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Two approaches for PMs exists and Non-exists Reply: Scoping will feed to this activity
Note on F21: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Two approaches for PMs exists and Non-exists Reply: Scoping will feed to this activity
Note on D22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: start the process with the quick win mobilization activity
Note on E25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Councilors trained by UNW will take part in this exchange programme