## Outcomes
Expected Results | Indicators | Baseline | Overall Target | Q3 Progress | Q4 Target | Q4 Progress | Q1 2020 Target | Q1 2020 Progress | Q2 2020 Progress | Q2 2020 Target
Outcome 1: Empowered female heads of households, including military and war widows have sustainable livelihoods, and access social support services with dignity | Outcome Indicator 1.1 % of Female Heads of Households - FHHs (including military and war widows) who are subjected to sexual bribery and sexual exploitation when accessing services. | Updated: 23.8% of FHHs (including military and war widows) report that the people in their area have to resort to sexual bribery to obtain services | Reduced to 15% | Perception and baseline survey ongoing to establish baseline and inform programming | N/A | Baseline survey completed | N/A; Endline survey will inform this indicator
| Outcome Indicator 1.2 % of FHHs (including military and war widows) beneficiaries who have used the grant provided to establish or upscale an existing business venture, disaggregated by widow type. | 0% | At least 50% of grant recipients | Implementation ongoing- EE curriculum development | 30% of FHH (including military and war widows) beneficiaries used the grant provided to establish or upscale an existing business by end of 4th quarter | 0; Curriculum developed and training ongoing | Beneficiaries selected in Anuradhapura and Kurunegala; Trainings started.
Outcome 2: Increased commitment of public institutions to prevent and respond to sexual bribery and to protect female heads of households, including military and war widows from sexual exploitation | Outcome Indicator 2.1 # of Circulars/ guidelines/ policies which incorporate explicit commitment and/ or accountability measures within the public sector to prevent and respond to sexual bribery and exploitation. | 1 | 2 | 0 | 1 new circulars/guidelines/policies by end of 4th quarter | 0 | --
| Outcome Indicator 2.2 # of complaints received and action taken by the Anti- Sexual Harassment Committees | 0 | 5 | 0 | N/A | 0; consultation (s) taking place | --; Target: 5 complaints received and action taken by end of 5th quarter

## Output 1.1
Expected Results | Indicators | Baseline | Overall Target | Q3 Target | Q3 Progress | Q4 Target | Q4 Progress | Q1 2020 Target | Q1 2020 Progress | Q2 2020 Progress | Q2 2020 Target
Output 1.1 Female heads of households, including military widows and war widows have increased knowledge of their rights and have access to complaint mechanisms on bribery.
Activity 1.1.1 Create/ strengthen collectives of military and war widows (inclusive of FHH) with a focus on asserting their rights and eliminating all forms of abuse. | Output indicator 1.1.1 # of widows’ collectives inclusive of FHH formed/ strengthened | 0 | 12 collectives created/ strengthened across 3 districts. | 9 | 54 created/ strengthened | 11 (?) | 7 created/ strengthened | Activity Completed and Target Reached 63 women's collectives created/strengthened as of Q1 2020 |  |  |  | UN Women
1.1.1.1 Mapping existing self-help groups and collectives. | # of self-help groups identified across the 3 districts | 0 | 30 | 0 | 21 | Activity Completed
1.1.1.2 Form new widows’ collectives (inclusive of FHH). | # of newly formed widows’ collectives | 0 | 12 collectives across 3 districts | 0 | 54 | 11 (?) | 7 | Activity Completed and Target Reached
1.1.1.3 District level capacity building sessions for reps of self-help groups and collectives. | # of self-help group reps capacitated | 0 | 6 district level sessions across 3 districts | 0 | 0 | 90 | 98 | -- | 147
1.1.1.4 District level and capacity building sessions with widows’ collectives (inclusive of FHH). | # of widows’ collectives capacitated | 0 | 15 sessions across 3 districts | 0 | 0 | 750 | 0 | --
1.1.1.5 Develop/revise and disseminate trilingual advocacy materials. | # of publications disseminated at the programmes | 0 | 1500 copies disseminated | 0 | 0 | 0 | 1300 | --
Activity 1.1.2 Conduct community-wide awareness programmes on “breaking the taboo” in relation to sexual bribery and exploitation through participatory methods such as ‘puppetry’ and ‘forum theatre’. | Output indicator 1.1.2 # of FHH (including military and war widows) that are members of collectives formed/ strengthened who have increased knowledge of their rights, disaggregated by type of widow | 0 | 750 across 3 Districts/ 6 awareness programme per district | 0 | 936 mobilized | 0 | 1092 mobilized | At least 250 widows after 1 year of implementation | 1119 (27 FHH in total including 8 war widow)
1.1.2.1 Awareness programmes in each district. | # of participants attending the awareness programmes | 0 | 750 | 0 | 0 | app. 1300 | 1268 (994 Female) | Target Reached
1.1.2.2. District-level public events with govt officials & women CSOs on SB. | #of government officials and members of CSO/ women’s organizations attending the event | 0 | 100 | 0 | 0 | 0 | 0
1.1.2.3 Social media awareness raising. | # of responses through social media engagement | 0 | 50 | 0 | 0 | 0 | 0 | 1,773,159 total reach with 20,623 comments, likes and shares
1.1.2.4 Newspaper articles, advertisements and at online Articles in the mainstream media. | # of articles/ advertisements of SB published on mainstream media | 0 | 25 | 0 | 0 | 0 | 0 | 6 articles in online and paper-based newspapers
1.1.2.5 Say No to SB/SE production and airtime in three languages. | # of times productions aired in 3 languages | 0 | 30 | 0 | 0 | 0 | 0 | 76 radio spots on two island-wide radio stations
1.1.2.6 Talk shows on national television in three languages. | # of talk shows completed | 0 | 3 | 0 | 0 | 0 | 0 | In discussion with contracted media firm Ngage
Activity 1.1.3 Conduct legal aid and documentation mobile clinics in ‘safe spaces’ linking with CSOs and Women Development Officers of the MWCA for delivery and develop and disseminate an information brochure of service providers together with a SOP on accessing these services collectively | Output indicator 1.1.3 % of FHH (including military and war widows) trained to access legal and other services, disaggregated by type of widow. | 0 | 70% of FHH (including military and war widows) within collectives trained | 0 | 0 | 25% of FHH (including military and war widows) within collectives trained by 4th quarter | 0 | Consultations in planning with district implementing partners and legal professionals to strategize on activities 1.1.3.1 - 1.1.3.6 moving forward as "women from the existing SHGs/WCs will not be willing to come forward to receive legal support concerning SB/SE given the existing culture of impunity, shame and stigma attached to the issue"
1.1.3.1 Prepare and print user-friendly trilingual awareness raising material | # of trilingual awareness raising material printed and disseminated | 0 | 1500 | 0 | 0 | 0 | 1300 | --
1.1.3.2 district-level & national level workshops to raise awareness/ capacitate officials on SB/SE. | # of officers made aware and capacitated with knowledge of SB/SE. | 0 | 160 | 0 | 0 | 0 | 0 | --
1.1.3.3 TOT for identified potential resource persons from the above workshops to conduct the sensitization programmes at district and divisional levels | # of potential resource persons trained | 0 | 30 | 0 | 0 | 0 | 0 | --
1.1.3.4 Conduct district level mobile legal and documentation clinics for widows (inclusive of FHH). | # of women provided with legal aid | 0 | 150 | 0 | 0 | 0 | 0 | --
1.1.3.5 Follow up meetings with stake holders regarding issues raised and documented during the mobile clinics | # of issues raised followed up | 0 | 30 | 0 | 0 | 0 | 0 | --
1.1.3.6 Consultations (in Colombo and districts) with CSOs and service providers providing legal support to factor in SB/SE into their mandate and services | # of CSO reps and service providers that participated in the consultations | 0 | 90 | 0 | 0 | 0 | 0 | --
Activity 1.1.4 Develop a pilot complaint reporting platform to report incidents of sexual bribery and exploitation, available online, through a mobile application and offline via SMS messaging, with geo-tagging location features. | Output Indicator 1.1.4 # of users accessing the online/offline complaints reporting platform | 0 | 100 | 0 | 0 | 0 | 0 | Activities 1.1.4.1 to 1.1.4.8 delayed due to the outbreak of CoVid-19, limited availability of time to conduct test runs and community consultations and unavailability of CIABOC officers to be involved in the process of developing and testing the app. Q1 2020 initial target - Platform developed and launched by 5th quarter.
1.1.4.1 Identify and commission suitable telecommunication partner to provide technical support. | Telecommunication partner selected from identified service providers | 0 | 1 | 0 | 0 | 1 | 0 | Recruitment ongoing as of 28/04/2020
1.1.4.2 Conduct consultations with stakeholders to add value and for CIABOC to feed into their existing complaints systems and procedures | # of consultations held | 0 | 3 | 0 | 1 | 1 | 2 consultations | --
1.1.4.3 Developing the app & linking to the website | # of persons that access website an App | 0 | 50 | 0 | 0 | 0 | 0 | --
1.1.4.4 Pilot testing with select collectives and front-line officials | # of widows and front line officials trained to use and respond to app complaints | 0 | 15 | 0 | 0 | 0 | 0 | --
1.1.4.5 District level Capacity building/ gender sensitization sessions of relevant officers who will handle new systems | # of officers trained to handle information gathered through the new system | 0 | 60 | 0 | 0 | 0 | 0 | --
1.1.4.6 Launch event/ integration of the systems into CIABOCs overall system. | Launch event held | 0 | 1 | 0 | 0 | 0 | 0 | --
1.1.4.7 Dissemination of advocacy material of the APP | # of advocacy materials disseminated | 0 | 500 | 0 | 0 | 0 | 0 | --
1.1.4.8 TOT's on the use of the application for public officials, civil society and SH Committees at SLIDA. | # of government officers trained to use the application | 0 | 150 | 0 | 0 | 0 | 0 | --
Activity 1.1.5 Provide widows’ collectives (inclusive of FHH) with leadership and life skills training, and strengthen them through the formation of cross-regional alliances to build social cohesion and to cope with SB/SE. | # of widow’s collectives trained | 0 | 100 | 0 | 0 | 90 | 0 | Scoping mission report submitted on 10 March 2020; The methodology, curriculum and the beneficiary selection criteria and processes based on baseline/perceptions survey of the two-day capacity building trainings and peacebuilding dialogues were submitted by the consultant.
1.1.5.1 Structured Exchange visits for widows’ collectives (inclusive of FHH) to cope with SB/SE. | # of MWs and WWs taking part in the exchange visit | 0 | 90 | 0 | 0 | 0 | 0 | --
1.1.5.2 Widows’ collectives (inclusive of FHH) (from 1.1.1) sharing of best practices of coping strategies at district level inter community common forum | # of MW and WW reps participating in the forum | 0 | 30 | 0 | 0 | 0 | 0 | --
1.1.5.3 Compilation of district level coping strategies. | coping strategy compiled | 0 | 1 | 0 | 0 | 0 | 0 | --
1.1.5.4 Support DS level village meetings to share the coping strategies with the women | # of women made aware of coping strategies | 0 | 150 | 0 | 0 | 0 | 0 | --
1.1.5.1 (a) Conduct a perception survey on widows (inclusive of FHH) and their adolescent children/youth in all three district | completed survey | in progress |  |  |  | baseline/perceptions survey completed
1.1.5.2 (b) Dialogues (based on the findings of the perception survey) with widows (inclusive of FHH) from each district to identify and achieve consensus on their role in peacebuilding. This would be succeeded by follow-up workshops at the end of the project. | # of dialogues/follow-up workshops # of participants | 0 | 0 | 0 | 0 | 0 | 0 | Planned dialogues in April 2020 postponed due to COVID-19
1.1.5.3 (c) Trainings for widows (inclusive of FHH) on leadership and life skills | # of trainings | 0 | 0 | 0 | 0 | 0 | 0 | See above. Planned workshops in April 2020 postponed due to COVID-19
Activity 1.1.6 Provide guidance and strategies to widows’ collectives (inclusive of FHH) to identify and respond to at-risk or negative changes in the behaviour of young/ adolescent children (to break the intergenerational impact of conflict). | n/a
1.1.6.1 Train WDOs and child (rights) protection officers to provide guidance and strategies to widows’ collectives (inclusive of FHH) to identify and respond to at-risk or negative changes in the behaviour of young/ adolescent children. | # of WDOs and child (rights) protection officers trained to identify at-risk or negative changes in the behaviour of young/ adolescent children. | 0 | 60 | 0 | 0 | 0 | 0 | 90+ WDOs and child (rights) protection officers, counseling officers
1.1.6.2 Training the widows’ collectives (inclusive of FHH) on identifying at-risk behaviour of their children etc. | # of widows collectives trained to identify at-risk or negative changes in the behaviour of young/ adolescent children. | 0 | 30 | 0 | 0 | 0 | 0 | 66 representatives of WCs/ SHGs in Kurunegala and Kilinochchi
1.1.6.3 Link FHH (inclusive of MW and WW) to support structures such as WIN, Shanthiham and counselors and child support organizations. | #of women referred to support services | 0 | 30 | 0 | 0 | 0 | 0 | --
Note on F3: User: JSAC 9 Viluthu 14 RPK 17 WRC 14
Note on G3: User: Based on October M&E meeting
Note on F4: User: CEJ Q1 & Q2 report
Note on G6: User: 30 per district
Note on H6: Mona Damdinjav: Law referrals trainings in three districts; Psychosocial in Kurunegala only
Note on J6: Mona Damdinjav: 49 from two-day psychosocial trainings in Anuradhapura and Kilinochchi; Double-counted currently
Note on G7: User: 250 collective members per district to receive training from 90 capacitated reps/CEJ/partners
Note on H8: Mona Damdinjav: 1850 if counting RTI and TISL or reprinting of existing documents
Note on F9: User: War widows 155 Military widows 257 Military widows disabled 20 Other FHH 504
Note on H9: Mona Damdinjav: War widows 176 (?) Military widows 311 Other FHH 605 Kilinochchi: 132 War widows (?) Anuradhapura: 92 Military widows Kurunegala: 219 Military widows
Note on G10: User: minimum of 800 individuals (including collective members) through the 12 puppet shows across Anuradhapura and Kurunegala minimum of 300 individuals via forum theatre in Kilinochchi
Note on H10: Mona Damdinjav: 12 shows total in Anuradhapura and Kurunegala;
Note on I16: Mona Damdinjav: CEJ Q1 2020 report
Note on H17: Mona Damdinjav: Same as 1.1.1.5
Note on F25: User: Design thinking workshop 24 September
Note on G25: User: Follow-up roundtable with CIABOC and HRCSL planned.
Note on G32: User: 30 reps of collectives per districts at phase 1 training noted in 1.1.1.3
Note on I42: Mona Damdinjav: Anuradhapura training postponed due to COVID-19

## Activity 1.1
Output 1.1 Female heads of households, including military widows and war widows have increased knowledge of their rights and have access to complaint mechanisms on bribery. | COLOMBO/NATIONWIDE |  |  | ANURADHAPURA (RPK) |  |  | KURUNEGALA (WRC) |  |  | KILINOCHCHI (JSAC and Viluthu)
| Date | Event Type | Target Beneficiaries | Date | Event Type | Target Beneficiaries | Date | Event Type | Target Beneficiaries | Date | Event Type | Target Beneficiaries
Activity 1.1.1 Create/ strengthen collectives of military and war widows (inclusive of FHH) with a focus on asserting their rights and eliminating all forms of abuse.
1.1.1.1 Mapping existing self-help groups and collectives. |  |  |  | Completed; Report submitted to UN Women 30 September 2019
1.1.1.2 Form new widows’ collectives (inclusive of FHH). |  |  |  | Completed; 21 collectives with 409 members December 2019 |  |  | Completed; 14 collectives with 230 members December 2019 |  |  | Completed; 28 collectives (JSAC 9 with 144 and Viluthu 19 with 336) with 480 members April 2020
1.1.1.3 District level capacity building sessions for reps of self-help groups and collectives. |  |  |  | 8/12/2019; 31/01/2020 01/02/2020 | One-day workshop on law and referrals; Two-day psychosocial workshop | Representatives of self-help groups and collectives | 16/12/2019; 17/12/2019 18/12/2019 | One-day law and referrals workshop; Two-day psychosocial workshop | Representatives of self-help groups and collectives | 16/10/2019; 09/01/2020 10/01/2020 | One-day workshop on law and referrals; Two-day psychosocial workshop | Representatives of self-help groups and collectives
1.1.1.4 District level and capacity building sessions with widows’ collectives (inclusive of FHH).
1.1.1.5 Develop/revise and disseminate trilingual advocacy materials. |  |  |  | 1300 CEJ's sexual bribery leaflet distributed by December 2019
Activity 1.1.2 Conduct community-wide awareness programmes on “breaking the taboo” in relation to sexual bribery and exploitation through participatory methods such as ‘puppetry’ and ‘forum theatre’.
1.1.2.1 Awareness programmes in each district. |  |  |  | 08/10/2019; 09/10/2019; 10/10/2019; | Six awareness raising puppet shows | General public, members of women's collectives and state officials from six villages - Kakirawa, Galnawa, Anuradhapura, Oyamaduwa, Kabithigollawa and Galenbidunuwewe | 15/10/2019; 16/10/2019; 17/10/2019; | Six awareness raising puppet shows | General public, members of women's collectives and state officials from six villages - Rideegama, Mawathagama, Thithtwelgala, Malkaduwawa, Godagama, Mudunduwa
1.1.2.2. District-level public events with govt officials & women CSOs on SB.
1.1.2.3 Social media awareness raising. | Three FB pages officially launched and operating since December 2019 with awareness raising content and 1923 followers; Total campaign reach 1,773,159 with 20,623 comments, likes and shares as of April 2020
1.1.2.4 Newspaper articles, advertisements and at online Articles in the mainstream media. | Total of six articles (four in English) published in online and paper-based newspapers as of April 2020
1.1.2.5 Say No to SB/SE production and airtime in three languages. | 76 Sinhalese and Tamil spots aired on radio stations Neth FM and Vasantham FM with island-wide coverage in February and March 2020
1.1.2.6 Talk shows on national television in three languages.
Activity 1.1.3 Conduct legal aid and documentation mobile clinics in ‘safe spaces’ linking with CSOs and Women Development Officers of the MWCA for delivery and develop and disseminate an information brochure of service providers together with a SOP on accessing these services collectively
1.1.3.1 Prepare and print user-friendly trilingual awareness raising material | Consultations in planning for Q2 2020 with district implementing partners and legal professionals to strategize on activities 1.1.3.1 - 1.1.3.6 moving forward as "women from the existing SHGs/WCs will not be willing to come forward to receive legal support concerning SB/SE given the existing culture of impunity, shame and stigma attached to the issue" |  |  | 1300 CEJ's sexual bribery leaflet distributed by December 2019
1.1.3.2 district-level & national level workshops to raise awareness/ capacitate officials on SB/SE.
1.1.3.3 TOT for identified potential resource persons from the above workshops to conduct the sensitization programmes at district and divisional levels
1.1.3.4 Conduct district level mobile legal and documentation clinics for widows (inclusive of FHH).
1.1.3.5 Follow up meetings with stake holders regarding issues raised and documented during the mobile clinics
1.1.3.6 Consultations (in Colombo and districts) with CSOs and service providers providing legal support to factor in SB/SE into their mandate and services
Activity 1.1.4 Develop a pilot complaint reporting platform to report incidents of sexual bribery and exploitation, available online, through a mobile application and offline via SMS messaging, with geo-tagging location features.
1.1.4.1 Identify and commission suitable telecommunication partner to provide technical support. | Ongoing as of 28/04/2020; Activities 1.1.4.1 to 1.1.4.8 delayed due to the outbreak of COVID-19, limited availability of time to conduct test runs and community consultations and unavailability of CIABOC officers to be involved in the process of developing and testing the app. Q1 2020 initial target - Platform developed and launched by 5th quarter.
1.1.4.2 Conduct consultations with stakeholders to add value and for CIABOC to feed into their existing complaints systems and procedures | 24/09/2019; 19/11/2019 | Design thinking Workshop; Follow-up Roundtable Discussion | Representatives from district-level CSO partners, Human Rights Commission, Bribery Commission, Police, NGO sector, Telco, and Tech industries.
1.1.4.3 Developing the app & linking to the website
1.1.4.4 Pilot testing with select collectives and front-line officials
1.1.4.5 District level Capacity building/ gender sensitization sessions of relevant officers who will handle new systems
1.1.4.6 Launch event/ integration of the systems into CIABOCs overall system.
1.1.4.7 Dissemination of advocacy material of the APP
1.1.4.8 TOT's on the use of the application for public officials, civil society and SH Committees at SLIDA.
Activity 1.1.5 Provide widows’ collectives (inclusive of FHH) with leadership and life skills training, and strengthen them through the formation of cross-regional alliances to build social cohesion and to cope with SB/SE.
1.1.5.1 Structured Exchange visits for widows’ collectives (inclusive of FHH) to cope with SB/SE.
1.1.5.2 Widows’ collectives (inclusive of FHH) (from 1.1.1) sharing of best practices of coping strategies at district level inter community common forum
1.1.5.3 Compilation of district level coping strategies.
1.1.5.4 Support DS level village meetings to share the coping strategies with the women
1.1.5.1 (a) Conduct a perception survey on widows (inclusive of FHH) and their adolescent children/youth in all three district |  |  |  | Completed; SSA report submitted to UN Women 04 December 2019
1.1.5.2 (b) Dialogues (based on the findings of the perception survey) with widows (inclusive of FHH) from each district to identify and achieve consensus on their role in peacebuilding. This would be succeeded by follow-up workshops at the end of the project. |  |  |  | Date to be confirmed; Delayed due to COVID-19 | Two-day dialogue program on peacebuilding and consensus | Approximately 40 (per work plan) military widows from Kekirawa, Nuwaragam Palatha Central, Mahawilachchiya, Kebithigollewa, Galnewa, Nuwaragam Palatha East, Galenbindunu Wewa. (who are having leadership skill, good communication skill, interest in reconciliation & other skills) | Date to be confirmed; Delayed due to COVID-19 | Two-day dialogue program on peacebuilding and consensus | Approximately 40 (per work plan) military widows from Kurunegala Polgahawela Rideegama Mawathgama Ibbagamuwa Wariyapola Nikaweratiya Galgamuwa | Date to be confirmed; Delayed due to COVID-19 | Two-day dialogue program on peacebuilding and consensus | Approximately 40 (per work plan) war widows from Karachchi Poonakary Pachchilapalli
1.1.5.3 (c) Trainings for widows (inclusive of FHH) on leadership and life skills |  |  |  | Date to be confirmed; Delayed due to COVID-19 | Two-day capacity development training on developing leadership skill, Communication skill, Problem analyzing & Solving, involving reconciliation process, action plan preparing, and other | Approximately 40 (per work plan) military widows from Kekirawa, Nuwaragam Palatha Central, Mahawilachchiya, Kebithigollewa, Galnewa, Nuwaragam Palatha East, Galenbindunu Wewa. (who are having leadership skill, good communication skill, interest in reconciliation & other skills) | Date to be confirmed; Delayed due to COVID-19 | Two-day capacity development training on developing leadership skill, Communication skill, Problem analyzing & Solving, involving reconciliation process, action plan preparing, and other | Approximately 40 (per work plan) military widows from Kurunegala Polgahawela Rideegama Mawathgama Ibbagamuwa Wariyapola Nikaweratiya Galgamuwa | Date to be confirmed; Delayed due to COVID-19 | Two-day capacity development training on developing leadership skill, Communication skill, Problem analyzing & Solving, involving reconciliation process, action plan preparing, and other | Approximately 40 (per work plan) war widows from Karachchi Poonakary Pachchilapalli
Activity 1.1.6 Provide guidance and strategies to widows’ collectives (inclusive of FHH) to identify and respond to at-risk or negative changes in the behaviour of young/ adolescent children (to break the intergenerational impact of conflict).
1.1.6.1 Train WDOs and child (rights) protection officers to provide guidance and strategies to widows’ collectives (inclusive of FHH) to identify and respond to at-risk or negative changes in the behaviour of young/ adolescent children. |  |  |  | 06/02/2020 18/02/2020 | Two-day capacity building workshop | 26+ WDOs and child (rights) protection and promotion officers, counseling officers | 24/02/2020 25/02/2020 | Two-day capacity building workshop | 43 WDOs and child (rights) protection and promotion officers, counseling officers | 2020-12-03 | One-day capacity building workshop | 21 WDOs and child (rights) protection and promotion officers, counseling officers
1.1.6.2 Training the widows’ collectives (inclusive of FHH) on identifying at-risk behaviour of their children etc. | [6 empty] | 26/02/2020 | One-day workshop | 27 representatives of WCs/ SHGs | 25/02/2020 | One-day workshop | 39 representatives of WCs/ SHGs
1.1.6.3 Link FHH (inclusive of MW and WW) to support structures such as WIN, Shanthiham and counselors and child support organizations.
Note on B13: Mona Damdinjav: Eng page link- https://www.facebook.com/101476694684832/photos/rpp.101476694684832/128347431997758/?type=3&theater Disaggregation: English (625,804 reach + 4980 comments, likes and shares) + Sinhalese (852,912 reach + 14,039 comments, likes and shares) + Tamil (294,443 reach + 1604 comments, likes and shares)
Note on B14: Mona Damdinjav: Article 1- Quid pro quo: a study of sexual bribery in Sri Lanka Article 2- Through my eyes: how sexual bribery seeps into the everyday Published in Daily FT, Daily Mirror, Daily Island, Veerakesari and Mawbima
Note on B15: Mona Damdinjav: Additional in planning
Note on E18: Mona Damdinjav: same as 1.1.1.5

## Output 1.2
Expected Results | Indicators | Baseline | Overall Target | Q3 Target | Q3 Progress | Q4 Target | Q4 Progress | Q1 2020 Target | Q1 2020 Progress | Q2 2020 Progress | Q2 2020 Target
Output 1.2 Civil society Is strengthened to provide services for the protection of victims of sexual exploitation and sexual bribery
Activity 1.2.1 Capacity building of civil society actors to provide services, information and referrals to victim survivors of sexual bribery and exploitation | Output Indicator 1.2.1 # of civil society organizations who are increasingly providing services, information and referrals for FHH including war and military widows | 0 | 10 | 0 | 4 | 5 | 0 | 4 implementing partners (additional CSOs have participated in capacity building) |  |  |  | UNW | UNDP
1.2.1.1 Three district level capacity building workshops to Civil Society organizations including women’s organizations partners | # of participants representing CSO and women’s organizations capacitated | 0 | 60 | 0 | 0 | 0 | 0 | 50+ CSO representatives in Kurunegala and Anuradhapura
1.2.1.2 Technical support to partner organisations on enhancing provision of services to survivors (supporting the filing of cases, follow up, documentation etc. | # of partner organizations provided with technical support to assist victim survivors of SB/SE | 0 | 4 | 0 | 0 | 0 | 0 | --
Activity 1.2.2 Support civil society on lobbying and advocating with national institutions and independent commissions to institutionalize response to complaints of sexual bribery (through setting up of special complaints mechanisms, gender- sensitive policies and procedures to investigate and handle sexual bribery cases). | Output Indicator 1.2.2 # of FHH (including military and war widows) provided with legal assistance through CSOs | 0 | 50 | 0 | 0 | 0 | 0 | --; Q1 2020 target 20 |  |  | 30
1.2.2.1 National and district level sensitization workshops for CSOs on SB/SE and response mechanisms | # of public officials sensitized on SB/SE | 0 | 150 | 0 | 0 | 0 | 0 | --
1.2.2.2 Capacity building of CSOs on effective advocacy and campaigning/serving as a 'watchdog' mechanism on SB/SE and form an advocacy group | # of capacity building trainings; one advocacy group formed | 0 | 0 | 0 | 0 | 0 | 0 | --
Activity 1.2.3 CSOs provide free legal aid to female heads of households, including war and military widows who are willing to file a complaint. | Output Indicator 1.2.3 # of complaints filed by FHH (including military and war widows). | 0 | 20 | 0 | 0 | 0 | 0 | --; Q1 2020 target 5
1.2.3.1 Two CSOs in different districts provide legal assistance to widows (UNDP) | # of CSOs | 0 | 2 CSOs per district? | 0 | 0 | 0 | 0 | --
Note on F3: User: 4 district-level partners
Note on I4: Mona Damdinjav: Two-day workshops in Colombo and Kilinochchi CSOs postponed due to COVID-19
Note on I9: Mona Damdinjav: Review comments under Activity 1.1.3

## Activity 1.2
Output 1.2 Civil society Is strengthened to provide services for the protection of victims of sexual exploitation and sexual bribery | COLOMBO/NATIONWIDE |  |  | ANURADHAPURA (RPK) |  |  | KURUNEGALA (WRC) |  |  | KILINOCHCHI (JSAC and Viluthu)
| Date | Event Type | Target Beneficiaries | Date | Event Type | Target Beneficiaries | Date | Event Type | Target Beneficiaries | Date | Event Type | Target Beneficiaries
Activity 1.2.1 Capacity building of civil society actors to provide services, information and referrals to victim survivors of sexual bribery and exploitation
1.2.1.1 Three district level capacity building workshops to Civil Society organizations including women’s organizations partners |  |  |  | 11/03/2020 12/03/2020 | Two-day sensitization/capacity building workshops with puppetry | 26 CSO representatives (including implementing partners and organizations focused on gender issues) | 06/03/2020 07/03/2020 | Two-day sensitization/capacity building workshops with puppetry | 24 CSO representatives (including implementing partners and organizations focused on gender issues) |  |  |  | UNW | UNDP
1.2.1.2 Technical support to partner organisations on enhancing provision of services to survivors (supporting the filing of cases, follow up, documentation etc.
Activity 1.2.2 Support civil society on lobbying and advocating with national institutions and independent commissions to institutionalize response to complaints of sexual bribery (through setting up of special complaints mechanisms, gender- sensitive policies and procedures to investigate and handle sexual bribery cases).
1.2.2.1 National and district level sensitization workshops for CSOs on SB/SE and response mechanisms
1.2.2.2 Capacity building of CSOs on effective advocacy and campaigning/serving as a 'watchdog' mechanism on SB/SE and form an advocacy group
Activity 1.2.3 CSOs provide free legal aid to female heads of households, including war and military widows who are willing to file a complaint.
1.2.3.1 Two CSOs in different districts provide legal assistance to widows (inclusive of FHH) (UNDP)

## Output 1.3
Expected Results | Indicators | Baseline | Overall Target | Q3 Target | Q3 Progress | Q4 Target | Q4 Progress | Q1 2020 Target | Q1 2020 Progress | Q2 2020 Progress | Q2 2020 Target
Output 1.3 Female heads of households, including military widows and war widows increase their entrepreneurial knowledge and skills
Activity 1.3.1 Conduct a needs assessment in targeted districts to understand gaps in skills and capacities of FHH (including military and war widows), and value chain analysis in identified sectors to understand market opportunities | Output Indicator 1.3.1 # of FHH (including military and war widows) who are trained to commence a business or enterprise. | TBD | 280 FHH (including military and war widows) | 0 | 0 | 140 | 0 | 69 FHH (including military widows) in trained Kurunegala as of April 2020 |  |  |  | UNW/Chrysalis/ISB | UNDP/Chrysalis/ISB
1.3.1.1 Conduct needs assessment in 3 districts | completed needs assessment | in progress |  |  |  |  | completed
1.3.1.2 Identify and conduct value chain analysis in 3 districts (in 2-3 sectors) | completed value chain analysis | in progress |  |  |  |  | in progress (report submitted for review) and WEE training programme piloted successfully in Kilinochchi with funding from another donor
1.3.1.3 Develop programme design for output 1.3 | developed programme | in progress
Activity 1.3.2 Provide skills training (product development and use of technology) and capacity building on business management (business planning, financial literacy and management, particularly information on accessing loans and linking with credible lending institutions, and marketing for FHH (including military and war widows) in identified sectors. | Output Indicator 1.3.2 # of FHH (including military and widows) provided with grants, disaggregated by type of widow. | 0 | 200 FHH (including military and war widows) (based on the strength and quality of proposals submitted) | 0 | 0 | 100 FHH (including military and war widows) have received special grants by end of 4th quarter | 0 | Beneficiary selection process completed in Kurunegala (114+ military widows) and Anuradhapura (81 (50 military widows); Planned trainings postponed due to COVID-19
1.3.2.1 Training for FHH (including military and war widows) on product development and use of technology related to specific sectors (3 workshops per district) | # of workshops | 0 | 9 (3 per district) | 0 | 0 | 0 | 0 | 2 workshops completed in Kurunegala (Two-day Product Development)
1.3.2.2 Training for front-line government officials (WDOs, EDO, Vidatha Officers) to provide business advisory services (12 divisions) | # of workshops | 0 | 12 divisions | 0 | 0 | 0 | 0 | --
1.3.2.3 Training on marketing (3 workshops per district) | # of workshops | 0 | 9 (3 per district) | 0 | 0 | 0 | 0 | --
1.3.2.4 Conduct 14 capacity building training programs (each 5 day duration) for FHH (including military and war widows) on business management skills (business planning, financial literacy and management particularly information accessing loans and linking with credible linking institutions and markets) 20 widows each training | # of trainings | 0 | 14 (with 20 widows at each training) | 0 | 0 | 0 | 0 | Beneficiary selection process completed in Kurunegala (114+ military widows) and Anuradhapura (81 (50 military widows); Planned trainings postponed due to COVID-19
1.3.2.5 Facilitation the preparation of viable new business proposals or proposals to upscale existing businesses of FHH (including military and war widows) (during and post training) | n/a | 0 | 0 | 0 | 0 | 0 | 0 | --
Activity 1.3.3 Support FHH (including military and war widows) to access markets and points-of-sale by linking them to Ranaviru villages, cooperatives, 'Hela Bojun Hala'/'Ammaarchi' outlets in the target areas, potential private sectors and existing UNDP supported women's associations and producer groups. | Output Indicator 1.3.3 # of Diversity Market Fairs held. | 2 | Target: 4 - 1 in each project district and 1 in Colombo) | 0 | 0 | 2 | 0 | --
1.3.3.1 Identify existing markets and points-of-sale including UNDP existing linkages | # of markets identified | 0 | 0 | 0 | 0 | 0 | 0 | --
1.3.3.2 Conduct 3 workshops in the 3 districts | # of workshops | 0 | 3 | 0 | 0 | 0 | 0 | --
Activity 1.3.4 Support entrepreneurship by setting up mentoring programmes linking widow collectives (inclusive of FHH) with successful women entrepreneurs, regional Chambers of Commerce and Women's Chambers of Commerce, together with the MWCA | n/a
1.3.4.1 Identify mentors through the Chambers of Commerce and other networks to link with widow collectives (inclusive of FHH) in the three districts +1 (UNW and UNDP) | # of mentors identified | 0 | 0 | 0 | 0 | 0 | 0 | 59 identified (4 women entrepreneurs from Colombo and 55 entrepreneurs from three districts)
1.3.4.2 Six workshops at the district level connecting mentors and mentees to jointly design an action plan on how to support widows' enterprises (inclusive of FHH) (3 by UNW and 3 by UNDP) | # of workshops | 0 | 3 | 0 | 0 | 0 | 0 | --
1.3.4.3 Follow-up workshop on progress | # of workshops | 0 | 0 | 0 | 0 | 0 | 0
1.3.4.1 Identify mentors through the Chambers of Commerce and other networks to link with widow collectives (inclusive of FHH) in the three districts +1 (UNW and UNDP) | # of mentors identified | 0 | 0 | 0 | 0 | 0 | 0 | 59 identified (4 women entrepreneurs from Colombo and 55 entrepreneurs from three districts)
1.3.4.2 Six workshops at the district level connecting mentors and mentees to jointly design an action plan on how to support widows' enterprises (inclusive of FHH) (3 by UNW and 3 by UNDP) | # of workshops | 0 | 3 | 0 | 0 | 0 | 0 | --
1.3.4.3 Follow-up workshop on progress | # of workshops | 0 | 0 | 0 | 0 | 0 | 0 | --
Activity 1.3.5 Provide special grants to identified FHH (including military and war widows) for a viable, innovative up-market business venture or scaling up of an existing venture (following the capacity building programmes) via a 'competitive challenge' exclusively for military and war widows where contenders will present business proposals which will be judged by an independent selection panel. | see output indicator 1.3.2
1.3.5.1 Follow-up on ensuring the submission of business proposals by FHH (including military and war widows). | # of business proposals | 0 | 0 | 0 | 0 | 0 | 0 | --
1.3.5.2 Presentation of business proposals at district level forums (6 forums) | # of forums | 0 | 6 | 0 | 0 | 0 | 0 | --
Activity 1.3.6 Conduct 'exposure visits' where entrepreneurs (FHH including military and war widows) from the North and South showcase their products in "Diversity Market fairs" held on rotational basis in all project locations to foster cross-regional learning, build social cohesion and inter-linkages for peace (including ILO/WFP PTK Cooperative) | see output indicator 1.3.3
1.3.6.1 Conduct 3 diversity market fairs (one in each district) organised- inclusive of neighboring non-project districts- where successful entrepreneurs and project beneficiaries showcase best practices/success stories | # of fairs | 0 | 3 | 0 | 0 | 0 | 0 | --
1.3.6.2 Conduct 3 district-level experience sharing sessions by a select number of entrepreneurs (FHH including military and war widows) from different project districts (cross-regional learning)- include ILO/WFP PTK Cooperative | # of experience sharing sessions | 0 | 3 | 0 | 0 | 0 | 0 | --
1.3.6.1 Conduct 3 diversity market fairs (one in each district) organised- inclusive of neighboring non-project districts- where successful entrepreneurs and project beneficiaries showcase best practices/success stories | # of fairs | 0 | 3 | 0 | 0 | 0 | 0 | --
1.3.6.2 Conduct 3 district-level experience sharing sessions by a select number of entrepreneurs (FHH including military and war widows) from different project districts (cross-regional learning)- include ILO/WFP PTK Cooperative | # of experience sharing sessions | 0 | 3 | 0 | 0 | 0 | 0 | --
Note on I20: Mona Damdinjav: Repeat of above 1.3.4.1 Color coding is for UNW/UNDP differentiation

## Activity 1.3
Output 1.3 Female heads of households, including military widows and war widows increase their entrepreneurial knowledge and skills | COLOMBO/NATIONWIDE |  |  | ANURADHAPURA |  |  | KURUNEGALA |  |  | KILINOCHCHI
| Date | Event Type | Target Beneficiaries | Date | Event Type | Target Beneficiaries | Date | Event Type | Target Beneficiaries | Date | Event Type | Target Beneficiaries
Activity 1.3.1 Conduct a needs assessment in targeted districts to understand gaps in skills and capacities of FHH (including military and war widows), and value chain analysis in identified sectors to understand market opportunities
1.3.1.1 Conduct needs assessment in 3 districts |  |  |  | Completed by 04 December 2019 and report submitted to UN Women.
1.3.1.2 Identify and conduct value chain analysis in 3 districts (in 2-3 sectors) |  |  |  | Draft reports submitted to UN Women. | [8 empty] | UNW/Chrysalis/ISB | UNDP/Chrysalis/ISB
1.3.1.3 Develop programme design for output 1.3 |  |  |  | Draft reports submitted to UN Women.
Activity 1.3.2 Provide skills training (product development and use of technology) and capacity building on business management (business planning, financial literacy and management, particularly information on accessing loans and linking with credible lending institutions, and marketing for FHH (including military and war widows) in identified sectors.
1.3.2.1 Training for FHH (including military and war widows) on product development and use of technology related to specific sectors (3 workshops per district) | [6 empty] | 10/03/2020 11/03/2020; 12/03/2020 13/03/2020 | Two days training session on Product Development for 2 batches (Total of 8 Batches to be completed) | 69 FHH and MWs
1.3.2.2 Training for front-line government officials (WDOs, EDO, Vidatha Officers) to provide business advisory services (12 divisions)
1.3.2.3 Training on marketing (3 workshops per district)
1.3.2.4 Conduct 14 capacity building training programs (each 5 day duration) for FHH (including military and war widows) on business management skills (business planning, financial literacy and management particularly information accessing loans and linking with credible linking institutions and markets) 20 widows each training
1.3.2.5 Facilitation the preparation of viable new business proposals or proposals to upscale existing businesses of FHH (including military and war widows) (during and post training)
Activity 1.3.3 Support FHH (including military and war widows) to access markets and points-of-sale by linking them to Ranaviru villages, cooperatives, 'Hela Bojun Hala'/'Ammaarchi' outlets in the target areas, potential private sectors and existing UNDP supported women's associations and producer groups.
1.3.3.1 Identify existing markets and points-of-sale including UNDP existing linkages
1.3.3.2 Conduct 3 workshops in the 3 districts
Activity 1.3.4 Support entrepreneurship by setting up mentoring programmes linking widow collectives (inclusive of FHH) with successful women entrepreneurs, regional Chambers of Commerce and Women's Chambers of Commerce, together with the MWCA
1.3.4.1 Identify mentors through the Chambers of Commerce and other networks to link with widow collectives (inclusive of FHH) in the three districts +1 (UNW and UNDP) | 59 identified (4 women entrepreneurs from Colombo and 55 entrepreneurs from three districts)
1.3.4.2 Six workshops at the district level connecting mentors and mentees to jointly design an action plan on how to support widows' enterprises (inclusive of FHH) (3 by UNW and 3 by UNDP)
1.3.4.3 Follow-up workshop on progress
1.3.4.1 Identify mentors through the Chambers of Commerce and other networks to link with widow collectives (inclusive of FHH) in the three districts +1 (UNW and UNDP) | 59 identified (4 women entrepreneurs from Colombo and 55 entrepreneurs from three districts)
1.3.4.2 Six workshops at the district level connecting mentors and mentees to jointly design an action plan on how to support widows' enterprises (inclusive of FHH) (3 by UNW and 3 by UNDP)
1.3.4.3 Follow-up workshop on progress
Activity 1.3.5 Provide special grants to identified FHH (including military and war widows) for a viable, innovative up-market business venture or scaling up of an existing venture (following the capacity building programmes) via a 'competitive challenge' exclusively for military and war widows where contenders will present business proposals which will be judged by an independent selection panel.
1.3.5.1 Follow-up on ensuring the submission of business proposals by FHH (including military and war widows).
1.3.5.2 Presentation of business proposals at district level forums (6 forums)
Activity 1.3.6 Conduct 'exposure visits' where entrepreneurs (FHH including military and war widows) from the North and South showcase their products in "Diversity Market fairs" held on rotational basis in all project locations to foster cross-regional learning, build social cohesion and inter-linkages for peace (including ILO/WFP PTK Cooperative)
1.3.6.1 Conduct 3 diversity market fairs (one in each district) organised- inclusive of neighboring non-project districts- where successful entrepreneurs and project beneficiaries showcase best practices/success stories
1.3.6.2 Conduct 3 district-level experience sharing sessions by a select number of entrepreneurs (FHH including military and war widows) from different project districts (cross-regional learning)- include ILO/WFP PTK Cooperative
1.3.6.1 Conduct 3 diversity market fairs (one in each district) organised- inclusive of neighboring non-project districts- where successful entrepreneurs and project beneficiaries showcase best practices/success stories
1.3.6.2 Conduct 3 district-level experience sharing sessions by a select number of entrepreneurs (FHH including military and war widows) from different project districts (cross-regional learning)- include ILO/WFP PTK Cooperative
Note on B21: Mona Damdinjav: Repeat of above 1.3.4.1 Color coding is for UNW/UNDP differentiation

## Output 2.1
Expected Results | Indicators | Baseline | Overall Target | Q3 Target | Q3 Progress | Q4 Target | Q4 Progress | Q1 2020 Target | Q1 2020 Progress | Q2 2020 Progress | Q2 2020 Target
Output 2.1 The capacity of public institutions and officials are built to prevent and respond to bribery and to protect female heads of households, including military and war widows from sexual exploitation.
Activities 2.1.1 Sensitization of public officials on sexual bribery and sexual exploitation as crimes, using ‘puppetry’ and ‘forum theatre’ to communicate the message in a non-contentious manner. | Output Indicator 2.1.1 # of sensitization programmes held for public officials on sexual harassment policies, legal frameworks, guidelines on response mechanisms, and accountability measures. | 0 | 20 | 0 | 0 | 10
2.1.1.1 National and district /divisional level sensitization workshops for public officials. | # of workshops | [10 empty] | UNW | UNDP
2.1.1.1 National and district /divisional level sensitization workshops for public officials. | # of workshops
Activities 2.1.2 Development of a special training programme for Public officials on handling complaints of sexual Exploitation and sexual bribery, in consultation with public training Institutions such as SLIDA/SLFI. | Output Indicator 2.1.2 # of public officials who complete the course on handling bribery complaints, including sexual bribery, harassment and exploitation. | TBC | 50 | 0 | 0 | 20
2.1.2.1 Draft, share and finalize special training module in consultation with the relevant institutions. | # of institutions consulted to draft training module | 0 | 3
2.1.2.2 TOT for SLIDA/SLFI trainers | # of officers participated at the ToT session | 0 | 60
2.1.2.3 Residential training programmes for public officials and SH Committees | # of SH committee members trained | 0 | 50
Activities 2.1.3 Capacity of National Human Rights Institutions are enhanced to receive and respond to complaints. | Output Indicator 2.1.3 # of legal aid clinics conducted by capacitated local public officers on preliminary assistance to survivors on possible legal remedies. | 0 | At least 15 legal aid clinics |  |  | 15 officers capacitated by end of 4th quarter.
2.1.3.1 Initiate discussions with Commissioners of HRC | # of discussions | 0
2.1.3.2 Conduct training for HRC officers on SB & SE | # of trainings | 0
Activities 2.1.4 Capacities of MWCA are enhanced to provide legal assistance through Women Development Officers, Counselling Assistants (and other relevant officers) on sexual bribery and exploitation in safe spaces. | see output Indicator 2.1.3
2.1.4.1 Formulate a module on para legal assistance for field officers of MWCA in S/T/E | # of discussions | 0
2.1.4.2 Identify WDOs and Counselling Officers to follow a residential TOT on providing legal assistance as para-legal officers | # of trainings | 0
2.1.4.3 Conduct 7 legal clinics linking with CSOs in relevant divisions led by capacitated officers | # of trainings | 0 | 7

## Activity 2.1
Output 2.1 The capacity of public institutions and officials are built to prevent and respond to bribery and to protect female heads of households, including military and war widows from sexual exploitation. | COLOMBO/NATIONWIDE |  |  | ANURADHAPURA |  |  | KURUNEGALA |  |  | KILINOCHCHI
| Date | Event Type | Target Beneficiaries | Date | Event Type | Target Beneficiaries | Date | Event Type | Target Beneficiaries | Date | Event Type | Target Beneficiaries | UNW | UNDP
Activities 2.1.1 Sensitization of public officials on sexual bribery and sexual exploitation as crimes, using ‘puppetry’ and ‘forum theatre’ to communicate the message in a non-contentious manner.
2.1.1.1 National and district /divisional level sensitization workshops for public officials.
2.1.1.1 National and district /divisional level sensitization workshops for public officials.
Activities 2.1.2 Development of a special training programme for Public officials on handling complaints of sexual Exploitation and sexual bribery, in consultation with public training Institutions such as SLIDA/SLFI.
2.1.2.1 Draft, share and finalize special training module in consultation with the relevant institutions.
2.1.2.2 TOT for SLIDA/SLFI trainers
2.1.2.3 Residential training programmes for public officials and SH Committees
Activities 2.1.3 Capacity of National Human Rights Institutions are enhanced to receive and respond to complaints.
2.1.3.1 Initiate discussions with Commissioners of HRC
2.1.3.2 Conduct training for HRC officers on SB & SE
Activities 2.1.4 Capacities of MWCA are enhanced to provide legal assistance through Women Development Officers, Counselling Assistants (and other relevant officers) on sexual bribery and exploitation in safe spaces.
2.1.4.1 Formulate a module on para legal assistance for field officers of MWCA in S/T/E
2.1.4.2 Identify WDOs and Counselling Officers to follow a residential TOT on providing legal assistance as para-legal officers
2.1.4.3 Conduct 7 legal clinics linking with CSOs in relevant divisions led by capacitated officers

## Output 2.2
Expected Results | Indicators | Baseline | Overall Target | Q3 Target | Q3 Progress | Q4 Target | Q4 Progress | Q1 2020 Target | Q1 2020 Progress | Q2 2020 Progress | Q2 2020 Target
Output 2.2 Strengthen existing accountability mechanisms to report and responsibility mechanisms to report and respond to sexual bribery and exploitation. | [11 empty] | UNW | UNDP
Activity 2.2.1 Technical support to the formation/ re- establishment of anti- sexual harassment committee in public institutions as per the recent directive issued by the Ministry of Women and Child Affairs. | Output indicator 2.2.1 # of public institutions with established and functioning Anti- Sexual Harassment Committees | 10 established though not functioning | 12 established and fully functioning | 0 | 0 | 5 anti-sexual harassment committees strengthened by 4th quarter | 0
2.2.1.1 Policy Dialogue with Ministries and District Secretariats to re-establish/set-up anti-SH committees with special attention to stories of widows’ experiences and inclusion of SB/SE into existing guidelines of the public institution. | # of meetings with Ministries and District Secretariats to re-establish/set-up anti-SH committees | 0 | 4 | 0 | 0 | 0 | 1
2.2.1.2 Trainings to the SH Committees in Sinhala and Tamil | # of trainings provided to the SH committees | 0 | 4
2.2.1.2 Trainings to the SH Committees in Sinhala and Tamil | # of trainings provided to the SH committees | 0 | 4
2.2.1.3 Develop a gender sensitive code of conduct, which addresses SB/SE explicitly, for public officers in consultation with SH Committees | # of SH committees consulted to draft gender sensitive code of conduct | 0 | 3
2.2.1.4 Launch of the code of conduct with policy makers, govt officers and district level govt officials. | # of policy makers, govt officers and district level govt officials attending the launch | 0 | 50
2.2.1.5 Follow-up discussion sessions/assessments of activities pertaining to the strengthening of existing anti-sexual harassment committees | # of follow-up discussion sessions/assessments | 0 | 0
Activity 2.2.2 Provide technical support to the Ministry of Women and Children to advocate for gender-sensitive Anti-Bribery legislation. | Output indicator 2.2.2 # of state/ public sector institutions provided with technical support to integrate adopt measures on addressing sexual bribery and sexual exploitation | 0 | 4
2.2.2.1 Meetings with the reps of MoWA to lobby for gender sensitive anti- bribery legislation | # of meetings held with the relevant MoWA representatives. | 0 | 4
2.2.2.2 Convene high-level ministerial meetings (with MWCA as the lead) ministries to highlight the need for gender sensitive anti-bribery legislation including sexual bribery | # of meetings | 0 | 0
2.2.2.3 Local consultant to support MWCA and inter-ministerial discussions | n/a
Activity 2.2.3 Provide technical support to Ministries who are willing to protect war and MWs from SB to draft policies/ circulars/ guidelines | see outcome indicator 2.1a
2.2.3.1 Meetings with the representatives of relevant ministries to draft policies/ circulars and guidelines | # of policies/ circulars and guidelines drafted with the support of the relevant Ministries. | 0 | 2
2.2.3.2 Local consultant to support MWCA in discussions and consultations aimed at drafting policies/circulars/guidelines
Note on H4: Mona Damdinjav: UNW, UNDP and CEJ meeting with MWCA on 24 October.

## Activity 2.2
Output 2.2 Strengthen existing accountability mechanisms to report and responsibility mechanisms to report and respond to sexual bribery and exploitation. | COLOMBO/NATIONWIDE |  |  | ANURADHAPURA |  |  | KURUNEGALA |  |  | KILINOCHCHI
| Date | Event Type | Target Beneficiaries | Date | Event Type | Target Beneficiaries | Date | Event Type | Target Beneficiaries | Date | Event Type | Target Beneficiaries | UNW | UNDP
Activity 2.2.1 Technical support to the formation/ re- establishment of anti- sexual harassment committee in public institutions as per the recent directive issued by the Ministry of Women and Child Affairs.
2.2.1.1 Policy Dialogue with Ministries and District Secretariats to re-establish/set-up anti-SH committees with special attention to stories of widows’ experiences and inclusion of SB/SE into existing guidelines of the public institution.
2.2.1.1 Policy Dialogue with Ministries and District Secretariats to re-establish/set-up anti-SH committees with special attention to stories of widows’ experiences and inclusion of SB/SE into existing+B6 guidelines of the public institution.
2.2.1.2 Trainings to the SH Committees in Sinhala and Tamil
2.2.1.3 Develop a gender sensitive code of conduct, which addresses SB/SE explicitly, for public officers in consultation with SH Committees
2.2.1.4 Launch of the code of conduct with policy makers, govt officers and district level govt officials.
2.2.1.5 Follow-up discussion sessions/assessments of activities pertaining to the strengthening of existing anti-sexual harassment committees
Activity 2.2.2 Provide technical support to the Ministry of Women and Children to advocate for gender-sensitive Anti-Bribery legislation.
2.2.2.1 Meetings with the reps of MoWA to lobby for gender sensitive anti- bribery legislation
2.2.2.2 Convene high-level ministerial meetings (with MWCA as the lead) ministries to highlight the need for gender sensitive anti-bribery legislation including sexual bribery
2.2.2.3 Local consultant to support MWCA and inter-ministerial discussions
Activity 2.2.3 Provide technical support to Ministries who are willing to protect war and MWs from SB to draft policies/ circulars/ guidelines
2.2.3.1 Meetings with the representatives of relevant ministries to draft policies/ circulars and guidelines
2.2.3.2 Local consultant to support MWCA in discussions and consultations aimed at drafting policies/circulars/guidelines