## OVERALL REPORTING INSTRUCTIONS
OVERALL INSTRUCTIONS
1 | All questions/sections must be responded to before submitting to secretariat. Once the document is uploaded in the relevant folder (as per instruction below) please email the secretariat.
2 | To ensure high quality narrative and results reports please pay attention to the following details: a) A well written, succinct summary that is very clear about what was done during the reporting period and results achieved, with a priority on concrete activities, beneficiaries reached and achievements beyond processes b) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document; c) In case certain indicators are not longer relevant, an explanation for why they are not. d) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document and how they align with the overall SERP joint workplan, and connection to reporting on global-level SERP indicators e) Indicate the relevant SERP monitoring framework global indicators that were contributed to as part of this project. f) An honest analysis of challenges faced, the responses to these challenges and the extent to which these responses were successful or not g) Go beyond generic, standard and well documented features of successful project implementation when reflecting on innovation and focus on what is truly new for you and which could enable replication efforts
3 | You must submit this completed workbook by uploading it in the relevant Project Folder here (https://undp.sharepoint.com/:f:/r/sites/covid19mptfcall1/Shared%20Documents/2020-REPORT?csf=1&web=1&e=j3cc3J). Please note if you are unsure of your project number please refer to http://mptf.undp.org/factsheet/fund/COV00
A | ANNUAL REPORT
DEADLINE: 31 January 2021
4 | ALL projects that received funds in 2020 must complete annual report, HOWEVER if you have your project ending on 31st December 2020 - your FINAL report is your annual report.
5 | If you received a no-cost extension on your project please do the annual report and in a few months time you can update the annual report to include activities to complete your end of project report.
6 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.
B | END OF PROJECT - FINAL REPORT
DEADLINE: 31 January 2021
7 | ALL projects that received funds in 2020 must complete annual report, HOWEVER if you have your project ending on 31st December 2020 - your FINAL report is your annual report.
8 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.

## General Information-Annual
Programme Title & Project Number |  | Programme Duration
Programme Title: | Strengthening crisis responsiveness of social protection systems during and beyond COVID 19–induced food emergency in Eswatini | Overall Duration (months) | 9 months
Programme Number (if applicable) |  | Start Date (dd.mm.yyyy) | 01/06/2020
MPTF Office Project Reference Number: | 121767 | Original End Date (dd.mm.yyyy) | 31/12/2020
Country | Eswatini | Current End date(dd.mm.yyyy) | 31/06/2021
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | FAO, UNICEF, UNDP and WFP | National counterparts (government, private, NGOs & others) and other International Organizations | Ministry of Agriculture, National Maize Corporation, World Vision Eswatini, National Disaster Management Authority
Report Cleared By
o Name:
o Title:
o Email address:
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the Secretary-General's Designate
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Annual
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum) | The project was part of the UN-Wide response to COVID-19 providing support to address immediate needs in food security, recovery in the agricultural and food systems, and leveraging existing programmes to inform needed reforms in the social protection mechanisms to address current and future shock-induced livelihoods and food security challenges. This project was implemented by WFP, FAO, UNDP, and UNICEF. WFP supported the emergency needs for priority populations impacted by secondary effects of COVID-19 that put them at high risk of food insecurity due to loss of employment, high food prices and declining incomes. WFP Provided cash-based transfers to the most vulnerable populations in 4 peri-urban constituencies namely Kwaluseni, Lobamba Lomdzala, Mbabane East and Mbabane West. This multi stakeholder assistance was provided between May to September 2020 to different groups affected by the pandemic including (1.) Urban poor household affected by COVID-19, (2.) Small Business Support (SBS), (3.) Refugees, (4.) Malnourished HIV/TB Clients (MHTC). The total number of beneficiaries reached were 46,591 people (8,993 households) who received cash-based transfers of SZL140.00 per person; 1,179 informal traders which received recovery startup capital SZL3000.00 per person; 1,205 malnourished people on HIV/TB treatment having received a total of SZL208.8 per person to meet their respective food and nutrition needs. The results showed that assisted affected populations improved their food security and reduce engaging on negative coping strategies but to address poor nutritional feeding habits, diets should be improved through education.FAOs mainly focused on addressing loss of livelihoods and food insecurity challenges caused by disruptions of the agro-food system. This involved the use of appropriate available e-solutions and supply chain platforms to facilitate the market linkages for smallholder farmers affected by market disruptions to be able to access markets and earn incomes and continue production. FAO supported 15 farmer groups to produce and supply vegetables required by the 200 market vendors in Manzini and Mbabane communities. A total of 6 transporters (3 in Mbabane and 3 in Manzini) were engaged to deliver the produce from the farm gate to the vendors. A further 30 (8 farmer groups and 22 individual smallholder farmers) were identified jointly with the National Maize Corporation (NMC) to produce maize (103.60ha) and 38ha of beans for winter production. The production shall be undertaken in the 2021 winter season as by the time the inputs were procured, it was the normal farming season and farmers fields earlier earmarked for the winter production were unavailable. As an ongoing initiative on the e-digital platform, all the stakeholders in the project were mobilized to register on a newly established marketing platform; Agricultural Marketing Information System (AMIS) currently managed by NAMBoard to facilitate ease of marketing the produce. For awareness creation, FAO engages the participants and shares with them awareness information on COVID 19 and all COVID 19 precautionary advice from the Ministry of Health is adhered to. As part of its integrator role for a stronger UN Development system, UNDP and UNICEF coordinated UNCT efforts to begin a process to review the Social Protection/Assistance Policy. The Social Assistance System in Eswatini indicates that 35,349 households are extremely poor, of which 19,903 HH are labour-constrained and 6,000 HHs are child-headed. The recurring shocks (droughts and COVID -19) have highlighted a number of gaps in the country’s Social Protection Systems in particular coverage of those who require support and ability to be used as platforms for shock responsive social protection (vertical and horizontal expansion).The need for social mitigation for the effects of COVID on communities will last beyond the disease. This is because the national lockdown, which affected non-essential businesses, had reduced business operations, and rendered many workers, especially those in informal sectors, to be on scaled down employment or completely losing their jobs. The social protection policy needs to be reviewed so as to capture new dynamics to develop a comprehensive appropriate and shock-responsive policies for the vulnerable. The completion of the National Social Assistance Policy in Eswatini will support the Department of Social Welfare’s (Deputy Prime Minister’s Office) current efforts of putting in place a robust National Social Assistance System platform that will provide efficiency, accountability (audit & reporting) and sustainable solution in the management of beneficiary information and flexible payment modalities that is accessible, robust and integrated. This is in pursuance of collective social welfare of the Eswatini nation for broader coverage, transparent targeting harmonization of social protection programs for the benefit of the most vulnerable. It is envisaged that Harmonized Social Assistance Policy will be shock responsive and recommend more efficient models. The review the social protection policy that will also serve the basis for development of the vulnerability register. Overall, this will support national goals to reduce poverty, inequality and vulnerability. A consultant was engaged to review the policy.
2 | Purpose (and Beneficiaries) | Please include the number of direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups | Direct emergency transfers WFP: 46,591 people (8,993 households) consisting of 23,451 Female and 23140 male who received cash-based transfers; 1,179 informal traders (70% female; 1,205 (62% female) malnourished people on HIV/TB treatment. Direct beneficiaries FAO: Market Vendors (200 individuals with 93% being women), Transporters (8 individuals with 33% being women), Vegetable production (15 farmer groups with about 300 individuals with 65% being women farmers and for Winter Production 30 (8 farmer groups and 22 individual smallholder farmers for bean production with 4 women farmers. Indirect beneficiaries under the project are the family members of the beneficiaries estimated to be above 10,000 individuals. Social protection UNICEF &UNDP: - 1 policy document 1 Beneficiary Register to benefit 35349 people requiring social protection services.
3.1 | Results: Outcome Level | Please include outcome level results achieved | Along the vegetable value chain, the stakeholders (smallholder farmers, the vendors and the transporters) are realizing income greater than the E600 monthly minimum wage and have improved their livelihood. Results are yet to be realized for the maize and beans value chains.
3.2 | Results: Output Level | Please include output level results achieved | The Cash based Transfer Monitoring indicate the following achievements among the 46591 beneficiaries who received transfers : Outcome on Food Consumption Score: The proportion of households with poor food consumption score reduced from 3.3% to 3% and that with borderline decreased from decreased from 20.9% to 10% and those with with acceptable food consumption score improved from 75.8% to 83% from before intervention and at end of intervention. This suggest improvements in food access due support provided. The measure of on nutrition access using Food Consumption Score – Nutrition suggest that the percentage of the never consumed Vitamin A rich food stagnated from 2.8%- M; 4.4%-F to 3% each, while that of households that never consumed Protein rich food increased from 5.6%- M; 5.0%-F to 10% each, and households that never consumed Hem Iron rich food worsened 27.1%- M; 17.0%-F to 14% each. This suggest that while the access to energy improved the nutritional value of accessed foods remained poor. On coping consumption-based Coping Strategy Index (Average) improved from 13.2 to 10 indicating lees pressure on households. On the recovery agriculture the stakeholder along the vegetable value chain (smallholder farmers, the vendors and the transporters) are realizing income greater than the E600 monthly minimum wage and have improved their livelihood. Results are yet to be realized for the maize and beans value chains. Though not yet assessed fully, the project has contributed to the livelihood’s of 1179 urban vendors, 200 vegetable vendors, 6 transporters and 15 farmers groups who are engaged in the vegetable value chain. The project has already contributed to increased incomes as well as improved food security for the beneficiaries. A consultant has been engaged to review the social protection policy.
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words) | The main challenge experienced under the project has mainly been with the selection of the beneficiaries under the respective interventions. The collaboration and layering of emergency lifesaving actions with resilience nexus actions which could support the recovery and building better coping capacity was limited due to variance in resource availability among partners – this affected planned joint targeting of recovery participants. The selection of vendors had to be undertaken cautiously but separately with a total of 1179 receiving re-establishment capital while 200 received agriculture related start-up capital, However, reached number was far less than those affected by the COVID 19 as assessments indicated that over 3,000 vendors were impacted. Informal traders continued to face slow recovery due to the restrictions in trading period during the COVID-19. Poor consumer demand and lack of access to credit to replenish stock limited recovery and hence the linkage with responsible government ministry for continued business support. In Mbabane the security force (police) had to be involved to work with MOA and FAO during the selection process in order to maintain peace and calm. As this involves wares support equivalent to US200/person, all the vendors wanted to be included and had proposal on how to benefit all of them than a few individuals. To avoid conflicts thereto the selection was undertaken with the executive committees of the various market vendors. Under the National Maize Corporation, supporting the winter production of maize and beans, there were also selection challenges as initially NMC anticipated Government support to produce about 600ha of maize and beans for over 300 farmers. However due to the limited funds allocated under the MPTF, the hectarage and number of farmers had to be reduced; something that had to be cautiously undertaken as the farmers were already informed of the support from NMC. This process took some time as NMC had to re-engage and consult with the farmers prior to the final beneficiary selection. Agricultural inputs remain a very sensitive area which requires due diligence when dealing with supplies especially to vulnerable smallholder farmers. The unavoidable due diligence process in technical clearances for farm inputs pesticides, herbicides, fertilizers and seeds by relevant FAO technical experts takes time and resulted in some delay. The offices for clearances were alerted to treat the requests coming through from Eswatini under this project as an emergency.
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words) | The winter production of maize and beans can be considered as a major lesson learned upon which the Government of Eswatini can further explore as an efficient way to fully utilize agricultural land alnd and also contribute to food security. There is presently very minimal winter production in the country, especially under smallholder farmers which this project is targeting.
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words) | WFP, have partnered and are supporting the country in tackling COVID-19 impact, through cash-based transfers with Mobile Telecommunication Network (MTN) as the service provider and World Vision Eswatini (WVE) for mobilization and monitoring and for emergency response and recovery, focusing on the most vulnerable populations in 4 urban constituencies namely Kwaluseni, Lobamba Lomdzala, Mbabane East and Mbabane West. The Coordination of this aspect of the project was done under the leadership of the National Disaster Management Authority.FAO engaged with the Ministry of Agriculture as the direct line ministry. The agency further engaged NMC which is a parastatal under the Ministry of Agriculture focusing on the production of cereals in the country. FAO under the vegetable production value chain established new partnerships with the Municipalities of both Mbabane and Manzini where the market vendors under the project are managed. Under this project an innovative approach of using transporters to pick produce from the farm gate level and move it directly to the vendors stalls is quite unique. This is more so the case as the transporters are guided or provided information on the farmers and on the produce they have. This element has further been strengthened by the introduction of the AMIS which is an e platform that links the producers to the markets. Members of the Social Assistance policy review task team include representatives form Government, Civil Society, Private sector and Development partners. The project is linked to the covid-19 response needs assessment (CRNA) which will identify the full impact of COVID on all sectors.
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken. | The Agencies in this project supported the following assessments and analysis for the government: Socio Economic Impact of COVID 19 (May 2020), Rapid Food Security Outlook Report (April 2020), Vulnerability Assessment and Analysis (June 2020 and November 2020), Impact of COVID-19 on the Food Systems and Food Security (August 2020)
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place | The Social Protection Registry was deferred to follow the review of the social protection policy which will establish the size of vulnrbale popualtions, type of vulerability. This will allow for better targetting of the most vulnerable.
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners.

## RBM-Annual
| Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 1[1] | The target has not been fully realized pending completion of the project activities. However along the vegetable value chain, the stakeholders (smallholder farmers, the vendors and the transporters) are realizing income greater than the E600 monthly minimum wage and have improved their livelihood. | Theproject activities have not been fully completed | FAO Report
SDG Indicator 2.3.2: Average household income of small-scale food producers, traders, and vendors by sex and indigenous status
Baseline: 0
Planned Target:Small scale farmers, traders and vendors can realize net income greater than the E600 monthly minimum wage
SDG Indicators 2.1.1 Prevalence of undernutrition among People Living with HIV (PLHIV) |  | The funding situation was not adequate to cover the needs of at risk populations. The VAC July reported indicated further deterioration of food inscurity from with 21,300 PLHIV being at risk of malnutrition | WFP Reports
Baseline: 13200 (6.6% of PLHIV/TB) | 21300 (11% of PLHIV/TB)
Traget: 1800 13% reduction in prevelance | 45% reduction (6025) supported
SDG Indicators 2.1.2. Prevalence of moderate or severe food insecurity in the population affected by covid |  | The funding situation was not adequate to cover the needs of at risk populations. The VAC July reported indicated further deterioration of food inscurity from 27% to 32% | WFP Reports, VAC reports
Baseline: 27% of population | 12% of population at risk of food insecurity
Target: 14% reduction in prevalence | 63%reduction of population at risk
Indicator: SDG 1.3 Implement nationally appropriate social protection systems and measures for all, including floors, and by 2030 achieve substantial coverage of the poor and the vulnerable
Baseline:
Planned Target:
Output 1 Reduced loss of livelihoods along agro-food value chain and food deficiencies among vulnerable groups of population
1.1 Number of people receiving cash transfer safety nets within project period |  | The scope of the project was centrered around Mbabane and Manzini cities hence the farmer groups selcted were those closer to the cities for monitoring purposes and due to the travel restrictions | MOA (RDA) Monthly Progress Reports
Baseline: 0
Target: 1800 households (9000 people with 60% women)
1.2 Number of small-scale farmers linked to markets | 15 farmer groups have been mobilized and linked to markets
Baseline: 0
Planned Target:80 groups of farmers (approximately 1120 households or 5600 people of which at least 60% are women
1.3 Number of small scale farmers receiving support to produce winter crops | 8 farmer groups and 22 individuals are engaged for the winter production of beans and maize | The recommendation by NMC and MOA was that farmers engaged should farm a minimum 3 ha for maize and 1 ha for beans in order for farmers to realize the benefits hence the numbers were then reduced in consideration of the hectarage | NMC Progress Reports
Baseline: 0
Planned Target: 80 groups of farmers (approximately 1120 households or 5600 people of which at least 60% are women
1.4 Number of Transporters (MSMSEs) linked to farmers downstream and to markets upstream | 6 transporters engaged | Some of the transporters who had applied did not have the initial capital to finance the procurement of the produce from the farmers (as one of the pre-requirements for transporters) | NFF from FAO
Baseline: 0
Planned Target: 10
1.5 Number of small-scale farmers, transporters, vendors and traders and households receiving awareness information on COVID-19 through the project | 250 | This was mainly due to the COVID restrictions for group meetings. | FAO Progress Report
Baseline: 0
Planned Target: +-5, 000 (60% women)
Output 2 Strong basis for strengthening the national social protection system developed through leveraging digital platforms and working through the two COVID-19 task teams (COVID-19 Emergency Agriculture and Food Security Technical Working Group, COVID-19 Social Protection Working Group)
2.1 Number of Government Task teams supported to deliver social protection services
Baseline: 0 | 2
Target: 2 Food and Nutrition and Social Protection | Food and Nutrition - use of SCOPE registry
2.2 Number of farmers, vendors, traders including women transacting through innovative and more efficient digital platforms
Baseline: 0 | 1385 peri urban vendors
Planned Target: 80 groups of farmers(approximately 1120 households or 5600 people of which at least 60% are women) -10 transporters -200 vendors | 37 farmer groups and 206 individuals have been sensitized on AMIS. 8993 household in a beneficirty registry ready accessible on WFP SCOPE | The number are low due to the COVID 19 meeting restrictions. | FAO/WFP Reports
2.3 Rapid Assessment Report
Baseline: 0 | 1
Target: 1 | 1 | Food security Outlook report | WFP
2.4 Vulnerability Assessment Report
Baseline: 0 | 2
Target: 1 | 2 | Due to prolonged COVID19 period updates of situation required | UN suported VAC reports
2.5 Social Protection Registry
Baseline: draft harmonised Social Assistance Policy available | Draft | Work started late | ToR and Consultant Contract
Planned Target: 1 Social Assistance Policy 1. Social protection Registry of vulnerable persons | 0
Please inlcude all three: Baseline, Planned Target and Achieved Targets
[1] Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.

## Communication-Annual
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
To be submitted
2. Upload here: Communications and Visibility (OPTIONAL)
Fund's Communication Guidelines is posted here: http://mptf.undp.org/document/download/25941
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well picture material please make sure you include all credits and upload them in high resolution Call1 countries.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board

## General Information-Final
Programme Title & Project Number | Programme Duration
Programme Title: | Overall Duration (months)
Programme Number (if applicable) | Start Date (dd.mm.yyyy)
MPTF Office Project Reference Number: | Original End Date (dd.mm.yyyy)
Country | Current End date(dd.mm.yyyy)
Recepient UN Organizations | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | National counterparts (government, private, NGOs & others) and other International Organizations
Report Cleared By
o Name:
o Title:
o Email address:
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the relevant decision-making body/Steering Committee.
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Final
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum) | The project is a response to the COVID-19 providing support in the agricultural and food systems leveraging digital platforms to address both livelihoods and food security challenges to inform the needed reform in the social protection mechanisms through supporting the current. FAOs focus is mainly addressing loss of livelihoods and food insecurity challenges caused by disruptions of the agro-food system. This involves the use of appropriate available e-solutions and supply chain platforms to facilitate the market linkages for smallholder farmers affected by market disruptions to be able to access markets and earn incomes and continue production. As part of the deliverables, FAO identified 15 farmer groups to produce and supply vegetables required by the 200 market vendors in Manzini and Mbabane communities. A total of 6 transporters (3 in Mbabane and 3 in Manzini) were engaged to deliver the produce from the farm gate to the vendors. A further 30 (8 farmer groups and 22 individual smallholder farmers) were identified jointly with the National Maize Corporation (NMC) for the production of maize (103.60ha) and 38ha of beans for winter production. The production shall be undertaken in the 2021 winter season as by the time the inputs were procured, it was the normal farming season and farmers fields earlier earmarked for the winter production were unavailable. As an ongoing initiative on the e-digital platform, all the stakeholders in the project were mobilized to register on a newly established marketing platform; Agricultural Marketing Information System (AMIS) currently managed by NAMBoard to facilitate ease of marketing the produce. For awareness creation, FAO engages the participants and shares with them awareness information on COVID 19 and all COVID 19 precautionary advice from the Ministry of Health is adhered to. As part of its integrator role for a stronger UN Development system, UNDP coordinated UNCT efforts to begin a process to review the Social Protection/Assistance Policy. The Social Assistance System in Eswatini indicates that 35,349 households are extremely poor, of which 19,903 HH are labor-constrained and 6,000 HHs are child-headed. The recurring shocks (droughts and COVID -19) have highlighted a number of gaps in the country’s Social Protection Systems in particular coverage of those who require support and ability to be used as platforms for shock responsive social protection (vertical and horizontal expansion). The need for social mitigation for the effects of COVID on communities will last beyond the disease. This is because the national lockdown, which affected non-essential businesses, had reduced business operations and rendered many workers, especially those in informal sectors, to be on scaled down employment or completely losing their jobs. The social protection policy needs to be reviewed so as to capture new dynamics to develop a comprehensive appropriate and shock-responsive policies for the vulnerable. The completion of the National Social Assistance Policy in Eswatini will support the Department of Social Welfare’s (Deputy Prime Minister’s Office) current efforts of putting in place a robust National Social Assistance System platform that will provide efficiency, accountability (audit & reporting) and sustainable solution in the management of beneficiary information and flexible payment modalities that is accessible, robust and integrated. This is in pursuance of collective social welfare of the Eswatini nation for broader coverage, transparent targeting harmonization of social protection programs for the benefit of the most vulnerable. It is envisaged that Harmonized Social Assistance Policy will be shock responsive and recommend more efficient models. The review the social protection policy that will also serve the basis for development of the vulnerability register. Overall, this will support national goals to reduce poverty, inequality and vulnerability. A consultant was engaged to review the policy.
2 | Purpose (and Beneficiaries) | Please include the number of both direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups | Direct beneficiaries: Market Vendors (200 individuals with 93% being women), Transporters (8 individuals with 33% being women), Vegetable production (15 farmer groups with about 300 individuals with 65% being women farmers and for Winter Production 30 (8 farmer groups and 22 individual smallholder farmers for bean production with 4 women farmers. Indirect beneficiaries under the project are the family members of the beneficiaries estimated to be above 10,000 individuals. Social protection:- 1 policy document 1 Beneficiary Register
3.1 | Results: Outcome Level | Please include outcome level results achieved | Along the vegetable value chain, the stakeholders (smallholder farmers, the vendors and the transporters) are realizing income greater than the E600 monthly minimum wage and have improved their livelihood. Results are yet to be realized for the maize and beans value chains.
3.2 | Results: Output Level | Please include output level results achieved | Though not yet assessed fuly, the project has contributed to the livelihoods of 200 vendors, 6 transporters and 15 farmers groups who are engaged in the vegetable value chain. The project has already contributed to inceased incomes as well as improved food security for the beneficiaries. A consultant has been engaged to review the social protection policy.
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words) | The main challenge experienced under the project has mainly been with the selection of the beneficiaries under the respective interventions. For the vendors, the selection process had to be undertaken cautiously as the targeted number of 200 was far lower than those affected by the COVID 19 as it was indicated that they were over 2,000 vendors. In Mbabane the security force (police) had to be involved to work with MOA and FAO during the selection process in order to maintain peace and calm. As this involves wares support equivalent to US200/person, all the vendors wanted to be included and had proposal on how to benefit all of them than a few individuals. To avoid conflicts thereto the selection was undertaken with the executive committees of the various market vendors. Under the National Maize Corporation, supporting the winter production of maize and beans, there were also selection challenges as initially NMC anticipated Government support to produce about 600ha of maize and beans for over 300 farmers. However due to the limited funds allocated under the MPTF, the hectarage and number of farmers had to be reduced; something that had to be cautiously undertaken as the farmers were already informed of the support from NMC. This process took some time as NMC had to re-engage and consult with the farmers prior to the final beneficiary selection. Agricultural inputs remain a very sensitive area which requires due diligence when dealing with supplies especially to vulnerable smallholder farmers. The unavoidable due diligence process in technical clearances for farm inputs pesticides, herbicides, fertilizers and seeds by relevant FAO technical experts takes time and resulted in some delay. The offices for clearances were alerted to treat the requests coming through from Eswatini under this project as an emergency.
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words) | The winter production of maize and beans can be considered as a major lesson learned upon which the Government of Eswatini can further explore as an efficient way to fully utilize agricultural land alnd and also contribute to food security. There is presently very minimal winter production in the country, especially under smallholder farmers which this project is targeting.
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words) | FAO engaged with the Ministry of Agriculture as the direct line ministry. The agency further engaged NMC which is a parastatal under the Ministry of Agriculture focusing on the production of cereals in the country. FAO under the vegetable production value chain established new partnerships with the Municipalities of both Mbabane and Manzini where the market vendors under the project are managed. Under this project an innovative approach of using transporters to pick produce from the farm gate level and move it directly to the vendors stalls is quite unique. This is more so the case as the transporters are guided or provided information on the farmers and on the produce they have. This element has further been strengthened by the introduction of the AMIS which is an e platform that links the producers to the markets. Members of the Social Assistance policy review task team include representatives form Government, Civil Society, Private sector and Development partners. The project is linked to the covid-19 response needs assessment (CRNA) which will identify the full impact of COVID on all sectors.
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken. | FAO conducted an Assessment on the Impact of COVID-19 on the Food Systems and Food Security in Eswatini.
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place | The Social Protection Registry was deferred to follow the review of the social protection policy which will establish the size of vulnrbale popualtions, type of vulerability. This will allow for better targetting of the most vulnerable.
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners.

## RBM-Final
| Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 1[1] | The target has not been fully realized pending completion of the project activities. However along the vegetable value chain, the stakeholders (smallholder farmers, the vendors and the transporters) are realizing income greater than the E600 monthly minimum wage and have improved their livelihood. | The project activities have not been fully completed | FAO Report
Indicator: SDG Indicator 2.3.2: Average household income of small-scale food producers, traders, and vendors by sex and indigenous status
Baseline: 0
Planned Target:Small scale farmers, traders and vendors can realize net income greater than the E600 monthly minimum wage
Output 1.1 Reduced loss of livelihoods along agro-food value chain and food deficiencies among vulnerable groups of population | 15 farmer groups have been mobilized and linked to markets | The scope of the project was centrered around Mbabane and Manzini cities hence the farmer groups selcted were those closer to the cities for monitoring purposes and due to the travel restrictions | MOA (RDA) Monthly Progress Reports
Indicator 1.1.1: Number of small-scale farmers linked to markets
Baseline: 0
Planned Target:80 groups of farmers (approximately 1120 households or 5600 people of which at least 60% are women
Indicator 1.1.2: Number of small scale farmers receiving support to produce winter crops | 8 farmer groups and 22 individuals are engaged for the winter production of beans and maize | The recommendation by NMC and MOA was that farmers engaged should farm a minimum 3 ha for maize and 1 ha for beans in order for farmers to realize the benefits hence the numbers were then reduced in consideration of the hectarage | NMC Progress Reports
Baseline: 0
Planned Target: 80 groups of farmers (approximately 1120 households or 5600 people of which at least 60% are women
Indicator 1.1.3: Number of Transporters (MSMSEs) linked to farmers downstream and to markets upstream | 6 transporters engaged | Some of the transporters who had applied did not have the initial capital to finance the procurement of the produce from the farmers (as one of the pre-requirements for transporters) | NFF from FAO
Baseline: 0
Planned Target: 10
Indicator 1.1.4: Number of small-scale farmers, transporters, vendors and traders and households receiving awareness information on COVID-19 through the project | 250 | This was mainly due to the COVID restrictions for group meetings. | FAO Progress Report
Baseline: 0
Planned Target: +-5, 000 (60% women)
Output 1.2 Strong basis for strengthening the national social protection system developed through leveraging digital platforms and working through the two COVID-19 task teams (COVID-19 Emergency Agriculture and Food Security Technical Working Group, COVID-19 Social Protection Working Group) | 37 farmer groups and 206 individuals have been sensitized on AMIS | The number are low due to the COVID 19 meeting restrictions.
Indicator 1.2.1:Number of farmers, vendors, traders including women transacting through innovative and more efficient digital platforms
Baseline: 0
Planned Target: 80 groups of farmers(approximately 1120 households or 5600 people of which at least 60% are women) -10 transporters -200 vendors
Indicator 1.2.2:
Baseline:
Planned Target:
Outcome 1[1]
Indicator: SDG 1.3 Implement nationally appropriate social protection systems and measures for all, including floors, and by 2030 achieve substantial coverage of the poor and the vulnerable
Baseline:
Planned Target:
Output 2.5… SDG TARGET_1.5: By 2030, build the resilience of the poor and those in vulnerable situations and reduce their exposure and vulnerability to climate-related extreme events and other economic, social and environmental shocks and disasters
Indicator :2.5 Social Protection Registry
Baseline: draft harmonised Social Assistance Policy available
Planned Target: 1 Social Assistance Policy 1. Social protection Registry of vulnerable persons
Please inlcude all three: Baseline, Planned Target and Achieved Targets
[1] Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.

## Communication-Final
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
2. Upload here: Communications and Visibility (OPTIONAL)
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well picture material please make sure you include all credits and upload them in high resolution Call1 countries.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board