## Work Plan
PBF SECRETARIAT PROJECT WORK PLAN
Project Title: Support to Project Coordination and Monitoring of the United Nations Peacebuilding Fund (PBF) Projects in Guinea-Bissau
Results | Baseline and targets | Activities | [9 empty] | Responsible partners | Budget description | Budget 2020 | Budget 2021 | TOTAL
|  |  | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Outcome 1: The effective developpment, implementations, monitoring, oversight of peacebulding projects and the overall strategic direction of the PBF portfolio in Guinea-Bissau is ensured.
Output 1.1: PBF Secretariat operations are running | [13 empty] | 342000 | 183000 | 525000
Indicator 1.1.1: Prodoc approved in 2019 | Baseline Target: 1 | A 1.1.1: Prepare and help to ensure approval of new Prodoc for PBF Secretariat 2019-2020 | bar: Q4
Indicator 1.1.2: Office has full complement of Staff | Baseline: 3 Target: 5 | A 1.1.2: Hire, evaluate and renew staff contracts | [10 empty] | Staff and other personnel | 300000 | 170000 | bar: Q4
Indicator 1.1.3: PBF Secretariat Staff attend approved trainings | Baseline: Target: 2 training completed | A 1.1.3: Staff Attend Approved Trainings | [10 empty] | Contracual services, Travel | 7000 | 3000
Indicator 1.1.4: Office has full complement of Staff | Baseline: Target: : 4 new computers by Dec. 2019 | A 1.1.4: Office equipped/oprtional with purchases of equipment supplies and fuel | [10 empty] | Supplies commodities, materials, Equipm, Vehic, and Furniture | 35000 | 10000
| Baseline: 3 Target: 5 | A 1.1.5: Draft and submit half-year, Annual and Final Reports of the PBF Secretariat Project and Annual Strategic peacebuilding report
Output 1.2: Effective project implementation, communication and coordination enabled to ensure proper Oversight, Coherence and Complementarity between Projects | [13 empty] | 25500 | 7500 | 33000
Indicator 1.2.1: Monthly Meetings Held | Baseline: 8 Target: 10 | A 1.2.1: Convene and facilitate monthly coordination meetings with RUNOS | bar: Q4
Indicator 1.2.2: Quality Reports Submitted by the Deadline | Baseline: 7 Target: 9 | A 1.2.2: Convene and facilitate 2 evaluation workshops per year to help RUNOS prepare Mid-year and Annual Reports | [10 empty] | Supplies commodities, materials, Equipm, Vehic, and Furniture, Contractual services | 1500 | 500
Indicator 1.2.3: UN Leadership provided quality support and documentation to make decisions | Baseline: Target: 1 update per semester | A 1.2.3: Review and support finalisation of Half-year, Annual Reports and Final Reports of RUNO projects
A 1.2.4: Support the development of TORs for consultants and for the Final Evaluations of RUNO projects
A 1.2.5: Attend monthly UNCT meetings as requested and Senior Management retreats and provide briefs and advice on PBF and general peacebuilding issues
|  | A 1.2.6: Contribute to SG, PBC briefings and other reports and support PBC and or PBSO monitoring missions | [10 empty] | Contractual services, Travel | 6000 | 2000
A 1.2.7: Hold phone meetings with PBSO as required to provide updates on Project Implementation as well as inform PBSO of the changing political context and support
Indicator 1.2.2: Leadership provided quality support and documentation to make decisions |  | A 1.2.8: Participate in PBSO convened meetings on PBF management, as requested | [10 empty] | Travel | 8000 | 0
A 1.2.9: Coordinate PBF business with Heads of Agencies and the DSRSG as needed and support the coordination role of the RC in the context of peacebuilding programming, including coordinating UN submissions to GYPI, clarifying the PBF added value/ niche in Guinea-Bissau and ensuring complementarity with other support
Output 1.3: Enable effective development of new project design (with appropriate emphasis on gender mainstreaming)
Indicator 1.3.1: New Projects Developed | Baseline: 2 Target : 2 for 2019 and X in 2020 | A 1.3.1: Design, convene and facilitate effective stakeholder consultation processes for identification of priorities to be supported by the PBF and for new project development | [10 empty] | Supplies commodities, materials, Equipm, Vehic, and Furniture, Contractual services, Travel | 10000 | 5000
Indicator 1.3.2: New Projects have at least 30% of funds allocated to Gender Issues or support Women’s Empowerment | Baseline: Currently higher than 15% Target: 30% of project budgets dedicated to Gender Issues or suport Women’s Empowerment | A 1.3.2: Advise, support and review project proposals for submission to PBF and ensure that PBF-funded projects incorporate peacebuilding best practices and respond to PBF quality criteria. It also requires ensuring that at least 30% of the total PBF envelope is allocated to gender issues and / or support for women's empowerment
Outcome 2: The agencies implementing PBF funded projects are able to deliver on the implementation, monitoring and evaluation of effectively designed peacebuilding projects and effectively communicate the results of their interventions
Output 2.1: Capacity-building of RUNOs and implementing partners enabled through tailored technical support and training | [13 empty] | 35000 | 10000 | 45000
Indicator 2.1.1: Number and type of training event convened | Baseline Target | A 2.1.1: Provide on-going tailored technical support in peacebuilding to RUNOS for project design and implementation | [10 empty] | Contractual services, Travel | 10000 | 5000
Indicator 2.1.2: Satisfaction with technical assistance provided | Baseline: 65% satisfaction Target: 80% satisfaction | A 2.1.2: Convene Training events in Peacebuilding Project Design, Implementation and Monitoring. Example topics include PB Mainstreaming; Dialogue Design and methodologies; National Reconciliation Models; Mediation skills training, Innovations and cutting-edge approaches to Peacebuilding; nexus between climate change/environment, gender, and/or human rights based approaches and peacebuilding | [10 empty] | Supplies commodities, materials, Equipm, Vehic, and Furniture, Contractual services, Travel | 25000 | 5000
Output 2.2: Strengthen social communication and peacebuilding advocacy: Increase awareness by national authorities, civil society and wider public of Peacebuilding Priorities and results | [13 empty] | 117000 | 27300 | 144300
Indicator 2.2.1: Communication Strategy developed | Baseline: 1 Target: 1 updated | A 2.2.1: Assist RUNOs and UN System with communication strategies to ensure visibility of PBF activities as well as the PBF’s visibility with print, TV, Radio and social media posts. Advance General Peace Advocacy, such as 21 September activities. SDG 16 | [10 empty] | Supplies commodities, materials, Equipm, Vehic, and Furniture, Contractual services | 12000 | 3000
Indicator 2.2.2: Facebook posts developed and posted/reposted | Baseline: 25 Target: 60 | A 2.2.2: Organize and facilitate national stakeholder meetings to ensure periodic updates on the implementation of the PBF portfolio. It includes public project presentations events to socialize new projects and/or closing projects | [10 empty] | Supplies commodities, materials, Equipm, Vehic, and Furniture, Contractual services, Travel | 6000 | 4000
Indicator 2.2.3: Number of Knowledge Products developed. | Baseline: 0 Target: 3 | A 2.2.3: Maintain and regularly update of a mapping of actors in the field of peacebuilding in GB
Indicator2.2.4: |  | A 2.2.4: Assist RUNOS in the development of stories in videos that feature emblematic stories and instructional videos that arise in implementation of projects | [10 empty] | Supplies commodities, materials, Contractual services, Travel | 9000 | 1000
Output 2.3 Strengthen the PBF project and portfolio level monitoring and evaluation
Indicator 2.3.1: % of Projects and completed log frames | Baseline: ? Target: 80% | A 2.3.1: Assist RUNOs with on-going tailored technical assistance in M&E, including assistance in preparing and reviewing project result frameworks and monitoring methodologies, ensuring their usability and coherence and looking for synergies in monitoring, data collection and analysis | [10 empty] | Contractual services, Travel | 10000 | 3000
Indicator 2.3.2: # of Structures M&E | Baseline: Target: | A 2.3.2: Organize and conduct structured M&E visits to project sites. This can include organizing monitoring missions alone, with PBF Coordinator or with national focal point ministries to review the implementation of the PBF portfolio | [10 empty] | Supplies commodities, materials, Equipm, Vehic, and Furniture, Contractual services, Travel | 6000 | 2000
Indicator 2.3.3: Data collection methodologies in place and being analyzed and reported | Baseline: 0 Target: 1 per project | A 2.3.3: Put in place portfolio level data collection and analysis methodologies, including perception surveys and community-based monitoring, as appropriate, to ensure there is higher level data and analysis on issues that the PBF aims to contribute to through its various projects | [10 empty] | Contractual services, Travel | 26000 | 2000
Indicator 2.3.4: |  | A 2.3.4: Put in place regular PBF project review and trouble-shooting mechanisms to ensure that implementation challenges are discovered and addressed early or reporting to UN management and PBSO for further action
Indicator 2.3.5: Portfolio level evaluation conducted | Baseline: Target: | A 2.3.5: Support PBF portfolio level evaluations and lessons learned. This includes conducting an assessment of the bottom-up strategy of the 5 projects of 2017 - 2020 | [10 empty] | Contractual services, Travel | 18000
General Operating and other Direct Costs | [13 empty] | 30000 | 12300
[15 empty] | TOTAL | 747300
[15 empty] | ISC 7% | 52311
[15 empty] | TOTAL | 799611