SECRETARY-GENERAL’S PEACEBUILDING FUND

PBF PROJECT PROGRESS REPORT TEMPLATE

PBF PROJECT progress report

COUNTRY: Yemen

TYPE OF REPORT: semi-annual, annual OR FINAL Final Report

date of report: 2018

| Project Title: Yemen Peace Support Project Project Number from MPTF-O Gateway: 00106143 |
| --- |
| PBF project modality: IRF PRF | If funding is disbursed into a national or regional trust fund: Country Trust Fund Regional Trust Fund Name of Recipient Fund: UNOPS - United Nations Office of Project Services |
| List all direct project recipient organizations (starting with Convening Agency), followed type of organization (UN, CSO etc): UNOPS List additional implementing partners, Governmental and non-Governmental: OSESGY-Office of the Special Envoy of the Secretary-General for Yemen |
| Project commencement date: 10 July 2017 Project duration in months: Nine (9) Months |
| Does the project fall under one of the specific PBF priority windows below: Gender promotion initiative Youth promotion initiative Transition from UN or regional peacekeeping or special political missions Cross-border or regional project |
| Total PBF approved project budget* (by recipient organization): PBF: $ 900,000 UK : $ 1,050,000 NL : $ 1,454,164 USA : $ 100,000 Total: 3,535,317 *The overall approved budget and the release of the second and any subsequent tranche are conditional and subject to PBSO’s approval and subject to availability of funds in the PBF account How many tranches have been received so far: 1 |
| Report preparation: Project report prepared by: Marija Batemen Project report approved by: Did PBF Secretariat clear the report: Any comments from PBF Secretariat on the report: Has the project undertaken any evaluation exercises? Please specify and attach: |

NOTES FOR COMPLETING THE REPORT:

- Avoid acronyms and UN jargon, use general / common language.

- Be as concrete as possible. Avoid theoretical, vague or conceptual discourse.

- Ensure the analysis and project progress assessment is gender and age sensitive.

PART 1: RESULTS PROGRESS

  - Overall project progress to date

Briefly explain the status of the project in terms of its implementation cycle, including whether all preliminary/preparatory activities have been completed (1500 character limit):

Considering the project’s implementation cycle, please rate this project’s overall progress towards results to date:

In a few sentences, summarize what is unique/ innovative/ interesting about what this project is trying/ has tried to achieve or its approach (rather than listing activity progress) (1500 character limit).

In a few sentences summarize major project peacebuilding progress/results (with evidence), which PBSO can use in public communications to highlight the project (1500 character limit):

By making available experts as well as through the provision of facilitation and operational support, the Project added robustness to OSESGY’s mediation efforts and ensured that logistical arrangements were in place to facilitate the Geneva consultations. Indicators of this Project are closely interlinked with those defined for the work of the Special Envoy.

The Project’s funding allowed for rapid support to complement OSESGY’s activities through the deployment of experts that would otherwise have been delayed, impacting OSESGY achieving some of its objectives.

The Project helped meet a critical need to appoint international experts, including three security sector experts. The Project also assisted in mobilizing funding sources for the upcoming deployment of a team to focus on women, peace, and security agenda for Yemen, including the role of women in Track-II related activities.

In a few sentences, explain how the project has made real human impact, that is, how did it affect the lives of any people in the country – where possible, use direct quotes that PBSO can use in public communications to highlight the project (1500 character limit):

If the project progress assessment is on-track, please explain what the key challenges (if any) have been and which measures were taken to address them (1500 character limit).

The main reason for not achieving sufficient progress against the outcomes has been the deteriorating situation on the ground and the unwillingness of the Yemeni partners to constructively engage in the peace process. During the reporting period and the ongoing conflict, there have also been internal clashes between two of the allies Ansar Allah and the General People's Congress (GPC), which led to the death of the GPC-leader and former president Ali Abdullah Saleh. During the reporting period, there has also been a blockade imposed by the Coalition in the areas controlled by the Houthis, which was seriously affecting the UN's possibilities to work on the ground. In the south, the situation has also deteriorated with increased fragmentation and escalating divisions between the Government of Yemen and forces with a separatist agenda.

These issues were foreseen in the risk matrix. For example, it was indicated as high risk that the "parties to the conflict persist in seeing an advantage in continuing fighting and do not engage in good faith with the OSESG political facilitation forces" and "fragmentations of the conflict and the entrenchment of the war economy diminish the capacity of key Yemeni belligerents to deliver commitments they sign up to."

If the assessment is off-track, please list main reasons/ challenges and explain what impact this has had/will have on project duration or strategy and what measures have been taken/ will be taken to address the challenges/ rectify project progress (1500 character limit):

NA

Please attach as a separate document(s) any materials highlighting or providing more evidence for project progress (for example: publications, photos, videos, monitoring reports, evaluation reports etc.). List below what has been attached to the report, including purpose and audience.

  - Result progress by project outcome

The space in the template allows for up to four project outcomes. If your project has more approved outcomes, contact PBSO for template modification.

Outcome 1:  Working towards attainment of agreements that progressively reduce violence, through geographically specific agreements, interim security arrangements or comprehensive ceasefires and build confidence for the sustainable return to a peaceful political process.

Rate the current status of the outcome progress:

Progress summary: Describe main progress under this Outcome made during the reporting period (for June reports: January-June; for November reports: January-November; for final reports: full project duration), including major output progress (not all individual activities). If the project is starting to make/ has made a difference at the outcome level, provide specific evidence for the progress (quantitative and qualitative) and explain how it impacts the broader political and peacebuilding context. Where possible, provide specific examples of change the project has supported/ contributed to as well as, where available and relevant, quotes from partners or beneficiaries about the project and their experience. (3000 character limit)?

After the inability to reach a comprehensive agreement between the parties in Kuwait in 2016, the Project supported the Office of the Special Envoy of the Secretary-General for Yemen (OSESGY) as part of the Yemeni peace process. The Special Envoy’s strategy involved securing small progressive steps that serve as confidence-building measures, to pave the way for a comprehensive peace agreement.

During the reporting period, the Special Envoy has worked to resume the stalled peace process. To this end, the Office has been working around a set of proposals that could represent confidence-building measures, such as the Al Hodeida port, salary payments, De-escalation Committees, and Sana’a Airport, etc.

During the reporting period, the OSESGY has continued its work on several activities that were initiated before the reporting period. Experts in the Security Sector Reform (SSR) Unit in the Office of the Special Envoy, deployed for a specific period, and local staff supported by the Project, worked on developing these proposals and enhancing engagement with Yemeni interlocutors, facilitated discussions and opened channels of communication. They primarily engaged in developing mappings, elements on the Military and Security Committees to be formed in Al Hodeida, engagement with the DCC and LDCs, as well as establishing direct contacts with Yemeni stakeholders through various Track II activities and workshops.

The Project contributed to the peace process mainly through the provision of technical expertise. Four of the appointed technical experts focused on security matters or the constitution-making process. They conducted follow up to previous trips to Cairo, Amman, Sana’a, Muscat, Berlin, and Riyadh to meet with Yemeni interlocutors and/or to participate in roundtables, including Track-II discussions that the OSESGY’s partners organize and host. The experts continued to assist by developing proposals, such as plans for the Cessation of Hostilities (CoH) and mechanisms to sustain it, and interim security arrangements that would be envisioned as part of a Comprehensive Peace Agreement. The experts also provided advice and analysis for key political, armed groups and militia interlocutors on security measures and local ceasefire agreements specific to the situation in Taiz and other fronts. Consultants also provided an ongoing analysis of the strategic and operational developments on the battlefields, focusing on changes in the fronts that could affect the parties’ interest to resume negotiations and the command and control arrangements that affect leadership and institutional arrangements for the security sector reform in the post-agreement phase.

Outcome 2:  Working towards attainment of agreements on a return to an orderly and peaceful political transition which builds on the outcomes of the National Dialogue Conference and ensures continued inclusive participation of women and youth and groups across Yemen’s political spectrum.

Rate the current status of the outcome progress:

Progress summary: (see guiding questions under Outcome 1)

Many Track II activities/events have been organized outside Yemen, including in the region, while others have been held in Yemen, particularly the consultation meetings by the UN Women, and Berghof's Strategic Support Group and Youth Platform. (2017) at least 25 consultative meetings and workshops have been organized by OSE  partners. The events have focused on a wide range of subjects, including peacebuilding, internal security (both in Ta'ez and the South), women's participation in post-conflict political processes, the economy (including salaries and the current state of the banking system), the Southern Question and the constitution-making process including issues such as federalism and the role of the National Body during the post-agreement transition period

OSESGY has continued to engage in a series of consultation meetings with the different Yemeni stakeholders to map and analyze the views of the different groups and those of national experts and civil society activists. The constitutional dialogue forum started in January 2017. Since then, 12 dialogue sessions were organized. They brought together 209 Yemeni participants representative of the country's social, political, and geographical diversity. They included, notably, 25% of female participants, while the objective was to have half the participants. As part of the constitutional expert's work, the Office continued its work on its strategy on the constitution-making process through participation in the Constitutional Dialogue Forum. The strategy elaborates on both procedural and substantive aspects of the constitution-making process. In terms of process-design, the strategy elaborates on key parameters to be taken into account while planning the resumption of the process. These include the adoption of a robust legal framework for the completion of the constitutional process (1); agreement on fundamental governing principles and objectives (2); decision on, and operationalization of institutions to lead the process (3) organization of their support in terms of technical and substantive assistance (4); adoption of reasonable timelines (5); developing plans for public participation (6) negotiation and adoption procedure (7) and; ensuring effective coordination and delivery of international support (8).

Outcome 3:

Rate the current status of the outcome progress:

Progress summary: (see guiding questions under Outcome 1)

Outcome 4:

Rate the current status of the outcome progress:

Progress summary: (see guiding questions under Outcome 1)

  - Cross-cutting issues

| National ownership: How has the national government demonstrated ownership/ commitment to the project results and activities? Give specific examples. (1500 character limit) |  |
| --- | --- |
| Monitoring: Is the project M&E plan on track? What monitoring methods and sources of evidence are being/ have been used? Please attach any monitoring-related reports for the reporting period. (1500 character limit)? |  |
| Evaluation: Provide an update on the preparations for the external evaluation for the project, especially if within last 6 months of implementation or final report. Confirm available budget for evaluation. (1500 character limit) |  |
| Catalytic effects (financial): Did the project lead to any specific non-PBF funding commitments? If yes, from whom and how much? If not, have any specific attempts been made to attract additional financial contributions to the project and beyond? (1500 character limit) | The project obtained further fundig from the UK and Netherlands expressed interest in funding the project in 2018. Japan expressed interest in the WPS work of the Office and also funded a separate UN Women project. |
| Catalytic effects (non-financial): Did the project create favourable conditions for additional peacebuilding activities by Government/ other donors? If yes, please specify. (1500 character limit) |  |
| Exit strategy/ sustainability: What steps have been taken to prepare for end of project and help ensure sustainability of the project results beyond PBF support for this project? (1500 character limit) |  |
| Risk taking: Describe how the project has responded to risks that threatened the achievement of results. Identify any new risks that have emerged since the last report. (1500 character limit) | NA |
| Gender equality: In the reporting period, which activities have taken place with a specific focus on addressing issues of gender equality or women’s empowerment? (1500 character limit) | The OSE strategies were multi-dimensional, involving direct negotiations, extensive Track II consultations with women’s leaders, political movements, civil society, and programmatic collaboration aimed at preserving key state institutions and macroeconomic stability. The OSE attempted to continue the NDC marker, including nearly 30% representation of women and sizable inclusion of Youth. SE, staff, and deployees conducted numerous meetings with the Yemeni political parties, women’s groups, and civil society, including Track II activities. The consultations held after Kuwait talks were complemented by numerous meetings hosted by partner organizations, including UN Women, that were critical for broadening support for the compromises enshrined in the framework proposed by the SE. With the support of the project, OSE worked closely with the Track II events in participant selection and agenda design for the meetings. Staff from the Office or Deployees would attend most meetings with the SE himself joining occasionally. The collaboration with UN Women has been particularly important as it facilitated the creation of the Women’s Pact for Peace and Security, which became the principal conduit for the participation of women in the peace process. The Pact nominated a delegation to observe and lobby during the Kuwait talks. |
| Other: Are there any other issues concerning project implementation that you want to share, including any capacity needs of the recipient organizations? (1500 character limit) | The collaboration with Track II partners has been most effective when the meetings addressed issues well in advance of their treatment in the official negotiations. Consultations with senior Yemeni security and political figures hosted by Berghof and UN Women on the interim security arrangement and interim governing arrangements helped build consensus and understanding of the Special Envoy’s proposals. To achieve this, the consultations needed to start many months before the actual talks. The PSP allowed such preparation and coordinated the efforts of international NGOs working on the Yemen file. |

1.3 INDICATOR BASED PERFORMANCE ASSESSMENT: Using the Project Results Framework as per the approved project document or any amendments- provide an update on the achievement of key indicators at both the outcome and output level in the table below (if your project has more indicators than provided in the table, select the most relevant ones with most relevant progress to highlight). Where it has not been possible to collect data on indicators, state this and provide any explanation. Provide gender and age disaggregated data. (300 characters max per entry)

|  | Performance Indicators | Indicator Baseline | End of project Indicator Target | Current indicator progress | Reasons for Variance/ Delay (if any) | Adjustment of target (if any) |
| --- | --- | --- | --- | --- | --- | --- |
| Outcome 1 Working towards attainment of agreements that progressively reduce violence, through geographically specific agreements, interim security arrangements or comprehensive ceasefires and build confidence for the sustainable return to a peaceful political process. | Indicator 1.1 Facilitation of consultations and talks aimed at reaching agreements for a reduction in violence, ceasefires and an eventual return to a political process. | Building of initial consultations in Geneva (2015) | At least one new round | During the fall, the OSESGY has been working to jumpstart the political process by advocating different proposals that can be confidence-building measures. Preparations for consultations with one party is going on in January 2018. |  |  |
|  | Indicator 1.2 Provision of technical advice to the mediation team and the parties in the conflict to assist in the development of credible proposals for ceasefires, monitoring mechanisms and associated disarmament mechanisms along with a mechanism to ensure broad | 0 | 5 | The OSESGY were able to employ consultant to give technical advice to the mediation team. 3 consultants were deployed during the reporting period who provided technical guidance. |  |  |
|  | Indicator 1.3 Consultations are conducted in order to ensure broad public input and support for ceasefire, disarmament and monitoring mechanisms including input from diverse groups of women’s representatives. | 22 | 22 | 25 Consultations held in coordination with track II partners. |  |  |
| Output 1.1 | Indicator 1.1.1 |  |  |  |  |  |
|  | Indicator 1.1.2 |  |  |  |  |  |
| Output 1.2 | Indicator 1.2.1 |  |  |  |  |  |
|  | Indicator 1.2.2 |  |  |  |  |  |
| Output 1.3 | Indicator 1.3.1 |  |  |  |  |  |
|  | Indicator 1.3.2 |  |  |  |  |  |
| Output 1.4 | Indicator 1.4.1 |  |  |  |  |  |
|  | Indicator 1.4.2 |  |  |  |  |  |
| Outcome 2 | Indicator 2.1 |  |  |  |  |  |
|  | Indicator 2.2 |  |  |  |  |  |
|  | Indicator 2.3 |  |  |  |  |  |
| Output 2.1 | Indicator 2.1.1 |  |  |  |  |  |
|  | Indicator 2.1.2 |  |  |  |  |  |
| Output 2.2 | Indicator 2.2.1 |  |  |  |  |  |
|  | Indicator 2.2.2 |  |  |  |  |  |
| Output 2.3 | Indicator 2.3.1 |  |  |  |  |  |
|  | Indicator 2.3.2 |  |  |  |  |  |
| Output 2.4 | Indicator 2.4.1 |  |  |  |  |  |
|  | Indicator 2.4.2 |  |  |  |  |  |
| Outcome 3 | Indicator 3.1 |  |  |  |  |  |
|  | Indicator 3.2 |  |  |  |  |  |
|  | Indicator 3.3 |  |  |  |  |  |
| Output 3.1 | Indicator 3.1.1 |  |  |  |  |  |
|  | Indicator 3.1.2 |  |  |  |  |  |
| Output 3.2 | Indicator 3.2.1 |  |  |  |  |  |
|  | Indicator 3.2.2 |  |  |  |  |  |
| Output 3.3 | Indicator 3.3.1 |  |  |  |  |  |
|  | Indicator 3.3.2 |  |  |  |  |  |
| Output 3.4 | Indicator 3.4.1 |  |  |  |  |  |
|  | Indicator 3.4.2 |  |  |  |  |  |
| Outcome 4 | Indicator 4.1 |  |  |  |  |  |
|  | Indicator 4.2 |  |  |  |  |  |
|  | Indicator 4.3 |  |  |  |  |  |
| Output 4.1 | Indicator 4.1.1 |  |  |  |  |  |
|  | Indicator 4.1.2 |  |  |  |  |  |
| Output 4.2 | Indicator 4.2.1 |  |  |  |  |  |
|  | Indicator 4.2.2 |  |  |  |  |  |
| Output 4.3 | Indicator 4.3.1 |  |  |  |  |  |
|  | Indicator 4.3.2 |  |  |  |  |  |
| Output 4.4 | Indicator 4.4.1 |  |  |  |  |  |
|  | Indicator 4.4.2 |  |  |  |  |  |

PART 2: INDICATIVE PROJECT FINANCIAL PROGRESS

  - Comments on the overall state of financial expenditures

Please rate whether project financial expenditures are on track, delayed, or off track, vis-à-vis project plans and by recipient organization:

How many project budget tranches have been received to date and when do you expect to request the next tranche if applicable: 1 /  no other tranches were planned

What is the overall level of expenditure/ commitment against the total budget and against the tranche(s) received so far: USD 799,493

If expenditure is delayed or off track, please provide a brief explanation (500 characters limit): NA

Please state what $ amount was planned (in the project document) to be allocated to activities focussed on gender equality or women’s empowerment and how much has been actually allocated to date: USD 900,000

Please fill out and attach the project document Excel budget Annex showing current project financial progress (expenditures/ commitments to date), using the original project budget table in Excel, even though the $ amounts are indicative only.

# Footnotes

Note: commencement date will be the date of first funds transfer.

Maximum project duration for IRF projects is 18 months, for PRF projects – 36 months.