## OVERALL REPORTING INSTRUCTIONS
OVERALL INSTRUCTIONS
1 | All questions/sections must be responded to before submitting to secretariat. Once the document is uploaded in the relevant folder (as per instruction below) please email the secretariat.
2 | To ensure high quality narrative and results reports please pay attention to the following details: a) A well written, succinct summary that is very clear about what was done during the reporting period and results achieved, with a priority on concrete activities, beneficiaries reached and achievements beyond processes b) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document; c) In case certain indicators are not longer relevant, an explanation for why they are not. d) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document and how they align with the overall SERP joint workplan, and connection to reporting on global-level SERP indicators e) Indicate the relevant SERP monitoring framework global indicators that were contributed to as part of this project. f) An honest analysis of challenges faced, the responses to these challenges and the extent to which these responses were successful or not g) Go beyond generic, standard and well documented features of successful project implementation when reflecting on innovation and focus on what is truly new for you and which could enable replication efforts
3 | You must submit this completed workbook by uploading it in the relevant Project Folder here (https://undp.sharepoint.com/:f:/r/sites/covid19mptfcall1/Shared%20Documents/2020-REPORT?csf=1&web=1&e=j3cc3J). Please note if you are unsure of your project number please refer to http://mptf.undp.org/factsheet/fund/COV00
A | ANNUAL REPORT
DEADLINE: 31 January 2021
4 | ALL projects that received funds in 2020 must complete annual report, HOWEVER if you have your project ending on 31st December 2020 - your FINAL report is your annual report.
5 | If you received a no-cost extension on your project please do the annual report and in a few months time you can update the annual report to include activities to complete your end of project report.
6 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.
B | END OF PROJECT - FINAL REPORT
DEADLINE: 31 January 2021
7 | ALL projects that received funds in 2020 must complete annual report, HOWEVER if you have your project ending on 31st December 2020 - your FINAL report is your annual report.
8 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.

## General Information-Final
Programme Title & Project Number |  | Programme Duration
Programme Title: | Enhancing Food Security and Building Socioeconomic Resilience to Covid-19 in Tuvalu | Overall Duration (months) | 10 months
Programme Number (if applicable) | UNJP/TUV/001/UNJ | Start Date (dd.mm.yyyy) | 25.05.2020
MPTF Office Project Reference Number: | UNJP/TUV/001/UNJ | Original End Date (dd.mm.yyyy) | 31.12.2020
Country | Tuvalu | Current End date(dd.mm.yyyy) | 31.03.2021
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | FAO, IOM and ILO | National counterparts (government, private, NGOs & others) and other International Organizations | Department of Labour, National Statistics Office, Tuvalu Overseas Seamen's Union, Tuvalu National Private Sector Organisation, Tuvalu Fisheries Department and the Tuvalu Maritime Training Institute.
Report Cleared By
o Name:
o Title:
o Email address:
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the relevant decision-making body/Steering Committee.
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Final
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum) | The ‘Enhancing food security and building socio-economic resilience to COVID-19 in Tuvalu’ project supported by the UN COVID-19 Response and Recovery Multi Partner Trust Fund, began implementation in June 2020 and aims to contribute towards reduced human, economic and social toll of the COVID-19 pandemic for at-risk people in Tuvalu. The programme is being delivered through a partnership of UN agencies: Food and Agriculture Organization (FAO), the International Organisation for Migration (IOM) and the International Labour Organization (ILO). (a) FAO: The interventions of FAO focused on strengthening the capacities to enhance food security and nutrition through provision of resources and materials available for small-scale fishing boat building and repair, aquaculture, and fish post-harvest. FAO also worked on the first report on agriculture statistics of Tuvalu and recommendations on agriculture module for the next Population and Housing Census. To date there are no COVID-19 cases in Tuvalu, and this is probably the result of strict lockdowns and restricted flights and shipping in and out of Tuvalu. Consistent with protection of the population, The Tuvalu Government decided to relocate 50 families to the outer islands as a measure to mitigate the spread of any COVID-19 cases. The strict lockdowns globally and in countries that produce fishing inputs have also severely disrupted supply chains. In addition to the pandemic, between 16-19 January 2020, Tropical Cyclone (TC) Tino battered the tiny, isolated country of Tuvalu (population 11,000) with heavy rain, squalls, thunderstorms, rough to high seas, heavy swell, and gale-force winds of 75 km/h. The high winds combined with a very high tide caused waves of 8 m (26 ft) causing catastrophic flooding. The storm caused damage to infrastructure including buildings, roads, and homes as well as damage to livelihoods. The government of Tuvalu declared a State of Emergency for the country on 24 January 2020, estimating that approximately half of the nation was "severely affected" by TC Tino. Due to the damages caused by the Cyclone Tino, FAO under the Technical Cooperation Program initiated an emergency project - TCP/TUV/3801 (E) entitled “Emergency assistance to reduce impacts and build resilience in the fisheries sector caused by Cyclone Tino and COVID-19 in Tuvalu” to assist these families to regain food security the country. These projects complement and supplement each other to support the restoration of food security caused by the pandemic and the damages caused by Cyclone Tino. The technical capacity, resources and materials for small-scale fishing boat building and repair and aquaculture and fish post-harvest to be provided to communities and fishers for fisheries production and post-harvest activities aimed to help restore and/or increased nearshore oceanic fisheries in the outer islands. To date the project has committed all the funds for fisheries to purchase the materials. The materials will be used to build 45 canoes, repair Community Fisheries centres in three (3) outer islands and provide fish handling and processing equipment to the Funafuti fish market. However, because of the strict restrictions, deliveries of these materials have been delayed. In addition, FAO in collaboration with the Tuvalu Central Statistics Division and South Pacific Community (SPC) Statistics for Development Division, prepared an analytical report that provided important agricultural data collected in the Population and Housing Censuses in 2012 and 2017, and the 2015/16 Tuvalu Household Income and Expenditure Survey (HIES). This can be used to develop recommendations for the agriculture sector. The Government of Tuvalu and other partners can utilize the interventions from this project to increase fish production for food security and develop evidence-based decisions on the development agriculture to further support food security. (B) IOM and ILO: The project has sucessfully completed development and dissemintation of final national assessment report evaluating the impact of COVID-19 on Tuvalu's labour market, specifically the impacts on employment, businesses and households. (Annex 1: Final Report) A field survey and focused group meetings were carried out from 11 to 21 November 2020 in collaboration with the National Tripartite Committee (NTC) comprising of the officials from the Department of Labour, National Statistics Office, Tuvalu Overseas Seamen's Union and Tuvalu National Private Sector Organization (Annex 2 (a): tripartite committee ToR and Annex 2(b) Tripartite Committee letter). A total of 32 businesses (comprising 10% of total businesses), 189 workers (20% of all workers), 23 laid-off employees (8% of all laid-off workers) and 87 households (comprising 10 % of households) on the main island of Funafuti were covered under the national survey. Survey results indicate that while the effects of COVID-19 during the immediate state of emergency period has been marginal on Tuvalu, the situation may deteriorate should the pandemic persist. This is primarily due to Tuvalu’s dependence on external supplies and remittances from the Tuvaluan diaspora. Fortunately, because Government and private sector are the principal employers, impact on majority of workforce has been minimal. The extensive analysis that was carried out and confirmed through an exhaustive validation exercise with both the Government of Tuvalu, NTC and members of the community who had participated in the national survey enabled the project team to formulate a robust set of innovative recommendations to support the Government of Tuvalu to embark on the path of economic recovery once the pandemic subsides. The report findings and recommendations have since been disseminated to 43 participants from Government of Tuvalu, as well as survey participants for discussion and for future planning and action during a roundtable meeting held on 10 March 21. Following this roundtable meeting, the report was submitted to the Government Advisory Committee and the cabinet for information. (Annex 3: Roundtable meeting report) The assessment also identified the significant impact of COVID-19 on employment of seafarers related to the closure of borders and suspension of flights. The seafaring sector plays a crucial role in Tuvalu's economy and has often contributed substantially towards the rate of remittances that are sent back to families and communities back home. Through a budget revision to reallocate excess funds, the project enabled economic recovery pathway in collaboration with the Department of Labour, Government of Tuvalu towards the implementation of refresher course trainings for seafarers with the Tuvalu Maritime Training Institute (TMTI). As a result, 23 candidates were selected to undergo the refresher course training between 2 March to 28 March 2021 that would essentially seek to upskill, renew and prepare seafarers for employment once borders were open. (Annex 4: Seafarer Refresher Course training report)
2 | Purpose (and Beneficiaries) | Please include the number of both direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups | (A) FAO: The FAO activities in the project focused on benefitting fishers (men and women across the value chain – harvesting, processing and selling) and fishing households as well as those using the community fisheries centres and participating in fishing associations. The direct beneficiaries for the fisheries component of the project are estimated to be 452 persons. It is estimated that 50 families consisting of some 200 persons (100 men and 100 women and girls) would benefit from the paddling canoes being built for the outer islands. For the repairs to the Community Fish Centres, an estimated of 80 women and 60 men will directly benefit and for the repairs. For the beneficiaries in the Funafuti fish market, the TFD had advised that the association operating the market has 112 members (22 female); they will be the direct beneficiaries. The broader population will benefit indirectly from improved fish supplies and products. (B) IOM and ILO: The national assessment covered the following indirect beneficiaries: • 32 enterprises • 189 workers of which 57% female and 43% male. In terms of age 50% below 35, 28% between 45-55 and 7% above 55. • 23 laid-off employees of which 92% male and 8 % female. In terms of age, 17% were below 30, 50% were between 30-40 and 33% above 40 • 87 households on the main island of Funafuti • In addition, 23 seafarers were covered under the seafarer training (100% male due to the limited number of women seafarers in Tuvalu; data collected for 18 seafarers- 11% below 30; 34% between 30-40; 55% between 40-60 ).
3.1 | Results: Outcome Level | Please include outcome level results achieved | (A) FAO: outcome 2.1 2.1 Number of communities who received technical guidance and materials for fishing and aquaculture activities The Vaitupu community will have their lost milkfish cages replaced and have received assistance on aquaculture farming. 50 families who receive canoes will also receive fishing gears to use with the canoes. (B) IOM and ILO: outcome 2.2 The project has successfully achieved outcome 2.2 "Government of Tuvalu develops a socioeconomic intervention to mitigate the impact of COVID-19 on labour market and remittances as a source of livelihoods." Following the completion of the national assessment evaluating the impact of Tuvalu's labour market in the context of COVID-19, the findings and recommendations were validated through a series of focus group discussions. The final report and findings were presented to Government, worker and employer representatives during a final rountable on 10 March 2021. As a conclusion to this meeting, participants agreed to submit an information paper with the report to the Government Advisory Committee (GAC), comprising Chief Executive Officers from all Government Ministries and then to the cabinet, as per (Annex 5). At the GAC meeting of 18 March 2021, the GAC supported the report and noted that it should be considered in the National strategic plan 'Te Kete' in terms of labour mobility (Annex 6). The Government's commitment to implementing the recommendation is also demonstrated through the joint-implementation of the seafarer refresher training courses, which builds off recommendations contained in the report. The socio-economic interventions put in place by the Government of Tuvalu will only be evident through ex-post evaluation.
3.2 | Results: Output Level | Please include output level results achieved | (A) FAO: output 2.1.1 2.1.1 [Boat building manual, kit sets and materials disseminated/distributed to targeted communities] Boat building manuals were prepared and shared with the two (2) boat builders and six (6) apprentices for the construction of one-man paddling canoes. Canoe building videos have also been filmed and shared with Tuvalu Fisheries Department (TVD). Canoe building tools have arrived and will be distributed to the beneficiaries in October 2021 while the materials for paddling canoes is set to arrive in the country at the end of April 2021. Construction of canoes has commenced (using existing locally available materials) and the building of the first canoes serves as the training platform for the apprentices to build all 45 canoes. A local boatbuilder was hired to train six (6) apprentices in the construction of the one-man paddling canoe using the compounded plywood technique. 2.1.2 [Technical guidance and materials disseminated/distributed to targeted fishers associations, community fisheries centres and aquaculture stakeholders] A step-by-step video training guide on how to assemble the solar fish dryers was prepared by the project team. In addition, a step-by-step video training guide on food safe production of novel tuna products has been developed as a training aid for the community fish centres. The guides will be translated into national language by the fisheries department. Central fish market equipment and fish processing equipment are expected to arrive in the country by the end of April 2021. Distribution to the beneficiaries will follow immediately. 2.1.3 [National Statistics Office received technical support to analyse agriculture data for 2017 PHC and recommendations for agriculture module in 2022 PHC by December 2020] The analytical report, which is an output of good collaboration between Tuvalu Central Statistics Division, SPC and FAO, provides important agricultural data collected in the Population and Housing Censuses in 2012 and 2017, and the 2015/16 Tuvalu Household Income and Expenditure Survey (HIES). The report covers issues of cropping and livestock activities, household fishing and handicraft activities, as well as details of climatic and natural disaster events impacting on households. The report has been well accepted by the national partners and will be disseminated at https://stats.gov.tv/. (B) IOM and ILO: output 2.2.1 The results achieved under output 2.2.1 include: • Final Report (Annex 1); • In-depth information has been collected from government officials, employer and worker organizations to inform the development of the assessment; • Validations sessions with stakeholders have taken place to corroborate the findings; • Validation exercises with Government of Tuvalu focal points; • Presentation of findings and recommendations of the Final Report to relevant Government focal points for future policy planning. Submitting brief to the Government Advisory Council (GAC) Secretary to inform Government Officials on the findings and recomendations that were highlighted in the final report. The presentation of the brief was well supported and recommendations were made during the meeting to ensure that the key points highlighted in the report were provided to the National Strategic plan Te Kete in terms of labour mobility. As a whole, the brief was well noted and supported by GAC members. (Annex 5 GAC paper, Annex 6 GAC meeting minutes). • Shipment and dissemination of final report (110 copies) to Government and other stakeholders • Seafarer refresher course training for 23 candidates with the Department of Labour and TMTI (Tuvalu Maritime Training Institute) to support with economic recovery. (See Annex 7: photographs of output level results.)
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words) | (A) FAO Implementing a project during the pandemic poses a lot of challenges as well as opportunities for learning. Travel and movement restrictions have affected mobility for both national and international staff and international procurements was identified as the most difficult challenge encountered. As not all of the required interventions are available in the country the purchase of materials that meet the technical specifications were done overseas. However, delays in the delivery were experienced due to the supply shortages and movement restrictions imposed because of the global pandemic. The effects of the delays were mitigated by using locally available materials as training and demonstration materials while waiting for the completion of the delivery of the necessary procurement. Supply chains have been disrupted globally and despite FAO's best efforts to procure the materials and equipment on time, there were still delays of up to three (3) – four (4) months for deliveries to materialise. These are in addition to the FAO procurement process which includes assessment, technical specifications, tender and award of bids. FAO uses the UN INTEND system to purchase goods and equipment. Most local stores and shops had very limited supplies and the even some international supplies had to wait on their own back orders before filling the orders for FAO. Small quantities available locally were purchased to be used as training materials while waiting for the international orders to arrive. Fisheries procurement of materials and equipment has been slow due to the disruption of supply chains caused by the pandemic. Suppliers could not supply all the materials required and some supplied short orders. The different procurements are expected to be delivered before end of April 2021. (B) IOM and ILO • Travel restrictions in Tuvalu also severely restricted mobility for national and international staff. In order to overcome this difficulty, the project engaged a home based research consultant to provide technical advice and input to the assessment, and a national consultant and enumerators based in Funafuti, Tuvalu. A budget revision was also undertaken to reallocate expenses towards implementing recommendations of the report with a view to achieve the expected outcomes. • Reduced time to complete report. To ensure the timely collection of data, the national consultant worked on data collection over extended periods of the day. • Unavailability of interviewees at times scheduled. The research team attempted to identify times suitable to the interviewees such as conducting interviews post-working hours; additional names were also identified as backups to ensure that the sample size was adhered to. • Assessment ‘fatigue’ related to several assessments on COVID-19 being conducted. In order to overcome this difficulty, the project team collected as much information as possible from secondary sources. Further, the project team has been working closely with a Tripartite taskforce to coordinate the assessment, reduce duplication and ensure sustainability of recommendations in the post-survey scenario. • The combination of Tuvalu’s geographical nature, inconsistent transport system, project budget & timeline affects data collection from remote atoll communities. Given these geographical and technological challenges, the mobile-based survey was concentrated in Funafuti, including 32 enterprises, 187 employees and 23 laid-off employees, and 87 households. Remote atoll communities were not included in the research. • Challenges in implementing seafarer trainings. The seafarer training suffered various challenges related to the limited time to implement the training; limited number of service providers in Tuvalu; limited number of women seafarers. Since the training was organized within 3 weeks, many seafarers that had registered were unable to apply and secure annual leave from their new employments to participate in the trainings; this includes Tuvalu's two women seafarers employed on the national navy patrol boats. Ultimately, only 23 seafarers were able to participate in the current training organized by the Department of Labour from 2 March 2021-23 March 2021. With the excess funds, the Government of Tuvalu has committed these expenses to a next cohort focusing on security training, to be provided before June 2021.
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words) | (A) FAO Implementing a project during the pandemic poses a lot of challenges as well as opportunities for learning. Travel and technical support by international consultants were hampered by the pandemic. Online platforms such as Zoom cannot replace face to face expertise on the ground. However, it should be also noted that even with expertise on the ground, the slow delivery of materials still hampered the work to be done. FAO does not have an in-country office in Tuvalu. However, to complement, the national project assistant hired under a regional project GCP/SAP/002/JPN assists in coordination between the Tuvalu Fisheries Department and Sub-Regional Office in Samoa to implement the project. A task force has also been set up and regular meetings have been held. Intra project support to achieve common goals helped reduce costs and increase cohesion and focus. It was seen that there is a great need for countries to develop better Disaster Risk Reduction Strategies and Plans and that there should be the accompanying training and integration of DRR into national legislative frameworks. This will help in mitigating the threats posed by future pandemics and natural disasters. This will complement the DRR assessment in the Fisheries Sector being undertaken by the TCP. The lesson in this pandemic is as travel and procurement was severely hampered, countries should pay more attention to risk reduction measures. (B) IOM and ILO • The establishment of the Tripartite taskforce to work towards output 2.2.1 promoted a close involvement of both government and other non-government stakeholders. This has ensured ownership of the study results in Tuvalu and its uptake in designing future projects and responses to COVID-19. • The assessment adopted a similar methodology used to conduct national assessments in other countries in the Pacific region, which was tailored and contextualized to Tuvalu, based on inputs from the tripatite committee. The assessment adopted lessons learned from other assessment processes undertaken in the region to quickly devise mitigation measures for many emerging challenges related to non-responsiveness of stakeholders, identification of target groups, etc. • In terms of gender markers, the programme aimed to ensure a gender balance in both the tripartite committee, as well as in data collection. Ensuring this balance has contributed to understanding the gender-differentiated impact of COVID-19 in Tuvalu and will support the developed of gender-responsive recovery strategies. • Supporting the Government to implement the seafarer training has also cultivated a sense of ownership of the report findings and ensured achievement of the project outcomes. Evidence towards policy development: • Businesses and workers under the marine sector are the most affected group, particularly fisheries observers and seafarer. About 52% of them are Fisheries Observers, 35% are seafarers and 13% are cleaners and others. • Government employment has not been largely affected by COVID-19, with nearly 97% of employees still having same working hours and 94% reporting no reductions in their wages • The top five key assistance businesses require from the government which include: tax relief exemption; Restore logistic channels; Financial assistance package; Access to credit; Assistance in obtaining supplies. Interestingly, 20% of businesses mentioned that they do not require assistance from the government. • If the pandemic continues longer, most of the workers were expecting an alternate source of incomes or jobs. One-third of workers had the option of getting into self-employment while 21% will opt for taking jobs in other fields. Nearly 19% will explore going back to their island for agriculture farming while 18% had not planned any alternate source of income. • In terms of food security, 68% of the households reported that the SOE had slight or no impact while around 18% mentioned that SOE had a significant impact on their food security. 40% of households’ income was towards food expenses and the next highest expense is borne by the households was on cultural and family obligations (17%) followed by school-related expenses (11%) and transportation (8%) and church obligations (6%). • Moreover, nearly 89% of households mentioned that their family members working overseas will not be returning to Tuvalu and those who did plan or planning to return admitted that the government has supported their repatriation. However, more than two-thirds of households mentioned that there is no government package to migrants returning to the country. • The vast majority of participants who were involved in the seafarers refresher course training were male as seafaring is a occupation that is widely accepted for men in Tuvalu. Further effort and attention is required to grow the number of females involved in the seafarers industry as the rate of participation is disproportionate.
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words) | (A) FAO The main partner for the fisheries aspects of the project was the Tuvalu Fisheries Department. The Tuvalu Fisheries Department is the Government Agency responsible for all aspects of Fisheries Management and Development in Tuvalu. To complement the interventions for this project, a Letter of Agreement was signed between the TFD and the FAO under the “Emergency assistance to reduce impacts and build resilience in the fisheries sector caused by Cyclone Tino and Covid 19 on Tuvalu” project, which is operationally active simultaneously with UNJP/TUV/001/UNJ. The synergies created by operating the project simultaneously has reduced the personnel costs and allowed the UNJP's project to focus and maximize its expenditures on supply of materials while the TCP project provided the labour costs to build the canoes The FAO Fisheries Team has regular meetings with the Tuvalu Fisheries Department on the project activities, procurement and delivery. FAO has also collaborated with Tuvalu Central Statistics Division and SPC for the analytical report containing agricultural data collected. (B) IOM and ILO •Through the establishment of a tripartite taskforce under output 2.2.1, the project team collaborated with the Government of Tuvalu (Department of Labour, the National Statistics Office), worker representatives (the Tuvalu Overseas Seamen’s Union) and employer representatives (Tuvalu National Private Sector Organisation). •The role of the tripartite taskforce was to provide multistakeholder input to the design and implementation of the survey, including sampling methodology, identifying target groups. The tripartite taskforce had also been critical in reviewing and informing the recommendations and the survey results. These partnerships had enabled buy-in and ownership from key stakeholders, which was important both for the delivery of the survey and will be for the up-take of the recommendations. • In particular, the project team developed a strong partnership with the Department of Labour and through this connection recommendations were received on how best to support the seafarers who were left unemployed due to the pandemic. The Department of Labour implemented the seafarer refresher course trainings through TMTI in an effort to action some of the recommendations that were identified in the final Report. • 6 Samsung galaxy tablets were purchased at the commencement of the project to support enumerators with the collection of data during the national survey. Thereafter, the samsung galaxy tablets were donated to the tripartite committee officials to support Government with constant evaluation of the economic conditions in Tuvalu during the pandemic. (See annex 8).
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken.
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place | •Tuvalu’s response to Covid-19, which included border closures and temporary halting of scheduled flights. To minimise the impact of these challenges, a budget revision was submitted by the IOM-ILO team to re-direct funds initially allocated for travel and daily standard allowance costs towards a more comprehensive implementation of the national survey. •This revision was submitted in November 2020 for a total amount of USD $27,640, redirected towards the recruitment of communications specialist and editor, communications and publications material and shipping, and tablets to be used by the enumerators and to be handed over to the tripartite taskforce. Additionally, the IOM-ILO team requested and was granted a three month no-cost extension to ensure that the budget is efficiently expended. The project reached completion on March 31, 2021. •Second budget revision request for IOM on 19/02/2021was approved by the donor as of 23/02/2021. Through the revision, excess funding amounting to US $24,000 will re-allocated to deliver “refresher courses” for seafarers as a response to the impacts of COVID-19. Training will be coordinated by the Department of Labour in Tuvalu, and conducted by the Tuvalu Maritime Training Institute (TMTI) for seafarers to ensure they are work-ready. As detailed above, the refresher training course was identified as a tangible way to respond to recommendations identified under the final Report. Annex 9: Media Press release.
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners. | •Output 2.2.1 is delivered through support of an international research consultant to provide technical advice and input to the assessment, as well as a national consultant and enumerators based in Funafuti, Tuvalu. The national consultant is responsible for the national oversight of the assessment, development of communications tools and data collection that has been provided to the research consultant to draft the national assessment. Annex 10: Tuvalu Project flyer. •Six tablets were procured under the project to support with data collection under the current assessment and will be handed over to implementing partners to support with future data collection activities. • In addition, the project underwent the procurement of venue hiring and food catering for the exhaustive validation exercises that were conducted after the national survey was completed in an effort to formulate a better understanding of the economic impacts of COVID-19 on Tuvalu's economy and communities. • The project team formalised an implementation agreement with the Department of Labour, Government of Tuvalu to conduct and implement the seafarers refresher course training with TMTI as a tangible method of responding to recommendations that were identified under the final Report. • The procurement of a professional photographer and videographer was also made to capture community consultation, validation exercises and government participation throughout the development of the project. Moreover, services were procured to ensure that the Reports were printed and disseminated accordingly through various delivery services.

## RBM-Final
| Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 2[1] Capacities strengthened to enhance food security and nutrition
Indicator: Number of communities who received technical guidance and materials for fishing and aquaculture activities
Baseline:
Planned Target:80% of households in targeted outer islands and 20% in Funafuti received technical guidance and materials for fishing and/or aquaculture activities by December 2020
Output 2.1.1 Resources and materials available for small-scale fishing boat building and repair | Boat building manual is being finalized. Boatyard location identified and concurred by the Tuvalu Fisheries Department (TFD) The most affected islands are remote with limited experience in building canoes for the affected populations. The project has made templates for wood cutting to speed up production for the boats to be built. However, it was decided to build the boats in Funafuti due to the difficult logistics problems. The canoes will be sent to the outer islands once they are completed. Construction of canoes has commenced and the building of the first canoes served as the training platform for the apprentices to build all 45 canoes. A local boatbuilder was hired to train six (6) apprentices in the construction of the one-man paddling canoe using the compounded plywood technique. Boat building materials such as marine plywood have been partially delivered and expected to be completed by April 2021. Technical guidance was provided through Mr. Derin Pendle. An additional local boat builder has been hired and six (6) boat building apprentices from the National trade school in Funafuti have been engaged to build capacity on canoe building. | The targeted beneficiaries remain the same. However, there are delays in the delivery of resources and materials because of the restrictions in movement of both personnel and supplies brought about by the COVID-19 pandemic. | • Boat building manual • Email communication with TFD • Shipments and Bill of Lading
Indicator 2.1.1a: Boat building manual, kit sets and materials disseminated/distributed to targeted communities
Baseline:0
Planned Target: Boat building manual, kit sets and materials disseminated/distributed to all targeted communities by December 2020
Output 2.1.2 Resources and materials available for aquaculture and fish post-harvest | Awaiting delivery of materials by the end of April 2021. Letter of Agreement (LOA) between FAO and TFD has been executed. This is complementary to the activities of the project. The LOA covers vessel construction, repairs and distribution of boats, post-harvest materials and equipment to the affected communities Similar to the boats mentioned above, the project also made templates for the postharvest solar fish dryers. | The target remains the same. However, the procurement of materials and equipment has been slow due to the disruption of supply chains caused by the pandemic. Suppliers could not supply all the materials required and some supplied short orders. Only one bid for tender of aquaculture supplies was received and another RFQ was launched and tendered for aquaculture materials. | • LOA with TFD • A step-by-step video training guide on how to assemble the solar fish dryers • Shipments and Bill of Lading
Indicator 2.1.2: Technical guidance and materials disseminated/distributed to targeted fishers associations, community fisheries centers and aquaculture stakeholders
Baseline: 0
Planned Target: Technical guidance and materials disseminated/distributed to targeted fishers associations, community fisheries centers and Vaitupu aquaculture stakeholders by December 2020 - beneficiaries (disaggregated by age and gender)
Output 2.1.3 Report on agriculture statistics and recommendations for agriculture module in next Population and Housing Census available
Indicator 2.1.3: National Statistics Office received technical support to analyze agriculture data for 2017 PHC and recommendations for agriculture module in 2022 PHC | The analytical report, which is an output of good collaboration between Tuvalu Central Statistics Division, SPC and FAO, provides important agricultural data collected in the Population and Housing Censuses in 2012 and 2017, and the 2015/16 Tuvalu Household Income and Expenditure Survey (HIES). The report covers issues of cropping and livestock activities, household fishing and handicraft activities, as well as details of climatic and natural disaster events impacting on households. The report has been well accepted by the national partners and will be disseminated in https://stats.gov.tv/. | There has been a delay in access to data which further delayed some of the planned activities. Currently the report is with the editor and graphic designer before the dissemination. | Final draft of Agriculture & Fishing Monograph of Tuvalu
Baseline: No agriculture data available for policy makers
Planned Target: National Statistics Office received technical support to analyze agriculture data for 2017 PHC and recommendations for agriculture module in 2022 PHC by December 2020
Please include all three: Baseline, Planned Target and Achieved Targets
[1] Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.
Outcome 2.2 Government of Tuvalu develops a socioeconomic intervention to mitigate the impact of COVID-19 on labour market and remittances as a source of livelihoods.
Indicator 2.2a: Government of Tuvalu endorses recommendations in the impact assessment | Final assessment completed. Exhaustive validation exercises have been completed with the national tripartite committee, Government officials and members of the Tuvalu community who participated in the national survey. | Covid-19 related delays in conducting the assessment | Final report completed (see annex 1), NTC meeting photographs, meeting minutes.
Baseline: No
Planned Target: Yes
Indicator 2.2b: Government of Tuvalu commits to pursing agreed upon recommendation | Yes The Government of Tuvalu, through the Government Advisory Committee supported the findings of the report and noted that the report findings be considered in the National Development Strategy, specifically for labour mobility. Further commitment was demonstrated through the implementation of seafarer trainings. | Covid-19 related delays in conducting the assessment | • Annex 4: Government of Tuvalu activity report on seafarer refresher training courses • Annex 5: Information note submitted by Department of Labour to Government Advisory Committee • Annex 6: Government Advisory Committee Meeting minutes, 18 March 2021
Baseline: No
Planned Target: Yes
Indicator 2.2c: # of people benefiting from socio-economic support. | The Government of Tuvalu has agreed to consider the recommendations in its national development strategy to cover its entire population. |  | Policy reports / Government releases
Baseline: No
Planned Target: 11,000 beneficiaries (disaggregated by age and gender)
Output 2.2.1: An assessment report evaluating the impact of COVID-19 on labour migrants and social protection needs of recipient households, and economy of Tuvalu is available
Indicator 2.2.1a: Impact assessment report produced | Yes Final assessment Report developed (Annex 1) Validations sessions with stakeholders conducted | Covid-19 related delays in conducting the assessment | Final Report / Meeting minutes/Photographs
Baseline: No
Planned Target: Yes
Indicator 2.2.1b: # stakeholders receiving reports | Yes Final assessment report disseminated to all stakeholders, relevant UN agencies and members of the national tripartite committee. 43 participants of the roundtable received the final draft of the report. Further 110 hardcopies were shipped to Tuvalu for further dissemination. | Covid-19 related delays in conducting the assessment | emails, invoices and payment for printing and shipment/delivery to Funafuti, Tuvalu.
Baseline: None
Planned Target: 15
Output 2.2.2:Aspirant and returned seafarers affected by COVID-19 have increased skills and knowledge to be able to seek employment.
Indicator 2.2.1a: No. of beneficiaries trained | 23 The project did not meet the target due to the short timeframe to organize the seafarer training. Despite registration of 52 seafarers, several were unable to participate due to various logistical reasons. The excess funds have been committed to a next cohort, to be completed by the Government of Tuvalu by June 2021. |  | Final Report / Meeting minutes/Photographs
Baseline: 0
Planned Target: 30

## Communication-Final
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
(A) IOM and ILO Impactful Story: Assessment on the economic impact of COVID19 in Tuvalu - Magao Eliu previously worked at the Funafuti Lagoon Hotel before the COVID-19 pandemic hit. Magao has always enjoyed work in the hospitality and hotel sector and took pride in welcoming tourists, international consultants and various visitors who would visit to undertake work with the Government of Tuvalu and communities. Magao told the project team how difficult it was to make ends meet after she was informed that she would have reduced working hours and a pay cut. Magao's family have adapted to the current economic climate by venturing into other modes of income. Magao has joined her mother's sewing business and together they intend on building a shirt sewing venture. The income she makes from her new sewing venture contributes towards food, medicine and other family expenses.
(A) IOM and ILO Impactful Story: Seafarers Refresher Course Training in Tuvalu - Mr. Pule Telsia. Prior to COVID-19, Pule use to work on fishing vessels as a seafaring fisherman. He loved life out at sea and was happy that he could contribute financially towards his families well-being. Tuvaluans are known for their seafaring skills, traditional knowledge of the ocean and their ability to read the waves. Many seafarers like Pule cannot find work on overseas vessels because of the closure of borders and now that reality is harder since certifications need to be updated on a regular basis. Pule did not hesitate to join the seafarers refresher course training that was organized by the project team, Department of Tuvalu and the Tuvalu Maritime Training Institute (TMTI) as it provided participants with a lifeline to undertake the expensive refresher course training for free. As a result, Pule now believes that he is in a better position to seek employment when border open.
2. Upload here: Communications and Visibility (OPTIONAL)
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well picture material please make sure you include all credits and upload them in high resolution Call1 countries.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board
(A) IOM and ILO
Mr. Pule Telsia: social media card posted on IOM social media platforms (twitter and facebook) to maximise visibility
Mr. Pule Telsia: social media card posted on IOM social media platforms (twitter and facebook) to maximise visibility
Opening day of Tuvalu's seafarers refresher course training. Photograph of participants of the course, representatives of the Government of Tuvalu, national consultant under project team and officials from TMTI.
(B) FAO Canoe building video - https://youtu.be/E5SRaDc6VRA
Canoe building at Tuvalu Fisheries department FAO TCP project
A step by step video training guide on how to assemble the solar fish driers for Tuvalu has been developed as the training aid to assemble 8 solar fish driers in Tuvalu
A step by step video training guide on food safe production of novel tuna products has been developed as a training aid for all 8 community fish process centres, the guide will be translated into local language by the National project assistant.