PROGRAMME ANNUAL PROGRESS REPORT

Period: 1 January – 31 December 2019

| Project Name | Building Inclusive and Accountable Parliaments for a Peaceful Somalia (PSP-II) Award/Project Number: 00099031/ 00102267 |
| --- | --- |
| Gateway ID | 00113070 |
| Start date | 01 January 2019 |
| Planned end date (as per last approval) | 31 December 2021 |
| Focal Person | (Name): Dragan Popovic |
|  | (Email): dragan.popvic@undp.org |
|  | (Tel): |
| Participating UN entities | UNDP, UNSOM (PAMG) |
| NDP Pillar | PWG Pillar 1: Inclusive Politics: Achieve a stable and peaceful federal Somalia through inclusive political processes and effective decentralization |
| UNSF Strategic Priority | Deepening federalism and state-building, supporting conflict resolution and reconciliation, & preparing for universal elections |
| Location(s) | Federal; Somaliland; Puntland, Galmudug, Jubaland, Southwest, and Hirshabelle states |
| Gender Marker | 2 |

| Total Budget as per ProDoc (in USD) | 20,018,656 |
| --- | --- |
| MPTF: | 2,501,292 |
| Non-MPTF sources: | PBF:0 |
|  | Trac: 1,853,069.23 |
|  | Other: 135,000 (IDB) |

|  | PUNO | Report approved by: | Position/Title | Signature |
| --- | --- | --- | --- | --- |
| 1. | PWG-1 UNDP | Jocelyn Mason | Resident Representative |  |

| Total MPTF Funds Received | Total non-MPTF Funds Received |
| --- | --- |
| PUNO | Semi Annual 2019 (2) | Cumulative | Annual 2019 | Semi Annual 2019 (2) | Cumulative | Annual 2019 |
| PWG1 | 1 July - 31 Dec 2019 | From prog. start date | 1 Jan – 31 Dec 2019 | 1 July - 31 Dec 2019 | From prog. start date | 1 Jan – 31 Dec 2019 |
| UNDP | 997,934.58 | 2,508,632.61 | 997,934.58 | 0 | 1,853,069.23 | 951,935.70 |
| JP Expenditure of MPTF Funds | JP Expenditure of non-MPTF Funds |
| PUNO | Semi Annual 2019 (2) | Cumulative | Annual 2019 | Semi Annual 2019 (2) | Cumulative | Annual 2019 |
| PWG1 | 1 July - 31 Dec 2019 | From prog. start date | 1 Jan – 31 Dec 2019 | 1 July - 31 Dec 2019 | From prog. start date | 1 Jan – 31 Dec 2019 |
| UNDP | 960,705.35 | 2,084,673.71 | 1,396,788.34 | 618,079.53 | 1,853,069.23 | 951,935.70 |

ANNUAL HIGHLIGHTS

Parliament passes Petroleum, Anti-corruption, Anti Money Laundering bills. Workshop for Somaliland Parliamentarians on Parliament’s Role in Realizing the 2030 Agenda UNDP Strengthened the Capacity of 75 Percent of the Members of the Puntland Parliament Puntland Parliament has adopted the most inclusive five-year strategic plan Institutionalized Cooperation between Puntland Parliament & Civil Society Organizations Joint Communique issued in the 3rd Annual Women MPs Conference advocating for a minimum 30% representation across all sectors.

HIGHLIGHTS OF KEY ACHIEVEMENTS Key bills approved: Anti-Corruption bill, Public Financial Management Bill, Revenue Bill, Petroleum Bill, Health Professional Bill, Amendment of the Public Procurement Law and Revenue Bill. The legislations support the provision of social services and financial reforms required for debt relief increased resource mobilization and economic recovery in Somalia. Review of 15 chapters of constitution finalized and special rules of procedures for adoption of the proposed amendments of the constitution tabled for debate as a result of the support provided to the Parliamentary Oversight Committee (OC) on Constitution Review and Implementation. The new MPs from Puntland House of Representatives (M:48, W:1) equipped with basic knowledge about Parliamentary processes, practices, and procedures. The parliament approved law establishing Puntland Civil Service Commission and Puntland Budget 2020. Puntland Parliament Strategic Plan 2019/2024 developed with M&E framework. Establishment of CSO Advisory Board in Puntland to address the lack of inclusiveness and full representation of women, youth and marginalized populations in parliament. Avenue in place to enhance inclusiveness in the legislature despite the lack of parity in the Puntland parliament. Knowledge increased on the protection and Promotion of Human Rights for the Members of the Hirshabelle Assembly. 35 MPs (M:27 W:8). As a result, oversight engagement of MPs on protections issues unlawful imprisonment, torture, GBV increased in Hirshabelle. Somaliland Parliamentarians understand the Parliament’s Role in Realizing the 2030 Agenda and in holding the government to account on the Sustainable Development Goals (SDG). Somali Federal Parliament (House of the People and Upper House) and Somaliland Parliament have Action Plans, following an in-depth Self-assessment exercise to support the advancement of Sustainable Development Goals in their role as parliamentarians. Joint Communique of women parliamentarians, resulting from multiple consultations and training processes in the 3rd Annual Women MPs Conference advocates a minimum 30% representation across the three arms of governance, private sector, and independent commissions. Changing article 3(5) to secure full inclusion through the Constitution Securing Gender Responsive Budgeting Prioritization of the Sexual Offenses Bill Knowledge products/toolkits developed for MPs of the Federal Parliament supporting advocacy work on the GEWE agenda (gender-sensitive legislation, constitution, budgeting, and leadership)

SITUATION UPDATE In March, the Somali President addressing the fifth session of the Parliament urged both houses of the federal parliament to speed up the processing and adoption of the key laws such as the electoral law and political parties act crucial to the country's democratic process. During the session, the Speaker of HoP, Mohamed Mursal Abdirahman, highlighted the progress made since the 4th session, such as the approval of key laws and the passing of the 2019 government budget. The Speaker reiterated that the House will focus on its legislative work on processing priority laws such as the electoral law, review of the political party law, and finalizing the constitution review process. He urged the executive to submit the laws to the House which are key to moving forward on scheduled 2020 elections. In 2019, notable progress on the political side has been made include the passing of bills for the establishment of anti-corruption commission, Public Financial Management, Telecommunication all of which will have a positive bearing to the planned and ongoing initiatives under the current Country Programme Document (CPD). However, the electoral law passed by the House of People, and the delay in the political parties’ bill are likely to affect the electoral process calendar scheduled to meet the constitutional deadline of June 2020. Somali federal parliament has also passed important bills including the controversial Petroleum bill that creates a regulatory and legal framework to manage discoveries and control of its natural gas reserves. During a parliamentary session in May 2019, the Somali lawmakers in the Houses of the People have overwhelmingly voted in favor of the bill. The approval of the bill comes as Somali Federal Government and the Federal Member States are in deadlock over the fair share of the country’s natural resources, mainly the potential oil and gas. In October, the Federal Government of Somalia and its international partners endorsed a Mutual Accountability Framework at Somalia Partnership Forum. In order to ensure that federal one-person-one-vote elections are held in late 2020/early 2021, the executive and legislative showed their commitment to adopt an Electoral Law by December 2019.

ANNUAL PROGRESS REPORT RESULTS MATRIX OUTCOME STATEMENT SOMALI WOMAN AND MEN, GIRLS AND BOYS BENEFIT FROM MORE INCLUSIVE, EQUITABLE AND ACCOUNTABLE GOVERNANCE, IMPROVED SERVICES, HUMAN SECURITY, ACCESS TO JUSTICE AND HUMAN RIGHTS. SUB-OUTCOME 1 STATEMENT Output 1: House of the Peoples and Upper House capacities and structures become effective and representative institutions that promote transparency, inclusion and participation in the political process. INDICATOR TARGET (Y 2) PROGRESS ON OUTPUT INDICATOR ANNUAL CUMULATIVE (Y 1+2) OP indicator 1.1: # of laws debated 1.1: 2 law debated. 14 19 OP indicator 1.2: # of public hearings held. 1.2: 2 public hearing organized with the participation of civil society, executive and media. 6 7 OP indicator 1.3: # of committees with approved work plans. 1.3: 4 committees with work plans adopted. 1 1 OP indicator 1.4: % of MPs satisfied with the training received. 1.4: At least 70% of MP are satisfied with the training received 80% 80% UNDP ONLY: sources of evidence: Output 2: The new federal network of legislatures and assemblies is strengthened processes. OP indicator 2.1: Speakers’ forum institutionalized. 2.1: 2 speakers’ forum organized 0 0 OP indicator 2.2: Coordination mechanism between states and upper house established. 2.2: Mandates of the upper house defined. 0 0 UNDP ONLY: sources of evidence (as per current QPR) Output 3: Capacities and structures of the Emerging State Assemblies are strengthened in support of peacebuilding, state-building, federalism, and development. OP indicator 3.1: Outreach strategy implemented in # of regions. 3.1: 3 outreach visits conducted in three regions with reports submitted to the parliaments 1 1 OP indicator 3.2: # of committees with approved work plans. 3.2: Capacity created to implement the committee workplans in each region. 0 0 OP indicator 3.3: # of MPs satisfied with the training received. 3.3: At least 80% MPs satisfied with the training received. 80% 80% OP indicator 3.4: Coherent legislative roles at state level regularized 3.4: An agreed upon coordination mechanism between federal and state level. 0 0 UNDP ONLY: sources of evidence: Output 4: Capacities and structures of Somaliland and Puntland Parliaments are strengthened in support of peacebuilding, state-building, federalism and development. OP indicator 4.1: Outreach strategy is implemented in SL and PL 4.1: 2 outreach visits conducted in PL and SL with reports submitted to the parliaments 2 2 OP indicator 4.2: # of committees with approved work plans. 4.2: Capacity created to implement the committee workplans in each region. 0 0 OP indicator 4.3: # of MPs satisfied with the training received. 4.3.: At least 80% MPs satisfied with the training received. 80% 80% OP indicator 4.4: Coherent legislative roles at state level regularized for PL. 4.4: An agreed upon coordination mechanism between federal and PL. 0 0 UNDP ONLY: sources of evidence: Output 5: Various assemblies engage with and respond to the needs of civil society, including the marginalized groups. OP indicator 5.1: Strategic partnership established between civil society and parliaments. 5.1: strategic partnership framework developed. 1 1 OP indicator 5.2: # of regions with youth and women’s caucus. 5.2: strategic action plan for women and youth caucus developed at NFP and 2 regions. 1 1 OP indicator 5.3: # of legislation with inputs from civil society (including vulnerable and marginalized groups) submitted before the parliament. 5.3: Create capacity within civil society to engage in the legislative and oversight work of the parliament. 0 0 UNDP ONLY: sources of evidence: MoU between Puntland Parliament and CSOs, Parliament newsletter, meeting minutes Output 6: Implementation of SDG 16 enhanced in Somalia through strengthened capacities for dialogue, research, and analysis. OP indicator 6.1: # of outreach and analytical reports on NDP and SDG 16 produced by the parliament. 6.1: Strengthen capacity within research units. 1 1 OP indicator 6.2: % of youth and women with positive perceptions the inclusivity in parliamentary processes. 6.2: Baseline data collected 0 0 UNDP ONLY: sources of evidence:

| NARRATIVE Output 1: House of the Peoples and Upper House capacities and structures become effective and representative institutions that promote transparency, inclusion, and participation in political processes. Capacity Development for the House of the People and the Upper House During the reporting period, technical advisory support has been provided to the Somali parliamentary institutions to strengthen the capacity of MPs to enact laws and engage through sectoral committees with efforts to establish a mechanism to monitor the implementation of the National Development Plan in line with SDGs. Bills Approved by Somali Federal Parliament The lawmakers of Somalia’s Federal Parliament approved important bills; Petroleum Bill, Anti-Corruption bill, Public Financial Bill, Public Procurement Bill and Revenue Bill. With the adoption of these legislations, Somalia’s Government continues to make progress in financial reforms and meet the requirement for debt relief, resource mobilization, and economic recovery. Establishment of Parliamentary Ad-Hoc Committee to review the electoral bill The Parliamentary Ad-Hoc Committee established in July 2019 to review the draft electoral bill completed its consultations and the report was shared with members of the parliament (24 Nov 2019) for debate. Electoral Law is essential for holding one-person-one-vote elections 2020/21 to meet the constitutional timeline for elections as outlined in the Government’s Inclusive Politics Roadmap. Training on Reviewing legislation on gender perspectives From 25-26 March 2019, the project partially supported a capacity building training for women lawmakers on “Reviewing Legislation with a Gendered Lens”. The training attended by 17 participants (M12:W5) of the federal parliament from the parliamentary committees on Justice, Religious Affairs & Endowment, Human Rights, Women and Humanitarian Affairs, and the women caucuses of both houses (House of People and the Upper House). The training also attended by members of the parliament secretariat and legal advisors. The training was particularly focused on building their abilities to identify gender gaps in legislation as well as formulate gender-responsive legislation. After the training, UNDP is developing a handbook on “Reviewing Legislations from a Gender Perspective” which will be a resource tool and a user guide for all MPs in reviewing legislations with a gender lens. Adoption of the amendment of the constitution by Parliamentary Oversight Committee The Parliamentary Oversight Committee developed rules of procedures for the adoption of the proposed amendments of the constitution, which will be debated in a joint session of both Houses of the Somali Federal Parliament. Constitutional review bodies also worked to develop a common approach and strategy as well as a work plan for the consultation process, identified the key constitutional review issues requiring consultation, and outlined the key stakeholders to be consulted on the reviewed chapters of Somali provisional constitution. Fourth Forum of the Parliamentary Oversight Committee (OC) on Constitution Review From 26 to 28 August 2019, the project facilitated the Fourth Forum of the Joint Parliamentary Oversight (OC) Committee on Constitution Review and Implementation held in Garowe, Puntland. The forum brought together constitutional review committees from the Federal Member States (FMS) parliaments. The Forum of Constitutional Committee urged the Federal Government, Federal Member States, and the Somali people to take part in the completion of the constitution review process and prioritize its implementation. The Forum reiterates its call to the Federal Member States to reach an agreement on Articles that need political dialogue to prevent further delays in the completion of the constitutional review process. Consultation and Public Hearings on Draft Bills in the Houses of the Somali Federal Parliament The Project through LoA with the Federal Parliament supported consulatations and public hearings on the following legislations in different stages of the Houses of the Somali Federal Parliament; Revenue Bill: The Budget and Finance Committee of the House of the People has conducted consultations meetings on Revenue Management Bill in Southwest state and Puntland state. The law is one of the priority legislation in this 6th session of the federal parliament. Amendment to the Media Law: On 1st December 2019, Upper House Committee of Social Services Development, Humanitarian Affairs, Media and Culture conducted consultations on the Amendment to Media Law with the attendance of more than 38 (M:34 W:4) participants from media and civil society organization. In the same vien, the committee held specific consultation meeting with 11 representatives from Federal Member States. Petroleum Bill: the project supported the Committee of National Resources, Infrastructure and Transportation of the Upper House on consultation of the Petroleum Bill. The meeting held on 19th December 2019 was attended by representatives from Federal Member States. Health Professionals Bill: on 13h November 2019, the Committee of Social Services Development, Humanitarian Affairs, Media and Culture of the upper House conducted a public consultation meeting with stakeholders from the medical practisioners on the Health Professional Bills. Output 3. Capacities and structures of the Emerging State Assemblies are strengthened in support of peacebuilding, state-building, federalism and development Human Rights Promotion and Protection training for Hirshabelle House of Representatives. On 26 & 27 June 2019, in Mogadishu, the Parliament Support Project with technical support of UNSOM organized a training workshop on Human Rights Promotion and Protection for the members of Hirshabelle House of Representatives. The training attended by 35 (M:27 W:8) MPs from the Hirshaballe parliament. As a result of the training, the ability of legislators enhanced to exercise their authority to better protect and realize human rights. Construction of Plenary Hall of Jubaland Parliament UNDP Project has supported the construction of parliament offices for the Jubaland House of Representatives. Construction was started in May 2019 and is expected to complete in the next few months. This will enable the Jubaland State Assembly to effectively discharge its functions in relation to law-making, oversight and representation. It is also anticipated that the work of Jubaland plenary hall will improve its internal regulatory framework and establish secretariat staff to work with the assembly. Good governance and federalism training for Hirshabelle MPs On 14 &15 August 2019, UNDP Parliamentary Support Project facilitated two-day training on the role of parliaments in promoting good governance and federalism for 45 MPs (M:45) of Hirshabelle State House of Representatives in Mogadishu. As a result of the training, it is expected that the MPs will work more effectively to promote transparency, accountability, peaceful citizenry and good governance through their legislative, representative, oversight and conflict resolutions functions thereby making Hirshabelle State responsive to the present and future needs of its people. Output 4: Capacities and structures of Somaliland and Puntland Parliaments are strengthened in support of peacebuilding, state-building, federalism and development During the reporting period, the Project sustained support to develop institutional capacities of Somaliland and Puntland Parliaments. The UNDP Parliamentary Support Project (PSP-II) strengthened the Puntland Parliament (as an institution) to improve its institutional and technical capacities, its service provision to MPs, parliament committees, and the people of Puntland, and its ability to contribute to the ongoing peacebuilding, state-building, federalism, and economic development projects. During the reporting period: Puntland Parliament Developed and Adopted Fraud Risk Management and ICT Policies In 2019, for the first time in 21 years, the Puntland Parliament had developed a Fraud Risk Management Policy and a Policy and Procedures Manual on Information and Communication Technology (ICT Policy). The Fraud Risk Management Policy comprehensively addresses, among other things designing fraud & corruption response plans, establishing investigation protocols, remediation policies, and uniform disciplinary processes. As a result of UNDP support to the Puntland Parliament, the Parliament now has a well-developed financial, administrative, and human resources management systems and functioning internal control framework. Puntland Parliament has Opened Up to the People UNDP supported the Puntland Parliament leadership to open up the Parliament to the people, and as a result, enabled hundreds of thousands of citizens to receive real-time information about the parliamentary business. UNDP provided support to live broadcasting of the House proceedings, which allowed PL citizens to watch and listen as MPs discuss and debate legislation and issues of national importance. This is a big leap to connecting the Parliament with the people of Puntland, and thereby significant progress made towards an inclusive democracy in the Puntland State of Somalia. Puntland Parliament has adopted the most inclusive five-year strategic plan (2019/2024) UNDP provided technical and advisory services for the development and adoption of a five-year strategic plan by the Puntland Parliament to enhance institutional effectiveness to discharge its mandate. In its new strategic plan document, Puntland Parliament prioritized ensuring the Parliament is well-positioned to contribute to strengthening federalism in Somalia, supporting and overseeing the implementation of state and National Development Plans, and supporting the implementation of the Sustainable Development Goals at the level of Puntland State of Somalia. Most important of all, the Puntland Parliament committed itself to contribute the finalization of the Constitutional Review, building institutions of the state, economic development, and youth and women development. UNDP Strengthened the Capacity of 75 Percent of the Members of the Puntland Parliament UNDP Parliamentary Support Project improved the capacity of 75% of the members of the Puntland Parliament. In Dec 2018, Puntland State had elected a new state parliament – 66 MPs of which 50 have been freshman MPs without prior knowledge about Parliamentary processes, practices, and procedures. In Feb 2019, UNDP trained the new MPs to bring them up to speed in exercising their duties in addition to providing MPs with information on available services and supports within Parliament. 90% of the MP trainees reported that they were in a better position to discharge their functions than they were before participating in the training workshop. For more, click on the link below. http://www.so.undp.org/content/somalia/en/home/presscenter/pressreleases/newly-elected-puntland-mps-attend-training-on-parliamentary-gove.html UNDP Enabled the Puntland Parliament to Triple Oversight-related Activities of the Parliament Puntland Parliament committees perform important functions necessary for democratization to take root in the region. These functions include oversight over the performance of the government, conflict resolution missions, and most importantly, the collection of the citizens' needs, priorities, and concerns. The parliament functions, however, are hindered by the lack of transportation equipment available for the parliament to carry out these critical functions without enlisting the support of the executive arm of the Puntland government. To enable the Parliament to discharge its oversight functions competently and independently from the government, UNDP transferred fro brand new vehicles to the Puntland Parliament as a result of which Puntland Parliament tripled the frequency of parliamentary oversight over government institutions outside the state capital of Garowe. In the span of five months, for instance, Puntland Parliament conducted nearly a dozen oversight missions to various parts and regions of Puntland; more information on these missions is available on the Parliament’s Facebook page. In addition to the provision of vehicles, UNDP has provided technical and financial support to one oversight mission where a Parliament committee and their staff visited various regions and districts in Puntland to evaluate government performance, including quality implementation of policies & programs and to monitor the availability of essential services. Giving Rights and a Voice to Hundreds of Citizens: Public Hearings by Puntland Parliament Committees In inclusive governance, whenever decisions are being made about issues that will affect the lives of the people, citizens and stakeholders should be consulted with and allowed to participate at every stage of the decision-making process. To this respect, the UNDP Inclusive Politics strives to increase the participation of citizens in decisions affecting their lives, both at the Federal and Federal Member State levels. Towards this end, UNDP Parliamentary Support Project provides the Puntland Parliament with technical and financial support to conduct public hearing of priority legislations. During the reporting period, UNDP supported a series of public hearings on Civil Servants’ Retirement and Pension Benefit legislation by the Committees of the Puntland Parliament, where hundreds of citizens in and outside Garowe are heard and engaged. Consultative meeting on Women Quota in the draft Election Bill With support of the UNDP Parliament project, the Somaliland MPs of women caucus have organized a consultative meeting and invited around 50 women from key civil societies organizations. The MPs from women caucus and women from CSOs organizations agreed to appoint a task force comprising of women MPs and CSOs to work together on pushing the draft election bill and make strong lobby within the parliament. The meeting agreed that the task force will work hard to secure women's quota has approved by the parliament and signed by president into law and to be enforced. Somaliland MP’s constituency visits Somaliland House of Representatives visited Sanag, where a number of deaths reported due to internal clan conflicts. The aim of their constituency visit was to assess the situation of the region after the presidential emergency bill was rejected by the parliament. The parliamentarian engaged public conversation and met a number of government officials and traditional leaders in order to defuse the tension, also the MP’s come back with further information about the region and is expected to present their findings and recommendation to the next plenary session of the house. Outreach campaign to reach rural communities of Somaliland (village level): In November 2019, with the support of UNDP, the Somaliland HoR provided logistical support to two teams (parliament staff) to undertake public outreach campaign. The team from Parliament reached to some villages in western regions (Gabiley, Kalabaydh, Wajaale, Dila, and Borama), and in eastern regions (Ceel-gaab, Oog, Badd-weyn and Boq-dharkeynley). They talked with the local people face-to-face and raise awareness among communities about the constitutional mandate of the state pillars, how Parliament works in terms of law-making, MPs representation role, and Parliament oversight on government as to hold executive into account. Public Consultations on Anti-Money Laundry Bill – Somaliland On 22 May 2019, Somaliland House of Representatives organized public consultation on Anti Money Laundering (AML). Participants from the Central Bank, banks, Ministry of Finance and independent financial experts and legal advisors attended the session. The outcome of this meeting will be incorporated with the 2nd reading of the bill. regional clan chiefs, traditional elders, lawyers, academic researchers and MPs from the Guurti. Consultation meeting on the legal framework – Somaliland On 5 October 2019, the Somaliland House of Elders (HoE) organized a 4-days consultation meeting in Berbera, Sahil region, the objective was to brainstorm and share ideas to initiate the legal framework of the House that will determine whether the Members Parliament (MPs) will come through the selection process or ballot boxes. This is the second consultation meeting targeting all Somaliland 6 regions. The participant who attended consultation meetings comprised of regional clan chiefs, traditional elders, lawyers, academic researchers and MPs from the Guurti. Output 5: Various assemblies engage with and respond to the needs of civil society, including the marginalized groups Building Cooperation between Puntland Parliament & Civil Society Organizations On 11 April 2019, a Memorandum of Cooperation between Puntland Parliament and Puntland Non-state Actors Association (PUNSAA) has been signed by the Speaker of the Puntland House of Representatives (HoR) and by the Chairman of PUNSA, giving birth to the first-ever “CSOs Advisory Board” to a parliament. The fundamental purpose of the CSO Advisory Board is to promote inclusive politics and representative democracy, by providing citizens with a platform to voice their aspirations, concerns, and opinions to lawmakers and policymakers. The process thereby aims to affect more responsive and more accountable public institutions in the Puntland state. The signed Memorandum of Understanding of Cooperation is an important and necessary step for democracy to thrive in the State. It is expected that CSOs Advisory Board will serve as a bridge between citizens and public authorities, and will give opinions of concerned citizens a chance to be heard at the parliament level. For the best interests of the people of Puntland, the Parliament will ensure maximum civil society and communities' participation through the provision of access to information, regarding future and ongoing activities of HoP committees, Puntland Parliament will involve civil society organizations in the legislative process by granting them right of speech, and encourage and pursue active participation by CSOs in legislative and budgetary discussions. The formation of the first institutionalized partnership between Puntland HoR and CSOs is the result of a hard-won process that took two years of discussions between UNDP and the Puntland Parliament. Supported by Switzerland and Norway, the Joint Parliamentary Support Project is piloting this Memorandum in Puntland and South West State. It is expected that CSOs Advisory Board will serve as a bridge between citizens and public authorities, and will give opinions of concerned citizens a chance to be heard at the parliament level. Annual Somali Women Parliamentarians Conference From 15-16 December 2019, the 3rd Annual Somali Women Parliamentarians Conference was held in Mogadishu attended by more than 300 women parliamentarians from Somali Federal Parliament and legislative assemblies from the Member States. The conference also attended by the Speaker of the Upper House of the Parliament, the Ministry of Constitution, the Ministry of Women and Human Rights, the National Independent Electoral Commission, Federal Women Parliamentarians, the UN, INGOs, Women from Federal Member States of Puntland, Jubaland, South West, Galmudug, and Hirshabelle as well as Banadir Region and other Civil Society sections. A communique was issued at the end of the conference that calls for the leadership of the country to end current political crisis, concern about the possible erosion of the women’s quota, rephrasing of Article 3(5) to expressly state women’s quota, demand for allocation of the national budget for women’s needs, recommendation for women not get involved in men’s clan-based conflicts, call or prompt passage and implementation of legislation relating to women’s rights. Upper House Women’s Caucus consultative meeting The project supported the Upper House Women’s Caucus consultative meeting on the reviewed chapters of the constitution. The participants raised their concerns about women participation in political leadership positions and emphasized the need for women’s quota in the Somali Constitution – at both Federal and Regional States level. Output 6: Implementation of SDG 16 in Somalia is enhanced through strengthened capacities for dialogue, research, and analysis. Training on 2030 SDGs agenda for Somaliland Parliament From 9 to 10 April 2019, a two-day workshop on Parliament's Role in Realizing the 2030 Agenda and in holding the government to account on the Sustainable Development Goals (SDGs), was held in Hargeisa, Somaliland. The event was attended by 50 (M:45 W:5) parliamentarians aimed to increase coordination between parliament and government ministries on the 2030 SDGs agenda. The meeting supported by UNDP Under a project that works with the Somaliland government to build the capacity of the parliament to enact legislation, and to ensure effective and inclusive implementation of the SDGs. The project is part of a broader regional UNDP Arab States programme called 'Parliaments for Agenda 2030', which has been developed in partnership with the Islamic Development Bank. www.so.undp.org/content/somalia/en/home/presscenter/pressreleases/2019/somaliland-parliament-meets-to-discuss-achievement-of-sustainabl.html Self-assessment exercise of the Somali Federal and Somaliland Parliament on Agenda 2030 From 21st November to 3rd December 2019, A self-assessment exercise on SDGs was conducted with Somali Federal and Somaliland Parliaments to take stock of the institutional capacity of the two parliaments to effectively mainstream the SDGs in the Parliament’s work. The main purpose of the exercise intended to help Parliaments identify (i) institutional strengths and weaknesses in terms of rules, procedures, information resources and staff strength to assist the Parliamentarians in streamlining SDGs into Parliamentary work; (ii) determine the capacity gaps of Parliamentarians and staff on the subject and (iii) priorities in the context of Agenda 2030 for the Somali Federal and Somaliland Parliaments. During the self-assessment, interviews and focus groups discussion were held with the secretariat of the parliaments and MPs as well as key informants from civil society organizations. The assessment exercise identified challenges, such as weak institutional capacity at parliament; lack of parliamentary engagement in the formulation, discussion, prioritization of focus areas including on SDGs in the NDP and further validation of the NDP by Parliament, weak policy space for SDG integration and lack of legal or procedural framework, lack of any data or information sources at parliament other than provided by government, if any, limited capacity and lack of access to qualified information for holding implementing agencies accountable and limited coordination with other oversight bodies. As result an action was developed with recommendations on following key areas: Trainings, information sharing, advocacy on SDGs for MPs, staff & with Parliamentary Committees To set up a Taskforce or a Committee on SDGs which can ensure sustained focus and coordination on SDG related work; The SDG or Committee should work on a comprehensive policy on SDGs for Parliament including processes to ensure oversight of SDG implementation by the government; Engagement on NDP (2018-22) and its linkages with the sectoral Committees & its localization Information sharing sessions on sector specific targets as identified in NDP (2018-22) and engagement regarding indicators and baselines of SDGs. Development of M&E plan for Parliamentary Committee work with an SDG component Development of a legislative checklist for the Legislative Department/Committee |
| --- |
| Other Key Achievements N/A |
| Challenges (incl: Delays or Deviations) and Lessons Learnt: Lack of cooperation between the two Houses of the Parliament (Upper House and the House of People) and mistrust between the federal government and federal member states are the major challenges in the smooth implementation of the project. Security remains limited to cities, through even Mogadishu and regional capitals face regular attacks from the Al-Shabaab insurgency. Challenges included limited secure options of venue, difficulty in accessibility for both counterparts and project staff. The outstanding mitigation measures highlighted are the construction of the upgrade of the security for the parliaments and assemblies such as the construction of a security screening room. |
| Peacebuilding impact (for Joint Programmes receiving PBF funding only) The Project primarily aimed at building the capacities of MPs and their staff in support of peacebuilding and national development. Ongoing capacity development support is being provided to the MPs including women on critical peacebuilding and development issues such as federalism, the NDP, the SDGs, human rights treaty obligations, gender mainstreaming in law-making, the budget process, and anti-corruption mechanisms. Another important role that the emerging state assemblies playing is peacebuilding and reconciliation, and the project is addressing this role in two ways: finding ways for Members to work together within and across clan lines and sending MPs as representative and prominent local leaders for dispute resolution. Through these outreach events, the MPs not only teaching citizens about the role of the state legislatures but also address the larger state-building idea. UNDP’s support of these activities is of the utmost importance for establishing lasting peace. The project has also supported meetings of the Forum of Federal and Federal Member States Parliament Committee to discuss the progress, concerns, and challenges faced during the constitutional review process as part of the peacebuilding initiative. |
| Catalytic effects (for Joint Programmes receiving PBF funding only) N/A |
| Gender During the reporting period, reviewing legislations from gender perspective training was provided to both houses of the Somali Federal Parliament (Upper House and House of People) attended by 17 participants (M12:W5) to help them to see the parliamentary legislation in gender lens. The Project also supporting parliamentary women caucuses of federal parliament, and also work with women MPs in other legislatures and assemblies with substantial numbers of women MPs to establish women’s caucuses and to provide specialized training to women MPs based on the unique challenges they are facing. As part of the work to develop CSO partnerships with the NFP and other legislatures, the Project also pays special attention to identifying women’s groups for engagement. These groups can be supported with advocacy training to enable them to more effectively lobbying parliaments. The Project will also facilitate connecting up these women’s groups with MPs and relevant parliamentary committees, especially during public hearings. Support was provided to parliamentary women caucuses of Somali federal parliament, and women MPs in other legislatures and assemblies with a substantial number of women MPs to establish women’s caucuses and to provide specialized training to women MPs based on the unique challenges they are facing. |
| The proportion of gender-specific outputs in the Joint Programme | Total no. of Joint Programme Outputs | Total no. of gender specific Outputs |
|  | 6 | 2 |
| Proportion of Joint Programme staff with responsibility for gender issues | Total no. of Staff | Total no. of staff with responsibility for gender issues |
|  | 4 | 1 |
| Human Rights On 26 & 27 June 2019, in Mogadishu, the project has delivered training on human rights issues attended by 35 MPs from the Hirshaballe parliament. The project is also promoting the inclusion of marginalized and minority groups on the nation-building dialogue, particularly in what concerns the legislative and representation mandates, to ensure that their rights and interests are reflected in the policies and programmes of the executive, as well as in the legislative process of parliaments. The project is making efforts to strengthen the promotion of women’s rights as an overarching theme, to improve social cohesion and to ensure conflict sensitivity, peace, and state-building. |
| Has the Joint Programme included a protection risk assessment in its context analysis, including on gender issues, and taken measures to mitigate these risks to ensure they are not exacerbated or new risks created? | Result (Yes/No) |
|  | Yes |
| No. of Joint Programme outputs specifically designed to address specific protection concerns. | Result (No.) |
|  | 0 |
| No. of Joint Programme outputs designed to build the capacity of duty-bearers to fulfill their human rights obligations towards rights holders. | Result (No.) |
|  | 1 |
| Other |
| Does the Joint Programmes have a national cost-sharing component (i.e. funds and/or other resources provided by the FGS and/or FMS (including in-kind contributions)? (if ‘Yes’, describe below). | Results (Yes/No) |
|  | No |
| Have FMS(s) been engaged in one or more of the following: design, planning, implementation, coordination and/or monitoring of the Joint Programme. | Results (Yes/No) |
|  | No |
| Describe the nature of cost-sharing: |
| Communications & Visibility The project team has prepared and disseminated quarterly newsletters to the project partners, stakeholders and donors. Project activities are being recorded in the form of reports, pictures, interviews, and short videos. Articles covering all activities by the Parliamentary UNDP website and social media platforms, such as Facebook and Twitter. UNDP staff ensures regular interaction with national counterparts, in addition to the deployment of national staff within the premise of the Parliaments and regional assemblies to ensure timely and continuous communication. In accordance with donor guidelines, the Parliament Support Project intended to guide information sharing and visibility of project activities. As a result, significant improvements have made in terms of sharing information with beneficiaries, donors and other stakeholders. |
| Looking ahead In the coming months, the project sustained support to the NFP on strengthening effectiveness and participation in its three constitutional functions of representation, legislation, and oversight to strengthen public confidence in the effectiveness of Parliament. The project will provide technical advisory and capacity building support, strengthen the capacity of MPs to enact gender-responsive laws and engage through sectoral committees with efforts to establish a mechanism to monitor the implementation of the National Development Plan and SDGs. An ongoing capacity development programme will be provided to all on critical peacebuilding and development issues such as federalism, the NDP, the SDGs. The efforts will be made to tie back the Strategic Plan to priorities from the NDP, SDGs implementation, peacebuilding and state-building. To make both the House of People and the Upper House effective and representative institutions, the project would continue enhance the capacities of the parliamentary committees; provide operational and administrative support to the secretariat. The project would also continue support to strengthen the capacity of the Women Caucus and to establish a network with regional assemblies Caucus (UH & HoP). The Somali Federal Parliament expected to approve Special Rules of Procedures for the Adoption of the revision of the 2012 Provsional Constitution. The Parliamentary Oversight Committee on the Constitutional Review will hold public outreach and consultations with all stakeholders on the reviewed chapters in 2020 as well as the resolution of adoption on the Constitutional Amendment will be debated and approved by the Federal Parliament in 7th session 2020. UNDP will continue to engage with the federal parliament and other regional assemblies to enhance its legislative performance, provide technical support and deliver capacity building training to empower the committees and secretariat staff in a manner that would strengthen parliament's role as an effective institution. |

# ANNEX 1.	RISK MANAGEMENT

| Type of Risk | Description of Risk | Mitigating Measures |
| --- | --- | --- |
| Environmental Security | Terrorist activities force UN / UNDP significantly reduce its activities. | UNDP has reduced movement of staff between MIA and UNCC, and reallocated Programme and Operation staff to MIA. As a result of operational challenges, project has sought alternative venues to conduct the trainings. Mitigation measures have taken by UN in Mogadishu and Garowe, such as flexible work arrangements for national staff. |
| Operational Organizational | Insufficient involvement of key stakeholders in defining and steering programme implementation | Open, consultative programme planning and development approach; close coordination with key counterparts in each region including project board meetings and endorsements of AWP by parliamentary counterparts; inclusion of senior stakeholder representatives on Programme Board. Risk Mitigation plans for implementation of LoAs developed and agreed with counterparts. |
| Environmental Political | Deterioration in relations between UNDP Somalia and the NFP or Government | Maintenance of respectful, collaborative approach and transparency. |
| Operational Organizational | Low absorption capacity among counter-parts – slower process of capacity building than expected aligned with ongoing high expectations | Regular revisions of implementation progress and aligning expected timing to current conditions of staff and infrastructure within each institution. Conduct assessment of parliaments’ administrative capacity; include capacity development and risk mitigation measures. |
| Political | Political conflicts between key state institutions or within Parliament hamper its ability to function as a legislative body | UNSOM / international community to conduct conflict mediation. |
| Political | Predominantly male members of parliament fail to adopt gender-sensitive legislation | Project includes activities such as workshops to familiarize MPs to gender-sensitive legislation and gender-sensitive budgeting aimed at increasing their knowledge toward concept of gender sensitive and importance of analyzing the impact of the national budget on women. Project also promotes activities to increase number of female MPs and empowerment of current female MPs. |
| Organizational | Trained parliamentary staff leave institution for better paid positions | Apart from staff training, the project focuses on institution building including organizational reform, preparation of guidelines and SoPs, which shall make the parliaments resilient to staff turn-over. |
| Political | Postponement of parliamentary elections in Somaliland may lead to lower levels of accountability and higher levels of mistrust in the public perception of MPs. | Through regional / constituency offices and other activities, the Project attempts to strengthen the linkages between citizens and Parliament to make the institution more accountable to citizens’ demands. |
| Social and Environmental risks | Duty-bearers do not have the capacity to meet their obligations in the Project | The project is providing capacity development activities to all duty bearers, as they are the core of the project activities and goals. These initiatives are contributing to the project’s goal to enhance operational and technical capacity of the duty bearers. |
|  | Rights-holders do not have the capacity to claim their rights | The project includes capacity-building activities in promoting the right holders to have the skills and knowledge to advocate for their rights and carry out awareness campaigns, MPs outreach to their constituents support and claim their rights. |

# ANNEX 2.	MONITORING AND OVERSIGHT ACTIVITIES

| Monitoring Activity | Date | Description & Comments | Key Findings / Recommendations |
| --- | --- | --- | --- |
| Project Board Meeting – Parliament Support Project | 20 March 2019 | This project board meeting took place in Mogadishu and attended by the speaker of the House of the People, the Deputy Speaker, by representatives from UNDP, UNSOM, and by donor partners. The objectives of this meeting was to discuss progress and achievements that UNDP and parliaments made during this reporting period and to seek guidance over challenges encountered during the period under consideration. They discussed the status of Parliament Support Project including current funding and fundraising strategies as well as priority activities to be implement in 2018 and the coming years. | The Speaker of the House of the People, Mohamed Mursal Abdirahman, thanked the UNDP Parliament project for their ongoing support, and mentioned that Federal Government of Somalia has made notable achievements under an inclusive politics agenda, in deepening federalism, and in completing the technical review of the constitutional chapters. Such achievements are key milestones along an inclusive political roadmap agreed by the Government and its international partners in 2018. The political roadmap includes milestones for achieving universal elections in 2020. Chief Technical Advisor for UNDP's Inclusive Politics portfolio, shared the progress made from September 2018 to March 2019 which includes technical and legal advisory support delivered to parliamentary committees; and development of technical plan for the constitutional review process by the Oversight Committee (OC), which was approved by the federal parliament. She also listed provision of logistical, administrative, operational and transportation support to the Upper House, the House of the People and OC; recruitment of 6 experts and 17 young graduates to assist the Upper House and the OC; and provision of ICT equipment to the OC. Hon. Mowlid Hussein, Deputy Speaker of Upper House highlighted the importance of the establishment of a joint committee for both Houses of the Federal Parliament of Somalia and outlined the efforts of the government in resolving disputes between the House of the People and the Upper House. Mr. Raisedon Zenenga, Deputy Special Representative of the Secretary General (DSRSG) for United Nations Assistance Mission in Somalia, discussed the critical bills to be tabled to both Houses for debate and approval and asked for both Houses to outline their priorities for the year. Donors at the meeting commended the work done by the Federal Parliament of Somalia and Parliamentary Oversight Committee and by UNDP in support of Constitution and Parliament Support projects. Mr. Siro underlined the importance of the review constitution as priority and adoptions of legislations. |

ANNEX 3.	TRAINING DATA (JAN-JUNE 2019)

| # | Target Group | Dates | # of participants | Title of the training | Location of training | Training provider |
| --- | --- | --- | --- | --- | --- | --- |
|  | Ministry. District or UN staff | Others |  |  |  |  |  |
|  |  |  |  | M | F | Total |  |  |  |
|  | Newly elected MPs Puntland | 2-4 February 2019 | 48 | 1 | 49 | Training for newly elected MPs Puntland on Parliamentary Governance and Law-making | Puntland Parliament, Garowe | UNDP |
|  | Somaliland Parliamentarians, SL Local Government Institute, SL Ministry of Planning officials | 9-10 April, 2019 | 45 | 5 | 50 | Induction workshop for Somaliland Parliamentarians on Parliament’s Role in Realizing the 2030 Agenda | Hargeisa, Somaliland | UNDP |
|  | Somaliland Members Parliament (Guurti MPs) | 9 June 2019 | 1 | 49 | 50 | Induction training for newly joined Elders (Guurti MPs) on the House mandates and parliamentary works. | Mansoor Hotel, Hargeisa | UNDP |
|  | Hirshabelle House of Representatives |  | 27 | 8 | 35 | Human Rights promotion and protection training for Hirshabelle MPs | Village Restaurant, Mogadishu |  |
|  | Parliamentary Women Caucus | 26 Feb to 5 March 2019 | 0 | 21 | 21 | Parliamentary Women Caucus to attend Women Leaders Programme study tour | Istanbul, Turkey | UNDP supported |
|  | Parliamentary Women Caucus | 25-26 March 2019 | 5 | 12 | 17 | Training on Reviewing Legislations from a Gender Perspective | Peace Hotel, Mogadishu | UNDP |
| Totals: |  |  |  |  |  |  |

ANNEX 4.	PICUTRES OF ACTIVITES (JAN-DEC 2019)

ANNEX 5.	UPDATED BILL TRACKER

| SN | Bill /Conventions | Status Update |
| --- | --- | --- |
|  | International Convention of People with Disabilities | President Assented |
|  | Establishment of Anti-corruption Committees | President Assented |
|  | Revenue Bill | President Assented |
|  | 2017 Final Accounts | President Assented |
|  | Pensions and Benefits of Somali Politicians | Awaiting Presidential Assent |
|  | Membership of the Convention of Multilateral Investment Guarantee Agency | Awaiting Presidential Assent |
|  | AU convention on IDPS in Africa (Kampala Accord) | President Assented |
|  | 2019 Budget Review | President Assented |
|  | International Convention on the protection and preservation of Cultural Heritage & the Natural Heritage. | Awaiting Presidential Assent |
|  | International Convention on the protection and preservation of the non physical heritage | Awaiting Presidential Assent |
|  | 2020 Budget | President Assented |
|  | Public Finance Management | President Assented |
|  | Company Law | President Assented |
|  | Petroleum Bill | President Assented |
|  | International Convention on Multilateral investment Guarantee | Awaiting Presidential Assent |
|  | Amendments to Customs Law | Awaiting Presidential Assent |
|  | Amendments to Procurement Law | Awaiting Presidential Assent |
|  | Amendments to Journalism Law | Awaiting Presidential Assent |
|  | Armed Forces Pensions and Gratitituties Bill | Awaiting Presidential Assent |
|  | National Statistics Bill | Awaiting Presidential Assent |
|  | National Electoral Bill | President Assented |
|  | Civil Aviation Bill | Awaiting Presidential Assent |
|  | Quality Control Bill | Awaiting Presidential Assent |
|  | Water Resource Management bill | Returned from the Upper House and waiting for the committee to discuss |
|  | Health Practitioners Bill | Returned from the Upper House and waiting for the committee to discuss |
|  | Amendment to the Auditors Law | Returned from the Upper House and waiting for the committee to discuss |
|  | 2018 Final Accounts | HOP Awaiting 2rd Reading |
|  | Somalia Education Bill | HOP Awaiting 2rd Reading |
|  | Amendments to Civil Service Law | HOP Awaiting 2rd Reading |
|  | Establishment of Medicines Quality Control Agency Bill | HOP Awaiting 2rd Reading |
|  | 1954 Convention on protection and preservation Cultural Heritage during war times | HOP Awaiting 2rd Reading |
|  | Somali Lawyers Bill | HOP Awaiting 2rd Reading |
|  | Public Notary Bill | HOP Awaiting 2rd Reading |
|  | City Planning Bill | HOP Awaiting 2rd Reading |
|  | Heavy Goods Vehicles Bill | HOP Awaiting 2rd Reading |
|  | Highway Code Bill | HOP Awaiting 2rd Reading |
|  | Anti – Terrorism Bill | HOP Returned to the Executive |
|  | Control of Fire Arms Bill | HOP Returned to the Executive |
|  | Sexual Offenses Bill | HOP Returned to the Executive |
|  | Targeted Economic Sanctions Bill | HOP Awaiting 1st Reading |
|  | Amendments to Political Party Law | HOP Awaiting 1st Reading |
|  | National Defense Bill | HOP Awaiting 1st Reading |
|  | Somali Turkish Defense Agreement | HOP Awaiting 1st Reading |

# Footnotes

Uncertified expenditures. Certified annual expenditures can be found in the Annual Financial Report of MPTF Office (http://mptf.undp.org/factsheet/fund/4SO00 )

Fill in only the numbers or yes/no; no explanations to be given here.

See Annex 5

Public consultation on Anti-Money Laundering Bill in Somaliland held. Public Consultations/hearings on Electoral Bill, Petroleum Bill, Amendment to Media Law, Revenue Bill and Health Professionals Bill.

Joint Parliamentary Oversight Committee on Constitution Review

Speakers forum could not be convened because of the severed relations between the Upper House and the House of the People of the Somali Federal Parliament.

Somaliland MPs conducted constituency visit to Sanag

There ere political and electoral disputes in Galmudug and Jubland respectively since late 2018. Similarly, the disputes that arose from the presidential elections in South West in December 2018 caused disruptions in the effective functioning of the State Assembly.

This is based on post training evaluation and feedback from participants.

Puntland House of Representatives in a working session to draft strategic plan for the new Puntland HoR, Garowe

In Puntland, the strategic plan has been developed and committee workplans will be adopted based on the Strategic Plan.

MoU signed between Puntland Parliament and Civil Society estabslishing the Parliamentary Civil Advisory Board in Puntland

Supported Upper House Women Caucus Elections

Establishment of the Library and Research for Puntland in progress

Gender Specific Outputs are those that are specifically designed to directly and explicitly contribute to the promotion of Gender Equality and Women’s Empowerment.

Staff members are those contracted to undertaken work for the Joint Programme including full time staff, consultants, advisors, interns, etc. Staff members with responsibility for gender issues are those who have gender related activities included in their Terms of Reference.

Environmental; Financial; Operational; Organizational; Political; Regulatory; Security; Strategic; Other.