## General Information-Final
Programme Title & Project Number |  | Programme Duration
Programme Title: | Support to Early Recovery and Inclusive Service Delivery for Vulnerable Groups Heavily Affected by the COVID-19 Crisis in Uzbekistan | Overall Duration (months) | 7
Programme Number (if applicable) | N/A | Start Date (dd.mm.yyyy) | 2020-06-04
MPTF Office Project Reference Number: | 00121958 | Original End Date (dd.mm.yyyy) | 2020-12-31
Country | Uzbekistan | Current End date (dd.mm.yyyy) | 2020-12-31
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | UNDP, UNICEF, UNFPA, IOM | National counterparts (government, private, NGOs & others) and other International Organizations | Gender Equality Commission under the Senate of Uzbekistan, Ministries of Economic Development and Poverty Reduction, Mahalla and Family Support, Finance, Labour, Public Education, and Interior Affairs, Republican Rehabilitation Center (RRC) for GBV survivors (RRC), Uzbektelecom, Uzinfocom, NGOs «Mehrimiz sizga» in Andijan, «Oydin Nur» in Bukhara, «Mehrjon» in Farghona, «Yuksalish»' in Qashqadarya, «Barqaror Hayot» in Surkhandarya
Report Cleared By
o Name:
o Title:
o Email address:
The MPTF Office Project Reference Number is the same as that on the Notification message. On the project’s factsheet page, the MPTF Office GATEWAY, it is also referred to as “Project ID”
The start date is the date of the first transfer of funds from the MPTF Office as Administrative Agent. The transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the relevant decision-making body/Steering Committee.
If there has been an extension, the revised, approved end date should be reflected here. If no extension has been approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Final
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum) | To alleviate COVID-19’s impact on the most vulnerable including women, gender-based violence victims, children affected by conflict, informally employed youth, unemployed returned migrants and the elderly, UNDP, alongside UNICEF, UNFPA and IOM, implemented the Joint Programme to strengthen the capacity of the Ministry of Mahalla and Family Support (MMFS) and associated service delivery civil society organizations (CSOs) to better respond to target groups’ needs, implement efficient policies and measures, and deliver basic socio-economic protection and services to them. Key activities were: i) technical and financial support to unemployed informal sector workers (particularly youth and women, women with disabilities, women-headed families); ii) legal and psychosocial support to families repatriated from armed conflict zones and children leaving specialized correctional institutions; iii) inclusive legal, psychosocial, and direct support to women and girls, including GBV survivors, through shelters, hotlines, and awareness raising iv) socio-economic, psychological, and legal support to vulnerable returning migrants/ migrants’ family members. UNDP provided technical, consultancy and mentoring support to unemployed/informally employed women and youth. Integrated Support Services Programmes (ISSP) helped 260 women develop digital skills, financial literacy and online trading skills. Nearly 400 women and youth in mahallas most affected by lockdown related unemployment in Karakalpakstan, Kashkadarya, Ferghana and Syrdarya launched family-based businesses. The Handicraft Training Center was established in Syrdarya region to train 1,500 unemployed women in early 2021. Over 9,400 users registered on private digital platforms focused on consultancy and job searches. UNFPA worked with national counterparts and CSOs to support GBV survivors, women with disabilities and mothers of children with disabilities. Twelve regional Republican Rehab Centre (RRC) branches received support to procure supplies for GBV survivors in shelters, and internet/mobile connection for shelter staff. In Tashkent Province, 154 poor target families received food packages; utility expenses were covered for 27 families most affected by lockdown; and 150 families were offered internet/mobile connection. UNFPA also created the “No to violence” Telegram channel, Instagram and Facebook pages (5,000 subscribers), broadcasting GBV statistics from shelters; contact details of service providers. UNICEF worked with MMFS, ensuring integration of 95 repatriated children and reintegration services for 356 girls and boys leaving closed institutions. Supervision was provided to 350 community specialists working with children from closed institutions and 57 specialists from regional and district Ministry divisions were trained to develop individual reintegration plans and become case managers of reintegration services. Regional and district level MMSF specialists in 14 regions were trained to monitor and supervise reintegration services provided by community specialists and other local stakeholders. IOM provided community outreach and reintegration assistance to vulnerable returned migrants and their families, implementing activities in five regions. In each of five regions, one partner NGO received sub-grant of $7,000 to conduct a needs assessment. Overall for five regions, 284 men and 224 women returned migrants were covered for needs assessment. NGOs delivered psychological, legal and socio-economic counselling to 580 returned migrants (274 men and 306 women). In kind reintegration assistance was given to 60 returned migrants (35 men and 25 women). Overall 60 beneficiaries received grants in the total value of $154,103 to start new entrepreneurship activities in 25 diverse areas.
2 | Purpose (and Beneficiaries) | Please include the number of both direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups | The total number of beneficiaries reached is 31,536 UNDP provided support to 10,235 beneficiaries, 3,106 women and 7,129 men, including: ● 393 women who established family-based businesses in four regions of Uzbekistan, of whom 60 passed intensive training in garment design. The average age of women is 32–34 years; 81 per cent are unemployed or informally employed and lost their income due to quarantine restrictions; 101 are under the age of 30; 43 per cent of women interviewed are married, some of the families have many children; about 53 women are divorced, more than 58 are widows or have lost their breadwinner; 30 women have a family disability or they themselves belong to a disability group; some of the women-beneficiary in their families have a husband abroad or their families are considered troubled. ● 200 women improved their business and soft skills within the re-launched ISSP programme, including 100 informal workers – women ‘mardikors’ (casual workers), with an average age of 32 years, and 46 young women under the age of 30. ● 104 women were employed in sewing workshop, beauty salons and pasta production; ● 60 women passed training in Handicraft Training Center and improved their skills on embroidery and knitting (hat, jumper, shoes), carpets weaving, making jewelry, production of souvenirs, sewing of national clothes and others; ● 9,478 active users registered with the mobile app “Job Café”, “Imkoniyat”; With the support of UNFPA, 14,702 beneficiaries were supported overall including: ● 2,139 rehabilitation center direct beneficiaries, including: - 301 women and their children-GBV survivors in temporary residence in 12 rehab centers/shelters nationwide were able to receive food and hygiene products and access psychological, medical and legal support from rehab centre staff; - 50 specialists of rehab centers in August received sim cards and internet access; - 1,788 appeals (including from GBV survivors) received through rehab centers’ helplines were responded up to end of December; ● 331 women “Opa-singillar” NGO of women with disabilities, a grass-root NGO led by the disabled women and providing services for disability community in Tashkent province, including: -154 families-members of the NGO (who are supported by NGO), received food packages during the project life-time; - 27 the neediest families’ municipal costs (gas and electricity) were covered; - 150 women with disabilities and mothers of children with disabilities received sim cards with internet and mobile connection ● 7,232 (total), including 5,623 women (out of which 970 cases related to family conflicts/ violence/ harassment in the working place) received free social, legal, psychological and referral services through applying to #1146 national hotline, officially re-launched October 27, 2020. 6 moderators and one IT specialist and operational expenses funded under the MPTF project allowed to maintain a smooth and effective response and monitor the appeals. ● 5,000 subscribers of informational, educational “No to violence” Telegram channel (along with its Facebook, Instagram pages) focused on empowering women and girls, as well as their protection against violence and harassment launched in partnership with the Senate Gender Equality Commission with a view of exaggerating gender-based violence during the period of COVID-19 epidemic. On a daily basis, women and girls were able to access the contact information on available sources to apply in case of GBV, informed on statistics and GBV situation nationwide, hear voices of survivors through the real cases, and receive free legal and psychological advice. UNICEF provided support to 451 children, including: ● 356 children (146 boys and 210 girls) left specialized correctional institutions. Age groups: 36 children (11-14 years); 320 children (15-17 years); ● 95 repatriated children and their families (including their relatives' families) living in communities (47-boys and 48 girls). Age groups: 57 children under 5 years; 18 children 6-10 years; 17 children aged 11-14 years and 3 children aged 15-17 years. IOM provided support to 6,148 beneficiaries, including 3,105 (51 per cent) women and 3,043 men (49 per cent), including: ● 6,915 individuals (around 1,000 in each selected region) involved in outreach activities for returned migrants and migrants’ family-members; ● 508 returning migrants and migrants’ family-members surveyed/interviewed, including 284 men and 224 women. Age groups: 195 respondents (39 per cent) aged 18-30; 171 respondents (34 per cent) aged 31-40; 97 respondents (19 per cent) aged 41-50 and 43 respondents (8 per cent) aged 51+; ● 580 returned migrants and migrants’ family-members including 274 men and 306 women were given counselling. Age groups: 193 (33 per cent) aged 18-30; 188 (32 per cent) aged 31-40; 133 (23 per cent) aged 41-50; 66 (11 per cent) aged 51+; ● 60 vulnerable returned migrants received reintegration assistance: 12 beneficiaries in each region, including 35 men and 25 women, with an average age of 35. Age groups: 25 (32 per cent) aged 18-30; 21 (35 per cent) aged 31-40; 9 (15 per cent) aged 41-50 and 5 (8 per cent) aged 51+.
3.1 | Results: Outcome Level | Please include outcome level results achieved | Three hundred ninety-three (393) women and youths in more than 175 mahallas (communities) in the Republic of Karakalpakstan, Ferghana, Kashkadarya regions, which, according to the ministry, are experiencing the highest unemployment rates due to the COVID-19 pandemic, received technical support and launched home based businesses, which helped them generate income and satisfy basic needs. In the Republic of Karakalpakstan, 60 women improved their skills during one-month intensive training courses on design and processing of garments. Three identified women-leaders were supported to launch a hair salon, a sewing workshop and a pasta production site in Syrdarya region, an area that was not only affected by COVID-19 but a dam break in May 2020. Nearly 100 unemployed women were employed: 10 women in the hair salon, 65 women in the sewing workshop and 25 women in pasta production. Groups of women were supported to establish and lead a handicraft training centre (HTC) in a 300m2 building in Gulistan City in Syrdarya region. The HTC is equipped with furniture, laptops, LSD projector, sewing equipment, bakery and appliances and devices. It is expected that the HTC centre will train at least 1,500 unemployed women in order to increase knowledge and skills to enhance their livelihood opportunities within the first half of 2021. By the end of 2020, 60 women passed training on embroidery and knitting (hat, jumper, shoes), carpets weaving, making jewelry, production of souvenirs, sewing of national clothes and others. About 5,623 calls from women and girls were received through the national hotline #1146 for GBV survivors nationwide. Out of 5,623 calls, 970 calls were related to family conflicts/ psychological, economic, physical violence/ harassment in the working place. There were 1,788 appeals for support received from women through GBV local hotlines under rehab centres and were met with assistance.
3.2 | Results: Output Level | Please include output level results achieved | In the framework of technical and financial support to unemployed informal sector workers, particularly youth and women, including women with disabilities and women-headed families: • the needs of 100 informal workers were addressed. Women ‘mardikors’ (casual workers) who have been particularly hard-hit were selected by MMFS and UNDP from 44 mahallas and 6 districts in Surkhandarya region and improved their skills through intensive training courses on basic private business and family entrepreneurship. This training was aimed at building entrepreneurial skills in the most popular business areas in the market (tourist, trading, sewing and others); • in Tashkent city, 100 women from more than 80 mahallas were identified, who received credits and bank loans for their businesses, attended training courses and improved their business management skills, including digital skills, financial literacy, supply chain management at a local level, online trading, product and services delivery and logistics skills and home-based entrepreneurship. The training was arranged by UNDP and the network of NGOs “Women’s Business Center” operating in each region of the country; • UNDP supported modernization of the online platform “Job Café” and developed a new mobile app “Imkoniyat” by attracting the help of two teams of five young girls – finalists in the “Technovation Girls-2020” project. These private online platforms cover a) job searches for the informally employed, and b) consultancy for families with children with disabilities. After launching the new version of “Job Café” by December 31, 2020 user numbers reached 9,478 (there were about 1,000 users of "Job Café" in June, while 12,000 users registered before the pandemic); In the framework of legal and psychosocial support to families repatriated from armed conflict zones and children leaving specialized correctional institutions: • UNICEF developed Guidelines for the Provision of Remote Counselling to Families and Children during COVID-19 as a recommendation for community service providers to deliver remote individual and group counselling. The Guidelines were presented to the MMFS for endorsement. The Standards of the community-based services were drafted and will be further discussed for the final submission to the Ministry. • guidance and supervision were provided to 350 community specialists working in areas where children from closed institutions live, to develop individual reintegration and family support plans, and to perform the role of case managers in the provision of reintegration services. • at regional and Republican levels, 20 Specialists of the MMFS were trained in monitoring and the skills to reintegrate children leaving specialized correctional institutions. • at district level, 134 Chief Specialists of the MMFS were trained monitor and supervise community-based specialists who provide reintegration services to children (and their families). • from divisions of the MMFS, 57 specialists from the target communities where repatriated children and families live were trained on the basics of social work, aspects of discrimination and stigmatization, the basics of family needs assessment and the stages of case management. They received supervisory support from professional social workers from the partner organization (RCSAC). • access to social services in line with individual reintegration plans was given to 356 children released from specialized correctional institutions; • a database on the implementation of the individual reintegration plans for children from closed institutions was regularly updated; • terms of reference for an Inter-Agency Coordination Group were drafted to ensure sectoral cooperation and sustain reintegration results for children leaving specialized institutions and repatriated families. • the Inter-Agency Action Plan for the third round of repatriation and re-integration was developed by all stakeholders and submitted to the Cabinet of Ministers, aimed at the smoothest re-integration of the children and families newly repatriated from armed conflict zones. As part of inclusive legal, psychosocial, and direct support to women and girls including support for gender-based violence (GBV) survivors through shelters, hotlines, and wider awareness raising activities: • 5,623 calls from women and girls were received through the national hotline #1146, which was established with support from UNFPA. Out of 5,623 calls, 970 calls were related to family conflicts/ psychological, economic, physical violence/ harassment in the working place. • 301 (206 women and 95 children) women and their children in temporary residence in shelters nationwide were able to receive food and hygiene products and access psychological, medical and legal support from rehab centre staff. • 154 families from the disability community in Tashkent province received food packages; the municipal costs (gas and electricity) of 27 of the neediest families were covered. 150 women with disabilities and mothers of children with disabilities received sim cards with internet and mobile connection. • The “No to violence” Telegram channel, Facebook, Instagram broadcast operational summaries with GBV statistics and cases on GBV survivors and other vital GBV related information and reached 5,000 subscribers. The channel collects statistics on GBV nationwide and it is practically the only source of reliable official GBV statistics in the country, being broadly cited and used by national partners, media and international development agencies. In total, 400 posts (average four daily) were published in Uzbek and Russian during the reporting period. In the framework of socio-economic, psychological, and legal support to vulnerable returning migrants and migrants’ family members: • partner NGOs have conducted community outreach with returned migrants and their families covering remote areas and districts. Overall, 6,915 flyers were distributed in five regions, around 1000 each. Outreach activities and flyers contained the contact information of NGO counsellors who could give socio-economic, psychological and legal counselling, and COVID-19 related information. Outreach was important for awareness and identification of the most vulnerable migrants in order to properly develop further reintegration support; • a comprehensive survey was conducted among 508 returned migrants in five regions, including 284 men and 224 women. Partner NGOs worked with Mahalla committees and regional departments of the MMFS to build a database of returned migrants and to reach survey respondents. Combining quantitative and qualitative approaches, the survey generated important conclusions and data on the extent of vulnerability of migrants; • counselling was provided to 580 migrants and their families, including 274 men and 306 women. The counselling was complex and included social, psychological, legal and business development. Counselling was essential for the emotional recovery of migrants from job loss during the pandemic and travel hardships; reuniting properly with family members; smoothly adapting to local society. Business counselling was very helpful to identify relevant skills and develop specific business plans for migrants’ start-ups. • under counselling activities: – psychological counselling was provided to 274 individuals including 130 men and 144 women; – legal counselling was provided to 244 migrants including 130 men and 114 women; – social counselling was provided to 310 migrants including 163 men and 147 women; – business development counselling was provided to 147 migrants including 92 men and 55 women. • reintegration assistance was provided to 60 beneficiaries, 12 in each region, including 35 men and 25 women. Each migrant received on average $2,568 ($154,103 overall) from IOM, and was facilitated by the partner NGO to purchase equipment, raw materials, and other components for their start-ups. Developing a business was very important for returned migrants, in order to bring stability and create stable income generation activities; new job creations included family business (the majority of startup created on average five more new employees) and the acquisition of new business and technical skills. The end of the project monitoring showed that all beneficiaries – who represented the most vulnerable migrants – were able to recover their personal financial and family situations and successfully reunite with their family members.
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words) | 1) Institutional challenges 1.1. The Government has strongly focused on reaching the most vulnerable categories of population, but the pandemic occurred at a time of significant transition for the new MMFS, charged with delivering coordinated assistance to vulnerable populations. Moreover, the merger absorption of the major national gender machinery, Women’s Committee of Uzbekistan (WCU), into the new Ministry, has impeded the ability of vulnerable women to access immediate support from the state during very challenging period. To address this challenge, with resources mobilized from the Government of Japan, UNDP supported the development of an integrated COVID-19 crisis management response system, which enhanced the capability of the MMFS, its regional branches, and nearly 9,600 local communities nationwide. 1.2. Re-launch of 1146 hotline for GBV survivors posed significant challenges due to: the transformation process within MMFS. Prior to the pandemic, 1146 was run by WCU; budgetary constraints funds for upgrading and to cover high traffic were not immediately forthcoming from the MMFS, which resulted in anxiety about hotline’s sustainability. To encounter the risk, the project team maintained regular consultations, and advocacy with MMFS, Uzbektelecom, Uzinfocom and RRC leadership. Capacity building efforts by UNFPA led to increased awareness among the Government on hotline’s importance to preventing and combating VAW. MMFS took the ownership of the hotline, allocated special premises to the service, and the Minister led an official opening ceremony for the 1146 re-launch. Significant budget allocations were made to cover 1146 traffic in 2020 with more funds due to sustain the hotline in 2021. Programme “Risk matrix” has been updated correspondingly. 2) Operational difficulties 2.1. Challenges occurred due to administrative barriers within the system of Uzbektelecom, Uzinfocom and Ministry of Finance (those companies monopolized the communications field of most state institutions). This challenge was overcome through continuous communication with focal points of those companies and MMFS. 2.2. NGOs faced difficulties in limiting reintegration assistance to only 60 beneficiaries where there were many other equally eligible migrants also desperate for financial support. In response, partner NGOs provided eligibility criteria information for migrants and migrants’ family-members. Other eligible applicants who did not receive in kind reintegration support were served by NGOs with counseling. 3) Compositional changes 3.1. Changes in the composition of community workers trained at the beginning of 2020 with technical UNICEF support to provide reintegration services to children from closed institutions caused challenges when existing governmental structures disappeared and the new MMSF was established. These challenges were mitigated by strengthening the capacities of regional and district departments of the new MMSF to monitor the social services provided to children from closed institutions. 3.2. The COVID-19 pandemic and lockdown-imposed restrictions on movement resulting in limited opportunities to conduct face-to-face core programme capacity building activities to initiate system level changes to address the needs of vulnerable. In response, by shifting to on-line capacity building training for MMSF staff at different levels. A Telegram based network was created for each region by project's regional staff, ensuring each community specialist had access to recommendations from project experts. Opportunities to closely monitor the provision of services to children appeared after lockdown was lifted.
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words) | 1. The project revealed a policy gap preventing the system of 197 rehab centres from adequately supporting GBV survivors. Based on the lessons learnt during project implementation, MMFS developed cost estimations and additional policy regulations to be endorsed by the Cabinet of Ministers. Based on the inventory assessment of the existing centres at the local level, it is not possible to host GBV survivors in some shelters as they do not comply with minimum standards: i.e., no separate building, no security, no sewage system, etc. Most rehab centres are based in temporary premises and staff of district level centres operate fully on a volunteer basis. 2. Considerable policy gaps were revealed in the national system of support for people with disabilities (PWD): a) the amount of current social allowances is insufficient to cover basic needs; b) the system of costs for municipalities should include the economic situation of PWDs, many of whom rely on the social allowance for disability; c) the existing employment system strongly limits the opportunities for PWD to access decent jobs and alternative income generation; d) there is strong informational inequality and lack of access to information on basic services for PWDs due to the scarcity of funds among members of the disability community, especially for mothers with disabled children. 3. Children from specialized correctional institutions and repatriated children from armed conflict zones face many challenges related to their reintegration including the accessibility and quality of services. The social service workforce (SSW), including community and district level specialists of the MMFS, often left have little professional guidance, standards for working with vulnerable families and need support from trained supervisors. Work carried out within the MPTF funded project to support vulnerable groups of children forms a good basis for advocating with the MMFS and other stakeholders for the introduction of social work-based approaches into the functional responsibilities of SSW. Draft social work case management guidelines were presented to the Ministry for endorsement. 4. Reintegration support for 60 beneficiaries demonstrated that each business start-up engages on average five employees and fosters significant job creation and community stabilization. Beneficiaries created new and high-demand businesses in remote areas, where no similar service was available and the project contributed significantly to the development of regional infrastructure, boosting competition. Reintegrating returning migrants helped bring in innovative technologies and entrepreneurial ‘know-how’ acquired while working abroad. 5. Newly created businesses also boosted self-esteem, confidence of future beneficiaries and migrants’ family-members. Beneficiaries are unwilling to continue with low-skilled jobs abroad, even after the pandemic. 6. IOM project good practices demonstrated that proper counselling and especially reintegration assistance to vulnerable migrants is beneficial for reuniting families and better child care. Proper reintegration helped children and spouses to be reunited, provided with employment and stable income generation sources. 7. For most NGOs, partnership with the IOM project was helpful for capacity building, by provision of complex assistance. NGOs acquired new skills, including the ability to conduct professional surveys, became specialized in relevant business areas and to provide gender sensitive services.
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words) | UNDP provided MMFS with sewing equipment for three new «Training Centers for Mahalla Communities” in Syrdarya region. The centres were established with the support of the Korean International Cooperation Agency (KOICA) to provide unemployed women with free trainings to develop relevant skills. Through the joint support from the COVID-19 MPTF and the Canada Funds for Local Initiatives (CFLI), MMFS and UNDP identified three women-leaders who received technical support to start women-led businesses such as pasta production, a hair salon and sewing workshop in Gulistan and ensured nearly 100 new jobs for informally employed women in Syrdarya region. Parallel efforts found a 300m2 building and groups of women, who received relevant equipment. As a result, a Handicraft Training Center (HTC) in Gulistan City was established. In 2021, the HTC will provide training for at least 1,500 unemployed women in order to increase knowledge and skills to enhance their livelihood opportunities. UNFPA upon approval of two Grant agreements with the NGO "Opa-singillar" (for disabled women and mothers of disabled children) and Republican Rehabilitation Center for the survivors of gender-based violence, staff communicated with Internet and cell phone providers about internet packages to make sure partners selected suitable packages. A partnership with “Macro” chain store was established to provide purchase and delivery of food packages for “Opa-singillar”. A partnership with Uzbektelecom and Uzinfocom was established to revive and re-launch 1146 hotline. The “No to Violence” Telegram channel entailed maintaining regular communication with national partners. GBV statistics collected through “No to Violence” were communicated on a regular basis within the UN Gender Thematic Group. UNICEF developed a partnership with the MMFS. The project promoted strengthening of interagency collaboration through regional stakeholder meetings in all 14 regions of the country. These served as a common platform to identify major issues caused COVID 19 and to identify appropriate solutions. In addition, the roles and responsibilities of key stakeholders involved in reintegration process for children leaving closed institutions were discussed at each meeting. The project also helped to establish a working relationship between the Ministry and the Republican Centre for Social Adaptation of Children, for a last decade on the frontline of professional social work development in the country. IOM cooperated with the MMFS and partner NGOs, regional branches of MMFS Mahalla committees to provide reintegration assistance. IOM also worked closely in pilot regions with the Agency for External Labor Migration of RUz to organize appeals from target groups. The IOM project also cooperated with the Gender Equality Commission under the Senate of Uzbekistan, and the Agency for External Labour Migration under the Ministry of Employment and Labour Relations of Uzbekistan. IOM project results were disseminated during a high-level International Forum on Migration and a Coordination Forum in December, 2020, involving stakeholders from key government entities, civil society, academia and international organizations, and other.
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken. | A number of assessments, evaluations and studies were undertaken within the Joint Programme: – with the support from UNDP, the MMFS conducted two rounds of assessment and baseline studies in pilot mahallas (local communities), which aimed to identify the beneficiaries of financial and technical support, and to register and analyze unemployment data among youth and women engaged in the informal sectors. As a result, 593 women were identified based on criterion set by UNDP. Final beneficiaries in the Republic of Karakalpakistan, Syrdarya, Kashkadarya, Surkhandarya and Fergana regions received technical support. – the IOM project prepared an analytical report based on results of a survey with returning migrants “Implication of Covid-19 pandemic on returning Uzbek migrants and their family”. 508 migrants who returned to Uzbekistan during 2020 participated in the survey (56 per cent men and 44 per cent women). The majority (71 per cent) of survey respondents were aged between 20 and 40 years. The main findings of survey analysis and in-depth interviews demonstrated that migrants relied on themselves or on help from family members or friends to return home; only 5 per cent received help from the Government. After returning home, 35 per cent did not have enough money and 33 per cent faced temporary shortages in buying basic necessities. Finding jobs in their homeland remained a key issue as 78 per cent of respondents did not have a job, while another 11 per cent were working unofficially; The IOM project team conducted interim and final reporting from partner NGOs. NGOs were providing detailed portfolios for each beneficiary including type of equipment purchased, business plan; counselling responses and other relevant project reporting documentation; – two national consultants were hired to conduct the monitoring of the project activities aimed to measure the satisfaction of beneficiaries, and also the contribution to sustainability of reintegration following a standardized approach of IOM. Consultants conducted in-depth interviews with selected beneficiaries, NGO staff and counsellors by collecting quantitative and qualitative data based on a “Monitoring Questionnaire” for each NGO. Independent assessment of consultants confirmed the proper delivery and efficiency of the reintegration assistance provided by NGOs. Detailed success stories were collected for each beneficiary revealing and documenting the true impact of the assistance received, and recording changes in the personal and family lives of migrants; – during the project timeframe a social services assessment of 20 communities was undertaken by project experts. The report gives an analysis of the community based social services, legal framework and human resources that communities have. Recommendations for developing the services in question were made and submitted to the Ministry; – with the support from UNFPA, - the technical condition and quantity of equipment in regional rehabilitation centres and in offices and shelters was checked and clarified. The data was used to procure equipment under grant conditions. In addition, the living conditions and requirements of shelters were checked during monitoring visits to selected regions. The data was shared with the national partners for consideration and action.
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place | N/A
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners. | UNDP established new partnerships with the Government of Japan and Government of Canada which resulted in securing additional resources for COVID-19 response parallel to the interventions of the Joint Programme, worth $514,620.

## RBM-Final
| Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 1[1] | Out of 497 informal workers selected from over 175 mahallas (local communities) who received technical support (100% are women), 84% unemployed or informally employed. The average age of the selected women is 33. 25.6% or 101 of informally employed are young girls under the age of 30. | N/A | Reports/official letters of the Ministry of Mahalla and Family Support (MMFS), Project report
Outcome indicator: 2.1a Percentage (%) of informally employed youth, women and men, targeted through this project interventions, included into the programmes of support of the Ministry of Mahalla and Family Support and benefiting from access to socioeconomic protection and inclusive services
Baseline: data not available
Planned Target: 20% of the informally employed in 30 pilot mahallas (out of which 10% are women). 10% of the total number of informally employed target group will be youth.
| Over 95% of GBV survivors who applied; 100% women with disabilities indicated under MPTF proposal; – 5,408 appeals for support were received from women by the rehabilitation centres nationwide, including 1,788 appeals, which were received through GBV local hotlines under rehab centres and met with assistance. By facilitating timely access to information by connecting 50 staff members of 14 regional offices to mobile operators and internet the rehab centres were able to receive calls from GBV survivors and provide them with legal and/or psychological counselling, place them and their children to shelters or redirect them for further assistance to relevant service providers: police, healthcare facilities, local community/mahalla and/or khokimiyat (local mayor’s office); Although the system of rehab centres was established in 2019, there is no funding for food provision and basic needs for GBV survivors to host them in the shelters, particularly while there is increased demand during the quarantine lockdown. The project, although quite short in timeframe, revealed deep gaps both at the policy and grass root levels. – By providing funds for food and hygiene products, rehab centres in 12 regions were able to host 301 women and their children (from August 15 through December 31) and to access necessary psychological, medical and legal support from rehab centre staff. – When required, the rehab centre’s administrations collaborated with local administrative authorities (local municipality, police, employment, healthcare, education bodies) to assist in resolving the issues of the survivors. – The National GBV hotline with the short number 1146 was officially re-launched on October 27, 2020. 6 moderators and one IT specialist were funded under the MPTF project to maintain a smooth and effective response and monitor the appeals. From 27/10/20 to 31/12/20 over 7,000 calls were received through the hotline, out of which 5,623 calls were from women and girls, including 970 cases related to family conflicts/ violence/ harassment in the working place. – 150 women with disabilities accessed mobile connection and internet. They joined the “No to violence” Telegram channel run by UNFPA in the framework of the MPTF project and are receiving vital information on GBV and the possibility of getting free psychological and legal counselling from available rehab centre hotlines during the lockdown period. – During the lockdown, due to the lack of public transport, many partially employed disabled people lost their jobs. Accordingly, their economic situation worsened dramatically. Debts for utilities grew and they had chosen between spending disability allowance funds on food and medication or cover municipality costs. Consequently, families of the disability community were very stressed. UNFPA project team assisted the NGO in concluding agreement between “Macro” chain store and ‘Opa singillar’ for food delivery to Tashkent province. The municipal costs of 27 of the most affected women with disabilities were covered in the framework of MPTF funding, which was extremely timely. | N/A | UNFPA and NGO reports, Reports of the Republican rehabilitation adaptation centres
Outcome indicator: 2.1b Percentage (%) of GBV survivors and their service providers, people with disabilities included into the programmes of support of the Ministry of Mahalla and Family Support and are benefitting from legal and psychosocial protection from GBV
Baseline: 0
Planned Target: 50% (for each group) GBV survivors, and people with disabilities applying to GBV hotline received needed assistance.
Output 1.1 | Special Programmes to support informally employed were piloted in Karakalpakstan, Surkhandarya, Syrdarya regions and Tashkent city. Out of 260 informally employed women and girls who participated in the Special Programmes, 60 selected women passed a one month-long basic (intensive) course in the design and processing of garments to ensure the sustainability of their family-based businesses; 100 women and girls – mardikors (casual workers) passed intensive training courses on private business and family entrepreneurship; 100 identified women, who received credits and bank loans for their businesses, attended training and improved their business and soft skills (digital skills, financial literacy, supply chain management at a local level, online trading, product and services delivery and logistics skills, home-based entrepreneurship). Entrepreneurship programmes were launched within a network of NGOs “Xotin Qizlar Tadbirkorlik Markazi” ("Women's Entrepreneurship Center) operating in each region of the country. 60 women passed training in Handicraft Training Center and improved their skills on embroidery and knitting (hat, jumper, shoes), carpets weaving, making jewelry, production of souvenirs, sewing of national clothes and others. | N/A | Reports/official letters of the Ministry of Mahalla and Family Support
Indicator 2.1.1a: gender responsive actions targeting unemployed and informally employed youth and women are implemented by the MMFS
Baseline: special programmes targeting specifically informally employed are not implemented by MMFS.
Planned Target: special programmes to support informally employed are piloted, including online skills development courses, entrepreneurship programmes
Output 2.1.2 | 356 children (including 210 girls) who left closed institutions received reintegration services. These services included legal advice/information, assistance with obtaining legal documents, psychosocial support, obtaining social allowances, medical support, assistance with employment and self-employment, assistance with education and professional training, placement to alternative care arrangements, improving living conditions etc. 95 children repatriated from the war conflict zones and their families were provided with medical services, educational services, developmental services in kindergartens, support for improvement of living conditions (new apartments, repairs etc.), employment support and Income Generating Activities support, getting material assistance and foster care arrangements. 100 repatriated and 105 children (60% are girls) reached by PSS services. | Closure of two closed institutions in 2020 and the need to organize support and reintegration for children leaving these institutions | Quarterly reports of the MMFS
Indicator 2.1.2b: number of children repatriated from armed conflict zones and girls and boys leaving specialized correctional institutions reached by assessment and psychosocial support activities during COVID 19
Baseline: 108 repatriated children and 0 children leaving institutions
Planned Target: additional 200 (40% of them are girls)
Output 2.1.3 | 60 beneficiaries (35 men and 25 women) were provided reintegration assistance to the amount of $154,103, or $2,568 per each. This included 12 beneficiaries in each pilot region. The average age of beneficiaries was 35, the youngest being 20 and the eldest being 60 years old. Age disaggregated data of beneficiaries: in 18-30 age: 25 migrants or 32% 31-40 range: 21 migrants or 35% 41-50 range: 9 migrant or 15% 51+: 5 migrants or 8% - First, NGOs conducted wide community outreach among 6,915 migrants (around 1,000 in region) including remote districts. Community outreach helped foster awareness of NGO counselling support for returning migrants and guides to the pandemic. - Each NGO conducted a comprehensive survey among 508 returned migrants and properly identified the most vulnerable 60 (12 in each region) for further reintegration assistance. Beneficiaries were selected based on appeals from community outreach and survey. - Each applicant received comprehensive counselling advice including psychological, legal, socio-economic directions. This complex counselling was essential for restoring the emotional condition of returned migrants, and more important - proper identification of potential business areas. - Each selected beneficiary developed a detailed business plan based on IOM expertise, ensuring the viability of planned start-ups. Where applicable, beneficiaries undertook additional training on new skills required for their business start-up. - Each NGO developed a unique equipment and resource specification plan for each beneficiary. Based on this specification plan, necessary equipment / machinery / raw materials / other business inputs were purchased in overall value of $154,103 - $2,568 on average for each beneficiary. - All business equipment of beneficiaries was successfully shipped, installed and put into operation. The returned migrants managed to operate their businesses and launch production. - Beneficiaries established new businesses in 25 different directions. The most popular types among women included sweets workshops, bakery, sewing workshops, mini-cafe, mini grocery shops, greenhouses for fruits. For men - these categories included construction and repair workshops, window and door production workshops, auto-tuning services, greenhouses for vegetables, cotton ginning shops, car washes, welding and plumbing; rabbit farms, furniture repair shops. Migrants selected their business area based on needs assessment of the migrants by NGO social workers and counseling received. | N/A | NGOs reports, Survey results, IOM monitoring Report
Indicator 2.1.3a: Number of the most vulnerable returning migrants (returnees) and migrants’ family members, benefitting from reintegration assistance (disaggregated by sex and age)
Baseline: N/A
Planned Target: 60 (35 men/25 women)
Indicator 2.1.3b: Number of vulnerable returning migrants (returnees) and migrants’ family members, received socio-economic, psychological and legal counselling and advice, (disaggregated by sex and age) | Actual: 580 (274 men / 306 women) 18-30:193 migrant or 33% 31-40: 188 migrant or 32% 41-50: 133 migrant or 23% 51+: 66 migrant or 11% Psychological counselling included 274 individuals, 130 men and 144 women. Legal counselling included 244 migrants, 130 men and 114 women Social counselling included 310 migrants, 163 men and 147 women Business development counselling 147 migrants, 92 men and 55 women - Complex counselling which included a balanced mix of 4 counselling areas was important for proper response and the delivery of reintegration assistance for returning migrants. This goes beyond only providing financial support for business start-up. In fact, 90% of migrants suffered from severe emotional downturns, depression and were facing the consequences of various hardships during the pandemic. - NGOs first conducted socio-economic counselling and redirected migrants for further relevant counselling. - During the psychological counselling, beneficiaries received repeated consultations to rebuild their emotional self-esteem, confidence in the future and in their own efforts. - When they returned to a solid emotional and psychological condition, beneficiaries undertook professional business counselling. They also learned how to develop detailed business plans for their new business, calculating the financial profitability and feasibility of new businesses. - Legal counselling was important for dealing the particular issues of migrants, including lost documents; resolving legal issues; legal advice for business registration and development. | N/A | NGOs reports, Survey results, IOM monitoring Report
Baseline: N/A
Planned Target: 400 (200 men/200 women)
Output 2.1.4 | Total of 301 women and children hosted by 12 rehab centres/shelters nationwide in the reported period Total appeals received 6,337, including: From women – 5,408 From children under 18 – 248 Survivors in shelters –Total – 686 (*figure is higher than above since it includes also those who stayed in the shelter for short periods as well). women – 496 children – 190 Over 5,000 subscribers of the Telegram channel “No to violence” accessed vital and regular information from the broadcasts containing: contact details of relevant state authorities and CSO service providers for GBV response, consultations of psychologists and lawyers; operational summaries with GBV statistics and cases on GBV survivors from MoI, RRC and CSO shelters; reposts from other media on most acute GBV cases. - UNFPA project team assisted the Republican Rehabilitation Center (RRC): - a) in capacity building of the staff to conduct market search and compile the list of basic food products, medication and hygiene for GBV survivors in the shelters; - b) developing and using reporting templates for regional centres and RRC on appeals received and survivors in the shelters; - c) preparing reports for obtaining approval from the Ministry of Justice to endorse the upcoming UNFPA grant funds; - d) preparing inventories for 14 regional centres on available IT equipment and that to be procured by UNFPA. |  | List of beneficiaries, Case reports from shelters, UNFPA monitoring reports
Indicator 2.1.4a: Number of women - survivors of GBV have access to safe shelters and referral services to receive psychosocial and legal support to reintegrate to the society (disaggregated by sex, age, disability)
Baseline: 26 women and children
Planned Target: 280 women and children
Indicator 2.1.4b: Number of families of women with disabilities and women with children with disabilities received social assistance, and access to information and services. | Total 260 women and families from the disability community: 150 women with disabilities and their family members Families from the disability community are receiving vital information on COVID-19 and available social and healthcare services, and have become aware about GBV through being connected to and having costs covered for internet/mobile plans. 154 families from the disability community in Tashkent province received food packages; the municipal costs (gas and electricity) of 27 most needy families were covered. UNFPA project team assisted “Opa-singillar” staff in: a) capacity building of the staff to conduct market search and compile a list of basic food products and other basic needs for medication and hygiene for women from the disability community; b) preparing a report for obtaining approval from the Ministry of Justice to endorse the upcoming UNFPA grant funds c) launching a Telegram group for disseminating information on GBV and other useful information for the disabled community, in particular on services related to COVID-19; also, on the opportunities and privileges for disabled people in accessing social services. d) developing selection criteria and compiling a list of families from the disability community in Tashkent province most affected by the pandemic to get them help with food and covering utility costs; Project team assisted Opa singillar to conclude agreement with the “Macro” Chain store on food delivery to Tashkent province, helped to organize volunteers to deliver to the doors of disabled members who were unable to pick up their package. Motivational interviews with Opa-singillar director and a few disabled community members were conducted together with the “No to violence” Channel journalists and promoted through social media networks to support and encourage the community. Such support is extremely important during the pandemic lockdown situation. Also the awareness of the importance of access to diverse useful information increased among those 150 members granted with sim cards and internet. At the start of the project the majority asked for food rather than internet packages. |  | List of beneficiaries, Reports from partner, UNFPA monitoring reports
Baseline: 20 families
Planned Target: 300 families
[1] Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.

## Communication-Final
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
Story#1 (Gender-based violence) N., 46-year-old woman from Tashkent province, a mother of a daughter with disabilities and two sons. When the girl was one-year-old she was paralyzed and became fully motionless as a result of a medical error and now she needs constant care. Thanks to the MPTF Covid-19 project, as one of the 150 neediest families of women with disabilities and mothers of children with disabilities from Tashkent province N. received a sim card and internet access. With this support N. made use of a free online course on the promotion of products through the Internet. Then she created her own Telegram Channel to sell her handmade soft toys and homemade pastries.
Story#2 (Gender-based violence) Dilnoza (name has been changed) works as a nurse at a medical clinic, an intensive job requiring frequent late nights which are perceived negatively by her husband. After many attempts to force her to leave her job, one night after Dilnoza came home late her husband became angry, beat her and kicked her out of the house. Not knowing what else to do, Dilnoza came to the 'Oydin Nur' centre where she received food, shelter and psychological support. This shelter is one of many supported by UNFPA in Uzbekistan, helping women and families in difficult situations, as well as GBV survivors. The centre staff worked with Dilnoza's local mahalla committee to resolve this problem. Together they engaged Dilnoza's brother, who had been aware of previous abuse but had not taken action for fear of attracting public attention. After learning what had happened to Dilnoza in the latest instance, he said he was ready to fully support her even if she wanted a divorce
Please, see the story of Said (https://www.unicef.org/uzbekistan/en/saids-story). Available in Russian, Uzbek and English
Please, see the story of Jamila and Nodir (https://www.unicef.org/uzbekistan/en/story-of-jamila-and-nodir-from-iraq). Available in Russian, Uzbek and English
Story #3: Female beneficiary (reintegration support for vulnerable returned migrants) Zulfiya Komilova (name changed) is a 39-year-old woman who lives in Surkhandarya region. She is a mother of two children: a 12-year-old boy and a 9-year-old girl. After the death of her husband in 2011, she had no choice other than leaving for migrant work to Russia as her life with parents-in-law was with conflicts. She faced dire times in Russia, due to delayed payment of her salary and other challenges related to her unofficial, low skilled job at a small supermarket in St. Petersburg. Due to COVID-19, Zulfiya returned to Uzbekistan in August 2020 and could not find a job in her village. The reintegration support of IOM channeled through the NGO “Barqaror Hayot” was very timely for Zulfiya. With the project help, Zulfiya managed to start her own greenhouse and is now very happy to be self-employed, having regular income generating activity and stability in her life. Her children also have bright future prospects thanks to the start-up business of her mother. Being now self-employed, Zuldiya can devote more time to her children and is no longer willing to go abroad for a low-skilled job. She is very grateful to the IOM project and NGO “Barqaror Hayor” for providing gratuitous assistance.
Story #4: Male beneficiary (reintegration support for vulnerable returned migrants) Sherzod Rahimov (name changed) is a 20-year-old man who lives in Andijan region. He is the youngest of six brothers and sisters. He could not pass entrance exams to University and therefore decided to leave for work to Russia, Yekaterinburg in August 2019. In Russia he was working in private houses and construction companies as a welding worker. When he started to improve in his welding practice, the СOVID-19 pandemic started. Throughout the pandemic, he faced different challenges such as a low salary, decrease in the demand for welding services which resulted in expiration of his official patent for work. Sherzod faced further hardships of being deported due to expired patent and short-term arrest in migration custody, which was further aggravated by travel limitations during the pandemic. Upon his return to Uzbekistan in May 2020, the chair of Yangi Bostonobod mahalla recommended his candidacy for the IOM project as a potential beneficiary. Sherzod was selected as one of 12 beneficiaries for receiving reintegration support in Andijan region. The IOM project in partnership with NGO “Mehrimiz Sizga” acquired welding equipment for Sherzod to start his own business and helped to build a small welding service centre. Currently Sherzod is successfully running his welding workshop and his brothers and friends are also engaged in his business. His personal life projects have also improved dramatically. Sherzod is very grateful to the IOM project and NGO for provided psychological, economic, legal and social counselling and support, which helped him to gain self-confidence and motivation.
2. Upload here: Communications and Visibility (OPTIONAL)
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well picture material please make sure you include all credits and upload them in high resolution Call1 countries.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board
UNDP in partnership with Ministry for Mahalla and Family support, Ministry for Innovation Development, maintains the “Job Café” mobile application with nearly 9,500 active users providing not only services to find a job but also analytical information for national partner ministries splitted by gender, regions;
A number of article news has been published at: https://www.gazeta.uz/ru/2020/08/13/programme/ (the launch of the MPTF Joint Programme); https://www.uz.undp.org/content/uzbekistan/ru/home/presscenter/pressreleases/2020/09/300-women-and-youth-to-receive-equipment-for-launching-businesse.html https://telegra.ph/300-dan-orti%D2%9B-ishsiz-fu%D2%9Barolar-%D1%9Ez-tadbirkorlik-faoliyatini-boshlash-arafasida-09-30 (300 women and youth to receive equipment for launching business) https://www.uz.undp.org/content/uzbekistan/en/home/presscenter/pressreleases/2020/10/jobcafe.html (‘Job Café’ application – a tool helping to find a job)
As part of a 16-day campaign against gender-based violence within UNDP’s Women Empowerment Project the following events were conducted: - A webinar on “Effective assistance to the victims of domestic violence: the experience of Sweden” with the participation of Swedish experts for employees of the Ministry of Internal Affairs, the Ministry of Higher Education, the Ministry of Health, the Academy of the Ministry of Internal Affairs, the Bar Association, and employees of the Republican Center for Rehabilitation; - An online mobile clinic to provide legal and psychological consultations for women and people with disabilities (with the help of a sign translation) on TV (Uzreport), radio, social networks (Telegram - Azizam channel); - Launch of a mobile application "Najot” to support the protection of rights of GBV victims and survivors and provision of timely assistance and access to information; - Launch of a “positive masculinity” campaign to raise awareness of gender-based violence among the general public: videos featuring religious leaders, publication and distribution of booklets, brochures and leaflets containing information on gender-based violence and women's rights; - A national contest "Gender Equality Activist" with the participation of representatives of ministries, departments, non-governmental organizations and journalists, who achieved high results in the field of gender equality at the end of the year, came up with initiatives for the development of society, defended the rights of women and performed relevant tasks in their field.
UNFPA in partnership with the Gender Equality Commission of the Senate supports the informational analytical channel “No to violence” which covers over 5,000 subscribers and is the source for many national and international players for GBV statistics and showcases spread in the country. Link: https://t.me/zoravonlikka_yol_yoq_netnasiliyu
The information about all components of the MPTF project was broadcasted through the following ways: 1) Launch ceremony of 1146 hotline on the National TV channel; 2) High-level advocacy event to kick-off “16 days of activism against GBV” campaign in Uzbekistan which was aimed at discussion of Uzbekistan's experience in addressing women's issues, especially during the COVID-19 pandemic, from both government agencies and civil society institutions. 3) Publishing news on the website and social media networks of UNFPA, Gender Commission of the Senate, MMFS, bloggers and journalists. 4) Producing video materials to promote the national state hotline 1146 and “Not to Violence” Telegram channel. 5) Development of a number of printing materials under MPTF funding: • “The Collection of human stories” from the TG channel accompanied by summaries of GBV dynamics, situation and an analytical overview to reflect the impact of the UNFPA interventions to respond to GBV and support to the institutions working with GBV survivors as well as analysis of gender stereotypes reflected in the human stories. The publications will be distributed to the Senate, Rehabilitation centres & shelters, regional mahallas, involved ministries, donors, international organizations. • Job aid informational and practical material in the form of calendar for mahalla specialists and rehab centre staff on how to interact with GBV survivors, for Social Workers and mahalla specialists on step-by step hands-on instructions how to identify, behave and act in GBV cases; practical recommendations on prevention of GBV during their duly routine work with families and communities; • information materials (in the form of posters and leaflets /for online publication as well) on women’s rights with focus to GBV prevention and with concise information on the services available for GBV violence survivors; on working with GBV survivors and abusers for the staff of mahalla and shelters in particular in the context of COVID-19 response. The posters will be disseminated to mahalla committees nationwide. The leaflet(s) on hotline and shelter services will be disseminated to pharmacies and/or shopping centres for further dissemination to women and girls.
UNFPA PHOTOS & VIDEOS FOR FINAL REPORT 2020 https://cutt.ly/khNNhHA
On December 22, 2020 UNICEF in cooperation with the Ministry of Mahalla and Family Support conducted the final Round Table to present the results of the MPTF-funded project. The objectives of the round table included to present and discuss the project’s achievements and lessons learned; to raise awareness on the social work case management standards for working with vulnerable families and children and advocate for the use of the case management approach in working with children and families in the communities and adoption of the Inter-Agency Resolution on its implementation and to adopt the Inter-Agency Plan of Action on support services to the children and women repatriated from the war conflict zones for their successful adaptation and re-integration in the society. The participants of the Round Table included Members of the Project’s Inter-Agency Coordination Group, MPs, members of the Youth Parliament. Link to UNICEF press release (in Russian, English and Uzbek): https://www.unicef.org/uzbekistan/en/support-for-repatriated-kids-pr (available in Russian, Uzbek and English). Link to other on-line media publications on the event:
The IOM project delivered successfully reintegration assistance to returned migrants in 5 pilot regions of Uzbekistan. All project implementation steps were properly shared with partner organizations including NGOs, MMFS, Mahalla committees and other migration related parties. The final project achievements were presented in Coordination Forum with the representative of these partners and the mass media. All project activities including community outreach, selected beneficiaries, award ceremonies were done with public awareness and relevant dissemination.
1) The IOM project has conducted massive outreach among returning migrants in 5 pilot regions. 5’000 informative, colored flyers were distributed among migrants.
2) IOM project beneficiaries were awarded with Certificates acknowledging received reintegration assistance. Selected award ceremonies were properly highlighted by regional news channels thus disseminating IOM activities on migration issues, partnership with MMFS, Mahalla committees, hokimiyats (local administrations), NGOs. Links: http://www.youtube.com/watch?v=HE3ak_EbN-E ttps://youtu.be/-XHQqW_swvQ
3) During the Coordination Forum held on December 24-26, 2020, the results of IOM project activities, survey findings among returned migrants, and success stories of beneficiaries. The Forum participants included Gender Equality Commission of the Senate of the Republic of Uzbekistan, Center for Human Rights Support, the Agency for External Labour Migration, Ministry of Interior, National Rehabilitation Center for victims of human trafficking, IOM partner NGOs, and the leading national TV news channels and bloggers. The Forum was very beneficial for proper awareness of migration related changes, new laws, applied practices and specifically IOM contributions in Uzbekistan. The Forum also provided fruitful platform for re-connection of mass media and NGOs, exposure to their activities, unique services, shelters provided for vulnerable groups and victims of human trafficking, domestic violence. Link: https://www.facebook.com/IOMUzbekistan/videos/161769599020410
4) The IOM project has maintained its Facebook and Twitter pages for timely sharing of project updates, achievements of beneficiaries. Link: https://twitter.com/un_uzbekistan/status/1339822129861308416 https://twitter.com/un_uzbekistan/status/1339856826184196097 https://www.facebook.com/UN.Uzbekistan/photos/a.183405948409311/3646333425449862/ http://www.facebook.com/IOMUzbekistan
5) Selected NGOs also shared IOM joint activities in mass media, regional news channels. Most NGOs and other local partners provided letters of gratitude and appreciation to IOM project acknowledging fruitful cooperation and reintegration assistance. NGO “Barqaror Hayot”, Surkhandarya region https://www.facebook.com/permalink.php?story_fbid=1225226317870325&id=100011489046051 https://www.facebook.com/permalink.php?story_fbid=1225239337869023&id=100011489046051 https://www.facebook.com/permalink.php?story_fbid=1227724547620502&id=100011489046051 https://www.facebook.com/permalink.php?story_fbid=1227820007610956&id=100011489046051 https://www.facebook.com/permalink.php?story_fbid=1270742086652081&id=100011489046051 NGO “Yuksalish”, Qashqadaryo region: http://nkgz.uz/read/uyazvimym-migrantam-vernuvshimsya-na-rodinu-okazana-reintegratsionnaya-pomoshch-v-ramkakh-proekta-mom NGO “"Mehrjon", Ferghana region http://www.youtube.com/watch?v=HE3ak_EbN-E 6) Migrant beneficiaries also expressed their deep gratitude for received assistance in “success stories” documented by independent monitoring consultants.